## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
67a5bddd-c246-5fde-9820-7b6aab55e180 | checklist | 10.01 - Plant Mixed Lightly Bound Pavements | itp | 10.01 - Plant Mixed Lightly Bound Pavements
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
243140dc-76f7-5961-9205-cdb0fce3a8fa | checkpoint | Construction Procedure
4b4ec2d3-c44f-57f3-a979-c9aacc74546d | note | ○ Documented procedure shall be prepared for all construction processes as defined in Clause 6 of MRTS50 and shall be submitted for approval at least 14 days prior to commencement of lightly bound pavement works (No work shall commence until accepted by the Administrator)
2f700929-d45d-5730-a114-535c32eb2f8c | note | Acceptance Criteria & Frequency (Project Specific) - Acceptance
6d88a7b2-0c4f-557b-8f30-dedf9aa7e2da | note | Check Item - Hold Point 1, Milestone
8d66f932-ce0c-51fb-b124-8fc1497d201c | note | Reference - Clause 5.2 MRTS10
6dac35f8-56fa-5881-a970-d3b9b186dcf7 | signoff | HOLD POINT
bc49bc48-2c20-50a8-89ce-4f9f4f8fafda | checkpoint | Material Requirements - Unbound Pavement Material
3a03f5ca-efda-598f-b43a-c1b2432a9b95 | note | ○ The Contractor shall not incorporate unbound pavement material into the works unless it has been demonstrated that the unbound pavement material lot conforms fully to the requirements of MRTS10. All conformance results shall be no more than six months old.
a2357c78-c4cd-5fa0-b567-c8a71e75ae4d | note | Acceptance Criteria & Frequency (Project Specific) - Acceptance
8602a0c9-19e4-5f78-9228-a3205053bf4b | note | Check Item - Hold Point 2
35de7388-4ddb-5f34-8476-2ae0942b1a30 | note | Reference - MRTS10 Clause 6.1.1
a3e7b37d-acd0-5bd9-9e26-64b49423c1a9 | signoff | HOLD POINT
25b7cfbd-b61f-5a9d-99de-6ff61d84939d | checkpoint | Mix Design Report
b12eb130-970a-5252-a956-4bc7e1d9cb4e | note | ○ A mix design must be submitted at least 14days before mixing operations commence. Construction of the lightly bound pavement layer shall not proceed until a conforming mix design (refer to Clause 7.2) has been deemed suitable and accepted by the Administrator.
c7a7cbe9-ece6-5984-a981-309965c5421d | note | Acceptance Criteria & Frequency (Project Specific) - Acceptance
c2c1d236-7e59-580b-9432-adf691ad29de | note | Check Item - Hold Point 3
d9757575-d960-540c-85c2-fdcca401667b | note | Reference - MRTS10 Clause 7.1
ed7486f1-e465-5f8a-93af-ee19363fbaec | signoff | HOLD POINT
d696ff76-9950-520d-a3bc-37efc8b22e56 | checkpoint | Moisture Content
25284aeb-e2a2-5415-8ffb-9703cba525a3 | note | ○ The Contractor shall nominate upper and lower moisture content limits as part of their Mix Design that will ensure:
c889df71-6ed8-56a4-9673-857e34cb7e55 | note | a) there is adequate moisture to achieve the specified compaction standard
6d0f01f7-1352-5bfb-bd6b-13c29396cc61 | note | b) the constructed lightly bound pavement layer is trafficked in accordance with requirements of Clause 8.2.11, and
2e9af4e3-ab5f-524e-bbc8-2012f068820c | note | c) the lightly bound pavement material does not exceed the optimum moisture content (OMC), determined in accordance with Test Method Q142A.
cdc860b7-c520-5c00-9d3d-46f3a57f3c34 | note | Acceptance Criteria & Frequency (Project Specific) - Testing - AS1289.2.1.1, 1 per 500m2, 4 per lot
c5e01a74-4809-5193-897f-1e0dd3a43df1 | note | Check Item - Test Report
3f887f4d-1503-58d3-94d8-b8c7899a3fef | note | Reference - MRTS10 Clause 8.2.5, Clause 9.4.8 Table A3
b11f1e9b-ede8-594a-8098-d0de12864985 | checkpoint | Construction - Trial Pavement
fdcdb6fe-fa4e-5c2f-b44f-9e17df1e4e5c | note | ○ Unless otherwise agreed by the Administator, a trial of the manufacturing and laying operations shall be caried out prior to commencement of the work.
06b6f855-f8a1-5327-841e-347c5b6b2483 | note | ○ The trial pavement shall be located within the site and be not less than 1000m2. It shall determine the characteristics highlighted in Clause 8.1 MRTS10. The trial may be incorporated into the permanent works at the Administrators discression.
62282f85-66a0-5a5b-aa28-954d8eb1d00a | note | ○ The Contractor is to undertake the material and construction compliance testing nominated in Clause 8.1 and the finished pavement complies with the technical specification of MRTS10. If deemed not conforming, further trialing shall be undertaken.
ac89084a-6b58-529b-9194-1f62e0a10318 | note | Acceptance Criteria & Frequency (Project Specific) - Visual & Check
8d301c89-718e-5c28-a735-cd74d31ad34d | note | Check Item - Witness Point 1 /Hold Point 4
d3befdd3-1134-5f78-91f9-f0eedacac6c3 | note | Reference - MRTS10 Clause 8.1
3b295591-2821-5562-b0cb-1b5aaeb4d9c0 | signoff | HOLD POINT
1cfc3111-1a9d-5d0d-b33f-99e2ac3bc23f | checkpoint | Material Compliance Testing
d2e7feba-deb1-5545-971f-d5a3554c5d57 | note | ○ Each supply lots shall be sampled and tested for compliance in accordance with the testing frequencies specify in MRTS05. No material shall be incorporated into the work unless it has demonstrated compliance fully with the requirements of MRTS05 and MRTS10
daf5895c-776a-53db-91f1-75845262fc9c | textbox | Material Type:
46fccaee-d1e6-5c8a-9aac-c2945d9513f1 | textbox | Material Stockpile Lot Ref:
c80bd8c5-4847-5bf6-87cf-cd7de9c3a595 | note | Acceptance Criteria & Frequency (Project Specific) - MRTS05 Cl. 7, Table A1, MRTS10 Cl.6, Table A2
c9f41c07-4206-5dca-b3af-8905dcfcd038 | note | Check Item - Check Item
2ea8b70f-733f-5b9f-b9e8-d5b421ede4a7 | note | Reference - MRTS05 Clause 7
56377b54-fde7-5406-837c-3890686afe74 | checkpoint | Equipment
ca99a0de-52a8-517c-b6f5-eb8b5b743725 | note | ○ Equipment as specified in approved construction procedure
7788f511-ca01-5f2b-bfa2-bc55d8d0250c | note | Acceptance Criteria & Frequency (Project Specific) - Construction Procedure Approval
911d87b5-b1e5-584c-98bf-8ba17564d7de | note | Check Item - Contract Notice
e0139a31-d133-5e0b-82db-d216d79f4fb8 | note | Reference - MRTS10 Cl.8.2.1.4
1d851571-a928-5a25-b90f-6dc4951d0941 | checkpoint | Weather Conditions
8c3eb78c-cf9d-5b7a-84d3-9e06740ee011 | note | ○ CMB material shall not proceed when:
28f9e562-cd7a-560a-af88-bdc567b294d3 | note | a) air temperature is less than 10°C or greater than 40°C
4fe12a30-2e88-5f3a-9f5a-26782f7b3718 | note | b) during rain or when rain is likely to fall during placement
fc5ec0d3-1e87-5f5c-a44a-e8c23c7e49d1 | note | c) evaporation rate due to the combined effect of air temperature, wind and relative humidity may result in excessive drying of the CMB
2d533ba3-e131-5ffa-b28c-551f3855daef | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
61452252-3564-5349-8578-1084bbe26381 | note | Check Item - Check Item
eddb9e5c-6209-5b24-9ab6-23ad7b63d9ed | note | Reference - MRTS10 Clause 8.2.4
4e03ab1e-e68b-54c4-841d-13eb989c51d8 | checkpoint | Allowable Working Time
25443fc0-9420-5181-83c1-65a0bbe66983 | note | ○ Define as the maximum period between mixing the modifying binder into the unbound granular material and the completion of compaction.
abd907a8-1fd7-56f3-940f-a32de332ccd1 | note | ○ The allowable working time for the plant-mixed lightly bound pavement is to be the lesser of the following
51dbbd4b-253e-588e-9e16-355a5a7a8c15 | note | a) Working time determined in accordance with Test Method Q136A
721e65be-38e3-5741-9138-f2d4fd2f81d9 | note | b) Four hours
3429c867-429b-54be-92c1-62b12cb11370 | note | Acceptance Criteria & Frequency (Project Specific) - Monitor
3c51e6ab-f007-5d89-8bcf-03afcb657b8b | note | Check Item - Check Item
8d57638f-a527-5fdc-87e3-8f9f321840bf | note | Reference - MRTS10 Clause 8.2.3
42fd55de-9d63-5d85-844a-49f359657c2f | checkpoint | Construction Joints
15aef852-d64e-53fa-a662-36f81f25d3a9 | note | ○ Deemed to be fresh when the material compacted on each side of the joint has been modified, placed and compacted within the allowable working time. In multi layer of lightly bound pavement, longitudinal joints of each layer shall be offset from the underlying layer by a minimum of 150mm.
d107e79c-c1b5-505f-b771-d58b993466e0 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
f59c5847-33ae-5c13-a9ea-00bbeb217b39 | note | Check Item - Check Item
c46f3098-ac31-57f3-b003-9ecdf9cc70f7 | note | Reference - MRTS10 Clause 8.2.10
09c077af-813c-5092-a8e3-c0018de0d0e2 | checkpoint | Fresh Joints
e67d1141-9cc6-5203-b7bb-87a10db44ecc | note | ○ Where fresh joint between adjoining or adjacent run is to be compacted, the outside 300mm of material from the first run shall be left uncompacted until the adjacent run is ready for compaction.
26c1fab6-c993-577c-8fdc-8c0f8d6b3298 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
166722e3-d852-5ce7-ab90-aef75dfef849 | note | Check Item - Check Item
1a44f8bb-16c5-5ea1-ac1d-e1510413caec | note | Reference - MRTS10 Cl. 8.2.10.1
fe775b8c-ae59-5b6c-9023-cee85f7e74d3 | checkpoint | Other (Cold) Joints
a55e0804-3cfc-5580-be16-0ea08c0a285f | note | ○ Joints that are not fresh shall be cut back to form a neat, clean vertical face.
408fb48f-6474-5d92-8e53-f97cf89b58d1 | note | ○ Cutback distance shall be a minimum of 150mm and before placing the adjoining layer or adjacent layer, the cut back edge of the existing layer shall have a cement/water slurry at a rate of 2kg/m2. The slurry cement/water ratio to be 0.6 and 0.7.
37f79193-e8c4-5136-aa1d-de278704da39 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
12405f01-70b4-575e-bf1b-8532c7c41ae8 | note | Check Item - Check Item
07b0f1dd-7de2-5e98-8f3b-c4b68d51c3ce | note | Reference - MRTS10 Cl. 8.2.10.2 Cl.6.4
41055705-a004-5593-8172-bad48792c3a7 | checkpoint | Curing of CMB Layers
6fd77482-455f-552e-85a6-3b814827a04c | note | ○ The surface of an existing layer of lightly bound pavement shall be water cured until placement of the next layer and/or bituminous surfacing is applied. Unless approved, within 7 days of placement the lightly bound pavement shall be covered by a subsequent layer and/or bituminous treatment. Water curing shall be completed in accordance with Cl. 8.2.1.5
180b0d17-08ef-5ed7-b9f0-adbc81a3df67 | note | Acceptance Criteria & Frequency (Project Specific) - Check & Verify
d44af67a-a3cc-5e36-a200-4fd148b95ced | note | Check Item - Check Item
94866467-792d-538c-b8f6-681b1d4a18db | note | Reference - MRTS10 Clause 8.2.9
1c825ecf-7382-5490-866d-b99a23800274 | checkpoint | Trafficking of CMB Layers during Construction
d81befe9-d628-53f2-8639-b66723356d77 | note | ○ Unless approved by the Administrator, lightly bound pavement layers shall not be opened to either construction traffic or general traffic until the lot has been tested for, and passes proof rolling (Cl 9.4.10)
21168a14-e415-56d3-a8f5-4804e07399ca | note | Acceptance Criteria & Frequency (Project Specific) - Check
c98b7623-b77b-56cf-9fca-fe83d208f373 | note | Check Item - Check Item
14a5dcd4-594b-5fb0-a982-07b7e7aa75cb | note | Reference - MRTS10 Clause 8.2.11
7fd44338-da44-5c5b-9f99-290fe3a4ff61 | checkpoint | Compaction Standard
8d60b723-1e22-50c4-8301-74ba0df4143c | note | ○ The characteristic value of relative compaction shall not be less than 100% standard, except for the upper most layer of lightly bound base which shall not be less than 102% standard
2d436cbe-1174-542a-a972-48cba44c6654 | note | Acceptance Criteria & Frequency (Project Specific) - 102% standard upper most layer
03d28018-81ba-5842-be6f-b97149fbef53 | note | ○ 100% standard lower layers
1660b746-1ca9-5449-9781-8b25d37d2332 | note | ○ (1/500m2, min 4/lot)
60ef7631-19ff-5c97-9168-aaeac0828f3f | note | ○ (1/1000m2, min 4/lot)
827ac221-bd7f-585e-af17-77f6647ed6a6 | note | Check Item - Test Report
7235a919-6f85-5455-8553-5a4e58d4e0a6 | note | Reference - MRTS10 Clause 8.3.4
ac9f11c6-86cb-54f1-bc10-08cb58380ce1 | checkpoint | UCS
ee36f699-ac57-5a6f-8059-12a4d7d021b2 | note | ○ Unconfined compressive strength between 1 - 2MPa
e4e91ca7-2975-56de-9e14-8c5944b9a3eb | note | Acceptance Criteria & Frequency (Project Specific) - UCS 1-2MPa (1 per lot)
444264d3-7193-5249-b7f3-6f643c242294 | note | Check Item - Check Item
add8098a-3cc0-5831-9dfa-d49152d5922e | note | Reference - MRTS10 Clause 9.4.9
ec616351-fefd-56b9-a41a-96f6f73ce7d7 | checkpoint | Stabilising Agent Content
14cc868f-bba2-52c6-b29b-a2db28d6b13f | note | ○ The actual content of stabilising agent for each lot shall be represented by both the:
ac682857-b8e0-5f67-ab1c-d45dc9602511 | note | a) minimum characteristic value of the actual content of stabilising agent, and
e69f96a4-8681-5a00-b6f7-b58a9aa7fc69 | note | b) maximum characteristic value of the actual content of stabilising agent.
c0cdfb5b-eb82-5656-bec1-52cd5d8f9dbc | note | ○ When UCS tests are being undertaken, the sample being used must also be tested for stabilising agent content.
6e7c14ce-88b4-53a0-934f-3cb6735f632c | note | Acceptance Criteria & Frequency (Project Specific) - Target content minus MPV, Min. test 1 per lot
4b84f01a-c741-5bec-bd6a-f482639fa883 | note | Check Item - Check Item
06110462-61a4-52a2-a00b-4a014bdc0fae | note | Reference - MRTS10 Clause 9.4.6
2f8e0836-4f19-5666-8540-e7e4a2288619 | checkpoint | Geometrics - Horizontal Tolerances
0187c15e-f8d7-58c7-98df-b0064edbcdc4 | note | ○ Shall not be more than ± 50mm except for the following:
6a9f9aa0-8298-5630-9063-6565e6774cc6 | note | a) Pavement edges not adjacent to any other part of the pavement and not adjacent to any structure or adjoining road, transverse tolerance shall be -50mm + 250mm
ba68197f-7af6-54d2-9fd6-c1f07d25eee6 | note | b) Where alignment of the pavement with an existing structure is necessary, the new work shall be joined neatly to the existing in a smooth manner
36a2e849-0e69-52e0-842d-6506faf83f06 | note | Acceptance Criteria & Frequency (Project Specific) - -50mm/+250mm (1 per 20m)
b096310d-54ad-5cdd-90cd-0fa53e3a12d3 | note | Check Item - Survey Report
01da8e46-342d-57e8-b2fc-a633cbffc9d8 | note | Reference - MRTS10 Clause 8.3.5.2
ba73a75c-9cae-5363-b414-be622914880d | checkpoint | Geometrics - Primary Vertical Tolerances
da5e3b78-a239-549b-9419-eae776232f69 | note | ○ The vertical tolerances specified in Table 8.3.5.3 shall apply or:
06ca456e-0619-5f71-8058-cc22d588e63b | note | – the surface level measured at any point on the surface of any layer.
2a3403ab-2092-50f0-9bd0-a164bd023252 | note | – The average total thickness of the constructed course compared to the specified total thickness.
f1a8a279-8c6a-526a-8847-39558523e655 | note | Acceptance Criteria & Frequency (Project Specific) - ±15mm for layers that have been hard cut ±10mm for all other layers
4e22db10-147b-58b7-b9f3-49fea0bfd830 | note | ○ Layer thickness -20mm, +unspecified (1 per 20m at shoulders, lane lines & grade changes)
e8c95565-6133-57af-884a-03f40600ecd1 | note | Check Item - Survey Report
fd9c5302-4326-5448-98cc-ee397b3d3ca0 | note | Reference - MRTS10 Clause 8.3.5.3
8738e606-f651-5773-8edf-24a0dcc81fc9 | checkpoint | Geometrics - Deviation from a Straight - Edge
78f79cf4-ad21-532d-b22f-689ac4fecd2a | note | ○ Deviation of a straight edge place anywhere on the surface shall not exceed 5mm over 3m
6539ba4c-ea3c-5341-a10c-935fa9e89cf5 | note | Acceptance Criteria & Frequency (Project Specific) - 5mm over 3m (1 per 20m and at joints)
66e3b8da-b91f-50a9-aeba-c84ac7b0e589 | note | Check Item - Check Sheet
baa923d1-c787-55de-80d6-7accce0deb74 | note | Reference - MRTS10 Clause 8.3.6
| checkpoint | Geometrics - Crossfall
| note | ○ Shall not differ from the designed crossfall by more than 0.5% absolute
| note | Acceptance Criteria & Frequency (Project Specific) - Check
| note | Check Item - Survey Report
| note | Reference - MRTS10 Clause 8.3.5.4
| checkpoint | Proof Rolling
| note | ○ The perceptible surface deformation test (Q723) shall be undertaken in the presence of the Administrator
| note | Acceptance Criteria & Frequency (Project Specific) - Visual
| note | Check Item - Witness Point 2
| note | Reference - MRTS10 Clause 9.4.10
421f98d1-ae52-52ac-842f-162ed2968175 | checkpoint | Final Verification
c14ee595-1d14-532d-ad46-4ee7732db52a | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
66049e80-e655-5708-9b88-af9ec1851ac4 | textbox | Print Name:
72024633-bc93-5956-b3f5-2dd9f0685706 | date | Date:
ed94c1b7-8efb-5bfa-b05a-d0c710042e0a | note | Project Manager Verify that the Above has been Constructed according to Specification
7e7c2a49-b05f-51a5-a505-753c02b2659c | textbox | Print Name:
ee26d3ac-5770-5c3e-99fa-a77611531d50 | date | Date:
fe9ea76b-5345-51c8-ade7-e3c6547f8103 | signoff | Sign ITP
14888512-b268-53b2-9251-8582a9665c2b | section | Final Sign Offs (to be completed at closure of Lot)
9f44b134-6a89-50ab-b5fa-4f130357fa2e | checkpoint | Agreed Quantities
d544edec-1f76-5f24-89bf-14c0130de8cd | signoff | Agreed Quantities Sign Off
c2c5a780-35dc-55f7-80d1-af38367605c7 | checkpoint | Closure of Lot
d0980bd6-b931-530d-b84f-4d56087c0dde | signoff | Closure of Lot Sign Off