## Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP-002 - Construction of Underground Stormwater Drainage | itp | ITP-002 - Construction of Underground Stormwater Drainage |  | 35e84f4e-47b9-4dcd-8b66-66f36824298f
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
3b00059a-90d4-57f5-8413-2810b9d0f211 | note | FREQUENCY: Prior to commencing any activity
65873ac1-a527-552c-959a-a178f069a5e9 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
c0724451-eb97-56fa-85a8-c31eb1a906b9 | note | – using the correct and complete set of drawings
68ba2bda-62f2-5683-a90f-61e08ca8d5fe | note | – all drawings are the latest revision
1190e8be-8aa9-56c2-984d-fc59058eab0f | note | REFERENCE DOCUMENTS: Drawings and drawing registers
6258f126-95da-5fe1-87a3-261b79ccc858 | note | INSPECTION/TEST METHOD: Visual inspection
3ae4a122-7cfc-535d-9246-b6de3552335c | note | RECORD OF CONFORMITY: This ITP signed off
dec15512-bb96-5134-b6ea-e58a6f24ba6b | note | HP*
98c7824e-dd40-5504-8659-0175986b5e8e | note | RESPONSIBILITY: Project Engineer / Site Foreman
0a06e974-3e41-55d7-9a07-829a0841b280 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
844cfebe-5f8c-5849-8e93-f489ee0b2b1e | note | FREQUENCY: Prior to commencing any activity
17eaf772-a363-54f1-8f8b-6a2be14d1f71 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
8c87b484-55e6-5baa-adc9-4a1bdf60212a | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
e616a3f9-cc74-5021-9e94-f4c58dba3c90 | note | INSPECTION/TEST METHOD: Visual Inspection
c569ab38-0655-59bc-acd4-aea91f1ee960 | note | RECORD OF CONFORMITY: This ITP signed off
30dba391-d4bb-55f7-b281-1d18adfb2714 | note | HP*
38d58eca-1d79-519a-8c9b-d06abb3ee47d | note | RESPONSIBILITY: Project Engineer / Site Foreman
9b65051b-5253-59b4-a5f8-744e3549e8e5 | date | Date Completed:
| checkpoint | 1.3 - Precast Materials Inspection
b627edb5-defe-5bc3-8786-3b23126f706d | note | FREQUENCY: Each Delivery
9727f4b6-ae44-5462-9792-d9d89ac5b0b2 | note | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
df40e990-6e44-5adf-9a7a-ef7a00740862 | note | REFERENCE DOCUMENTS: 701.04b
141fd8ed-bb65-5d20-b498-727d411e1c4b | note | INSPECTION/TEST METHOD: Visual Inspection
b986f5ed-8551-58d1-9e07-64d9a0e36a40 | note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
a3e9ccce-eff7-5c46-bc3a-35b89e015bfb | note | IP
c134aad7-5196-5e43-9b78-f3fd3ac937a7 | note | RESPONSIBILITY: Project Engineer
4a53a748-26a9-572b-bdc5-6ff27bf2c84d | date | Date Completed:
| checkpoint | 1.4 - Precast Pipe Compliance
ac9cb674-a37f-5cf2-bb3c-8892864bf2c0 | note | FREQUENCY: Prior to Commencing
c0dd9232-df07-5b33-b4d5-acfd5b6266fc | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058. Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2.
4978016b-1718-5046-8581-0184af0cce72 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619, Cl. 701.04(a), Cl. 701.04(b)(i), Cl. 705.04(d), Cl. 705.11, AS4058, AS4680
ab7a4fb4-411f-574e-8505-48de374c98e2 | note | INSPECTION/TEST METHOD: Document review & Site inspection
4a6f95c3-b189-5a3b-9652-5d2127beea6a | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
b35e6f51-dd71-5b1f-b267-7807b834322e | note | IP
3332c61e-c97c-5eb4-81a0-f1a91f62b936 | note | RESPONSIBILITY: Project Engineer
8d197119-1758-5d11-ae80-9fef365ef692 | date | Date Completed:
| checkpoint | 1.5 - Bedding material classification
25480f94-c38a-5f81-8a67-5d20764f17fa | note | FREQUENCY: Prior to start
cef266b8-6d45-5441-af55-342da7c574f1 | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
cbc9fc9c-95cc-53ab-9590-b1ea17653cc3 | note | ○ 100% passing 19mm sieve.
882232b7-c12f-579b-84ea-74a73ee8db17 | note | ○ 5%-40% passing 0.075mm.
3553e848-efa8-5902-aea3-decae7f8d97c | note | ○ PI = 20 max.
c165bdbd-fde4-5431-9c33-643005b535b7 | note | REFERENCE DOCUMENTS: 701.04e Table 701.041, Table 701.042, Table 701.231
283f4168-f9c3-5eb3-a27f-ecbb635c0086 | note | INSPECTION/TEST METHOD: Verify
58d26048-60c6-5513-8929-daeffb317f7f | note | RECORD OF CONFORMITY: Test Reports from supplier
3c2bd8d3-e195-597c-b8ba-e491ebdb7b93 | note | TP
7e8ce218-3183-5db2-91d2-85b97cd98769 | note | RESPONSIBILITY: Project Engineer
1b594d36-fdf7-57b4-af77-080f05313aac | date | Date Completed:
| checkpoint | 1.6 - Backfill material Classification
1a5b1b26-8045-5145-b5ef-59e3336f65cb | note | FREQUENCY: Prior to start
d0b6ccb2-6b25-5511-ae63-7302f20b6b55 | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
2c1bdf2f-03e1-5261-a1f4-1fa8ff08e09b | note | ○ 100% passing 37.5mm sieve.
792be897-2c25-52ff-9a46-d7893d82931a | note | ○ 5%-40% passing 0.075mm sieve.
7b2b9552-7fa1-567c-9466-a1b496e9f12f | note | ○ PI = 20 max.
371aa836-1f06-5820-8514-b81ef0e9be26 | note | REFERENCE DOCUMENTS: 701.04e Table 701.041, Table 701.042, Table 701.231
302ff433-4ec0-5542-9a34-88530546f490 | note | INSPECTION/TEST METHOD: Verify
0b091728-872f-52b9-bd88-949e9254e383 | note | RECORD OF CONFORMITY: Test Reports from supplier
a167305d-b096-5415-9e4b-10436fe19e5b | note | TP
5d108530-c494-5709-b0e0-6bd4302563f3 | note | RESPONSIBILITY: Project Engineer
317b5211-b975-5bfb-9c01-e7e07ffcbde1 | date | Date Completed:
| checkpoint | 1.7 - Mortar material classification
2f13a589-2f0e-546c-9d46-aa4a2fbed9ae | note | FREQUENCY: Prior to start
15a5d656-a377-510a-b056-f4a1443a9688 | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
2931f9a4-fb6a-52ca-bd0a-58c35cf5e674 | note | REFERENCE DOCUMENTS: 610.33
f2256057-bb34-5e7a-be83-1b70e34d6a53 | note | INSPECTION/TEST METHOD: Verify
a4d5116c-97c3-56c2-8bd6-cc656c0a2830 | note | RECORD OF CONFORMITY: Test Reports from supplier
e512f48a-40d9-5e25-ab6e-3887eb7b5bac | note | TP
aba87e95-1a54-58df-9f95-8951b8a50020 | note | RESPONSIBILITY: Project Engineer
c9d70005-e8ff-55ea-a4f2-7dddf0e26540 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Excavation Permit
f696b7ce-7e18-5656-8b57-c5be31ed4e09 | note | FREQUENCY: Each lot
afaea3c0-c8bf-58fd-ac8c-d0b06d342767 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
e8b798a4-f500-5d29-a6f1-7d25c413cc60 | note | ○ Plant and equipment shall be appropriate for the task.
607aace2-baa5-5771-9b67-6a0879298df7 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
801230b4-a35f-581d-9f7d-44b1c9616ebd | note | REFERENCE DOCUMENTS: Excavation permit
d1f74d1b-1475-5ced-84c9-e0434cd7a777 | note | INSPECTION/TEST METHOD: Verify
30176be0-98db-5d32-98fe-ab398ebe8e28 | note | RECORD OF CONFORMITY: ITP Signed
150ae914-e09b-5887-9c5d-3a8ca730303a | note | HP*
faddeac7-8ec6-533f-8918-ac0d8570d78d | note | RESPONSIBILITY: Project Engineer
447de313-bf42-5752-9633-07e273129c8d | date | Date Completed:
| checkpoint | 2.2 - Set out drainage
deca8f1b-55c4-5f0b-82b6-0d3b451212e7 | note | FREQUENCY: Prior to excavation
2a8d6824-ba37-5c7a-b0e2-4ce4be47903e | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
58659295-77ef-5e35-a04c-387408d70db7 | note | REFERENCE DOCUMENTS: Drawings 701.10
d908ff1b-ff1b-56db-b5a0-200bb91dab01 | note | INSPECTION/TEST METHOD: Visual Inspection
825c5087-a800-5cdb-831d-2a5a6063457b | note | RECORD OF CONFORMITY: ITP Signed
92a4951d-3e10-5b50-9754-725ece568cec | note | HP
69e357f2-a72b-5e66-af6f-5b6b9687bc95 | note | RESPONSIBILITY: Engineer / Forman & Superintendent
a997b6e8-5838-5fba-b17c-4d283e3bb1b0 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Excavation (pipes)
850106bb-3995-5073-ba3c-6a1a77a896f4 | note | FREQUENCY: Each Trench
25bb23b8-e05c-5187-9c79-b454165a8b61 | note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical.
ea7c1357-f24d-54ae-b7b0-f8141638feeb | note | Depth of trench:
22130333-4446-51c7-8d22-a134be15bdd8 | note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
83a85c44-a6a7-5646-a881-e00b5bc55fd1 | note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
17917f45-0502-5a1e-9a28-df3d06f3f1e0 | note | REFERENCE DOCUMENTS: 701.15 Table 701.151
ac787a29-7148-5f45-a6c1-454b248b8f99 | note | INSPECTION/TEST METHOD: Visual Inspection
43bae29f-c621-5471-95b6-83beed67c3d5 | note | RECORD OF CONFORMITY: ITP Signed
d904add4-3db6-5458-ad09-305f3abf138c | note | IP
75278921-a59a-553a-a1a1-ae6fd792d984 | note | RESPONSIBILITY: Site Foreman
3dd98056-41ac-5dfc-8d7a-2de49ed3f697 | date | Date Completed:
| checkpoint | 2.4 - Compact base of trench
9136c7bf-5879-5c2a-8b60-2f1e6930edf8 | note | FREQUENCY: Each Trench
28ecbe2b-9699-57bd-bf0f-b4762c2789af | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
f5983272-f511-5dd4-9c3f-04fc722cb534 | note | REFERENCE DOCUMENTS: 701.1
cdfda3ee-65c7-5adc-8a78-19713dec4cad | note | INSPECTION/TEST METHOD: Visual Inspection
b1999e9e-3b36-568f-bd23-c2457a9aeaab | note | RECORD OF CONFORMITY: ITP Signed
511d9c33-688b-52fd-8846-a949a8f6c30b | note | IP
c2b338d9-2bf2-59b1-b9eb-e49b8df45a6d | note | RESPONSIBILITY: Project Engineer
86295443-08cd-537f-8510-c361f04fa77d | date | Date Completed:
| checkpoint | 2.5 - Place bedding material & compact
c7b4da25-5e0e-5023-9757-482dedaa7637 | note | FREQUENCY: Each Trench
0a938ec6-ac25-50cb-a19c-740660a0d0fb | note | ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness:
723d6886-1fe9-5b4a-8f09-7aaaa0b96791 | note | – 100mm under pipes.
e7c7ac38-9887-5048-8f0b-f6ba9b1542f0 | note | – 80mm (earth foundation)
340f519e-e10f-5645-b2a7-cd398d08a978 | note | – 150mm (rock foundation)
ef9b662f-5728-5f3b-94d2-13516fb17391 | note | REFERENCE DOCUMENTS: 701.19
17928ac5-45e6-5b40-8e04-bdeb2b9eb726 | note | INSPECTION/TEST METHOD: Visual Inspection
7dd9d481-1102-5b6f-8283-c672beb2dbaf | note | RECORD OF CONFORMITY: ITP Signed
906b625b-9eb4-505f-9e79-4245b4c58708 | note | IP
d61e42d2-9fb5-5bdb-b60a-9562bbc63b34 | note | RESPONSIBILITY: Project Engineer
1a250424-699c-5a06-9977-ebbbfef2d0c3 | date | Date Completed:
| checkpoint | 2.6 - Place pipes
d673e7ba-436a-541a-b65a-dd87311f9a5d | note | FREQUENCY: Each Line/Pit
14c5348d-88e7-57f9-bc69-99bf491b1307 | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
cca0cd77-8850-5b2f-aad1-d7788faf1c80 | note | REFERENCE DOCUMENTS: Drawings 701.17
8835b93c-7ec1-5b96-8c02-e6c945b6f560 | note | INSPECTION/TEST METHOD: Visual Inspection
e4014d3c-29fb-5c89-a12d-653997072b56 | note | RECORD OF CONFORMITY: ITP Signed
3dc1309a-f67f-5989-95c7-fdb813c0e5df | note | IP
94c4b7a2-bea9-5017-a77b-3ad237fe95f0 | note | RESPONSIBILITY: Project Engineer / Site Foreman
46d04e05-c762-5626-acb3-7f632dda71f2 | date | Date Completed:
| checkpoint | 2.7 - Jointing pipe sections
b66c7497-7ddc-5127-a9fe-cd0ec42f9596 | note | FREQUENCY: Each Line
bf9dc61e-d75f-543f-9aec-039148c9a59f | note | ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance to manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
8b0f4414-ce05-54d6-9a6b-37e3a4ec14c3 | note | REFERENCE DOCUMENTS: 701.18
dace5fd7-a3ec-530c-a9b1-e84503a3d07f | note | INSPECTION/TEST METHOD: Visual Inspection
f2f26693-60f4-5e0d-a882-eb49b9b689eb | note | RECORD OF CONFORMITY: ITP Signed
69772af1-6e4b-5a62-8d38-f923882556e9 | note | IP
6f868c51-4577-5ffc-b298-6f005f58dc9b | note | RESPONSIBILITY: Project Engineer / Site Foreman
82badfb4-c48c-59c3-8bf8-50daf69156b5 | date | Date Completed:
| checkpoint | 2.8 - Place & compact backfill material over pipes
1d44a2d4-a0c3-5ec4-8da0-adf2da0805f5 | note | FREQUENCY: each lot
f717f073-eac0-5f6a-9db2-b3425fc58ca8 | note | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
a11f724b-5b65-5df0-8a9c-61221c812bc3 | note | ○ Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
03c1f6c8-27d8-5b62-b326-7cb003b1d5a6 | note | ○ Loose layer thickness <= 150mm.
25aa419a-c0ff-579f-bd28-c956abee83e0 | note | ○ 1 lot = 150mm layer
5177870d-b693-5d3f-aafa-ed0a5095a096 | note | REFERENCE DOCUMENTS: 701.14, 701.15
fd128c4d-6421-5110-980a-a0fd442e2fca | note | INSPECTION/TEST METHOD: Visual Inspection
7198ed0a-690c-5b56-8ea1-0e66764f1dd7 | note | RECORD OF CONFORMITY: ITP Signed
b0dc0348-ba88-5689-a6ab-7d79cbcb80a2 | note | IP
8bfaf508-ba3d-5b75-b7c2-49fa42d5fe9d | note | RESPONSIBILITY: Site Engineer / Site Foreman
8ccbc6c3-4353-5cbd-933b-cfc5d2bb50cf | date | Date Completed:
| checkpoint | 2.9 - Repairs to damaged pipes
3457f486-a04a-58fc-a037-9c8cbe871ff2 | note | FREQUENCY: Each damaged pipe
f316ff77-088f-54f9-8d6c-509a158f0a46 | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedure. All repair procedures undertaken in accordance with Cl 701.25.
85035a6f-72a7-5066-a667-6e1843eb5a3a | note | REFERENCE DOCUMENTS: 701.31
2611a22f-0939-56af-bb8b-7c774077f61e | note | INSPECTION/TEST METHOD: Verify
7e2b5bec-2a4b-573e-bdc6-5750e6bd365c | note | RECORD OF CONFORMITY: ITP Signed
584e62a2-53e8-57ff-86b0-06a52bd08d9c | note | HP
11b50d49-21f1-568d-881d-8d4bd268b5d6 | note | RESPONSIBILITY: Engineer / Forman & Superintendent
90828d2b-3c8d-5c8d-9627-4f276ee7e18d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Testing & Completion
| checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
dbad5f66-c098-5868-a766-2bf995b479a4 | note | FREQUENCY: as required/requested
c2fa83ce-a3b3-5796-9855-09e3ec1fe4ed | note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort. Bedding material shall be compacted using a compaction plated to refusal.
bc0189a5-07bd-514d-8cf2-1d9b41883fe5 | note | REFERENCE DOCUMENTS: 701.2
0fb5ec72-ddc5-5ce9-9f13-eebe26561bdc | note | INSPECTION/TEST METHOD: Verify
adffaa68-68db-5486-8fa8-f7bad6151239 | note | RECORD OF CONFORMITY: Test Reports
7e7bd1c3-d9d3-59da-97aa-ecd2bc157a81 | note | TP
03bf7908-91b1-550b-97a9-6e835daba90f | note | RESPONSIBILITY: Project Engineer
f9e582f0-b4be-5f62-99d9-36faa60f2d64 | date | Date Completed:
| checkpoint | Final Inspection
b98dbd29-f630-5f49-8131-4658d328eb71 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
3d5d66a1-b4bb-5e25-a18e-2e5631e09d84 | textbox | Print Name:
e5d4f361-6c4c-548f-bac2-509ba2812c88 | textbox | Position:
88567b37-3040-5d68-9887-16d8d31f4fa0 | date | Date:
| checklist | ITP-008 - Line Marking | itp | ITP-008 - Line Marking |  | 8c982c53-5a98-4ef5-af26-7cb5171181c7
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Line marking Conformance
e51f6ec5-cf9e-5e50-a813-391afa791cf6 | note | FREQUENCY: Prior to commencing any activity
8a994ac8-4bc1-5fb8-8668-ea3e2a95e6a6 | note | ACCEPTANCE CRITERIA: Materials to be used conform with specification
74dcfb0e-e870-5e4b-b1c7-6b4fb62894d0 | note | REFERENCE DOCUMENTS: Review Materials Sheet
5ebf045a-0561-5f43-a366-1dae5e858d13 | note | INSPECTION/TEST METHOD: Visual inspection
f49d82a6-79aa-59ce-9415-15fe0e26c110 | note | RECORD OF CONFORMITY: ITP Signed
dbaf8dc4-0bc2-5e6b-bdc7-28d72c8071a5 | note | WP
231264ab-b6e0-51ca-a15b-67cfa11bee44 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
e47f9407-fcb3-517f-9719-51148b635aca | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
509c4975-efec-5a49-9cc2-242a9d947c10 | note | FREQUENCY: Prior to commencing any activity
89ce5401-b9f1-5263-8c8d-e3bf14c9c64e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
9040a301-b8b1-59ab-a6b3-ef9b5e7e90ed | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
368e01e0-628d-5d93-b7e7-9de9492b416f | note | INSPECTION/TEST METHOD: Visual inspection
67f5da2d-7fd3-5f88-a538-1bef1e22e6c2 | note | RECORD OF CONFORMITY: ITP Signed
5c9eb5d3-e83f-5690-b1f1-0eb7d8b1cf3f | note | WP
8f1eb9e5-4d05-5614-b6d3-f9618cd94de2 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
421c21dc-a65f-543b-94f4-7dc792d6a509 | date | Date Completed:
| checkpoint | 1.3 - Site preparation
b17d7348-79b2-5a9e-b4db-94009aea40d8 | note | FREQUENCY: Prior to commencing any activity
7f3511c0-99e3-52ae-9d0d-06315d044915 | note | ACCEPTANCE CRITERIA: Removal of any existing unsound,obsolete or redundant pavement markings. Removal of any foreign material or debris.
15dc6e2b-02e1-5d2c-a1f9-0c014c467796 | note | REFERENCE DOCUMENTS: 721.A06
deb874cc-a75f-5f11-b180-9893927d1cb7 | note | INSPECTION/TEST METHOD: Visual inspection
d4069913-7897-5f71-8276-66a539a4630c | note | RECORD OF CONFORMITY: ITP Signed
a61af16c-83ab-5e3b-9812-ab40b0ceb507 | note | WP
2a3873e2-596f-50ae-aa14-dc99b4d84f1d | note | RESPONSIBILITY: Project Engineer/ Site Foreman
430715e4-50e6-5127-a4cc-7fc088762055 | date | Date Completed:
| checkpoint | 1.4 - Set-out of Pavement Markings
59379889-dcbe-5a69-be68-c8376665b86c | note | FREQUENCY: Prior to commencing any activity
54eed798-defc-5d07-822d-6a50d630b9f9 | note | ACCEPTANCE CRITERIA: Pavement markings to set-out in accordance with IFC Drawings.
8499ca4f-285f-5de0-90ee-0b637b7a391d | note | REFERENCE DOCUMENTS: 721.A09
af0bd7c1-33e2-5d72-93cb-8ad2d31bdf9a | note | INSPECTION/TEST METHOD: Visual inspection
f86a7037-1111-5435-9748-06889d700836 | note | RECORD OF CONFORMITY: ITP Signed
445bb139-c224-5f96-b3a8-a352399ca60a | note | HP
aef3237a-acfb-5c3a-9aae-0e1e3f9abb1e | note | RESPONSIBILITY: Project Engineer/ Site Foreman
07633d12-cc21-57f7-9ca0-dfc89ca0db0e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Construction Works
| checkpoint | 2.2 - Line marking Installation
0412d20b-d3c0-5853-b6f4-00ade16df6aa | note | FREQUENCY: During Construction
9a9a0543-bb17-5a72-b275-60c0f3d832dd | note | ACCEPTANCE CRITERIA: Line marking installed as per IFC Drawings
21d83128-deb8-53c4-9c62-de11eaccc697 | note | REFERENCE DOCUMENTS: 7210
09c36c91-c0ff-5279-8eb6-366ec7e0b91f | note | INSPECTION/TEST METHOD: Visual inspection
f86ec83e-5fd9-5449-9c38-f73f35b9a60a | note | RECORD OF CONFORMITY: ITP Signed
63c3ce01-6f55-5091-bc3b-a1dcafdae156 | note | WP
651e1e3f-f735-5360-88e1-6a56301c5976 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
63131896-156e-5c82-9044-70928e6f7b24 | date | Date Completed:
| checkpoint | 2.3 - Glass bead Install
3a0ff434-bf4e-5f12-b97f-cbbfd626525d | note | FREQUENCY: During line marking works
4e04dff8-42a1-5155-ba42-fc7dc244d17d | note | ACCEPTANCE CRITERIA: Glass beads sprinkled/sprayed on to line marking while in a fluid state to ensure embedment. Glass beads to have uniform distribution
6a537998-9a69-50b8-9d36-7f97093a05bf | note | REFERENCE DOCUMENTS: 72100
f0d378d2-8fec-5bf9-999d-0cddfedb0cbb | note | INSPECTION/TEST METHOD: Visual inspection
b147462e-7b79-5e36-96ad-10dab7c5a128 | note | RECORD OF CONFORMITY: ITP Signed
60b5d14e-bbc2-55cd-a40f-af2f6137de4d | note | WP
c934d419-e4a9-5119-a9da-2a4f68156495 | note | RESPONSIBILITY: Project Engineer/ Superintendent
3649f08e-b35c-52c6-9aa8-2f293ba9142e | date | Date Completed:
| section | 3 - Completion
| checkpoint | 3.1 - Completion Inspection
459a4857-ab1e-5ae6-96b7-1f28992a4ac6 | note | FREQUENCY: Each lot
cccf0f1e-44af-56f9-8863-575e47edd7f1 | note | ACCEPTANCE CRITERIA: Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, streats, overlaps, unbeaded areas, tyre marks or other defects. Edges and cuts-offs shall be neat and sharp, and there shall be no visible run-off, overspray, dribbles,splash or spiliage on to the surrounding area, or on to parked or passing vehicles.
67d4336e-02d5-548b-b637-324a926660d6 | note | REFERENCE DOCUMENTS: 7210
310b93e9-0e9d-5208-b92a-403631158fe0 | note | INSPECTION/TEST METHOD: Visual inspection
85ffe2e8-07db-58f5-89fa-435f8973c45c | note | RECORD OF CONFORMITY: ITP Signed
fa88d637-e283-5c93-ba42-e1dff9cf9159 | note | WP
1eefb71e-49ed-521f-b3ee-93f1193e28f4 | note | RESPONSIBILITY: Project Engineer/ Superintendent
36f6dc6e-1bc1-5778-b1d2-c31669f7fed6 | date | Date Completed:
| checkpoint | Final Inspection
54e162ee-0319-56ad-a27c-277525bcbb8b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
67719fbb-2d6e-5218-ba9f-0a2a105f64e6 | textbox | Print Name:
14ae69af-3cb6-5fbb-8dfe-1790fb18e0b5 | textbox | Position:
cd546b46-eb38-5a7e-a8e8-bad56be8f349 | date | Date:
| checklist | ITP-015 - Construction of Concrete Paving | itp | ITP-015 - Construction of Concrete Paving |  | 8bff6586-4565-4448-b109-6a2cbd74875a
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
bd71d61d-0169-596e-aed3-20cb33792829 | note | FREQUENCY: Prior to commencing any activity
08f2f3cb-b9c6-54ab-992d-860175761592 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
ada3c414-aa30-5f8a-ab7e-6ca5217b181e | note | – using the correct and complete set of drawings
37adf05f-9d6e-5a82-b8fb-fb0d8803a0ec | note | – all drawings are the latest revision
d48131f1-ba8b-59ca-886e-46d51bfb8bd9 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
6741b0ca-1827-5ced-99a6-b94d658d40cb | note | INSPECTION/TEST METHOD: Visual inspection
cfde19e6-9687-5a7f-91ee-a426fef5aeb5 | note | RECORD OF CONFORMITY: ITP Signed
967f6c10-3fcc-5932-a7c5-ff58ba9419b0 | note | HP*
e3320f8d-7dd1-5b42-aa8a-94deb5789dbe | note | RESPONSIBILITY: Project Engineer/ Site Foreman
ff88e19d-c1cc-5644-9977-c15ffc70fe36 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
5b2e53b8-77d8-5552-bb56-94877c0cc09a | note | FREQUENCY: Prior to commencing any activity
f5403dbc-55e2-5d7c-a9f3-9196cf120d41 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
f01b3af5-ef6e-5a3f-a374-e15d7cd10cfb | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
5cb14d45-b517-50e8-a85e-810c598dbaa9 | note | INSPECTION/TEST METHOD: Visual inspection
f1f17270-e58d-579b-858e-42610aa07c0d | note | RECORD OF CONFORMITY: ITP Signed
39677397-9561-538c-aaa9-a0fd47ec0849 | note | HP*
01a6b871-e5a6-5f4c-8701-794a69320bf4 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
2a8866ee-8fee-5af2-8a1a-559fc911788d | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
13bc0da9-c263-5ba5-a45e-e2f6a0aca968 | note | FREQUENCY: Prior to start
c4b3c324-8b02-5e2c-bacf-3638137b18e4 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
2b4b531d-7157-5940-90a7-081d61a24851 | note | REFERENCE DOCUMENTS: 703.17
ebfdf7ad-576e-5475-a5ac-dc2ab14eaa7f | note | INSPECTION/TEST METHOD: Verify
47c29dbb-7280-51a5-af73-74735c580ed7 | note | RECORD OF CONFORMITY: ITP Signed
86cc25d8-1766-5403-8e5f-cc8816a2ecd4 | note | HP
526e2ff7-4066-503a-aa40-e8aa115a3d64 | note | RESPONSIBILITY: Project Engineer/ Superintendent
265adcd6-6a0a-5b8a-bf2b-af83cdc12dab | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Temporary Drainage Provisions
fea4ed5a-0f8c-5c9b-a6cd-76d6ae9ecd03 | note | FREQUENCY: If Required
1d08f1bb-595a-5409-86ab-ffb0719cb4b4 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
effa9cce-8ac9-5476-a1a1-3624c0d7aace | note | REFERENCE DOCUMENTS: Cl 703.18
d50d932d-5ddb-5f8c-996c-b1b2d43b35a9 | note | INSPECTION/TEST METHOD: Visual inspection
b89dd53e-ac78-5b4d-9e1a-7c1a49d8526b | note | RECORD OF CONFORMITY: ITP Signed
93a48324-c4d4-5d60-a379-f929ebfd5dac | note | WP
0a63f92e-fef7-5069-9ad9-28fe57174f9c | note | RESPONSIBILITY: Project Engineer/ Site Foreman
930bf079-8d14-526a-ba81-ec64bd986a14 | date | Date Completed:
| checkpoint | 2.3 - Bedding
2989fd24-aa2d-58f6-8b3f-d513dfec0053 | note | FREQUENCY: Each lot
ef9f111d-1415-5574-a74d-560c994e170e | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
f7badc7e-c94f-5b55-8f09-8dffc48a446b | note | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
7d593009-4110-5223-a691-6945cd53c700 | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
590b7927-fe70-5e10-9476-aa3f15c368b8 | note | REFERENCE DOCUMENTS: Cl 703.21
4203c89f-8f30-5c04-ba8e-d36b52e0bc08 | note | INSPECTION/TEST METHOD: Visual inspection
6d7a3225-a6b6-5691-b1fe-4c81d596ff52 | note | RECORD OF CONFORMITY: ITP Signed
b04d5f0c-3fd0-5d7c-b024-300eff0d75ba | note | WP
5d544a71-b5ae-52a0-b186-04f33a455b7b | note | RESPONSIBILITY: Project Engineer/ Superintendent
30695287-422a-53ba-b276-15e305b2e87c | date | Date Completed:
| checkpoint | 2.4 - Pre-concrete check
71b7fc6d-7aec-5607-9053-0c2a960695be | note | FREQUENCY: Each lot
ce13afe3-f877-5aca-bb6c-6429d212ee5d | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
51e4b6ba-43da-58c6-88f9-2e18153458e3 | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
6afe278c-9c74-5514-9174-c58d710d425a | note | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
51d80e42-dac8-59b8-a8bd-394e85a9da6f | note | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
9ce191b2-b568-5944-b4e1-cf05a2abcb1b | note | REFERENCE DOCUMENTS: Cl 703.08
ba10ed34-240f-57f2-80f0-e9b63b60cc4b | note | INSPECTION/TEST METHOD: Verify
a1b423a9-8c62-5c5c-a4d8-29519cba9412 | note | RECORD OF CONFORMITY: ITP Signed
ca7590df-73eb-5041-9a6e-f3e0389c35be | textbox | Ambient Temperature |  |  | °C
b774888c-9737-50f6-854f-cbe3272eb3a3 | textbox | Concrete Temperature |  |  | °C
2aaf5f4d-1c2d-558e-8160-6d804d6c383d | note | HP*/ WP
962c321e-7c44-5ae2-8b1a-3712b512246e | note | RESPONSIBILITY: Project Engineer/ Superintendent
664cc381-3c44-55e7-a86c-db692bd59f4a | date | Date Completed:
| checkpoint | 2.5 - Reinforcement
60d65895-49e5-5273-b9a9-0b1b0fdeb83b | note | FREQUENCY: Each Lot
35a232a7-98d0-5969-bf08-5969aa88aca7 | note | ACCEPTANCE CRITERIA: Steel reinforcement shall comply with the requirements of AS/NZS 4671, Minimum cover of 50mm
87cbe599-37d6-5745-9ea5-9624d0e6ccf9 | note | REFERENCE DOCUMENTS: AS/NZS 4671
3cb76b81-8d69-5683-ab6a-7ef2c0c2323f | note | INSPECTION/TEST METHOD: Visual inspection
0aa7a1c7-4237-5df9-8766-4f4c830687fe | note | RECORD OF CONFORMITY: ITP Signed
03f3b61f-a020-5487-a6ec-00909f1b1787 | note | IP
fd45f52f-01c5-587d-b931-a937adb1ca4d | note | RESPONSIBILITY: Project Engineer
7e57462a-54c9-5885-9660-aabba9319989 | date | Date Completed:
| checkpoint | 2.6 - Concrete Placement
47139ffe-bfda-5937-b7c1-6ed27fc7ea07 | note | FREQUENCY: Each lot
f01924d2-3e11-5388-80b1-25292cb57ccf | note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
8b9b3c84-f6a1-5626-9023-c7d640830f60 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl 703.23
290ce906-ac5a-5f8f-9db0-b1dfe90c43e5 | note | INSPECTION/TEST METHOD: Site Inspection
4c3a7b70-fc47-5887-96ed-cec322e00240 | note | RECORD OF CONFORMITY: ITP Signed
90df1799-f4ca-5486-8c8b-017114b72816 | note | IP
8568dbc4-4c12-53c8-926f-543e7eb5aebe | note | RESPONSIBILITY: Project Engineer
d6309be4-e159-5341-a5a9-e0c4063252c9 | date | Date Completed:
| checkpoint | 2.7 - Finish Surfaces
84b7d1b8-fe86-51f1-91de-80ea8cbec8b8 | note | FREQUENCY: Each Lot
98337e7b-f8fc-5e44-b615-8a59253ad682 | note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished. Concrete to have a neat appearance and uniform colour.
f868899a-ec97-5a3f-83ef-f2ca0b3bdef3 | note | REFERENCE DOCUMENTS: 703
911da2d0-4ead-5dce-902f-e48d1cd5ead2 | note | INSPECTION/TEST METHOD: Visual inspection
34106ae2-3e0a-5d08-a6c7-b7304e05b814 | note | RECORD OF CONFORMITY: ITP Signed
c0c8fe8d-a976-5831-9061-1317a3f20d44 | note | IP
473777f5-e521-52e2-9a4b-1eeaa72368e9 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
1f7cd936-bcf2-5a44-a9d1-eaea7119cd1f | date | Date Completed:
| checkpoint | 2.8 - Joints
044585fd-06ba-5f58-b6ba-57f36e5d4cae | note | FREQUENCY: Each joint
52c7a848-6ac4-5910-a25b-bacccd3ca964 | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
173b847f-dd5b-58ed-b43d-1d526778ebfc | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
ebc597b3-ccb8-5dfb-82bb-43dc6ba7e976 | note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
edc50600-ff53-5170-9e47-9a0e303fe305 | note | REFERENCE DOCUMENTS: 703.26
691f99a6-4d84-53ec-a7d1-bb419d2be38a | note | INSPECTION/TEST METHOD: Verify
286e5c9b-fc39-5e14-8887-51fbd4296897 | note | RECORD OF CONFORMITY: ITP Signed
1b2b6d0f-038d-56a4-82fc-b4f5e09ffaba | note | IP
2f6ec615-c87e-570a-aee9-5e93c2609861 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
bbf8206d-2dfe-549a-9ab6-5436cef69f2a | date | Date Completed:
| checkpoint | 2.9 - Backfilling
8708a91b-b7bb-50e9-b91e-056ec7025468 | note | FREQUENCY: Each Lot
458e2054-3751-52f6-bb7c-22eae0ca19f9 | note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
87f7458f-4a86-5242-b097-2180a9a8d2fe | note | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
563a5621-3bb7-5670-9d63-ab1b9224552f | note | ○ Layers shall not exceed 150mm compacted depth
4d4a9d43-dc86-5819-8182-316fee3d365d | note | REFERENCE DOCUMENTS: 703.29
af5cc883-4ef1-540f-a875-35be9c349208 | note | INSPECTION/TEST METHOD: Verify
3abdbc25-cb6d-5cb7-abdd-444b5a28b81b | note | RECORD OF CONFORMITY: ITP Signed
d2277e07-5501-5f99-95ff-698ef1433a01 | note | IP
b632a396-59ca-5acc-bd10-b6a90635f388 | note | RESPONSIBILITY: Project Engineer
35a0878f-4c50-532b-a5b0-d2e6b98bbbb7 | date | Date Completed:
| checkpoint | Final Inspection
845fa6fb-285b-5773-8dbc-92af6345dccf | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
3c10f214-1346-59ce-aa43-0a411c6d0261 | textbox | Print Name:
afc7d99c-a876-5b5f-9979-d31673a02662 | textbox | Position:
b9013239-dc03-51e1-ae5b-18859e044453 | date | Date:
| checklist | ITP-017 - Sealing Works - Asphalt Laying Works | itp | ITP-017 - Sealing Works - Asphalt Laying Works |  | 0609baa4-9cc1-4906-aa0d-44b7c23c2888
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Submission of Mix Design
42037825-3b74-588d-9305-59b8f6ce99e7 | note | FREQUENCY: Prior to commencing paving
09793862-d113-5880-8528-d594d05c7451 | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
f4a16217-bb2b-5f3a-8d73-e0cfa92c857a | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
d282dd9c-2f8b-5283-87f6-43ff2d021e90 | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
76b6b88a-8032-513c-b679-72ac5c3d0ba8 | note | RECORD OF CONFORMITY: VR approval, Completed ITP
a8ff7ecf-07ad-5a56-9905-78541fa7142f | note | HP
781dae48-d96c-5d1b-a190-da91efa7c7e5 | note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor/Superintendent
321c30ab-00aa-5834-acfa-a6649a5d7750 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Implementation of all measures and controls
a52f00ac-d58e-574b-a3ff-9f4009b2b8de | note | FREQUENCY: Prior to commencing any activity
df0ec0f2-4e71-5ade-9aa2-8f2db3a37953 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & WP
08781c95-e7af-502d-9327-1a2b104d8156 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
17f3da20-4213-58ec-8645-3238074bc9ce | note | INSPECTION/TEST METHOD: Visual Inspection
5cd201e0-9ce1-5214-83b8-58220cdafa36 | note | RECORD OF CONFORMITY: This ITP signed off
9a172c78-364a-5adf-8a0a-2f1eb8c8802f | note | HP*
2da4de7d-3fdc-54f5-a78b-7260952c2388 | note | RESPONSIBILITY: Site Engineer/Site Foreman
dce5c831-10ca-5173-ade7-5bcedbfdc26a | date | Date Completed:
| checkpoint | 1.3 - Site Inspection and Base Condition
fcc7be22-fe01-5c08-b463-aad2ffdbfc51 | note | FREQUENCY: Prior to commencing paving
9e2f2e45-3d3f-577e-aed8-4753a976d5f8 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
de08bc0a-cb66-5048-8c8a-b7b7189668f5 | note | REFERENCE DOCUMENTS: 407.14, AS2150 10.1, AS2150 10.3
966a5866-494b-5c8c-a112-7335580ced1c | note | INSPECTION/TEST METHOD: Visual Inspection
7b201112-dac7-54ab-b265-741450f5f223 | note | RECORD OF CONFORMITY: ITP Signed
c3108045-80c9-5de7-a45b-9bbb601ec06d | note | WP
11e55b01-5ea4-5a57-a9bf-4f5afaec90d1 | note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
196269c2-a376-593a-b418-89f8d55751b2 | date | Date Completed:
| checkpoint | 1.4 - Ambient Conditions for Placing
8e480b07-56f4-53b5-aabd-1254fad10ac2 | note | FREQUENCY: Prior to commencing paving
eed6264c-b48a-5bed-b9dc-adc3bf1c7cfa | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
ee04701f-ed40-50d0-a116-b1ec3324d7ec | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
42f162a7-885b-50d2-8ebd-841177a3d819 | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
591cc03e-1d3d-529c-963f-f7d2c810d5b3 | note | REFERENCE DOCUMENTS: 407.13
04172167-f742-5e67-bcd8-24297def7f26 | note | INSPECTION/TEST METHOD: Verify
d71f8a86-fd7f-5f9a-8f5b-fad431983941 | note | RECORD OF CONFORMITY: Thermometer
5d7e2786-66a0-5d5f-9f4f-5af7207e8535 | note | IP
98d1a15d-621c-590f-998d-8ba2ad3c654f | note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
117340db-86b4-5ba4-8759-92bb5e98266a | date | Date Completed:
| checkpoint | 1.5 - Planning of Joints
786b7686-94b7-566d-b258-5f336448c4dc | note | FREQUENCY: Prior to commencing paving
62673e84-8cad-5d1c-a6ef-253bd80a0823 | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
cdcbad1b-23af-59ee-80d5-5cf8175c8b24 | note | ○ Transverse Joints Offset from layer to layer by at least 2m
c06aa43c-ea15-569f-bff6-6ae3ef0554e3 | note | ○ Longitudinal Joints Offset from layer to layer by at least
7af1f427-3890-5b10-aa9e-6d118ebe94d6 | note | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
24b56500-009e-5270-b085-2815951c915f | note | REFERENCE DOCUMENTS: 407.17 (b) & (c) Pavement Drawings
139b98c3-1e62-5d7f-b7a2-38246b60b821 | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
82c9f1a5-9fc6-54c9-9f6d-f53a112f4b04 | note | RECORD OF CONFORMITY: Paving Plan
a9d0c54a-799a-5a1f-86d8-e5d929a886e2 | note | WP
2fe65da1-ff8b-547c-8242-c6f11bb3ca38 | note | RESPONSIBILITY: Project Engineer/Asphalt Supervisor
f54fda83-177f-50f4-9410-c7da88ee9549 | date | Date Completed:
| section | 2 - Asphalt Placement works
| checkpoint | 2.1 - Commencement of Placing
56bccd24-fce1-5427-9cdf-0c215f60cf87 | note | FREQUENCY: Prior to commencing Paving
7d0e3e67-4c50-5e12-b14d-769b634df2a2 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
3110ee10-db09-5663-8bcd-19d3e30137df | note | REFERENCE DOCUMENTS: 407.18
3064bde4-e238-5b8d-894b-24e3406b7428 | note | INSPECTION/TEST METHOD: Visual Inspection
7f9f3eea-c80d-5d0f-83f8-a0335aae1af4 | note | RECORD OF CONFORMITY: ITP Signed
aac785e3-1246-5088-b8eb-cd83b0e40d56 | note | HP
935c3a37-652d-5513-a86f-3efeadf3db54 | note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor/Superintendent
e67babe9-5f31-5949-abbf-c8adbad297ef | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Delivery of Mix
f31e83e3-0c7a-5023-85dd-c17654bc5700 | note | FREQUENCY: Each load
7cf50ace-45f5-54c5-8bc6-5bb689c1e2df | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
827657b3-c704-5bcf-a251-f7fdcd4a9f61 | note | REFERENCE DOCUMENTS: 407.16 Table 407.081
20ee3cbd-cad0-564a-80b8-ca92ed66906d | note | INSPECTION/TEST METHOD: Visual Inspection
0a0d5c78-b587-5730-b110-d3664cc64692 | note | RECORD OF CONFORMITY: Delivery Docket
e171c0a9-9d0d-5b03-9325-61534f438f5d | note | WP
51b41786-d081-5ed1-9a17-311c42a5961d | note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
ef064ea4-3a5c-533d-a41e-fde9d95587f9 | date | Date Completed:
| checkpoint | 2.3 - Traceability
e2f26a1c-9267-57ea-b969-76e38355b4cb | note | FREQUENCY: Each lot
0f807fa7-21a6-5e7b-9859-601cd789ed37 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
967d380e-eefe-5f09-ba9c-6129cf356829 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
4af58515-67b7-53f2-94cb-263c3110ab97 | note | INSPECTION/TEST METHOD: Verify
540ab8f2-ca69-5bb5-82d5-e6adf125898b | note | RECORD OF CONFORMITY: Daily Lot Record
d41d2531-5cf4-50b4-b5c7-55a4f5f046f5 | note | IP
7c9adbd6-6b2e-5e8f-b245-859eb3a0ee63 | note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
32abc9ea-9b84-5f11-90c5-32c076cc5d2a | date | Date Completed:
| checkpoint | 2.4 - Layer Thickness and Level Control
e9db2eb9-3560-593f-9c08-e9be6ea8db5f | note | FREQUENCY: Regularly during paving
b84f53e7-69a3-5f97-a80e-ba9c58f115ad | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
c3c6e1e0-a615-595f-88c1-429b799cd3ca | note | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
b560325f-2b52-52b8-a288-d9eb9e2213c1 | note | INSPECTION/TEST METHOD: Verify
4555c9f3-d539-527a-b48b-f327f0afe6f9 | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
ade563c6-d346-5b52-895a-a2e7cd42c5ea | note | WP
61b6cffa-4744-5a8c-8da6-60f366fa78bc | note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
c97b5882-5698-5815-9067-954a471b3a2c | date | Date Completed:
| checkpoint | 2.5 - Surface Finish of Wearing Course
748775d3-2ad1-57c4-9de4-1c9420614d0e | note | FREQUENCY: During paving and after final roll
3e98d9ad-75f3-56d4-b7e0-f22284e6b4b3 | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
85fd6a30-ba4c-571e-a0e3-9bdf71687e3f | note | REFERENCE DOCUMENTS: 407.23 (a)(i)
8a4d07d3-3989-5974-bf11-d7f795f50672 | note | INSPECTION/TEST METHOD: Visual Inspection
1d064589-7c4d-57d6-8476-7d63c7baaa5a | note | RECORD OF CONFORMITY: ITP Signed
b2cc8fff-c314-53c0-89a9-ffb5e3a2cf6b | note | WP
8fdd4ef1-e176-5fdb-b85b-3a4354f3d536 | note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
c715591d-e547-5c34-b602-c9bb0dd1444e | date | Date Completed:
| checkpoint | 2.6 - Kerb and Channel
9d0119d2-d02c-5407-aef7-29c75e0bab07 | note | FREQUENCY: During paving and after final roll
a6e36f2d-2147-5136-bbc0-dd1cafb2bc87 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
5e50e4a1-ae49-554a-9d5d-ea3f0940d9c1 | note | REFERENCE DOCUMENTS: 407.23 (a)(ii)
c1ede7c9-3787-560f-8045-69f851b04b10 | note | INSPECTION/TEST METHOD: Visual Inspection
14c501fb-697f-51b0-9f5e-540eea5d3bbf | note | RECORD OF CONFORMITY: ITP Signed
1d839173-941f-51ae-8b4a-7481067db0e7 | note | WP
432e2ccb-77e2-5b06-8435-a3ba78f36e07 | note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
edcf4168-8cc7-5731-b9a7-760de4a66922 | date | Date Completed:
| checkpoint | 2.7 - Alignment of layers not placed against concrete edge
d41d8f76-8e0f-5bc0-91ac-a5e183614fb6 | note | FREQUENCY: During paving and at completion of work
88da41f7-76f2-53a8-9248-4865204a019e | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
eed31010-8761-5c70-8799-bd221128ae56 | note | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
32abc3ab-8081-5eb4-bd0e-f5048e8dfdc0 | note | REFERENCE DOCUMENTS: 407.23 (a)(iv) Drawings
16cd7e51-d1f3-5c74-b30f-454d380b4461 | note | INSPECTION/TEST METHOD: Visual Inspection
ebb64f7b-f281-58d0-96d7-ebdb0395cd98 | note | RECORD OF CONFORMITY: ITP Signed
179023f0-d1e6-5efc-9833-14b058712c9b | note | IP
dcd1318f-87a6-56db-82c0-c9164a47e11c | note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
55788eee-1622-5934-8a5a-d8bdd82e595f | date | Date Completed:
| section | 3 - Testing
| checkpoint | 3.1 - Compaction
97e08fc5-1880-5ab1-98f5-d38c538cb2ff | note | FREQUENCY: Per Lot
789f174e-2f19-5676-ab9f-02bdf4520693 | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
45cb841f-d5d2-59e4-b386-aa443728fae6 | note | ○ 94.0% or greater Accept lot
a33b2d7a-205b-5623-be37-faa5429cbbc0 | note | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
f5f4200f-9db5-5cda-8170-49c8e962dbf7 | note | For layers ≥50mm, if characteristic thickness is:
b4d58f70-fcd8-52c8-9528-49f8310ac73c | note | ○ 96.0% or greater Accept lot
42dc58ce-37e9-5e83-8b96-325627d75990 | note | ○ 91.0% to 95.9% Lot may be accepted at reduced rate
7f1dc38f-763d-5466-b1bc-225ab1608f02 | note | REFERENCE DOCUMENTS: Table 407.221
aa3e2506-b494-590e-ad7d-e6f584ed2d4d | note | INSPECTION/TEST METHOD: Verify
1deaac1e-190d-5dc7-ba15-6d47a2638dff | note | RECORD OF CONFORMITY: Test Report
268f2ae2-ea7d-56a5-a7d1-4fb154ebc22a | note | TP
b31c06a0-55c6-50a5-b120-2efb4ef834dc | note | RESPONSIBILITY: Site Engineer/FH Lab Technician
1a2d4405-bcb7-5a8f-b270-6947b6122b2a | date | Date Completed:
| checkpoint | 3.2 - Level Conformance
f07b2775-dcab-5f56-8c94-afd3a8c3185a | note | FREQUENCY: Per Lot
802e429d-3512-54f6-a9ab-566d0ecd0f2d | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm
a689f754-6004-5373-a645-b9ee9608cb37 | note | REFERENCE DOCUMENTS: Table 407.232
761d5054-fd48-5638-b3bf-42a83e39626e | note | INSPECTION/TEST METHOD: String Sheet
35fc3e83-1ccc-59c3-a390-34575c852b8a | note | RECORD OF CONFORMITY: Survey Conformance
da3c40f3-8ae1-5f2e-9665-1f70e1effd83 | note | SCP
4c74d3ed-05e6-5d88-96b1-3786c8c604b7 | note | RESPONSIBILITY: Site Engineer/Supervisor
a2ffae04-a17f-5e96-ba46-1249921162f2 | date | Date Completed:
| checkpoint | Final Inspection
a0e44491-b076-5a99-bc80-4daf27107809 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
9a7808ec-b2cf-564e-a22d-c35633705d81 | textbox | Print Name:
bd59a3b4-e63f-50ac-9582-ecb75adc7032 | textbox | Position:
49a37ace-c1f9-503f-a98c-ce1c14e0fa13 | date | Date:
| checklist | ITP-031 - Aspahlt Wombat Crossing | itp | ITP-031 - Aspahlt Wombat Crossing |  | 1ed6d19e-2be3-4c9c-b8e4-46a80a614a52
| section | 1 - Preliminary works
| checkpoint | 1.1 - Submission of Mix Design
415aac38-908f-5095-933e-42203d18dd47 | note | FREQUENCY: Prior to commencing paving
fd05ac17-b73e-55bf-ba21-df10ae0235d0 | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
d3a62bc2-9c1e-5f67-8a34-4a97e5f079d3 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
35273299-746b-5c86-a9dc-b273dae92d2e | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
639f6051-4d1b-5bc9-b160-ddd61ddaa17a | note | RECORD OF CONFORMITY: VR approval, Completed ITP
1344d882-45c7-5d82-b172-5528f7d258be | note | HP
cbf536b8-cbbf-5ca3-b16e-c85230e712af | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
45f88d4a-4733-50ea-9e33-f1bbf8bed85d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Check for correct documentation
e57b7826-2ee3-5fd5-b560-bc87d18ca3ea | note | FREQUENCY: Prior to commencing any activity
8adba076-c3d6-5cc6-be42-1598b33ba053 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
76fd6434-1890-5536-8179-ac91fc4a435d | note | – using the correct and complete set of drawings
9cc642f1-f2c2-59fe-8b82-2d58d8300b08 | note | – all drawings are the latest revision
f889b8ae-4d21-5eca-9a7b-008651c94b77 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
f015cdc1-c7d8-5424-b5c1-f5fd68328250 | note | INSPECTION/TEST METHOD: Visual inspection
11e8ee6a-f99d-5aec-9e21-97e61f1da350 | note | RECORD OF CONFORMITY: This ITP signed off
f748c208-8d82-5e74-8e6e-98d7f380acfb | note | HP*
acc170fa-67cc-5191-993f-8bfad8193e8f | note | RESPONSIBILITY: Project Engineer / Site Foreman
034509c4-3333-50db-b3ec-ce7bf0d0392b | date | Date Completed:
| checkpoint | 1.3 - Implementation of all measures and controls
5d671a08-44ad-5b64-824b-3f4bbeecc393 | note | FREQUENCY: Prior to commencing any activity
e6beeaae-09e0-514e-ad7a-38636c874cb0 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & WP
960eb691-c90d-57d6-b94b-e565d4cc9ef7 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
7440c3b9-1bbd-5c31-a098-ce429a8862b5 | note | INSPECTION/TEST METHOD: Visual Inspection
304e5c7a-c974-54df-acc8-e10fd763a925 | note | RECORD OF CONFORMITY: This ITP signed off
92a3cd2c-12be-5ba9-aaf9-07fb4d62c697 | note | HP*
cf27c296-fcd1-5416-8af4-f29dda3fb8ee | note | RESPONSIBILITY: Site Engineer / Site Foreman
c9d98c06-c533-5026-a21b-9897437f38d2 | date | Date Completed:
| checkpoint | 1.4 - Site Inspection and Base Condition
73843ae8-a9e8-5a7b-aad5-723eadb74615 | note | FREQUENCY: Prior to commencing paving
9451d9c9-ebdf-532f-8bc5-e1d6665ea22c | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
8675c2c2-c65b-5890-b455-d693dc287ea9 | note | REFERENCE DOCUMENTS: 407.14 AS2150 10.1, AS2150 10.3
9cefe7d6-40ea-5574-b8e8-8d7a95eb1aff | note | INSPECTION/TEST METHOD: Visual Inspection
b3af89ac-50c7-5800-9240-8f9a12cf583c | note | RECORD OF CONFORMITY: ITP Signed
2a296fde-4c46-5d4e-9d98-8e9c00ffd36a | note | WP
c33d1551-1837-5c17-bcf7-c2b275c6fe32 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
a8f0c3fb-3367-5b43-9de9-04fed00e9322 | date | Date Completed:
| checkpoint | 1.5 - Ambient Conditions for Placing
07e3affc-22c0-55fb-bfe2-725dff5891dd | note | FREQUENCY: Prior to commencing paving
3951aacb-def1-57f7-84d4-556d36a75172 | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
41fd7acc-d123-5b06-bc88-92f2d2e6e50e | note | ○ Base & Intermediate Courses: 5°C for conventional binders or
08362a72-132c-56a2-825a-d08db0be49ea | note | ○ 10°C for PMBs & Class 600
52610ad5-a712-5954-a8da-641a00eb8a75 | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
95752c82-2e8d-589d-b759-ef6b9d1e637b | note | REFERENCE DOCUMENTS: 407.13
f17b611d-23e0-548a-a225-ecf7c0e0aa3d | note | INSPECTION/TEST METHOD: Verify
c8f2c76f-c85b-506f-9b07-0ccc2835f975 | note | RECORD OF CONFORMITY: Thermometer
d6723b83-f6a1-51c5-a605-e0cf623f4b12 | note | IP
66124e20-4dba-505c-aead-2ce2655a9d2d | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
1113f851-7346-5406-a722-e62b148e7a2f | date | Date Completed:
| checkpoint | 1.6 - Planning of Joints
8304f302-4a32-512c-bfbf-1f9ee8de1c9b | note | FREQUENCY: Prior to commencing paving
1c88932a-9f9f-59e3-8f1e-b27fd7464938 | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
f07d1581-a517-5793-8c23-0b84c1257035 | note | ○ Transverse Joints Offset from layer to layer by at least 2m
dc25c11b-fc1f-5275-ac91-3d5db4db9691 | note | ○ Longitudinal Joints Offset from layer to layer by at least
ce612c68-c8f7-5937-95c7-2c678eafbde2 | note | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
8d29b796-6102-5f2e-a262-8fe668940405 | note | REFERENCE DOCUMENTS: 407.17 (b) & (c) Pavement Drawings
d1d9c2b2-2cbd-501b-9c4c-483c5d094bef | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
9b95c499-f667-505c-99b5-a85967a8c470 | note | RECORD OF CONFORMITY: Paving Plan
c0e7e668-f9e0-5f8e-b93c-c1b3ea085182 | note | WP
8d9eae85-2e50-5130-b7da-ac2b1a9f3557 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
3eef6e9a-331d-5ffd-9da5-8d7d3846e3e7 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Cut Chase out
05df85d2-4dc0-5133-9eed-804884bd7982 | note | FREQUENCY: Prior to commencing paving
aac8609d-2be3-5213-b3da-8c494b9d08c8 | note | ACCEPTANCE CRITERIA: Cut Chase out of existing pavement to a depth equil to wearing course + regulation course. Slope of chase out should not be greater than 1 in 20
e59ffa8e-6adc-54d1-acf5-37a9518e26ac | note | REFERENCE DOCUMENTS: Design Drawings
307aa93d-ddf8-5ea4-814e-db964a886648 | note | INSPECTION/TEST METHOD: Visual inspections / Measurements
e1b20e82-9f29-5466-9a9c-4fa8763ee13a | note | RECORD OF CONFORMITY: ITP Signed
f1188a1b-c96f-525c-bb81-75407c968c1f | note | WP
1225f9ad-41a6-59f3-b155-4f0fc2518f8a | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
e5d914dd-04fd-5439-bda8-b343a751390d | date | Date Completed:
| checkpoint | 2.2 - Commencement of Placing
faa252ab-2d23-5ebb-b06a-061f26c1ecf1 | note | FREQUENCY: Prior to commencing Paving
08bd5843-3e4d-55b8-bf55-1a5e9290b693 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
e369ded6-1e5e-5490-bc6a-179f94cc7c2a | note | REFERENCE DOCUMENTS: 407.18
c0a0f337-c99b-5b97-9fd0-3deaa4f7c2de | note | INSPECTION/TEST METHOD: Visual Inspection
9427bdb3-d90a-563a-bd75-81c8f48b1e12 | note | RECORD OF CONFORMITY: ITP Signed
a715c0f9-94b1-58b3-b904-ca79377c70f4 | note | HP
93ae3c89-0c1a-5a95-89fb-dcb27ac43897 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
fec03fb0-3269-5e80-a611-08354697bb18 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Delivery of Mix
bf089f80-c131-54a3-a77c-e924eebb0b35 | note | FREQUENCY: Each load
7bef9a36-0852-5c77-9023-d8c1514bc333 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
18c2805d-8034-5d0e-8ebe-1c951eea5044 | note | REFERENCE DOCUMENTS: 407.16 Table 407.081
638483f7-368a-5f3d-8636-d27b0a3b5fc0 | note | INSPECTION/TEST METHOD: Visual Inspection
a1cf8be7-d3f0-5669-a24d-f4bd2da90985 | note | RECORD OF CONFORMITY: Delivery Docket
7855d290-75e2-5d96-8992-7e663a4c8052 | note | WP
130949ff-33f7-5095-9c9c-3b224aa4e4b0 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
67df2de3-34cd-5ec9-9d21-8d12ae812fae | date | Date Completed:
| checkpoint | 2.5 - Layer Thickness and Level Control
4fd227b6-e60b-54a5-a44b-a8248590f63b | note | FREQUENCY: Regularly during paving
c1d7d15a-58c7-5a28-8d84-4a9527b27500 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
e5886089-b3c3-51b9-a204-ab579d1c98b2 | note | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
0684c3ff-d7cb-5971-8f96-eff4722b96a9 | note | INSPECTION/TEST METHOD: Verify
a1864438-0c3e-5a00-b81d-5ecdff62f885 | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
e8dae008-b7ed-5c0e-988f-08c267bc75f5 | note | WP
04c310c0-34cf-575f-b56f-d66bbb46fe19 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
2b7256c7-7a47-5629-9fdb-a3e85f58a7df | date | Date Completed:
| checkpoint | 2.6 - Surface Finish of Wearing Course
1d960389-74e7-5f5f-b1c6-33c30568b351 | note | FREQUENCY: During paving and after final roll
d1e956a6-0e5c-513d-8680-7fb7e69c861d | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
57e16737-16cc-5248-9966-4377d0de83c7 | note | REFERENCE DOCUMENTS: 407.23 (a)(i)
e6ada602-0c43-59d5-a18e-d619f1f97022 | note | INSPECTION/TEST METHOD: Visual Inspection
863f8f72-e9e0-585f-a47e-7b1c3fdbeb71 | note | RECORD OF CONFORMITY: ITP Signed
e550705f-0e34-50f8-8875-8ada51457c7a | note | WP
0f165e3e-8b2b-5a05-b7f9-5d7ecc7e323d | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
706c3484-70f6-5c0f-b325-00d9100bea6b | date | Date Completed:
| checkpoint | 2.7 - Kerb and Channel
734fe189-9f1a-5579-8426-b9a94dbbe9c7 | note | FREQUENCY: During paving and after final roll
0ba73938-101b-540f-bcd7-64aeed102a54 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
3b3672d7-f3da-5259-af07-5bf41111337a | note | REFERENCE DOCUMENTS: 407.23 (a)(ii)
f32ea50f-35d9-5c63-91e4-5a644821af82 | note | INSPECTION/TEST METHOD: Visual Inspection
275a2c19-751c-5202-a860-4ecc9d4b79be | note | RECORD OF CONFORMITY: ITP Signed
f3ea90bd-f014-5afc-bbec-d3b167f74d1d | note | WP
0c64cb54-8ac5-5168-8367-1a6e8891efec | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
23781b39-2b78-5782-9170-3fb78a6a531a | date | Date Completed:
| checkpoint | 2.8 - Alignment of layers not placed against concrete edge
0eb2d204-b743-5470-8902-059bff32fb5a | note | FREQUENCY: During paving and at completion of work
d45bdf70-a5da-5755-bee3-b41d1d4e8a87 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line. The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
88b2b8c0-1d9c-5a4f-a4f8-f81de3ddb613 | note | REFERENCE DOCUMENTS: 407.23 (a)(iv) Drawings
622259a0-01cb-5131-b90d-c3e515dc7513 | note | INSPECTION/TEST METHOD: Visual Inspection
785f8ca2-7db4-5698-93cb-8e22990a3b38 | note | RECORD OF CONFORMITY: ITP Signed
ab2ff73d-e6a8-5fa7-8e4e-1836478dda66 | note | IP
3cb35e05-0911-5360-9fe1-9c0d7f83e118 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
4e20bddd-d1d5-5034-bbc0-b28c477c32dc | date | Date Completed:
| section | 3 - Testing
| checkpoint | 3.1 - Compaction
9309b2f0-1442-5605-a106-5f6c488446c9 | note | FREQUENCY: Per Lot
1508ec2a-59f4-5c15-9fc6-d9397c9f2403 | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
c027b290-3d83-514c-b4f4-67dcb7685c1b | note | ○ 94.0% or greater Accept lot
35653f8b-2313-50a6-9145-36f4b8e44709 | note | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
cb4d1572-f258-557a-ac53-4c7494acbb39 | note | For layers ≥50mm, if characteristic thickness is:
71bcf2c9-69ce-527f-b2d9-51ace570bc69 | note | ○ 96.0% or greater Accept lot
38d775cd-be7e-5142-ae5e-9f8523b32db5 | note | ○ 91.0% to 95.9% Lot may be accepted at reduced rate
a633f279-32ec-59e6-b038-f159f915ca3d | note | REFERENCE DOCUMENTS: Table 407.221
cc5d8515-d2dd-5cd9-8509-9f2178481eb2 | note | INSPECTION/TEST METHOD: Verify
7bfa1842-94fa-5afe-982a-8122b54cd96f | note | RECORD OF CONFORMITY: Test Report
818c0005-e0c9-5495-8ba2-fd0004753ca2 | note | TP
457f6624-80e3-5250-8557-c7730482a8d4 | note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
957d061b-eec7-5cd1-becc-c336aa5ce417 | date | Date Completed:
| checkpoint | 3.2 - Level Conformance
0db6c88e-3728-5abe-ae47-c2ba028b10b4 | note | FREQUENCY: Per 4,000m2 at completion of work
0f8172a4-59a8-5752-82b9-c6ab515befcc | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
983e128b-05ec-5991-93d8-5e76b2d50289 | note | REFERENCE DOCUMENTS: Table 407.232
27c35f75-312e-5a7d-9270-ceb9600cadd1 | note | INSPECTION/TEST METHOD: Survey by VicRoads Section 173
4cf25209-7172-5a73-93e8-a93932f4ccd3 | note | RECORD OF CONFORMITY: Survey Conformance
f033d004-1d0a-5002-8ad4-85ff7ec2e8b7 | note | SCP
de3dd6a8-0ca4-532d-947b-3a9e55cc824b | note | RESPONSIBILITY: Site Engineer/ Surveyor
d1de0663-6a88-5e2c-9d10-8b1925634b36 | date | Date Completed:
| checkpoint | Final Inspection
02e1e831-f23c-59cc-94f0-7569684441fb | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
3f432b89-0c5a-5c9a-8e07-cca8fe83bd4b | textbox | Print Name:
958c0fb0-376d-5347-a152-9e3d50cd8f8e | textbox | Position:
38c87e2a-54d4-5f5f-8ae3-22aa3e81645f | date | Date:
| checklist | ITP-032 - Construction of Kerb & Channel | itp | ITP-032 - Construction of Kerb & Channel |  | 4528b5b5-729f-4dd1-9b3a-8dc2bbb3a27a
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
8cd86970-efbe-5295-8520-30c71f82930b | note | FREQUENCY: Prior to commencing any activity
10aeeff1-0b6c-5344-88b6-ff62ff4761cb | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
6cd2db7e-55c9-5ff4-aa2e-c131d4c355d5 | note | – using the correct and complete set of drawings
f39804b0-e191-50be-b77a-f008d585f9dc | note | – all drawings are the latest revision
39c1f5c0-1eb0-50c0-8d08-48ad10855231 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
eab79161-1563-576d-8c6c-793585a12227 | note | INSPECTION/TEST METHOD: Visual inspection
92fe6767-58fc-5559-83ec-836473e31042 | note | RECORD OF CONFORMITY: ITP Signed
1c64d760-ac7e-5a7e-abf6-ad1eb842fa2d | note | HP*
f788abf8-ec59-5ca4-92c3-c0ed0006d56e | note | RESPONSIBILITY: Project Engineer/ Site Foreman
3681c104-9e75-5d3d-97d2-75429a6f15ba | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
4ae4ce6d-e8cc-5800-9637-892849565bda | note | FREQUENCY: Prior to commencing any activity
a8e0f0fd-6522-55d2-82e4-24ef0c9ae6aa | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
a7ab522d-d1c8-5981-b20b-7df0f3dd9555 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
8791567c-a0de-5c9b-b5aa-8a52ee13c2bc | note | INSPECTION/TEST METHOD: Visual inspection
4f606151-b63e-51f6-b759-624c40e1dd4b | note | RECORD OF CONFORMITY: ITP Signed
b42f2e8e-4405-58b0-b791-fafb4e3c6df9 | note | HP*
86749114-45db-5532-af48-136763b1447c | note | RESPONSIBILITY: Project Engineer/ Site Foreman
ab762529-837b-5634-bf97-0410c50a27c3 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
779fb46b-5ecb-5d81-81eb-dee8638b85e4 | note | FREQUENCY: Prior to start
6c8bd877-937b-5fbd-8306-901af297885f | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
3da6c46e-53ea-596d-bfe0-09d464bf5673 | note | REFERENCE DOCUMENTS: 703.17
7db87f66-2327-528c-80d8-4f4ce6224fd9 | note | INSPECTION/TEST METHOD: Verify
a58d1e14-8f24-5c4b-89ea-16fde53d6fbe | note | RECORD OF CONFORMITY: ITP Signed
4c47a069-ec61-5d4e-b725-5199a13cc6a4 | note | HP
73770d5a-51e7-59c1-b866-eb178f8b3b00 | note | RESPONSIBILITY: Project Engineer/ Superintendent
6af4c888-f52b-5d54-a994-7e5e40075b20 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Temporary Drainage Provisions
dd2772db-8914-5ee8-966f-b3343ef9dfcd | note | FREQUENCY: If Required
58d40271-690a-5563-976b-2ab4d31fc6ba | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
5828df72-8b8a-59bf-8d58-37100f361435 | note | REFERENCE DOCUMENTS: Cl 703.18
8555873b-3bd1-5dd5-b143-8ed36c105d3f | note | INSPECTION/TEST METHOD: Visual inspection
bfe7881f-e7ad-5943-894a-0aa61e7d304b | note | RECORD OF CONFORMITY: ITP Signed
85d11c41-b5c8-5e65-ace1-a5992bbc42cc | note | WP
13ed4b56-32c1-5da0-80d7-ebb2bf5ce703 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
2a6e7fc6-6e06-5016-ad7d-51db0f859857 | date | Date Completed:
| checkpoint | 2.3 - Bedding
7689b144-f843-5845-9331-6b317a197311 | note | FREQUENCY: Each lot
664f209b-fa76-5022-8125-47a02256338b | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
61cd794b-1d4b-56cc-99ce-cb3139445d58 | note | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
d158a0fa-2e37-56df-9d48-1bc0e33fc5db | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
b2f24de2-4029-564a-bd89-de241be73651 | note | REFERENCE DOCUMENTS: Cl 703.21
f39742da-37f5-5834-8553-bc3747c286f3 | note | INSPECTION/TEST METHOD: Visual inspection
e31814ac-7f7e-53b7-8c0d-e45b1cd02044 | note | RECORD OF CONFORMITY: ITP Signed
c94c9cbd-503e-5156-837a-5adf9238db5b | note | WP
167af16e-9fb7-596c-90e1-080a378b965e | note | RESPONSIBILITY: Project Engineer/ Superintendent
5cc722c4-9ff1-5171-8b42-db590f6821cd | date | Date Completed:
| checkpoint | 2.4 - Pre-concrete check
9533c182-dbcb-56f3-815f-4a7e526cae6b | note | FREQUENCY: Each lot
5bff7d5e-2a48-5b7b-83f1-209a176336f9 | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
f62ab0ec-fe2e-5f5a-ace3-a56925b5457e | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
df1c5c82-4fd8-5a50-b3f3-bcb99b465da2 | note | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
1a53ed08-d8d8-5ff2-b709-3365cb283984 | note | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
0b6dcf76-894f-5e39-bad2-b545d1b60cd2 | note | REFERENCE DOCUMENTS: Cl 703.08
8bee8158-cd91-5950-89da-b9a80b1b77d7 | note | INSPECTION/TEST METHOD: Verify
bcf793b9-40ef-59f1-bb55-86d171204f60 | note | RECORD OF CONFORMITY: ITP Signed
430f0d0e-eb55-5b03-a6df-32b549d146ef | textbox | Ambient Temperature |  |  | °C
dcf12436-8f07-5877-9068-23fbe1cf7c0f | textbox | Concrete Temperature |  |  | °C
e8ac939d-bbd8-51b1-a6b3-de4f19f1ee12 | note | HP
f4f6b1ab-86fa-5ac5-a000-794d580f9d07 | note | RESPONSIBILITY: Project Engineer/ Superintendent
cb5a7115-8aa5-5232-af7c-b1b73cde18aa | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Concrete Placement
f118e8ab-cd4e-5e6c-9424-cdfb0876869d | note | FREQUENCY: Each lot
d2c90e38-bf90-5a93-a7e3-4e6208d6ef91 | note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
280bea29-9dd2-5b90-9ee2-7467f5013016 | note | REFERENCE DOCUMENTS: VicRoads Spec Cl 703.23
d2ff7ad4-239b-55a8-8e76-d3c9e6c91496 | note | INSPECTION/TEST METHOD: Site Inspection
7ffff856-5cab-5a22-b7ef-7453a0ee0eb8 | note | RECORD OF CONFORMITY: ITP Signed
1a86af70-6b80-5c92-a62d-d42f5fdb623b | note | IP
c06eb44b-bf10-5682-8501-108f425d5594 | note | RESPONSIBILITY: Project Engineer
3870b58c-e4d2-5e84-8e07-d72b0c0d7e78 | date | Date Completed:
| checkpoint | 2.6 - Finish Surfaces
40f3f1b6-a8ee-5375-b800-d79b6cc8ba9a | note | FREQUENCY: Each Lot
585ec63f-fda4-5961-bf9d-2fdf7067c3b3 | note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished. Concrete to have a neat appearance and uniform colour
3699b0e3-8c56-5bf6-b3ee-b72d8087df43 | note | REFERENCE DOCUMENTS: 703.25
9f610488-0251-5fa8-bfe9-f1ec2afd3296 | note | INSPECTION/TEST METHOD: Visual inspection
aadcb40e-7a8b-537f-b18a-ab2c19db19cb | note | RECORD OF CONFORMITY: ITP Signed
c6011f8c-ae78-5fd6-98e6-eacfd44a52ca | note | IP
5d165158-246e-5393-8a1f-04b0d6ef59f2 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
4a1bce47-84da-5d52-8e8d-ad263dd1bb5d | date | Date Completed:
| checkpoint | 2.7 - Joints
1324037e-5adf-50c4-bce5-d538dc773b3b | note | FREQUENCY: Each joint
a29a5a91-dac8-5ab9-9e78-c759779c0f08 | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
3c58e5e1-2387-54ca-923a-5482889a3976 | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
17ae19e7-59a6-58d7-8ea0-22094739c6c9 | note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
6b6453c9-0af4-524a-87d1-994571a216ad | note | REFERENCE DOCUMENTS: 703
e1c147d1-6f5b-590e-b222-1caaa53790d4 | note | INSPECTION/TEST METHOD: Verify
a2586c68-944d-5eeb-af37-56a9d0e4130b | note | RECORD OF CONFORMITY: ITP Signed
c0452f07-b53c-536a-809d-a28cb1c840dc | note | IP
932113fb-ebc5-5615-abdf-3a772508fcb0 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
13b6d89f-dd44-5de1-bce7-f583e63954c2 | date | Date Completed:
| checkpoint | 2.8 - Backfilling
e06cda44-a059-5df6-b0bd-cc0459884b00 | note | FREQUENCY: Each Lot
2f8aeb81-86ed-5665-93ec-434285d40dd9 | note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
e925f477-5b20-5912-ac47-b339a9b85f1b | note | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
21c75048-2178-5080-a199-8ff3d35d5ab8 | note | ○ Layers shall not exceed 150mm compacted depth
a44f690e-c6ae-591d-b6e7-999cbfe2ec5c | note | REFERENCE DOCUMENTS: 703.29
14b283de-8659-5ab4-825a-4b30c61548e8 | note | INSPECTION/TEST METHOD: Verify
0a80e5d2-b41f-55e2-b28b-430a41d3f1b6 | note | RECORD OF CONFORMITY: ITP Signed
7e2420d8-fde6-51b0-a859-959cdf897545 | note | IP
1dc61cfe-dd52-57db-8a54-d9c8f8e098a0 | note | RESPONSIBILITY: Project Engineer
d0b8e846-142a-5966-9f2e-bdab2cae6700 | date | Date Completed:
| checkpoint | Final Inspection
ac187b8a-aa0a-55dd-bcea-3b64462d0063 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4060064f-3808-55a7-8826-e1e133e3be29 | textbox | Print Name:
3a68750e-6add-52a9-826a-45c1b8997c2c | textbox | Position:
4f9916a4-a9c8-545b-9afb-e140d7498ba8 | date | Date:
| checklist | ITP-033 - Insitu Concrete Pit | itp | ITP-033 - Insitu Concrete Pit |  | d529660c-560e-405e-b9fa-84fbb1d03825
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
15204b47-040b-5edb-a7be-9263e1289fe6 | note | FREQUENCY: Prior to commencing any activity
bff54d5e-dcc3-5d6e-a397-83e3ce76dda8 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
d83d9d3e-940d-542d-8177-17ba85e70cef | note | REFERENCE DOCUMENTS: Drawings and drawing registers
fd99bebf-2ba3-5d6f-a239-dabbedaca1e0 | note | INSPECTION/TEST METHOD: Visual inspection
b8192dff-e042-5f6b-88e0-ff0bcc6aeb08 | note | RECORD OF CONFORMITY: This ITP signed off
5605055a-756d-552a-a49c-cebe9dde3de6 | note | HP*
e7b10d90-110e-51e6-8775-aa480111a9f3 | note | RESPONSIBILITY: Fulton Hogan Engineer
6dd5db90-dca0-5de8-88bf-0726899572c8 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
6a029ed9-2d97-5deb-ab38-9c60081f2b63 | note | FREQUENCY: Prior to commencing any activity
8c41aaea-75cb-5e69-ae92-b29713bbcb61 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
8de94bee-1c9c-5e6b-a1a7-bef54909683b | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
41982aa0-0b4a-5788-b36d-e7ad56d01b47 | note | INSPECTION/TEST METHOD: Visual Inspection
140b5434-95ac-5565-b0aa-ce1bffe33a80 | note | RECORD OF CONFORMITY: This ITP signed off
e2d1b63b-454d-592d-abed-046f8e308de3 | note | IP
2c86a548-b72e-573f-ad89-f1e873966032 | note | RESPONSIBILITY: Fulton Hogan Engineer
c37a1767-d47e-5126-9c2e-66b6f00fa492 | date | Date Completed:
| checkpoint | 1.3 - Pit material classification
1c6f1fbd-5ac3-5068-95f6-0a4eb1609762 | note | FREQUENCY: Each delivery
c8d463ab-fce8-5f0d-9841-e455aba1c3f2 | note | ACCEPTANCE CRITERIA: Concrete used shall have a mininmum strength of 32MPa and be
182372c7-fd4b-557b-8df8-eb5787e1ba91 | note | ○ Steel fabric shall be SL82 reinforcement and conform with the requirements of AS4671-2001.
25f07313-74d7-5cfd-baf7-ef356e3d8732 | note | REFERENCE DOCUMENTS: IDM SD415
952c45ad-db7b-5b07-b5e3-46904df5b8b0 | note | INSPECTION/TEST METHOD: Visual Inspection
bd3a281a-7546-539f-837f-f223c40271ec | note | RECORD OF CONFORMITY: This ITP signed off
ace35bb1-ba72-5ccc-b896-2edb22db432b | note | HP*
054f8cd8-b28e-5fd0-8731-5ecf00e2de87 | note | RESPONSIBILITY: Fulton Hogan Engineer
4fe73d02-7298-53f3-9120-848ed1d7fd94 | date | Date Completed:
| checkpoint | 1.4 - Backfill and bedding material classificaiton
3a864233-8612-540a-b879-9989ce256797 | note | FREQUENCY: Prior to start
93a70076-25b7-5c2a-bd23-e65d3dda2b30 | note | ACCEPTANCE CRITERIA: All crused rock used in the works shall be Class 2, 20mm nominal size.
70318551-35d5-54f7-9c04-f81bbd786a57 | note | ○ Sand shall conform with the requirements of AS2758 - 1998 and AS1141 - 1997 and shall have grading within the limits as defined in the code.
8c8358ae-7290-5f09-a754-f5e357ada5ae | note | REFERENCE DOCUMENTS: Cl 18.0
b34ba1d9-185b-5849-a3b2-ef48fc417ee2 | note | INSPECTION/TEST METHOD: Verify
23467d78-3c37-5a73-93df-9dcd10c9a388 | note | RECORD OF CONFORMITY: Test reports from supplier
d5a8f42b-3710-5428-b51e-0537907b358f | note | HP*
442ed39b-86c3-5986-b45e-bc6ba2c2b585 | note | RESPONSIBILITY: Fulton Hogan Engineer
603ae620-6a61-5a1e-ab9a-d640892c03e2 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Set out pit location
4bf0512d-3b96-56fc-a140-408687ab8286 | note | FREQUENCY: Prior to backfilling
52562f53-068a-518d-9683-fadec32c4fb6 | note | ACCEPTANCE CRITERIA: The line, level and location of all pits & structures must be in accordance with the provided design drawings.
c020e341-711a-5755-b079-5a07d88bee69 | note | ○ The position of all pits are to be confirmed with the superintendent if ambiguity arises from the drawings.
142eeec2-f6c0-5bef-9315-e872836e0b68 | note | REFERENCE DOCUMENTS: Dwgs Appx 2: Cl 8.0
92c24246-c187-537b-94f4-c08a3eeedb46 | note | INSPECTION/TEST METHOD: Survey Conformance Report
a2b839ff-2a8b-59bf-8a0e-3f7700e62f1b | note | RECORD OF CONFORMITY: Survey Report. This ITP signed off
c538bb17-216f-5233-aaf7-5f837e99a962 | note | WP
cf2e6226-c3a4-59b0-baa7-8141b8e3d4fc | note | RESPONSIBILITY: Fulton Hogan Engineer / Superintendent
8c288261-3a06-55d6-94a5-d95700935e2a | date | Date Completed:
| checkpoint | 2.2 - Excavation
643aa295-de79-5d91-a288-e9837c7af668 | note | FREQUENCY: Each trench
d9fc4948-6ae7-56ab-8af1-63729f16448a | note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth greater than 75mm below the specified level of the invert of the pipe to allow for appropriate bedding.
cf7070e8-66ed-53ad-b080-1deb0fab2091 | note | ○ Any trench which may have been excavated to a greater depth than necessary shall be filled into the required level with concrete 1:3:6 mix. Any loose material shall be removed.
65caa6e4-76d0-5efc-9277-2d33ba6bd51b | note | ○ Trench shall be battered, benched or shored in line with WorkSafe code of practice when required by assessment under 1.5m in depth and is mandatory over 1.5m.
c031a516-5864-548c-9350-cfd1e014ccda | note | ○ No stockpiles within 2m of end of the trench to reduce bearing pressure.
8b285a61-5883-5a9e-8499-098ef52dd1b7 | note | REFERENCE DOCUMENTS: Appx 2: Cl 8.0, Cl 9.0, Cl 11.0
b22c4a20-1f4d-57f4-89df-bd1635261bca | note | INSPECTION/TEST METHOD: Visual Inspection
f3cc31cd-1987-51e4-83a3-b37d961136a4 | note | RECORD OF CONFORMITY: This ITP signed off
e93c65b3-9c9c-589f-8975-52def1f3aded | note | IP
4cbe1f26-18b9-5c50-9371-48e0d7478e20 | note | RESPONSIBILITY: Fulton Hogan Foreman
7a09087d-ce81-53f6-b739-4e43e9d183f6 | date | Date Completed:
| checkpoint | 2.3 - Inspection of trench base
455fc866-144b-5903-a09f-9759df4abec7 | note | FREQUENCY: Each Lot
6de967d4-5938-5924-a662-67f46f1d7b4c | note | ACCEPTANCE CRITERIA: Base of the trench shall be inspected prior to placement of bedding.
365d68f3-8437-51f9-80cc-bcafc3a1100a | note | REFERENCE DOCUMENTS: Appx 2: Cl 8.0
6cb664fb-6722-5555-a04e-12cac86bb27d | note | INSPECTION/TEST METHOD: Visual Inspection
b78fe6e6-819c-527a-b542-6117d60827b0 | note | RECORD OF CONFORMITY: This ITP signed off
274ed1f4-66b2-5df0-9ab6-e8b841ebcc93 | note | IP
f14211fc-91ef-5596-92d8-7270a2699b00 | note | RESPONSIBILITY: Fulton Hogan Engineer
82c606d7-8181-5217-a60d-c6bf43522c82 | date | Date Completed:
| checkpoint | 2.4 - Placement of bedding material
e4874690-8c83-5ce9-a2d5-1b00eb2f2335 | note | FREQUENCY: Each Lot
6714e708-8cad-5b1e-9d6b-945cc72ba5b2 | note | ACCEPTANCE CRITERIA: A 75mm minimum layer of compacted class 3 crushed rock shall be used under base of pit
f7e9ec93-a85a-5a57-8cd4-3fc04e744b32 | note | REFERENCE DOCUMENTS: IDM SD415
c7385e1f-4107-52dd-8d61-2d153e5916b5 | note | INSPECTION/TEST METHOD: Visual Inspection
70109490-ce60-5193-90ad-73a438f58c81 | note | RECORD OF CONFORMITY: This ITP signed off
88114ad8-9e19-5a22-8033-12607507c93c | note | IP
d79dc6a7-2a9a-5835-a771-9bb1fdee86be | note | RESPONSIBILITY: Fulton Hogan Foreman
ab2574e8-8973-5909-bcdf-07c9b47bdefb | date | Date Completed:
| checkpoint | 2.5 - Concrete pre-pour inspection
a086807e-b455-5bc4-88eb-8bcf49be4046 | note | FREQUENCY: Each Lot
aa267129-dacc-52e4-991d-11e9d16bfe44 | note | ACCEPTANCE CRITERIA: The site of the concrete pour for the cast in-situ pit shall be inspected by a client supervisor before proceeding.
e7cd3ff9-1aae-57b2-ac3c-81a66668bd33 | note | ○ Reinforcement shall be check for correct cover & lap as per drawings
958dcd0e-80fd-5657-a595-1d21fd6e8af8 | note | REFERENCE DOCUMENTS: IDM SD415
0e572912-c2c3-59da-8f9d-78cf5636072a | note | INSPECTION/TEST METHOD: Visual Inspection
147d1549-e442-50cb-9136-06d81629b937 | note | RECORD OF CONFORMITY: This ITP signed off
c9766c66-4b23-58ac-b97f-0f43d0926a1c | note | WP
47b2a1f6-fdab-51d4-a5f7-b13ef198ebd4 | note | RESPONSIBILITY: Fulton Hogan Engineer / Superintendent
09ae1457-4e2e-5dc8-b27a-177236e06b63 | date | Date Completed:
| checkpoint | 2.6 - Concrete pour and pit construction
32fd6e84-bc81-5778-b24a-99e7b43ddf75 | note | FREQUENCY: Each Lot
e2b9df1f-7caf-5aa3-b317-fc4107fa6b73 | note | ACCEPTANCE CRITERIA: All pits are to be constructed in accordance with IDM Spec 415. Pit should also be constructed in accordance with site specific drawings.
cd369189-dee6-5cca-a1b5-e299ec39e93c | note | REFERENCE DOCUMENTS: IDM SD415
f5967b23-8da7-5f62-b18c-d49e0339292f | note | INSPECTION/TEST METHOD: Visual inspection
bdb10e85-0632-5028-8d8f-136aeb015d5d | note | RECORD OF CONFORMITY: This ITP signed off
0cdbf495-d8df-5530-908a-aeff3c850225 | note | IP
a0ed70a0-ded8-5952-a965-b6aae9327ef8 | note | RESPONSIBILITY: Fulton Hogan Engineer
ccc35758-1ed7-5d6b-bf48-38ee627c413e | date | Date Completed:
| checkpoint | 2.7 - Pit base shaped with concrete to match pipe invert
d3e546e2-198b-5133-ac9f-3173e2fb51ee | note | FREQUENCY: Each Lot
e1027ae0-5de0-5ecd-b712-c328423d24b0 | note | ACCEPTANCE CRITERIA: Construct as shown on Standard Drawing 1P50318
78071a8f-4b46-51f9-9ac4-c32b2bd207ee | note | REFERENCE DOCUMENTS: IDM SD415
00d7b539-08c5-51fc-9714-9786c7db337a | note | INSPECTION/TEST METHOD: Verify
8a049663-c804-5ea7-8457-e3755aed5200 | note | RECORD OF CONFORMITY: This ITP signed off
3daeb99f-0172-54ce-9adc-9439ccafef13 | note | IP
f04099d4-e3e1-597b-b2b4-66e23ef768c3 | note | RESPONSIBILITY: Fulton Hogan Engineer
b029399e-ea5f-57bb-b8fc-04ecfdb7cc5a | date | Date Completed:
| checkpoint | 2.8 - Placement of pit covers
0cb7a3d4-b698-5e24-873e-ac82aa2a6a36 | note | FREQUENCY: Each Lot
5df50a57-5c5b-5aeb-82a9-88986e49c252 | note | ACCEPTANCE CRITERIA: All pits shall be fitted with standard City of Melbourne covers specificed on the drawings of appropriate class.
0374afb6-662d-5f6f-96ca-85fd74e1eddd | note | REFERENCE DOCUMENTS: IDM SD415
abc34caa-6ebb-550b-82d8-25553ad330c7 | note | INSPECTION/TEST METHOD: Verify
365286cf-3382-56be-8488-3097598f03fe | note | RECORD OF CONFORMITY: This ITP signed off
47128506-1ef5-50a9-8b1d-ec4a58e564cf | note | IP
f956aa79-7561-5d29-bf42-1e1888523977 | note | RESPONSIBILITY: Fulton Hogan Engineer
a409f67c-6976-5e5f-bc60-61e7fa5a9015 | date | Date Completed:
| checkpoint | Final Inspection
1d85a9e6-8404-5779-b1ae-a0c6d1692ba4 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
303cf3f1-307f-532e-b6c0-4058cf46e240 | textbox | Print Name:
6286e5c3-56c9-5d01-9e4b-ef932bba81e1 | textbox | Position:
d7206c4d-5ecb-5fa2-9b38-7b3bbdd5e836 | date | Date:
| checklist | ITP-045 - Pipe Conection to Main Drain | itp | ITP-045 - Pipe Conection to Main Drain |  | 52256833-89db-4e43-af0e-453569450a2c
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
40c4380b-ad50-585b-93e3-52b3d6c9d4e8 | note | FREQUENCY: Prior to commencing any activity
780f2722-2ca7-5f63-850a-2e66153f7fa9 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
54b8ac59-ecdb-5712-88e1-e6c7b018cdf4 | note | – using the correct and complete set of drawings
23f18fe0-f4d7-5b9b-b670-468b6a8052ac | note | – all drawings are the latest revision
67a3b783-ff1b-5fd9-a0e7-e5c26d95eed1 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
db5eb141-cb7f-545f-9c21-6a6f1f292fb3 | note | INSPECTION/TEST METHOD: Visual inspection
c1bf93ba-7170-5b78-962d-c84992ef3435 | note | RECORD OF CONFORMITY: This ITP signed off
e3e1dca2-26c2-59e6-b6e1-b1f02eb54613 | note | HP*
2c964337-c9c5-51ca-a752-7179ec5a6870 | note | RESPONSIBILITY: Project Engineer / Site Foreman
bc580dc4-cb8c-592d-840a-c32ea052a29e | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
b155360d-635e-55db-9487-fba8693a5a5a | note | FREQUENCY: Prior to commencing any activity
3864ead6-e846-5cc8-966a-abead941fe0d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
5229d343-ccff-5686-b665-87a37f51f423 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
98c23051-f8da-52a4-ab21-a9db4fdd1ad8 | note | INSPECTION/TEST METHOD: Visual Inspection
25edfa82-97bc-5c6b-a789-baa717c4ecda | note | RECORD OF CONFORMITY: This ITP signed off
f017653e-4610-5eb3-82ec-4c82dc4e21ca | note | HP*
0ab1265c-7aa6-59e5-8800-d87ee03be15d | note | RESPONSIBILITY: Project Engineer / Site Foreman
dcbaa5ee-3746-57a3-a11d-b2cfa617a6c0 | date | Date Completed:
| checkpoint | 1.3 - Precast Materials Inspection
6a62c025-f8e5-51bc-94a4-e5105a2c3755 | note | FREQUENCY: Each Delivery
8592c2e2-b43b-572d-a145-0b4d9f5cb277 | note | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
3b613947-b408-5c05-924b-b61250489fdd | note | REFERENCE DOCUMENTS: 701.04b
11be1205-b34e-54bf-b681-2a8aac987c79 | note | INSPECTION/TEST METHOD: Visual Inspection
4954a2cb-1213-59f7-88de-34c3067c0eb2 | note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
8773e0f0-ab37-5374-8c81-ac9b9d6a5bf6 | note | IP
fcb3bfdd-ef00-5a5a-a1f6-0a54593e95ba | note | RESPONSIBILITY: Project Engineer
ee2e345b-b18f-58ff-9efc-25ad18d7384b | date | Date Completed:
| checkpoint | 1.4 - Precast Pipe
98ce9a96-79ca-514f-b07d-a046d01af091 | note | FREQUENCY: Prior to Commencing
fdf3680f-ffac-5c09-b667-ded812734101 | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058
840b6bfe-63a7-5682-8283-0b4ec12deae2 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619, Cl. 701.04(a), Cl. 701.04(b)(i), Cl. 705.04(d), Cl. 705.11, AS4058, AS4680
42c7d44d-56b9-50ae-a8b9-acf26f3ff7b3 | note | INSPECTION/TEST METHOD: Document review & Site inspection
862cc7c9-e2b7-5c6b-892a-5a6fe6fa4919 | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
62a525bf-4bf3-526a-bb32-1f4947b3adb4 | note | IP
8fd0922b-91e2-5151-91ed-ff6d3ff9300e | note | RESPONSIBILITY: Project Engineer
475b32f9-104e-555c-8b96-7a19570677d6 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Excavation Permit
69616e90-851d-59c1-981e-82fb45d5fe97 | note | FREQUENCY: Each lot
9e4f48e2-dc67-546f-82b9-2d2ede18fb95 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
5f48a6cb-df4a-595e-b817-083b2e66dd85 | note | ○ Plant and equipment shall be appropriate for the task.
0c432e5e-cc7b-5a3e-8523-4e494ee451a3 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
49ff8b1b-196d-5915-bc5b-1235fdf8eafb | note | REFERENCE DOCUMENTS: Excavation permit
48a2061b-f0f0-5fc7-9710-477c34aa3822 | note | INSPECTION/TEST METHOD: Verify
59056c9f-43f6-5290-bcb5-a3f4ead4940f | note | RECORD OF CONFORMITY: ITP Signed
e71a5172-9e2b-5728-b507-c470fe31f9ad | note | HP*
10fc74e3-8333-50d6-a3b0-bc31b5171c6f | note | RESPONSIBILITY: Project Engineer
97b95dc0-c328-5dde-8f17-f60bba7684b2 | date | Date Completed:
| checkpoint | 2.2 - Set out drainage
08799d9d-87a8-5107-bf4a-d6c431432415 | note | FREQUENCY: Prior to excavation
3d1e0728-1bb1-5f63-a01c-411f292bf91c | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
eb87a11c-abe4-5b0b-820a-e797d2d8e1a6 | note | REFERENCE DOCUMENTS: Drawings 701.10
80a76916-0960-5a48-a229-765451e737fc | note | INSPECTION/TEST METHOD: Visual Inspection
e5e50c00-57cc-5abe-9724-7c793827c531 | note | RECORD OF CONFORMITY: ITP Signed
571eb621-2143-5d6a-a635-abe5309d14f0 | note | HP
5f1ccc6f-aec6-5e3e-be2b-20521464b98d | note | RESPONSIBILITY: Engineer / Forman & Superintendent
971e8ba4-1d8a-523f-86d8-6db3fc714a39 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Excavation (pipes)
558cfcbb-4367-5c57-ac03-a64c7fd2f60b | note | FREQUENCY: Each Trench
a45b6301-576a-56fe-a38a-46127291dd9a | note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical.
fdfb2c47-9856-5057-90f7-eaa115de3a2a | note | Depth of trench:
b93d7c15-0041-56bf-a45d-2fe74866cd34 | note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
96aa626a-2f01-5b82-b32a-99de0079aeb5 | note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
6a231db5-f11d-57dc-9a66-db67b9309649 | note | REFERENCE DOCUMENTS: 701.15, Table 701.151
766af842-977f-5003-89a8-e9f458b673a0 | note | INSPECTION/TEST METHOD: Visual Inspection
2c749336-e6c5-5a3d-9130-659fc8741f4e | note | RECORD OF CONFORMITY: ITP Signed
2fd04e0f-336f-5398-983e-6881408c55c7 | note | IP
da0a38c2-76c8-5812-8ed2-aaa7cdd447e2 | note | RESPONSIBILITY: Site Foreman
089c4e30-f739-5918-b07b-c0d37382d9d5 | date | Date Completed:
| checkpoint | 2.4 - Bedding & Support
f23c4095-5016-5f7a-bfe5-4f37d9749650 | note | FREQUENCY: Each Lot
5d04e1a9-d0a2-52b7-88ab-8fd5f6170e5a | note | ACCEPTANCE CRITERIA: Provide mass Concrete support around branch pipe minimum 150mm thick. Concrete shall be grade S40 with a maximum water cement ratio of 0.50.
d2cf38b2-36b8-5b14-a312-9d99a996dd6e | note | REFERENCE DOCUMENTS: MELBOURNE WATER CORPORATION 7251/08/425
bab4dd58-6486-50aa-ab69-637f82688d22 | note | INSPECTION/TEST METHOD: Visual Inspection
7d06f9b2-196b-5c78-8925-81cd56339daf | note | RECORD OF CONFORMITY: ITP Signed
2020e284-4abc-5540-9813-4bc1a8c5f350 | note | IP
4585ec8e-e926-506a-b610-eb9d9618f13e | note | RESPONSIBILITY: Site Engineer / Site Foreman
6b3df55f-dc7c-5d6f-84b9-9292aeb4a2b5 | date | Date Completed:
| checkpoint | 2.5 - Break Into main drain
3f6cbeb0-a512-5779-904e-73f6f8e2101c | note | FREQUENCY: Each Lot
4052a2a5-b24b-5bad-affa-9b8fc232100e | note | ACCEPTANCE CRITERIA: Reinforment in main drain to be cut and formed into collar. Care should be taken to prevent damage to pipe and to enshore opening is kept to a minimum.
3e394441-d0b5-5f14-b085-b3662a4bc762 | note | REFERENCE DOCUMENTS: MELBOURNE WATER CORPORATION 7251/08/425
a5c348f1-ae6a-5b0a-991d-44037e0863b8 | note | INSPECTION/TEST METHOD: Visual Inspection
3eda918f-104f-5450-abda-bd1eb7918e56 | note | RECORD OF CONFORMITY: ITP Signed
e2bb67ab-f491-5500-abcd-c443924b90ff | note | HP
3980e9eb-f48d-5483-9c27-61ae32ae63ad | note | RESPONSIBILITY: Site Engineer / Site Foreman, Superintendent
e2646088-7416-570a-866b-8904efa2545f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Pipe to Pipe Conection
0ea24c1d-1bb5-554b-bf7d-3ce5fed6bba5 | note | FREQUENCY: Each Lot
5cfeb4f9-dd20-5869-b3f7-fb952344abea | note | ACCEPTANCE CRITERIA: Where connection cannot be rendered from inside main drain, connection to consists of 300mm long stub to allow rendering from outside. Bonding of new to old concrete shall be sufficent to ensure no cracks or leaks form. Concrete surfaces to be scabbled, cleaned primed with parchem nitobond SBR. All reinforcement without adequite cover to be sealed with epoxy or similar.
7af7cff7-9ad5-5113-996b-88b1adfd689b | note | REFERENCE DOCUMENTS: MELBOURNE WATER CORPORATION 7251/08/425
ead09b74-cb14-53e9-b886-16a9383bdea4 | note | INSPECTION/TEST METHOD: Visual Inspection
f3b4e4d5-8681-5bfc-9193-bc0a08649714 | note | RECORD OF CONFORMITY: ITP Signed
2c12921b-47e4-58b7-a3de-889f8a3899b6 | note | IP
6cb3cbad-6f87-56e5-85a5-516bf2b9b6e4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
ae820b23-0b49-5f92-b38d-4c7e4ab0cd0e | date | Date Completed:
| checkpoint | 2.7 - Place & compact backfill material over pipes
f4cf5df9-ee9d-56de-afc0-cbe56013a202 | note | FREQUENCY: each lot
56bc0f68-7328-5e06-ba99-bf90df7d1a8e | note | ACCEPTANCE CRITERIA: Ordinary earth from excavation which contains no rock fragments compacted in layers no greater than 150mm. Compaction to be minimum 92% modified A.A.S.H.O. using handheld mechanical equipment. Top 100mm to be topsoil and seeded
c97098f1-bd53-5e70-89bb-470e16f28423 | note | REFERENCE DOCUMENTS: RFI.01
7deeb075-0bb8-5edf-8bbf-d25e581ad13c | note | INSPECTION/TEST METHOD: Visual Inspection + Testing
54677b12-3d47-55c3-8677-fcce4ef98636 | note | RECORD OF CONFORMITY: ITP Signed
1f77a884-dd45-5ec4-9a31-ef868778ba52 | note | IP
4c12bc30-6443-541c-ae9f-43a8da34c239 | note | RESPONSIBILITY: Site Engineer / Site Foreman
9b45be9d-0280-5dfd-9c03-210fcd371411 | date | Date Completed:
| section | 3 - Testing & Completion
| checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
2c3c8f52-d729-533f-9339-b910abc114f0 | note | FREQUENCY: as required/requested
e43173bc-d3bb-594a-8831-ab207110d098 | note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort. Bedding material shall be compacted using a compaction plated to refusal.
fdd3e814-b8bb-5669-bfc9-3cec765921e0 | note | REFERENCE DOCUMENTS: 701.2
46c78a18-4d64-599c-8240-90ecabc8466f | note | INSPECTION/TEST METHOD: Verify
6b7910e7-eda9-5384-b4c5-8e17adaf3cb8 | note | RECORD OF CONFORMITY: Test Reports
5891d8c6-8e0f-56da-8019-f1d2b8c6710f | note | TP
8bdec850-16e3-5349-a541-0f52da136aec | note | RESPONSIBILITY: Project Engineer
9a3f2ab4-e46d-5fd0-ab5a-ba848ee824a3 | date | Date Completed:
| checkpoint | Final Inspection
b7df19b0-78fc-539e-8da9-1aa131a20868 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
b196d884-3047-5314-ad25-8db2db257f7f | textbox | Print Name:
0d2d336d-65c9-5abd-a61f-7c97a7e43d91 | textbox | Position:
76d1508a-d127-55b5-b7cf-553ee963db88 | date | Date:
| checklist | ITP-050 - Omnigrip Road Surfacing | itp | ITP-050 - Omnigrip Road Surfacing |  | 2f0e585c-fe63-4191-b61f-16ca33b491f1
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for Correct Documentation
b9d470c9-ba43-5993-aa9b-adc7a68b9bbe | note | FREQUENCY: Prior to Commencing Activity
f43efe95-c1f2-5000-b141-2c0ec458d0b2 | note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
7e3875bf-3044-5431-ba1e-73e2655b3bce | note | REFERENCE DOCUMENTS: Contract Drawings and Registers
96191e9e-1328-5f90-8e19-aadb544db25f | note | INSPECTION/TEST METHOD: Visual Inspection
377ab259-63c0-5345-8b1b-b38e482e0a29 | note | RECORD OF CONFORMITY: This ITP Signed off
246b46d3-416d-5dba-9f76-99b6df2f6efd | note | HP*
b35b23a2-dc20-5438-a82f-4d25fc39a42f | note | RESPONSIBILITY: Fulton Hogan Engineer
16d0c116-d85e-5015-8177-b1a2376aea92 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
01e3a13c-6b7d-5b06-8a45-fccfc7d6abd4 | note | FREQUENCY: Prior to Commencing Activity
64e7497f-ba2c-566e-8481-61f5d763274d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
7bafe269-0fc1-5d26-b9ab-b2bc54cb5037 | note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
b375099d-d3e6-51a8-a58a-dc9e66754a50 | note | INSPECTION/TEST METHOD: Inspection
acc19bf2-c653-5fb6-bca4-744ead73d2d5 | note | RECORD OF CONFORMITY: This ITP Signed off
79eb3582-3737-59f2-916a-773762b51c33 | note | IP
7a9c01ee-bd6a-57cb-9b62-88896b18ba4b | note | RESPONSIBILITY: Fulton Hogan Engineer
a501bb58-4003-5131-9165-79d5428bbccf | date | Date Completed:
| checkpoint | 1.3 - Check Materials
e71778e4-0f90-54e5-939c-5b6095d95ee1 | note | FREQUENCY: Each Delivery
f17656b6-50fd-5e1a-a7f7-21e078bbe1cf | note | ACCEPTANCE CRITERIA: Ensure the correct materials have been received including:
106b1d0e-0954-5f71-97c3-98bd481569b0 | note | – Part A Epoxy Compound
5f44b956-9eff-5524-9224-0596787be293 | note | – Part B Epoxy Harderner
9765c484-04f8-5e02-84a8-44c85174c884 | note | – Coloured Aggregate Dressing
aab3af70-9f29-5fb7-849c-57cda66dc238 | note | REFERENCE DOCUMENTS: Receivable Inspection Checklist
fa72ac57-f1af-54c9-a0df-a13580b993b5 | note | INSPECTION/TEST METHOD: Inspection
0573ea64-122b-51e2-8664-8968979e6edc | note | RECORD OF CONFORMITY: This ITP Signed off
6f14bef6-1899-5574-b808-2612cb655569 | note | IP
c137c3ae-9abc-5154-b6bd-8b027f85fe06 | note | RESPONSIBILITY: Fulton Hogan Engineer
2959c050-5625-5bc4-8274-71f0e9e9dfab | date | Date Completed:
| checkpoint | 1.4 - Setting out
99d30083-e1c4-5fd2-8166-e15bb950daac | note | FREQUENCY: Each Lot
ce310edf-1fb0-58c1-bec9-5f3247133a3e | note | ACCEPTANCE CRITERIA: Alignment and location of Omnigrip road sufracing shall be marked in accordace with the appropriate design drawings.
53e0cb20-0ece-5517-8d2c-04524327704a | note | REFERENCE DOCUMENTS: Work Procedure
7997aa30-7216-5f91-bf9d-e7b38981c9b2 | note | INSPECTION/TEST METHOD: Inspection
356d0cda-6e76-59f4-bbc0-ebef43b1b797 | note | RECORD OF CONFORMITY: This ITP Signed off
406755b9-6e81-508e-b641-b275c87b27c9 | note | WP
c99fff6c-6483-5842-bd41-0a98d320a071 | note | RESPONSIBILITY: Fulton Hogan Engineer, Client
72cb53eb-81df-5dd0-88c4-cfb136f57b47 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Monitoring Conditions
2b89646e-5aad-58da-b480-d52ba7f87015 | note | FREQUENCY: Prior to start
506f8f74-a11f-59e2-a357-2381057eba7b | note | ACCEPTANCE CRITERIA: Omnigrip CST must not be applied to wet pavements under any circumstances and suspension of application should be considered:
2650232a-c244-5257-adb5-8d98acfb7fa5 | note | – During periods of dew, drizzle or rain
bae08739-5406-53cb-ab23-f77a129458af | note | – If the surface temperature exceeds 60°C
0509cbb7-577c-5580-bdc4-ca38fa5af911 | note | – If the surface temperature drops below 10°C and is in decline.
7045c468-24a3-553a-a715-8e17e9fd1832 | note | REFERENCE DOCUMENTS: Omnigrip Technical Data Sheet
bf6df310-95eb-51cc-afd8-61dc11513d73 | note | INSPECTION/TEST METHOD: Verify
b45ee12e-4755-58e3-a33d-bdf312299bd3 | note | RECORD OF CONFORMITY: This ITP signed off
be3b9348-abf1-5204-9232-5516fee4b905 | note | IP
bae33dc7-efcd-56cc-992e-cdccbb95507e | note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
ff0a0868-bcdb-52a8-8a81-ab5ac6d88082 | date | Date Completed:
| checkpoint | 2.2 - Asphalt Surface Preperation
03d4037b-ca6d-5e38-b3d3-8e52b8e46ab2 | note | FREQUENCY: Each Lot
4697d276-de3d-50a3-ba36-3113e6dae889 | note | ACCEPTANCE CRITERIA: Ensure that the substrate is dry and clean of all contaminates. Asphalt pavements shall be virgourously brushed or treated with compressed air to remove dust and loose aggregate.
d42f63c0-914f-5826-8245-75b4be993cf9 | note | REFERENCE DOCUMENTS: Omnigrip Technical Data Sheet
792ab266-ed6e-5350-add1-f1d6f9dabb45 | note | INSPECTION/TEST METHOD: Visual Inspection
19e5ca99-3c1c-5af2-890e-00add98e39ee | note | RECORD OF CONFORMITY: This ITP Signed off
0eb578cb-eac2-5af6-913c-5476459bb222 | note | IP
3a76f4e7-bdba-543e-b289-831e72c7b171 | note | RESPONSIBILITY: Fulton Hogan Engineer
faff4bf5-4198-5e0a-95a8-71ec570ae2d1 | date | Date Completed:
| checkpoint | 2.3 - Material Mixing and Installation
d8dc9399-299d-5ddb-9cbe-6699d66663bb | note | FREQUENCY: Each Lot
b30bb674-7150-55e2-9a83-efa7ff061956 | note | ACCEPTANCE CRITERIA: The Epoxy Part A should be added to Epoxy Part B at a ratio of 1:1 and mixed using a slow speed for 90 to 120 seconds to obtain a homegenous mix. Add pigment colouring throughout the mixing process.
6d1ecb47-3862-5c23-9a07-c7de8c85de21 | note | ○ Once mixed the resin should be immediately applied & spread evenly using a serrated squeegee or notched trowel at an average rate of 1.35 - 1.7 kg/m2.
605d779b-9531-53c6-b2f8-da55f0edb98e | note | ○ The resion should self-level, however, the use of a 20mm find nap roller should be used to back roll and level the resin.
72cae3a4-70c4-5e1d-8037-6a54dc467635 | note | ○ The applied resin should receive the aggregate dressing within 10-15 minutes of application ensuring no wet resin is left exposed.
2cd60730-ae54-51dc-b24f-7f08708328c3 | note | REFERENCE DOCUMENTS: Omnigrip Technical Data Sheet
d6c70e92-f569-5d2c-ae51-87e00adf9848 | note | INSPECTION/TEST METHOD: Visual Inspection
6c6a0d41-9fbb-53d0-8e57-a241cd1b877f | note | RECORD OF CONFORMITY: This ITP Signed off
f5d1c14f-4e06-5576-9527-d38c242b0f19 | note | IP
63725e84-ef79-5c51-bf2d-1ea3dd6426aa | note | RESPONSIBILITY: Fulton Hogan Engineer
355522fb-e01e-5617-827e-c952118d7978 | date | Date Completed:
| checkpoint | 2.3 - Curing
15129e55-6c40-5a4c-821c-d778cc4d10ae | note | FREQUENCY: Each Lot
bd819513-2e9f-526e-bb52-509a4bf50df4 | note | ACCEPTANCE CRITERIA: For any surface works on asphalt there must be a minimum curing period of 7-10 days.
201a0274-1565-5623-bf26-9b26a41f51e5 | note | REFERENCE DOCUMENTS: Omnigrip Technical Data Sheet
32d3e149-2dcb-518c-95fe-88026f8b3ec1 | note | INSPECTION/TEST METHOD: Visual Inspection
2d891875-e49a-55dd-a4e5-7a94563f5fba | note | RECORD OF CONFORMITY: This ITP Signed off
2001275f-0042-5713-9693-b0ed64c192c9 | note | IP
20e3e87f-7283-5c3f-a639-a4a04adbeeb1 | note | RESPONSIBILITY: Fulton Hogan Engineer
92c72755-b6cc-568d-a7ee-5cb070e57f8e | date | Date Completed:
| checkpoint | Final Inspection
ba2c9228-ec05-5a2e-a5fb-fab17d3bee6b | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
853c03b7-0659-51ec-b6c6-bb05b228910f | textbox | Print Name:
79970c15-f9bd-5d6d-867d-5d96c7c56251 | textbox | Position:
1167fc63-cc26-5af0-bc23-b349d4eb0569 | date | Date:
| checklist | ITP-068 - Construction of Trench Grate | itp | ITP-068 - Construction of Trench Grate |  | 3c9be845-c7ea-4990-a978-d866422e0bbf
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
c4c68885-48ee-563a-88e4-b6b0a5ac56a1 | note | FREQUENCY: Prior to commencing any activity
c8ea4ebb-8ae4-5862-a454-8f7c5404a774 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
242ff6ee-ca7a-58a7-8f93-f13137298b13 | note | – using the correct and complete set of drawings
f975dcf6-e017-5eaa-9017-a1f21dabc4dd | note | – all drawings are the latest revision
8e4ead16-abfe-53cb-bf9b-59d768b56064 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
4d1d4379-c943-5ae7-8b7c-2aed77ce4e35 | note | INSPECTION/TEST METHOD: Visual inspection
8f6106b4-5df6-504b-b9fb-16df83af3f75 | note | RECORD OF CONFORMITY: ITP Signed
92e9a435-565c-5f8f-8805-d2628fec75b4 | note | HP*
c72f528e-8eb3-5784-8bc3-4444bb3529d1 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
126f3897-43ab-5394-ba7d-bf48214264c9 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
12e6bb98-b569-56e2-b476-bfd21d133c8f | note | FREQUENCY: Prior to commencing any activity
ed2f59a9-77a0-5196-970f-9e0de114bd23 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
1437bc34-f72f-5ec2-af79-438b92b07134 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
0aa40e72-d2e1-5597-a599-7b1723a621b8 | note | INSPECTION/TEST METHOD: Visual inspection
5b5399f0-39ca-51d1-9235-ea71365727b4 | note | RECORD OF CONFORMITY: ITP Signed
68ada451-5aae-5ab8-9d38-094a057f4b2b | note | HP*
6748830f-2ef3-5c3e-bee6-1a9e0189850c | note | RESPONSIBILITY: Project Engineer/ Site Foreman
41bcdde0-a504-5378-83d5-315eff67f14f | date | Date Completed:
| checkpoint | Trench Grate Material Procurement
9aa76603-5225-5432-af35-0413fea61012 | note | FREQUENCY: Prior to commencing any activity
b97642f4-09b2-530c-b117-13e5af10d33d | note | ACCEPTANCE CRITERIA: Approved durham ductile heelguard trench grate and frame product NO. CHP30C or approved
f53cd526-9dc6-5ddd-a2e4-dd2730706b34 | note | REFERENCE DOCUMENTS: Drawings
ed59a335-8337-5b22-9c60-c7b3190aba7c | note | INSPECTION/TEST METHOD: Check Material Specs
1e91cf40-fa57-533b-a825-883b5b99cfe0 | note | RECORD OF CONFORMITY: ITP SIGNED
193e8aad-efbf-5b14-99f6-7bf2d582210a | note | HP
641e5a59-ce43-54e9-ac2b-b8c7b24057b2 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
8f6f9d7b-a155-57ee-b0f6-adf0219789b4 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
91472af4-dec5-53a4-8a2e-d2aa5863fcab | note | FREQUENCY: Prior to start
8bcf018a-dddb-53ae-9639-d2d9216af0e2 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
26d8ef59-19cd-5a67-907a-16d71d8c2627 | note | REFERENCE DOCUMENTS: 703.17
d208264b-30cb-511c-98ca-7326c47e3f26 | note | INSPECTION/TEST METHOD: Verify
c9cac56b-95a2-59de-866f-1861e39e9ac7 | note | RECORD OF CONFORMITY: ITP Signed
cbb2c52b-fb84-594f-b57b-09d620e7b0a5 | note | HP
56c86260-29d4-5a55-86c1-1fd7c71a7ec8 | note | RESPONSIBILITY: Project Engineer/ Superintendent
2ab121ff-33c4-5031-81ab-679b015bc922 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Temporary Drainage Provisions
843825a9-9adc-55c5-8ee9-7a9f0b720fc0 | note | FREQUENCY: If Required
8439d103-98e4-5040-b6b8-65caa7acd825 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
87a63cbe-9b6b-5888-a67d-f45727d5cf1e | note | REFERENCE DOCUMENTS: Cl 703.18
e9c29a7f-e482-5a98-be01-79af7a5514bd | note | INSPECTION/TEST METHOD: Visual inspection
59c1e76f-5633-533f-ba07-2860511a9e38 | note | RECORD OF CONFORMITY: ITP Signed
70c14c6f-f1d3-57df-8fcb-69fa059a6274 | note | WP
944d0be1-b492-583c-a4c1-618735677275 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
95c95246-e62a-56a4-8b0a-4b2448d97b7a | date | Date Completed:
| checkpoint | 2.3 - Bedding
0ebeec03-df1d-59d9-b39a-76d9ab45603b | note | FREQUENCY: Each lot
e8205cca-88cd-5cf4-ab9b-380c45b61610 | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
24fe2510-19af-508e-a95a-6afa3ec3afca | note | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
1e4b9060-86b0-5a93-a81e-bc10f2ad6495 | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted. A Slurry of low to medium slump concrete should be poured on the base of the excavated trench prior to placing the PVC in position. The Height of the slurry bed should be determined based on figure c in the intallation guildlines
1fa19630-6fd5-5c38-b623-2315f527cf12 | note | REFERENCE DOCUMENTS: Cl 703.21 Installation guidelines
fbf5fb3f-70a2-56f6-8ebf-e53d7e38f077 | note | INSPECTION/TEST METHOD: Visual inspection
3da8d951-c78b-52e5-8863-6a0916a1dd56 | note | RECORD OF CONFORMITY: ITP Signed
d94f535a-a31e-571d-a26e-4a7da1019acd | note | WP
31c71c6c-2217-5697-bc22-d894d27b01bb | note | RESPONSIBILITY: Project Engineer/ Superintendent
569a5192-cd37-5ab7-a360-041cd3359ed3 | date | Date Completed:
| checkpoint | 2.4 - Joining PVC sections
fdd68e6b-9022-563a-bea5-baa49afeb4db | note | FREQUENCY: Each lot
dc49e416-b118-515a-86af-2caeb4862ceb | note | ACCEPTANCE CRITERIA: Place each section of PVC in position under the string line. Align each end of the connecting PVC/frame sections so that they are touching. use clamp or bolts to hold the PVC/frame sections together
06da5f3e-de35-543d-8304-2f2f872ada7d | note | REFERENCE DOCUMENTS: Installation Guidelines
1d312907-b86f-5309-a69f-d3dfed7ed517 | note | INSPECTION/TEST METHOD: Visual inspection
e4dc6d2d-26df-5009-8b07-20f09c8d89cd | note | RECORD OF CONFORMITY: ITP Signed
25991b24-bedc-5f8b-b011-e3ba4288e989 | note | HP
18c837fa-a61f-5146-9e55-81271c6df288 | note | RESPONSIBILITY: Project Engineer
0a2b7489-6472-51fd-9f12-073cbcf4e4b7 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - 1st Pour
41efd4c2-54fa-56b4-bff7-a2332d448bd7 | note | FREQUENCY: Each lot
0fd7f541-7fb9-59ee-981e-304fbea7d389 | note | ACCEPTANCE CRITERIA: Pour Concrete to approximately half the depth of the excavated trench. The concrete should now be compacted to remove air pockets and ensure that the grooves of the. PVC trench are sufficiently filled.
b47cfa62-5235-575a-a7ef-2ee011c6bf10 | note | REFERENCE DOCUMENTS: Installation Guidelines Drawings
6bab87dd-4c59-585c-88a6-1a79d3aef5fd | note | INSPECTION/TEST METHOD: Site Inspection
acc659ef-4f7e-56cc-b325-432d0c3e366b | note | RECORD OF CONFORMITY: ITP Signed
252f8a1b-62a7-5f7b-b7a0-8bcbad0d071e | note | HP
f1ac3219-e101-5b42-8ac3-ba5b672206a5 | note | RESPONSIBILITY: Project Engineer
2f5ba85e-f484-5d92-92cc-b852e3a8c262 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Final Pour
1a1f4191-b1ba-5095-8707-198b32c2b5b8 | note | FREQUENCY: Each Lot
cec7bf5b-4feb-55b5-8f4a-5f724846e40f | note | ACCEPTANCE CRITERIA: The final concrete pour should be completed to finish height, with the finish surface being graded towards the trench, as required.
f18963e2-a349-5bd6-9a1a-0016f1f047d6 | note | REFERENCE DOCUMENTS: Installation Guidelines Drawings
c4311252-4f5e-5f54-98b2-54701eb00a86 | note | INSPECTION/TEST METHOD: Visual inspection
7c1321e2-d44e-5bb2-9bd0-30b07d5dba71 | note | RECORD OF CONFORMITY: ITP Signed
eaff81ae-5422-5219-b04d-d383f3cca2ee | note | IP
ab661e86-246f-5a3c-a36e-361d287c18a5 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
43152029-0392-5d3c-aad7-34d57c8e00c3 | date | Date Completed:
| checkpoint | 2 - Tie Into existing curb
f30064fc-8721-5b7c-b1c4-754a6e3f2618 | note | FREQUENCY: Each Lot
b2854351-f24e-577a-bd6c-bb0d17827ec7 | note | ACCEPTANCE CRITERIA: Transition from trench grate to existing curb in a neat transition
0323a674-75fc-5083-8e50-d013bba2ed02 | note | REFERENCE DOCUMENTS: Drawings
53c6a929-1a75-55b0-bf6b-242d31ef4326 | note | INSPECTION/TEST METHOD: Visual inspection
edd4532a-0629-53bb-aa45-ba4d2f1e8d66 | note | RECORD OF CONFORMITY: ITP Signed
50f3350a-8645-57f4-8bf5-77a5264dc6c2 | note | HP
5b384eee-d007-54b3-a82b-d80a01fde0d3 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
3c9d961a-ecb2-51b9-8b31-e9ab1ee0857f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Joints
05f58aa4-e2d7-57db-9f77-30bd7730f7da | note | FREQUENCY: Each joint
5cce8005-26dc-503b-8174-e3f154371365 | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
416bf737-f06b-512c-9fe0-81efb515c436 | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
e9895bad-36d2-5f39-a9c3-a52a3efde7c9 | note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
edeb9e3b-4986-5660-96b0-938e5191edae | note | REFERENCE DOCUMENTS: 703.26
0c830d45-c09a-59c0-8934-5f42abbc6039 | note | INSPECTION/TEST METHOD: Verify
1f5a090a-6ce5-55c3-9e38-3b33608f4ee9 | note | RECORD OF CONFORMITY: ITP Signed
14f2b095-74c1-5dfd-a2f6-9c6e9cb68c23 | note | IP
5cb39552-3b2c-5388-8950-3151919e3dd0 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
d042b66f-f0cf-5584-bf8d-2964b2f03492 | date | Date Completed:
| checkpoint | 2.8 - Backfilling
814e69a0-4ee1-55e1-a60d-83e4733619ee | note | FREQUENCY: Each Lot
204b8a29-e584-52ff-af92-5909886f207c | note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
12ef87af-b073-508f-b09b-19cb0167f3af | note | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
ebdaac5a-4087-5d61-9450-d032eb40254f | note | ○ Layers shall not exceed 150mm compacted depth
9c174bbe-b5f2-50fe-8127-0e8684af1663 | note | REFERENCE DOCUMENTS: 703.29
504ddcea-8342-591a-9706-f766d601b5d6 | note | INSPECTION/TEST METHOD: Verify
a4b28f56-233c-5e4b-87f5-1a6e7bf5dc5a | note | RECORD OF CONFORMITY: ITP Signed
a1aff1f5-a5aa-50c7-a504-62ca9e1ac2b7 | note | IP
a3e81fc5-1dca-5a28-8d4f-b37b8548b624 | note | RESPONSIBILITY: Project Engineer
5b11c3bb-00c6-5921-8167-0193f0ccdadd | date | Date Completed:
| checkpoint | Final Inspection
06afc756-d65e-5d63-ac6e-eeb85cf3d7dc | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
804d3621-a0ac-5e2f-85e3-6261eff434fe | textbox | Print Name:
7529f00a-0e78-56fe-8d8f-d08211bde2c5 | textbox | Position:
1ec9596e-5c17-5b88-8b23-5a0bf9e6c523 | date | Date: