## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP-002 - Earthworks | itp | ITP-002 - Earthworks
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
| note | – using the correct and complete set of drawings
| note | – all drawings are the latest revision
| note | REFERENCE DOCUMENTS: IFC Drawings
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: SWA Project Manager
| date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
| note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: SWA Project Manager
| date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Survey Set-Out
| note | FREQUENCY: Prior to commencement of excavation.
| note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
| note | REFERENCE DOCUMENTS: Work Procedure
| note | METHOD: Verify
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: SWA Project Manager
| date | Date Completed:
| checkpoint | 2.2 - Excavation Permit
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
| note | REFERENCE DOCUMENTS: Excavation Permit
| note | METHOD: Verify
| note | RECORD: Signed ITP
| note | IHP/IP
| note | RESPONSIBILITY: SWA Project Manager/SWA SEQ Adviser
| date | Date Completed:
| checkpoint | 2.3 - Sub grade Material Properties
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: In situ material within 400mm of cut ﬂoor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%.
| note | ○ If parameter met, rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.06 (e)
| note | METHOD: Site Inspection/Test Report
| note | RECORD: Signed ITP & Test Report
| note | TP/AP
| note | RESPONSIBILITY: SWA Project Manager/External testing Company representative/RRV Superintendent
| date | Date Completed:
| checkpoint | 2.4 - Inspection of Subgrade Material
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to veriﬁcation by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.06 (e)
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IHP/AP
| note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
| date | Date Completed:
| checkpoint | 2.5 - Material Classiﬁed as Silt
| note | FREQUENCY: Prior to commencing
| note | ACCEPTANCE CRITERIA: Material classiﬁed as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Superintendent.
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.04 (e)
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IHP/AP
| note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
| date | Date Completed:
| checkpoint | 2.6 - Acceptance of Rock Subgrade (when applicable)
| note | FREQUENCY: Prior construction of the regulating layer.
| note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
| note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.04 (f)
| note | METHOD: Site Inspection/ Document Review
| note | RECORD: Signed ITP
| note | IHP/AP
| note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
| date | Date Completed:
| checkpoint | 2.7 - Unsuitable Material
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.07 (d)
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP & Test Reports
| note | IHP/AP/TP
| note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representat ive
| date | Date Completed:
| checkpoint | 2.8 - Groundwater
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.07 (h)
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP & Test Reports
| note | IHP/AP
| note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
| date | Date Completed:
| checkpoint | 2.9 - Trimming and level conformity
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
| note | ○ Level tolerances: Range x (Mean value of all measurements) (Scale A) x = +5, -25mm (Scale B )x = +5, -15mm
| note | ○ Max S (Standard deviation of all readings) (Scale A) = 12 mm (Scale B) = 15 mm
| note | ○ No. measurements (Scale A) 80 per lot (Scale B) 40 per lot
| note | REFERENCE DOCUMENTS: VcRoads Std 204.03 (f,g,h) Table 204.031
| note | METHOD: Survey
| note | RECORD: Signed ITP & Survey Report
| note | SCP
| note | RESPONSIBILITY: SWA Project Manager/External Surveyor
| date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Test Rolling
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep. ( Cl 173) Plant to comply with requirements of Cl 173.03.
| note | ○ Pneumatic tyred plant nominated for test rolling procedures shall have a mass of not less than 20 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre.
| note | REFERENCE DOCUMENTS: Vicroads Speciﬁcatio n Section173.03 173.03 (ii)
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IHP/WP
| note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
| date | Date Completed:
| checkpoint | 3.2 - Compaction Testing
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Ripped and re- compacted material below Cut Floor Level = minimum compaction 98%.
| note | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 98%.
| note | ○ Type B material 400mm below the top of Type B material and Top 150mm of where ﬁll is to be constructed = minimum compaction 95%.
| note | REFERENCE DOCUMENTS: Vicroads Speciﬁcatio n Table 204.131
| note | METHOD: Compaction Test
| note | RECORD: Signed ITP & Test Reports
| note | IHP/AP/TP
| note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representative
| date | Date Completed:
| checkpoint | Final Inspection
| note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| signoff | Sign ITP
| checklist | ITP-004 - Underground Drainage | itp | ITP-004 - Underground Drainage
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Obtain MOA and Traﬃc Management Plans. Ensure Traﬃc Management Plan is adhered to.
| note | FREQUENCY: Prior to commencing works
| note | ACCEPTANCE CRITERIA: Refer to the VicRoads Traﬃc Management speciﬁcation 166
| note | REFERENCE DOCUMENTS: Traﬃc Mgmt. Plan
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: SWA Project Manager
| date | Date Completed:
| checkpoint | 1.2 - Purchase of pre-cast pits, pipes and end-walls
| note | FREQUENCY: Approval prior to placement of order
| note | ACCEPTANCE CRITERIA: Refer to Construction Drawings
| note | REFERENCE DOCUMENTS: Vic roads Standard drawings
| note | METHOD: Review and approval of documentation, Visual inspection
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: SWA Project Manager
| date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - CONFORMITY WITH DRAWINGS - The Contractor shall set out the drainage work in accordance with the drawings or as speciﬁed.
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall conﬁrm the position of all culverts with the Superintendent.
| note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
| note | METHOD: Construction Drawings
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
| date | Date Completed:
| checkpoint | 2.2 - CONFORMITY WITH DRAWINGS – The culverts constructed shall be constructed true to line and level
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Unless speciﬁed otherwise the tolerance on location of pipes compared to the design or a change to the design notiﬁed in accordance with this clause shall be:
| note | (a) oﬀset of entry pits required to match lines of kerbs or barriers ±20 mm
| note | (b) plan location of pits other than oﬀsets to kerb lines or barriers ±100 mm
| note | (c) invert level of pipes at pits ±50 mm (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
| note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
| note | METHOD: Construction Drawings
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
| date | Date Completed:
| checkpoint | 2.3 - EXCAVATION
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm
| note | REFERENCE DOCUMENTS: VicRoads Std Specs 701.14
| note | METHOD: On-site Measurement
| note | RECORD: Signed ITP & Drainage Checklist
| note | WP
| note | RESPONSIBILITY: Project Engineer/Site Supervisor
| date | Date Completed:
| checkpoint | 2.4 - CULVERT BEDDING - Bedding material shall be provided and placed for the full width of the trench or, where the culvert is to be placed without trenching, to a width 0.8 m greater than the overall width of the culvert
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: The compacted thickness of bedding material following any shaping necessary shall be not less than:
| note | ○ 100 mm where D < 1500 mm
| note | ○ 200 mm where D ≥ 1500 mm where D is the nominal pipe diameter or culvert width.
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.15
| note | METHOD: Site Inspection
| note | RECORD: Signed ITP
| note | WP
| note | RESPONSIBILITY: Project Engineer/Site Supervisor
| date | Date Completed:
| checkpoint | 2.5 - PLACEMENT OF FILLING
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: (a) Unless the culvert is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15.
| note | (I) Culvert Under Area not to be Paved
| note | ○ The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level.
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.18
| note | METHOD: Site Inspection
| note | RECORD: Signed ITP
| note | WP
| note | RESPONSIBILITY: Project Engineer/Site Supervisor
| date | Date Completed:
| checkpoint | 2.6 - INSPECTION OF DRAINAGE LINES BENEATH PAVEMENTS
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV).
| note | ○ Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.28
| note | METHOD: Visual inspection
| note | RECORD: Signed ITP
| note | HP/AP
| note | RESPONSIBILITY: Project Engineer/Clients Superinten dent
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Where required installation of Geofabric or Jute matting and beaching material in swale drains
| note | FREQUENCY: After installation of pipes, pits, end-walls and placement of asphalt wearing coarse
| note | ACCEPTANCE CRITERIA: Rock used, should be an assortment of sizes where possible. The smallest rock size must be able to resist dislodgment in peak ﬂows. Rock shall be placed with a geo-textile liner.
| note | REFERENCE DOCUMENTS: NIL
| note | METHOD: Visual inspection
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: Project Engineer/Si te Supervisor
| date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION AND MOISTURE CONTENT - Bedding and backﬁll materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
| note | FREQUENCY: 3 per Lot (A lot shall consist of one layer of bedding or backﬁll for a culvert length between adjacent pits or endwalls)
| note | ACCEPTANCE CRITERIA: (a) Bedding Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
| note | (b) Backﬁll
| note | (i) Material of Nominal Size 40 mm or Less After Compaction Backﬁll material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
| note | (ii) Material of Nominal Size Greater than 40 mm After Compaction Backﬁll material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
| note | REFERENCE DOCUMENTS: Vicroads std sec 701.19
| note | METHOD: Lab Test
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: SWA Project Manager
| date | Date Completed:
| checkpoint | Final Inspection
| note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| signoff | Sign ITP
| checklist | ITP-005 - Flexible Pavement Construction | itp | ITP-005 - Flexible Pavement Construction
| section | 1 - Preliminary Works
| checkpoint | 1.1 - SET OUT OF WORKS
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Ensure relevant construction drawing are being used to determine set-out of works.
| note | ○ Ensure all survey pegs are aligned max 40m apart and the oﬀset distances and heights are in accordance with relevant drawings
| note | ○ Refence checking to be conducted with string lines
| note | REFERENCE DOCUMENTS: Vicroads std sec 100.6
| note | METHOD: Survey set-out
| note | RECORD: Signed ITP
| note | SCP
| note | RESPONSIBILITY: SWA Project Manager
| date | Date Completed:
| checkpoint | 1.2 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173 – Examination and Testing of Materials and Work (Roadworks). The number of measurements taken within each lot shall not be less than the number speciﬁed in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
| note | REFERENCE DOCUMENTS: Vicroads std sec 204.03
| note | METHOD: Survey Report
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: SWA Project Manager
| date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (a) General
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Material during compaction shall have a moisture content of not less than 85% of optimum. After completion of compaction of a layer, the moisture content of the material in the layer shall be maintained at a moisture content of not less than 85% of optimum until test rolling has been completed.
| note | REFERENCE DOCUMENTS: Vicroads std sec 304.08
| note | METHOD: Visual & Laboratory Report
| note | RECORD: Signed ITP
| note | IHP/AP
| note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
| date | Date Completed:
| checkpoint | 2.2 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (b) Material of Nominal Size 40 mm or Less
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: The calculation of density ratio shall be based on tests performed using Modiﬁed compactive eﬀort. The work shall be assessed for compliance with Scale B requirements being not less than 97%. See table 304.081.
| note | ○ For work to be tested for compliance with Scale B requirements, the number of tests per lot shall be six. See table 304.121.
| note | ○ The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm.
| note | ○ The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
| note | REFERENCE DOCUMENTS: Vicroads std sec 304.08
| note | METHOD: Laboratory Test Report
| note | RECORD: Signed ITP
| note | IHP/IP/AP
| note | RESPONSIBILITY: SWA Project Manager/SWA Site supervisor/RRV Superintendent
| date | Date Completed:
| checkpoint | 2.3 - TEST ROLL PAVEMENT LAYER
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any ﬁll on the prepared areas until the area has been reviewed by the Superintendent. The Contractor shall provide for the Superintendent to be present during all test rolling.
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 173.03 & 204.12
| note | METHOD: Proof roll
| note | RECORD: Signed ITP & Test Report
| note | HP/AP
| note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: The surface level of the pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet either Scale B requirements as speciﬁed in Clause 304.12.
| note | ○ Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
| note | ○ Each level measurement shall be taken at random locations over the area of the lot in accordance with the VicRoads Test Method and the number of measurements taken within each lot shall not be less than the number speciﬁed in Table 304.061. Surface Level Tolerance as per Table 304.062
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 304.06
| note | METHOD: Survey report
| note | RECORD: Signed ITP
| note | IHP/WP
| note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
| date | Date Completed:
| checkpoint | Final Inspection
| note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations
| textbox | Print Name:
| textbox | Position:
| date | Date:
| signoff | Sign ITP
| checklist | ITP-006 - Kerb & Channel | itp | ITP-006 - Kerb & Channel
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
| note | – using the correct and complete set of drawings
| note | – all drawings are the latest revision
| note | REFERENCE DOCUMENTS: Vicroads std sec 100.6
| note | METHOD: Drawing Register
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: Site Supervisor
| date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
| note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
| date | Date Completed:
| checkpoint | 1.3 - Setting Out
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor. Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
| note | REFERENCE DOCUMENTS: Vicroads std sec 703.13
| note | METHOD: Survey Setout
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
| date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Excavation
| note | FREQUENCY: Check prior to placing material
| note | ACCEPTANCE CRITERIA: The base preparation for kerb and channel shall consist of a boxed out area to a depth of 355mm below FL and 1150mm wide. Excavation shall not extend more than 150mm from the edge of the adjacent face.
| note | REFERENCE DOCUMENTS: Vicroads std sec 703.20
| note | METHOD: Survey/Site Inspection
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
| date | Date Completed:
| checkpoint | 2.2 - Subgrade Inspection
| note | FREQUENCY: Check prior to placing material
| note | ACCEPTANCE CRITERIA: Test roll subgrade to check for No visual deformation or springing. Where deformation is exhibited, the Engineer or Superintendent is to be notiﬁed immediately.
| note | REFERENCE DOCUMENTS: Vicroads std sec 173.03, 173.03 (ii)
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
| date | Date Completed:
| checkpoint | 2.3 - Bedding Preparation
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Bedding material to be used for base preparation shall consist of size 20mm Class 3 or Class 4 crushed rock at a minimum of 100mm compacted thickness. Preparation of ﬁnished base shall be 190mm below lip of kerb as per survey marks.
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21
| note | METHOD: Site Inspection
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
| date | Date Completed:
| checkpoint | 2.4 - Kerb Concrete Mixture/Strength
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Traﬃc routes a minimum of or equivalent to 320kg of cementitious binder material or geopolymer binder per m3 of concrete – VR 330/32
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.05, 703.11
| note | METHOD: Delivery Dockets
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
| date | Date Completed:
| checkpoint | 2.5 - Tolerances on Line, Level & Shape
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: All surfaces shall be ﬁnished in conformity with the lines, grades, thicknesses and cross sections shown on the drawings or as speciﬁed. Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10mm. Except on curves or in shaped areas, the deviation of the ﬁnished work from a 3m straight edge shall not exceed 5mm at any point.
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
| date | Date Completed:
| checkpoint | 2.6 - Kerb and Channel Finish
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: All edging shall consist of a smooth, uniformed and of a trowel ﬁnish. The mortar used shall consist of two parts of ﬁne aggregate, one part cement and suﬃcient water to produce a mix of suitable consistency. Thickness of the rendering shall not exceed 3mm.
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21 (a)
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
| date | Date Completed:
| checkpoint | 2.7 - Kerb Backﬁll
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Once concrete has cured, topsoil which is free from perishable matter, shall be placed ﬁrmly compacted in layers less than 150mm thick and to a width of no less than 300mm behind the edging to the top of the edging.
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.29
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
| date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Compaction Testing
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six. A small lot is classed as an area equivalent to or less than 500m2 and requires only 3 individual tests. Compaction testing for crushed rock material shall be no less than 98%.
| note | REFERENCE DOCUMENTS: Vicroads std sec 304.08 (b) Table 304.081, 173.04 (d)
| note | METHOD: Test Point
| note | RECORD: Signed ITP
| note | TP/HP/AP
| note | RESPONSIBILITY: External Geo tester/SWA Project Manager/RRV Superintendent
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Conformance Testing for concrete strength & consistency.
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: The minimum compression strength requirements for each strength grade shall be as shown in Table 703.111
| note | REFERENCE DOCUMENTS: Vicroads std sec Table 703.111
| note | METHOD: Survey Report
| note | RECORD: Signed ITP & Test Reports
| note | TP/HP/AP
| note | RESPONSIBILITY: External Surveyor/SWA Project Manager/RRV Superintendent
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
| note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| signoff | Sign ITP
| checklist | ITP-007 - Hot Mix Asphalt | itp | ITP-007 - Hot Mix Asphalt
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Site Inspection and Base Conditions
| note | FREQUENCY: Prior to commencing paving.
| note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from surface water. All manhole and valve covers have been raised or lowered to the new surface level of the pavement.
| note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.1
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | WP
| note | RESPONSIBILITY: Site supervisor
| date | Date Completed:
| checkpoint | 1.2 - Ambient Conditions for Asphalt Placement
| note | FREQUENCY: Prior to commencing paving.
| note | ACCEPTANCE CRITERIA: Asphalt shall not be placed if the majority of the surface area is below:
| note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
| note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs.
| note | REFERENCE DOCUMENTS: Vicroads std sec 407.13
| note | METHOD: Calibrated thermometer
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: Project Engineer/Site supervisor
| date | Date Completed:
| checkpoint | 1.3 - Surface Preparation
| note | FREQUENCY: Prior to commencing paving.
| note | ACCEPTANCE CRITERIA: The area to be paved is free of all loose and deleterious material
| note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.3
| note | METHOD: Sweep Clean and Inspect
| note | RECORD: Signed ITP
| note | WP
| note | RESPONSIBILITY: Project Engineer/Site Supervisor
| date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Application of Tack Coat
| note | FREQUENCY: Prior to commencing paving
| note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform ﬁlm over the surface area at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
| note | REFERENCE DOCUMENTS: Vicroads std sec 407.15, AS2150 11
| note | METHOD: Visual Inspection & photo evidence
| note | RECORD: Signed ITP/Spray Record
| note | WP
| note | RESPONSIBILITY: Project Engineer/Site Supervisor
| date | Date Completed:
| checkpoint | 2.2 - Planned Joints
| note | FREQUENCY: Prior to commencing paving
| note | ACCEPTANCE CRITERIA: A site speciﬁc paving plan shall be generated by the contractor prior to asphalt commencement to adhere to the following: Transverse Joints: Oﬀset from layer to layer by at least 2m Longitudinal Joints: Oﬀset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines. Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an oﬀset from layer to layer of not less than 150mm.
| note | REFERENCE DOCUMENTS: Vicroads std sec 407.17 (b) & (c)
| note | METHOD: Measure and mark out runs and submit Paving Plan to Client if requested
| note | RECORD: Signed ITP/Job Sheet
| note | WP
| note | RESPONSIBILITY: Project Engineer/Site Supervisor
| date | Date Completed:
| checkpoint | 2.3 - Commencement of Placing
| note | FREQUENCY: Prior to commencing Paving
| note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub- base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Vicroads Superintendent.
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.18
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | HP
| note | RESPONSIBILITY: SWA Project Engineer
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Delivery of Mix
| note | FREQUENCY: Each Load
| note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.16, Table 407.081
| note | METHOD: Visual Inspection & Delivery Docket
| note | RECORD: Signed ITP & Production Dockets
| note | WP
| note | RESPONSIBILITY: Project Engineer/Site Supervisor
| date | Date Completed:
| checkpoint | 2.5 - Traceability
| note | FREQUENCY: Each Load
| note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, oﬀset/lane and layer
| note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
| note | METHOD: Project Engineer/Site Supervisor
| note | RECORD: Signed ITP & Traceability
| note | IP
| note | RESPONSIBILITY: Project Engineer/Site Supervisor
| date | Date Completed:
| checkpoint | 2.6 - Layer Thickness and Level Control
| note | FREQUENCY: Regularly during paving
| note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or speciﬁcations
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20
| note | METHOD: Dips, string line, measurements oﬀ kerb
| note | RECORD: Signed ITP & Traceability
| note | WP
| note | RESPONSIBILITY: Project Engineer/Site Supervisor
| date | Date Completed:
| checkpoint | 2.7 - Paver Stoppages
| note | FREQUENCY: If paver stops
| note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
| note | Asphalt should be ramped down by constructing a temporary wedge of dense graded or cold mixed asphalt. Max ramp grade:
| note | ○ 40km/h – 20-1
| note | ○ 60km/h – 30-1
| note | ○ 80km/h – 40-1
| note | ○ >80km/h – 50-1
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20 (c)
| note | METHOD: Thermometer
| note | RECORD: Signed ITP & Traceability
| note | WP
| note | RESPONSIBILITY: Project Engineer/Site Supervisor
| date | Date Completed:
| checkpoint | 2.8 - Surface Finish of Wearing Course
| note | FREQUENCY: During paving and after ﬁnal roll
| note | ACCEPTANCE CRITERIA: The ﬁnished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (i)
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP & Traceability
| note | WP
| note | RESPONSIBILITY: Project Engineer/Site Supervisor
| date | Date Completed:
| checkpoint | 2.9 - Kerb and Channel
| note | FREQUENCY: During paving and after ﬁnal roll
| note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either ﬂush with or not more than 5 mm above the lip of the channel unless otherwise speciﬁed
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (ii)
| note | METHOD: Visual Inspection & Measurement
| note | RECORD: Signed ITP & Traceability
| note | WP
| note | RESPONSIBILITY: Project Engineer/Site Supervisor
| date | Date Completed:
| checkpoint | 2.10 - Alignment of layers not placed against concrete edge
| note | FREQUENCY: During paving and at completion of work
| note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed oﬀset from centreline or design line. The rate of change of oﬀset of the edge of layer shall not be greater than 25mm in 10m
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (iv)
| note | METHOD: Alignment as marked by Surveyor and measured
| note | RECORD: Survey Report
| note | SCP
| note | RESPONSIBILITY: Client Surveyor, Project Engineer, Site Supervisor
| date | Date Completed:
| checkpoint | 2.11 - Width of layers not placed against concrete edge
| note | FREQUENCY: During paving and at completion of work
| note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or speciﬁed width of layer by more than 50mm or greater than the design or speciﬁed width by more than 100mm.
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
| note | METHOD: Measurement
| note | RECORD: Survey Report
| note | IP
| note | RESPONSIBILITY: Project Engineer/Site Supervisor
| date | Date Completed:
| checkpoint | 2.12 - Traﬃcking of Asphalt & Paving of multiple layers
| note | FREQUENCY: During paving and at completion of work
| note | ACCEPTANCE CRITERIA: Traﬃcking of asphalt or placement of asphalt over freshly laid asphalt layer is not permitted unless the majority of the asphalt has a surface temperature lower than 50°C
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
| note | METHOD: Measurement or suﬃcient time has lapsed
| note | RECORD: This ITP
| note | IP
| note | RESPONSIBILITY: Project Engineer/Site Supervisor
| date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Compaction
| note | FREQUENCY: Per Lot (6 shot test)
| note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
| note | ○ 95.0% or greater Accept lot
| note | ○ 94.9% to 93.0% Lot may be accepted at reduced rate
| note | ○ 92.9% or less Remove and replace asphalt
| note | For layers ≥50mm, if characteristic thickness is:
| note | ○ 96.0% or greater Accept lot
| note | ○ 95.0% to 94.0% Lot may be accepted at reduced rate.
| note | ○ 93.9% or less Remove and replace asphalt
| note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.221
| note | METHOD: Compaction Testing
| note | RECORD: Asphalt Field Compaction Report
| note | TP
| note | RESPONSIBILITY: Fulton Hogan Laboratory Technician Veriﬁed by Project Engineer
| date | Date Completed:
| checkpoint | 3.2 - Surface Levels
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
| note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.222
| note | METHOD: Survey
| note | RECORD: Signed ITP & Survey Reports
| note | SCP
| note | RESPONSIBILITY: External Surveyor Project Engineer to verify
| date | Date Completed:
| checkpoint | Final Inspection
| note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| signoff | Sign ITP
| checklist | ITP-009 - Road Signage Checklist | itp | ITP-009 - Road Signage Checklist
| checkpoint | Inspection Checklist Items
| textbox | Sign Code & Dimensions
| textbox | Chainage Location
| textbox | Number & Post per Assembly
| textbox | Mounting Height (H) (mm) & Spacing b/w post(S) (mm)
| textbox | Post Hole Depth (D) (mm)
| textbox | Fitting Type and Number of Fitting
| date | Footing and Sign Installation Date
| note | Photos
| checkpoint | Final Inspection
| note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| signoff | Sign ITP
| checklist | ITP-010 - Guardrail | itp | ITP-010 - Guardrail
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
| note | – using the correct and complete set of drawings
| note | – all drawings are the latest revision..
| note | REFERENCE DOCUMENTS: Design Drawings
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: Project Manager/ Site Supervisor
| date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS
| note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: Project Manager/ Site Supervisor
| date | Date Completed:
| checkpoint | 1.3 - Setting Out
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor.
| note | ○ Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
| note | REFERENCE DOCUMENTS: Drawings 708.08
| note | METHOD: Document Review
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: Project Manager/ Site Supervisor Superintendent
| date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Supply of materials
| note | FREQUENCY: Each Delivery
| note | ACCEPTANCE CRITERIA: All materials are to be on VicRoads current accepted products list and conform with the detailed design
| note | REFERENCE DOCUMENTS: 708.04, 708.05 Detailed design
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: Project Manager/ Site Supervisor
| date | Date Completed:
| checkpoint | 2.2 - Installation
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: The oﬀset, height and post spacing is to conform with VicRoads speciﬁcations and the detailed design
| note | ○ Where the face of guardrail is less that 1m behind back of kerb, the mounting height should be measured from lip of kerb. Otherwise measure from ground level Fasteners are to be snug tightened to AS4100
| note | REFERENCE DOCUMENTS: Detailed design 708.08 SD3661 AS4100
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: SWA Engineer/Site Supervisor
| date | Date Completed:
| checkpoint | 2.3 - End Treatments
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Guardrail end treatments are to be installed to VicRoads speciﬁcations
| note | REFERENCE DOCUMENTS: Detailed design 708.08
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: SWA Engineer/Site Supervisor
| date | Date Completed:
| checkpoint | 2.4 - Motorcycle rub rail
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Where speciﬁed, motorcycle rub rail is to be installed on the new length of guardrail
| note | REFERENCE DOCUMENTS: Detailed design 708.09
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: SWA Engineer/Site Supervisor
| date | Date Completed:
| checkpoint | Final Inspection
| note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| signoff | Sign ITP
| checklist | ITP-015 - Drainage Checklist | itp | ITP-015 - Drainage Checklist
| checkpoint | Pit Details
| textbox | Pit No.
| textbox | Pit Type
| textbox | Dimension
| textbox | Inlet Level
| textbox | Outlet Level
| textbox | FSL
| textbox | Pit Depth
| checkpoint | Checklist Items
| textbox | Drainage Line Number
| textbox | Pipe Size
| textbox | Trench Width (mm)
| textbox | Minimum Cover (mm)
| textbox | Beading Depth (mm)
| date | Start Date
| date | Finish Date
| checkpoint | Pipe/Pits/End Walls
| note | Pipes/Pits/End Wall in sound condition?
| date | Start Date
| date | Finish Date
| checkpoint | Laying Direction
| note | The direction of Laying Satisfactory i.e Collar on Upstream?
| date | Start Date
| date | Finish Date
| checkpoint | Rubber Joint
| note | Rubber Joints in Satisfactory condition?
| date | Start Date
| date | Finish Date
| checkpoint | Gap Filling
| note | All the holes have been mortared to satisfactory condition?
| date | Start Date
| date | Finish Date
| checkpoint | Step Irons
| note | Step Irons Installed in the Pit greater than 1000mm?
| date | Start Date
| date | Finish Date
| checkpoint | Final Inspection
| note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| signoff | Sign ITP
| checklist | ITP-045 - General Concrete Paving | itp | ITP-045 - General Concrete Paving
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
| note | – using the correct and complete set of drawings
| note | – all drawings are the latest revision
| note | REFERENCE DOCUMENTS: IFC Drawings
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: SWA Project Manager
| date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
| note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: SWA Project Manager
| date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Survey Set-Out
| note | FREQUENCY: Prior to commencement of excavation.
| note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
| note | REFERENCE DOCUMENTS: Work Procedure
| note | METHOD: Verify
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: SWA Project Manager
| date | Date Completed:
| checkpoint | 2.2 - Excavation Permit
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
| note | REFERENCE DOCUMENTS: Excavation Permit
| note | METHOD: Verify
| note | RECORD: Signed ITP
| note | IHP/IP
| note | RESPONSIBILITY: SWA Project Manager/SWA SEQ Adviser
| date | Date Completed:
| checkpoint | 2.3 - Formwork
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
| note | REFERENCE DOCUMENTS: AS 3610
| note | METHOD: Site Inspection
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: SWA Project Manager
| date | Date Completed:
| checkpoint | 2.4 - Reinforcement
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Steel reinforcement shall comply with the requirements of AS/NZS 4671. Minimum cover of 50mm.
| note | REFERENCE DOCUMENTS: AS/NZS 4671
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IP
| note | RESPONSIBILITY: SWA Project Manager
| date | Date Completed:
| checkpoint | 2.5 - Temporary Drainage Provisions
| note | FREQUENCY: Prior to commencing
| note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place. Obtain written approval from relevant waterway authority.
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: SWA Project Manager
| date | Date Completed:
| checkpoint | 2.6 - Bedding
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Crushed rock bedding material as per drawings
| note | ○ Bedding trimmed, moistened, and compacted as necessary
| note | ○ Bedding compacted thickness: Footpaths and other surfacing ≥ 50mm
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.18 IFC Drawings
| note | METHOD: Site Inspection/ Document Review
| note | RECORD: Signed ITP
| note | IHP/AP
| note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
| date | Date Completed:
| checkpoint | 2.7 - Concrete Placement
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Concrete strength as per drawing speciﬁcation
| note | ○ Comply with requirements of AS1379
| note | ○ Aggregates to comply with Table 703.051
| note | ○ Extrusion machines cement content ≥ 320kg/m3
| note | ○ Surface pitting < 5mm diameter
| note | ○ Concrete to be satisfactorily compacted. Proﬁle transitions between 10-20mm per metre.
| note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.04(b), VicRoads Std Specs 703.20, VicRoads Std Specs 703.21 IFC Drawings AS 1379
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP & Test Reports
| note | IHP/AP/TP
| note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representat ive
| date | Date Completed:
| checkpoint | 2.8 - Finish Surfaces
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Footpaths and other Surfacing: Wooden ﬂoat ﬁnish
| note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.22
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP & Test Reports
| note | IHP/AP
| note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
| date | Date Completed:
| checkpoint | 2.9 - Tolerances
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Match existing surfaces ± 5mm
| note | Section dimensions:
| note | ○ Within 5mm and 15mm for width; and
| note | ○ Within ±3mm for dimensions less than 25mm.
| note | Concrete footpath:
| note | ○ 150mm thick
| note | ○ SL72 reinforcement
| note | Concrete Surfacing:
| note | ○ Type 1 100mm
| note | ○ Type 2 150mm
| note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.13 IFC Drawings
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: SWA Project Manager
| date | Date Completed:
| checkpoint | 2.10 - Joints
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Footpaths and other surfacing:
| note | ○ Expansion joints at 12.5m regular intervals
| note | ○ Control joints at 2.5m regular intervals
| note | ○ 20mm deep and 5mm wide
| note | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
| note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.23
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: SWA Project Manager
| date | Date Completed:
| checkpoint | 2.11 - Backﬁlling
| note | FREQUENCY: Each lot as required
| note | ACCEPTANCE CRITERIA: Topsoil compacted in layers < 150mm
| note | ○ Width ≥ 300mm behind edging to top of edging
| note | ○ Topsoil placed after 3 days of concrete placement
| note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.26
| note | METHOD: Visual Inspection
| note | RECORD: Signed ITP
| note | IHP
| note | RESPONSIBILITY: SWA Project Manager
| date | Date Completed:
| checkpoint | Final Inspection
| note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| signoff | Sign ITP
| checklist | SWA-013 - Pre - Construction | itp | SWA-013 - Pre - Construction
| section | 1.0 - Pre-Construction Checklist
| checkpoint | 1.1 - Communication (1)
| note | ACTIVITY / DESCRIPTION: Community and emergency services
| date | Date:
| checkpoint | 1.1 - Communication (2)
| note | ACTIVITY / DESCRIPTION: Emergency response plan
| date | Date:
| checkpoint | 1.2 - Approved Construction Documentation (1)
| note | ACTIVITY / DESCRIPTION: IFC drawings (PDF, hardcopy)
| date | Date:
| checkpoint | 1.2 - Approved Construction Documentation (2)
| note | ACTIVITY / DESCRIPTION: Digital (CAD) files (Surveyor)
| date | Date:
| checkpoint | 1.2 - Approved Construction Documentation (3)
| note | ACTIVITY / DESCRIPTION: Budget / Resource arrangement POs (incl. sub-contract agreements)
| date | Date:
| checkpoint | 1.2 - Approved Construction Documentation (4)
| note | ACTIVITY / DESCRIPTION: Quantities / Specifications
| date | Date:
| checkpoint | 1.3 - Dilapidation Report (records and photographs) (1)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Residential (ie: structures, access/gate, letterbox, fence)
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Dilapidation Report (records and photographs) (2)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Business (ie: structures, access/fence/gate, signs/letterbox)
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Dilapidation Report (records and photographs) (3)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Agricultural (ie: access, livestock, fence/gate)
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Heritage / Cultural listed areas: (1)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: "No Go Zone"
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Heritage / Cultural listed areas: (2)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Tourist attraction
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Protected Environment (1)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Flora
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Protected Environment (2)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Fauna
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Protected Environment (3)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Water bodies
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (1)
| note | ACTIVITY / DESCRIPTION: Dial Before You Dig
| date | Date:
| checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (2)
| note | ACTIVITY / DESCRIPTION: Excavation Permit
| date | Date:
| checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (3)
| note | ACTIVITY / DESCRIPTION: Assess and arrange for Service location
| date | Date:
| section | 2.0 - Pre-Commencement Checklist
| checkpoint | 2.1 - Traffic Items (1)
| note | ACTIVITY / DESCRIPTION: VMS boards
| date | Date:
| checkpoint | 2.1 - Traffic Items (2)
| note | ACTIVITY / DESCRIPTION: TGS/TMP, MoA
| date | Date:
| checkpoint | 2.2 - Site marks / references (1)
| note | ACTIVITY / DESCRIPTION: Limit of Works
| date | Date:
| checkpoint | 2.2 - Site marks / references (2)
| note | ACTIVITY / DESCRIPTION: Survey control point
| date | Date:
| checkpoint | 2.3 - Services, inspect/identify clash points: (1)
| note | ACTIVITY / DESCRIPTION: Sewer, Water
| date | Date:
| checkpoint | 2.3 - Services, inspect/identify clash points: (2)
| note | ACTIVITY / DESCRIPTION: Gas, Electricity
| date | Date:
| checkpoint | 2.3 - Services, inspect/identify clash points: (3)
| note | ACTIVITY / DESCRIPTION: Telecommunication
| date | Date:
| checkpoint | 2.3 - Services, inspect/identify clash points: (4)
| note | ACTIVITY / DESCRIPTION: Drainage (ie: council/shire, Other state authority)
| date | Date:
| checkpoint | 2.3 - Services, inspect/identify clash points: (5)
| textbox | ACTIVITY / DESCRIPTION: Other specify:
| date | Date:
| checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (1)
| textbox | ACTIVITY / DESCRIPTION: O/H and U/G services flagged "No Go Zone"
| date | Date:
| checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (2)
| textbox | ACTIVITY / DESCRIPTION: Trees(s) marked and approved for trimming or removal
| date | Date:
| checkpoint | 2.5 - SWMSs reviewed: (1)
| textbox | ACTIVITY / DESCRIPTION: Site-specific
| date | Date:
| checkpoint | 2.5 - SWMSs reviewed: (2)
| textbox | ACTIVITY / DESCRIPTION: Spotter required / arranged
| date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (1)
| textbox | ACTIVITY / DESCRIPTION: Sight and Clearance Distances:
| date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (2)
| textbox | ACTIVITY / DESCRIPTION: Stop-slow areas, spotter, slips, confined space/work at height
| date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (3)
| textbox | ACTIVITY / DESCRIPTION: Vehicle access to properties
| date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (4)
| textbox | ACTIVITY / DESCRIPTION: Proximity to Services: clearance requirements
| date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (5)
| textbox | ACTIVITY / DESCRIPTION: Proximity to Water: supply point, watertable/dam/river/coast/port
| date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (6)
| textbox | ACTIVITY / DESCRIPTION: Site compound/Plant parking, material stockpile area, "dumpsite"
| date | Date:
| section | 3.0 - Construction
| checkpoint | 3.1 - Vegetation Removal (1)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Spotter, Traffic Control
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Vegetation Removal (2)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Equipment, Access
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Vegetation Removal (3)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Soil erosion / water contamination
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Contaminated Materials
| note | ACTIVITY / DESCRIPTION: Contaminated Materials
| date | Date:
| checkpoint | 3.3 - Traffic Items (1)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: External review: Road Safety Audit
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Traffic Items (2)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Internal review: adjust hold-time (traffic lights / traffic controller), flowbias, identify peak-hour period(s) / public transport / rubbish collection
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Trenching works (1)
| note | ACTIVITY / DESCRIPTION: Review escape plan (routes)
| date | Date:
| checkpoint | 3.4 - Trenching works (2)
| note | ACTIVITY / DESCRIPTION: Review ground / water conditions
| date | Date:
| checkpoint | 3.4 - Trenching works (3)
| note | ACTIVITY / DESCRIPTION: Indentify Shoring / Benching requirements
| date | Date:
| checkpoint | 3.5 - Drainage Works (1)
| note | ACTIVITY / DESCRIPTION: Assess surface-water impact – flow-path / catchment / outlet
| date | Date:
| checkpoint | 3.5 - Drainage Works (2)
| note | ACTIVITY / DESCRIPTION: Surface drainage (swale drain)
| date | Date:
| checkpoint | 3.5 - Drainage Works (3)
| note | ACTIVITY / DESCRIPTION: Sub-surface drain pipe and aggregate (agricultural drains / "agi pipe")
| date | Date:
| checkpoint | 3.5 - Drainage Works (4)
| note | ACTIVITY / DESCRIPTION: Review confined space entry
| date | Date:
| checkpoint | 3.5 - Drainage Works (5)
| note | ACTIVITY / DESCRIPTION: Review lifting methods (load / equipment / plant / crane)
| date | Date:
| checkpoint | 3.5 - Drainage Works (6)
| note | ACTIVITY / DESCRIPTION: Levels
| date | Date:
| checkpoint | 3.5 - Drainage Works (7)
| note | ACTIVITY / DESCRIPTION: Pit covers / Grates
| date | Date:
| checkpoint | 3.6 - Structural Items (1)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Crown units / culvert
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Structural Items (2)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Retaining structure works
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Structural Items (3)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Bridge works
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Concrete kerb works: (1)
| note | ACTIVITY / DESCRIPTION: Alignment / level
| date | Date:
| checkpoint | 3.7 - Concrete kerb works: (2)
| note | ACTIVITY / DESCRIPTION: profile / finish
| date | Date:
| checkpoint | 3.8 - Concrete Works (1)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION:
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (1)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: (in-situ & pre-cast) - Bedding material / blinding material
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (2)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: (in-situ) - Formwork, duct-work
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (3)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: (pre-cast) Alignment/dimensions
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (4)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: (in-situ) - Rebar layout
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (5)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: (in-situ) - Concrete mix / Compaction / Placement method(s)
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (6)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: (pre-cast) - Lift points / placement method
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (7)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: (in-situ & precast) - Pre-stress works (where applicable)
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (8)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: (in-situ & precast) Finish
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (1)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Require in-situ testing / laboratory report (where required)
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (2)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Material dockets (ie: Lime / Cement)
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (3)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Density results
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (4)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Proof-roll
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.10 - Pavement Works (1)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Density results
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.10 - Pavement Works (2)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Proof-roll / Test Rolling
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.10 - Pavement Works (3)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Dryback results (NB: required prior to sealing works)
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.10 - Pavement Works (4)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Ball Penetration Test
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.11 - Utility Services, Traffic / Public lights (1)
| note | ACTIVITY / DESCRIPTION: Level & Location (ie: clearance requirement)
| date | Date:
| checkpoint | 3.11 - Utility Services, Traffic / Public lights (2)
| note | ACTIVITY / DESCRIPTION: Approved equipment for installation
| date | Date:
| checkpoint | 3.11 - Utility Services, Traffic / Public lights (3)
| note | ACTIVITY / DESCRIPTION: Pit and conduit (ie: clearance requirement)
| date | Date:
| checkpoint | 3.11 - Utility Services, Traffic / Public lights (4)
| note | ACTIVITY / DESCRIPTION: Audits by relevant authority / hand-over procedure
| date | Date:
| checkpoint | 3.12 - Pavement Surface Works (1)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Seal (ie: suitable material, spray-sheet details)
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.12 - Pavement Surface Works (2)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Asphalt (ie: material dockets)
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.13 - Landscape (1)
| note | ACTIVITY / DESCRIPTION: Seed / Grass
| date | Date:
| checkpoint | 3.13 - Landscape (2)
| note | ACTIVITY / DESCRIPTION: Hydro-seed / Hydromulch
| date | Date:
| checkpoint | 3.13 - Landscape (3)
| note | ACTIVITY / DESCRIPTION: Street furniture
| date | Date:
| checkpoint | 3.13 - Landscape (4)
| note | ACTIVITY / DESCRIPTION: Maintenance arrangement / period: 3 / 6 / 12 / 18 / 24 months
| date | Date:
| section | 4.0 - Practical Completion
| checkpoint | 4.1 - Road Fixtures (1)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1 - Road Fixtures (2)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Signs
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1 - Road Fixtures (3)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Guide posts
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Safety Barrier Works (1)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Guardrail
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Safety Barrier Works (2)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Wire-rope
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Safety Barrier Works (3)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Motorcycle-safe fixtures
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Fences and Gates
| note | ACTIVITY / DESCRIPTION: Fences and Gates
| date | Date:
| checkpoint | 4.4 - Quality Ride Test
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Quality Ride Test
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| section | 5.0
| checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (1)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (2)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Signs, guide posts
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (3)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Seal / Asphalt surface
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (4)
| note | EXTERNAL REFERENCE: Hold Point (HP)
| note | ACTIVITY / DESCRIPTION: Landscape (where applicable)
| date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
| note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| signoff | Sign ITP
| checklist | ITP-002 - Construction of Underground Stormwater Drainage | itp | ITP-002 - Construction of Underground Stormwater Drainage
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
| note | – using the correct and complete set of drawings
| note | – all drawings are the latest revision
| note | REFERENCE DOCUMENTS: Drawings and drawing registers
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | HP*
| note | RESPONSIBILITY: Project Engineer / Site Foreman
| date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
| note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | HP*
| note | RESPONSIBILITY: Project Engineer / Site Foreman
| date | Date Completed:
| checkpoint | 1.3 - Precast Materials Inspection
| note | FREQUENCY: Each Delivery
| note | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
| note | REFERENCE DOCUMENTS: 701.04b
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
| note | IP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| checkpoint | 1.4 - Precast Pipe Compliance
| note | FREQUENCY: Prior to Commencing
| note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058. Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2.
| note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619, Cl. 701.04(a), Cl. 701.04(b)(i), Cl. 705.04(d), Cl. 705.11, AS4058, AS4680
| note | INSPECTION/TEST METHOD: Document review & Site inspection
| note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
| note | IP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| checkpoint | 1.5 - Bedding material classification
| note | FREQUENCY: Prior to start
| note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
| note | ○ 100% passing 19mm sieve.
| note | ○ 5%-40% passing 0.075mm.
| note | ○ PI = 20 max.
| note | REFERENCE DOCUMENTS: 701.04e Table 701.041, Table 701.042, Table 701.231
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: Test Reports from supplier
| note | TP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| checkpoint | 1.6 - Backfill material Classification
| note | FREQUENCY: Prior to start
| note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
| note | ○ 100% passing 37.5mm sieve.
| note | ○ 5%-40% passing 0.075mm sieve.
| note | ○ PI = 20 max.
| note | REFERENCE DOCUMENTS: 701.04e Table 701.041, Table 701.042, Table 701.231
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: Test Reports from supplier
| note | TP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| checkpoint | 1.7 - Mortar material classification
| note | FREQUENCY: Prior to start
| note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
| note | REFERENCE DOCUMENTS: 610.33
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: Test Reports from supplier
| note | TP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Excavation Permit
| note | FREQUENCY: Each lot
| note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
| note | ○ Plant and equipment shall be appropriate for the task.
| note | ○ Excavation operations shall not disturb areas outside the limit of excavation
| note | REFERENCE DOCUMENTS: Excavation permit
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP*
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| checkpoint | 2.2 - Set out drainage
| note | FREQUENCY: Prior to excavation
| note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
| note | REFERENCE DOCUMENTS: Drawings 701.10
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP
| note | RESPONSIBILITY: Engineer / Forman & Superintendent
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Excavation (pipes)
| note | FREQUENCY: Each Trench
| note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical.
| note | Depth of trench:
| note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
| note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
| note | REFERENCE DOCUMENTS: 701.15 Table 701.151
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Site Foreman
| date | Date Completed:
| checkpoint | 2.4 - Compact base of trench
| note | FREQUENCY: Each Trench
| note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
| note | REFERENCE DOCUMENTS: 701.1
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| checkpoint | 2.5 - Place bedding material & compact
| note | FREQUENCY: Each Trench
| note | ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness:
| note | – 100mm under pipes.
| note | – 80mm (earth foundation)
| note | – 150mm (rock foundation)
| note | REFERENCE DOCUMENTS: 701.19
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| checkpoint | 2.6 - Place pipes
| note | FREQUENCY: Each Line/Pit
| note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
| note | REFERENCE DOCUMENTS: Drawings 701.17
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Project Engineer / Site Foreman
| date | Date Completed:
| checkpoint | 2.7 - Jointing pipe sections
| note | FREQUENCY: Each Line
| note | ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance to manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
| note | REFERENCE DOCUMENTS: 701.18
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Project Engineer / Site Foreman
| date | Date Completed:
| checkpoint | 2.8 - Place & compact backfill material over pipes
| note | FREQUENCY: each lot
| note | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
| note | ○ Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
| note | ○ Loose layer thickness <= 150mm.
| note | ○ 1 lot = 150mm layer
| note | REFERENCE DOCUMENTS: 701.14, 701.15
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Site Engineer / Site Foreman
| date | Date Completed:
| checkpoint | 2.9 - Repairs to damaged pipes
| note | FREQUENCY: Each damaged pipe
| note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedure. All repair procedures undertaken in accordance with Cl 701.25.
| note | REFERENCE DOCUMENTS: 701.31
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP
| note | RESPONSIBILITY: Engineer / Forman & Superintendent
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Testing & Completion
| checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
| note | FREQUENCY: as required/requested
| note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort. Bedding material shall be compacted using a compaction plated to refusal.
| note | REFERENCE DOCUMENTS: 701.2
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: Test Reports
| note | TP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| checkpoint | Final Inspection
| note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| checklist | ITP-008 - Line Marking | itp | ITP-008 - Line Marking
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Line marking Conformance
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Materials to be used conform with specification
| note | REFERENCE DOCUMENTS: Review Materials Sheet
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
| note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| checkpoint | 1.3 - Site preparation
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Removal of any existing unsound,obsolete or redundant pavement markings. Removal of any foreign material or debris.
| note | REFERENCE DOCUMENTS: 721.A06
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| checkpoint | 1.4 - Set-out of Pavement Markings
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Pavement markings to set-out in accordance with IFC Drawings.
| note | REFERENCE DOCUMENTS: 721.A09
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Construction Works
| checkpoint | 2.2 - Line marking Installation
| note | FREQUENCY: During Construction
| note | ACCEPTANCE CRITERIA: Line marking installed as per IFC Drawings
| note | REFERENCE DOCUMENTS: 7210
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| checkpoint | 2.3 - Glass bead Install
| note | FREQUENCY: During line marking works
| note | ACCEPTANCE CRITERIA: Glass beads sprinkled/sprayed on to line marking while in a fluid state to ensure embedment. Glass beads to have uniform distribution
| note | REFERENCE DOCUMENTS: 72100
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Project Engineer/ Superintendent
| date | Date Completed:
| section | 3 - Completion
| checkpoint | 3.1 - Completion Inspection
| note | FREQUENCY: Each lot
| note | ACCEPTANCE CRITERIA: Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, streats, overlaps, unbeaded areas, tyre marks or other defects. Edges and cuts-offs shall be neat and sharp, and there shall be no visible run-off, overspray, dribbles,splash or spiliage on to the surrounding area, or on to parked or passing vehicles.
| note | REFERENCE DOCUMENTS: 7210
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Project Engineer/ Superintendent
| date | Date Completed:
| checkpoint | Final Inspection
| note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| checklist | ITP-015 - Construction of Concrete Paving | itp | ITP-015 - Construction of Concrete Paving
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
| note | – using the correct and complete set of drawings
| note | – all drawings are the latest revision
| note | REFERENCE DOCUMENTS: Drawings and drawing registers
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP*
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
| note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP*
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
| note | FREQUENCY: Prior to start
| note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
| note | REFERENCE DOCUMENTS: 703.17
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP
| note | RESPONSIBILITY: Project Engineer/ Superintendent
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Temporary Drainage Provisions
| note | FREQUENCY: If Required
| note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
| note | REFERENCE DOCUMENTS: Cl 703.18
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| checkpoint | 2.3 - Bedding
| note | FREQUENCY: Each lot
| note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
| note | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
| note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
| note | REFERENCE DOCUMENTS: Cl 703.21
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Project Engineer/ Superintendent
| date | Date Completed:
| checkpoint | 2.4 - Pre-concrete check
| note | FREQUENCY: Each lot
| note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
| note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
| note | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
| note | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
| note | REFERENCE DOCUMENTS: Cl 703.08
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: ITP Signed
| textbox | Ambient Temperature
| textbox | Concrete Temperature
| note | HP*/ WP
| note | RESPONSIBILITY: Project Engineer/ Superintendent
| date | Date Completed:
| checkpoint | 2.5 - Reinforcement
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Steel reinforcement shall comply with the requirements of AS/NZS 4671, Minimum cover of 50mm
| note | REFERENCE DOCUMENTS: AS/NZS 4671
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| checkpoint | 2.6 - Concrete Placement
| note | FREQUENCY: Each lot
| note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
| note | REFERENCE DOCUMENTS: VicRoads Spec Cl 703.23
| note | INSPECTION/TEST METHOD: Site Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| checkpoint | 2.7 - Finish Surfaces
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished. Concrete to have a neat appearance and uniform colour.
| note | REFERENCE DOCUMENTS: 703
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Site Engineer/ Site Foreman
| date | Date Completed:
| checkpoint | 2.8 - Joints
| note | FREQUENCY: Each joint
| note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
| note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
| note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
| note | REFERENCE DOCUMENTS: 703.26
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| checkpoint | 2.9 - Backfilling
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
| note | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
| note | ○ Layers shall not exceed 150mm compacted depth
| note | REFERENCE DOCUMENTS: 703.29
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| checkpoint | Final Inspection
| note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| checklist | ITP-017 - Sealing Works - Asphalt Laying Works | itp | ITP-017 - Sealing Works - Asphalt Laying Works
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Submission of Mix Design
| note | FREQUENCY: Prior to commencing paving
| note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
| note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
| note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
| note | RECORD OF CONFORMITY: VR approval, Completed ITP
| note | HP
| note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor/Superintendent
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Implementation of all measures and controls
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & WP
| note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | HP*
| note | RESPONSIBILITY: Site Engineer/Site Foreman
| date | Date Completed:
| checkpoint | 1.3 - Site Inspection and Base Condition
| note | FREQUENCY: Prior to commencing paving
| note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
| note | REFERENCE DOCUMENTS: 407.14, AS2150 10.1, AS2150 10.3
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
| date | Date Completed:
| checkpoint | 1.4 - Ambient Conditions for Placing
| note | FREQUENCY: Prior to commencing paving
| note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
| note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
| note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
| note | REFERENCE DOCUMENTS: 407.13
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: Thermometer
| note | IP
| note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
| date | Date Completed:
| checkpoint | 1.5 - Planning of Joints
| note | FREQUENCY: Prior to commencing paving
| note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
| note | ○ Transverse Joints Offset from layer to layer by at least 2m
| note | ○ Longitudinal Joints Offset from layer to layer by at least
| note | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
| note | REFERENCE DOCUMENTS: 407.17 (b) & (c) Pavement Drawings
| note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
| note | RECORD OF CONFORMITY: Paving Plan
| note | WP
| note | RESPONSIBILITY: Project Engineer/Asphalt Supervisor
| date | Date Completed:
| section | 2 - Asphalt Placement works
| checkpoint | 2.1 - Commencement of Placing
| note | FREQUENCY: Prior to commencing Paving
| note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
| note | REFERENCE DOCUMENTS: 407.18
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP
| note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor/Superintendent
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Delivery of Mix
| note | FREQUENCY: Each load
| note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
| note | REFERENCE DOCUMENTS: 407.16 Table 407.081
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: Delivery Docket
| note | WP
| note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
| date | Date Completed:
| checkpoint | 2.3 - Traceability
| note | FREQUENCY: Each lot
| note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
| note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: Daily Lot Record
| note | IP
| note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
| date | Date Completed:
| checkpoint | 2.4 - Layer Thickness and Level Control
| note | FREQUENCY: Regularly during paving
| note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
| note | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: Dips using ruler or dip stick
| note | WP
| note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
| date | Date Completed:
| checkpoint | 2.5 - Surface Finish of Wearing Course
| note | FREQUENCY: During paving and after final roll
| note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
| note | REFERENCE DOCUMENTS: 407.23 (a)(i)
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
| date | Date Completed:
| checkpoint | 2.6 - Kerb and Channel
| note | FREQUENCY: During paving and after final roll
| note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
| note | REFERENCE DOCUMENTS: 407.23 (a)(ii)
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
| date | Date Completed:
| checkpoint | 2.7 - Alignment of layers not placed against concrete edge
| note | FREQUENCY: During paving and at completion of work
| note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
| note | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
| note | REFERENCE DOCUMENTS: 407.23 (a)(iv) Drawings
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Site Engineer/Asphalt Supervisor
| date | Date Completed:
| section | 3 - Testing
| checkpoint | 3.1 - Compaction
| note | FREQUENCY: Per Lot
| note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
| note | ○ 94.0% or greater Accept lot
| note | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
| note | For layers ≥50mm, if characteristic thickness is:
| note | ○ 96.0% or greater Accept lot
| note | ○ 91.0% to 95.9% Lot may be accepted at reduced rate
| note | REFERENCE DOCUMENTS: Table 407.221
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: Test Report
| note | TP
| note | RESPONSIBILITY: Site Engineer/FH Lab Technician
| date | Date Completed:
| checkpoint | 3.2 - Level Conformance
| note | FREQUENCY: Per Lot
| note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm
| note | REFERENCE DOCUMENTS: Table 407.232
| note | INSPECTION/TEST METHOD: String Sheet
| note | RECORD OF CONFORMITY: Survey Conformance
| note | SCP
| note | RESPONSIBILITY: Site Engineer/Supervisor
| date | Date Completed:
| checkpoint | Final Inspection
| note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| checklist | ITP-031 - Aspahlt Wombat Crossing | itp | ITP-031 - Aspahlt Wombat Crossing
| section | 1 - Preliminary works
| checkpoint | 1.1 - Submission of Mix Design
| note | FREQUENCY: Prior to commencing paving
| note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
| note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
| note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
| note | RECORD OF CONFORMITY: VR approval, Completed ITP
| note | HP
| note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Check for correct documentation
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
| note | – using the correct and complete set of drawings
| note | – all drawings are the latest revision
| note | REFERENCE DOCUMENTS: Drawings and drawing registers
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | HP*
| note | RESPONSIBILITY: Project Engineer / Site Foreman
| date | Date Completed:
| checkpoint | 1.3 - Implementation of all measures and controls
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & WP
| note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | HP*
| note | RESPONSIBILITY: Site Engineer / Site Foreman
| date | Date Completed:
| checkpoint | 1.4 - Site Inspection and Base Condition
| note | FREQUENCY: Prior to commencing paving
| note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
| note | REFERENCE DOCUMENTS: 407.14 AS2150 10.1, AS2150 10.3
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
| date | Date Completed:
| checkpoint | 1.5 - Ambient Conditions for Placing
| note | FREQUENCY: Prior to commencing paving
| note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
| note | ○ Base & Intermediate Courses: 5°C for conventional binders or
| note | ○ 10°C for PMBs & Class 600
| note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
| note | REFERENCE DOCUMENTS: 407.13
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: Thermometer
| note | IP
| note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
| date | Date Completed:
| checkpoint | 1.6 - Planning of Joints
| note | FREQUENCY: Prior to commencing paving
| note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
| note | ○ Transverse Joints Offset from layer to layer by at least 2m
| note | ○ Longitudinal Joints Offset from layer to layer by at least
| note | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
| note | REFERENCE DOCUMENTS: 407.17 (b) & (c) Pavement Drawings
| note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
| note | RECORD OF CONFORMITY: Paving Plan
| note | WP
| note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
| date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Cut Chase out
| note | FREQUENCY: Prior to commencing paving
| note | ACCEPTANCE CRITERIA: Cut Chase out of existing pavement to a depth equil to wearing course + regulation course. Slope of chase out should not be greater than 1 in 20
| note | REFERENCE DOCUMENTS: Design Drawings
| note | INSPECTION/TEST METHOD: Visual inspections / Measurements
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
| date | Date Completed:
| checkpoint | 2.2 - Commencement of Placing
| note | FREQUENCY: Prior to commencing Paving
| note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
| note | REFERENCE DOCUMENTS: 407.18
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP
| note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Delivery of Mix
| note | FREQUENCY: Each load
| note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
| note | REFERENCE DOCUMENTS: 407.16 Table 407.081
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: Delivery Docket
| note | WP
| note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
| date | Date Completed:
| checkpoint | 2.5 - Layer Thickness and Level Control
| note | FREQUENCY: Regularly during paving
| note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
| note | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: Dips using ruler or dip stick
| note | WP
| note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
| date | Date Completed:
| checkpoint | 2.6 - Surface Finish of Wearing Course
| note | FREQUENCY: During paving and after final roll
| note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
| note | REFERENCE DOCUMENTS: 407.23 (a)(i)
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
| date | Date Completed:
| checkpoint | 2.7 - Kerb and Channel
| note | FREQUENCY: During paving and after final roll
| note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
| note | REFERENCE DOCUMENTS: 407.23 (a)(ii)
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
| date | Date Completed:
| checkpoint | 2.8 - Alignment of layers not placed against concrete edge
| note | FREQUENCY: During paving and at completion of work
| note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line. The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
| note | REFERENCE DOCUMENTS: 407.23 (a)(iv) Drawings
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
| date | Date Completed:
| section | 3 - Testing
| checkpoint | 3.1 - Compaction
| note | FREQUENCY: Per Lot
| note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
| note | ○ 94.0% or greater Accept lot
| note | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
| note | For layers ≥50mm, if characteristic thickness is:
| note | ○ 96.0% or greater Accept lot
| note | ○ 91.0% to 95.9% Lot may be accepted at reduced rate
| note | REFERENCE DOCUMENTS: Table 407.221
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: Test Report
| note | TP
| note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
| date | Date Completed:
| checkpoint | 3.2 - Level Conformance
| note | FREQUENCY: Per 4,000m2 at completion of work
| note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
| note | REFERENCE DOCUMENTS: Table 407.232
| note | INSPECTION/TEST METHOD: Survey by VicRoads Section 173
| note | RECORD OF CONFORMITY: Survey Conformance
| note | SCP
| note | RESPONSIBILITY: Site Engineer/ Surveyor
| date | Date Completed:
| checkpoint | Final Inspection
| note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| checklist | ITP-032 - Construction of Kerb & Channel | itp | ITP-032 - Construction of Kerb & Channel
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
| note | – using the correct and complete set of drawings
| note | – all drawings are the latest revision
| note | REFERENCE DOCUMENTS: Drawings and drawing registers
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP*
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
| note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP*
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
| note | FREQUENCY: Prior to start
| note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
| note | REFERENCE DOCUMENTS: 703.17
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP
| note | RESPONSIBILITY: Project Engineer/ Superintendent
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Temporary Drainage Provisions
| note | FREQUENCY: If Required
| note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
| note | REFERENCE DOCUMENTS: Cl 703.18
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| checkpoint | 2.3 - Bedding
| note | FREQUENCY: Each lot
| note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
| note | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
| note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
| note | REFERENCE DOCUMENTS: Cl 703.21
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Project Engineer/ Superintendent
| date | Date Completed:
| checkpoint | 2.4 - Pre-concrete check
| note | FREQUENCY: Each lot
| note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
| note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
| note | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
| note | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
| note | REFERENCE DOCUMENTS: Cl 703.08
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: ITP Signed
| textbox | Ambient Temperature
| textbox | Concrete Temperature
| note | HP
| note | RESPONSIBILITY: Project Engineer/ Superintendent
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Concrete Placement
| note | FREQUENCY: Each lot
| note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
| note | REFERENCE DOCUMENTS: VicRoads Spec Cl 703.23
| note | INSPECTION/TEST METHOD: Site Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| checkpoint | 2.6 - Finish Surfaces
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished. Concrete to have a neat appearance and uniform colour
| note | REFERENCE DOCUMENTS: 703.25
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Site Engineer/ Site Foreman
| date | Date Completed:
| checkpoint | 2.7 - Joints
| note | FREQUENCY: Each joint
| note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
| note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
| note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
| note | REFERENCE DOCUMENTS: 703
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| checkpoint | 2.8 - Backfilling
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
| note | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
| note | ○ Layers shall not exceed 150mm compacted depth
| note | REFERENCE DOCUMENTS: 703.29
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| checkpoint | Final Inspection
| note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| checklist | ITP-033 - Insitu Concrete Pit | itp | ITP-033 - Insitu Concrete Pit
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
| note | REFERENCE DOCUMENTS: Drawings and drawing registers
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | HP*
| note | RESPONSIBILITY: Fulton Hogan Engineer
| date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
| note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | IP
| note | RESPONSIBILITY: Fulton Hogan Engineer
| date | Date Completed:
| checkpoint | 1.3 - Pit material classification
| note | FREQUENCY: Each delivery
| note | ACCEPTANCE CRITERIA: Concrete used shall have a mininmum strength of 32MPa and be
| note | ○ Steel fabric shall be SL82 reinforcement and conform with the requirements of AS4671-2001.
| note | REFERENCE DOCUMENTS: IDM SD415
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | HP*
| note | RESPONSIBILITY: Fulton Hogan Engineer
| date | Date Completed:
| checkpoint | 1.4 - Backfill and bedding material classificaiton
| note | FREQUENCY: Prior to start
| note | ACCEPTANCE CRITERIA: All crused rock used in the works shall be Class 2, 20mm nominal size.
| note | ○ Sand shall conform with the requirements of AS2758 - 1998 and AS1141 - 1997 and shall have grading within the limits as defined in the code.
| note | REFERENCE DOCUMENTS: Cl 18.0
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: Test reports from supplier
| note | HP*
| note | RESPONSIBILITY: Fulton Hogan Engineer
| date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Set out pit location
| note | FREQUENCY: Prior to backfilling
| note | ACCEPTANCE CRITERIA: The line, level and location of all pits & structures must be in accordance with the provided design drawings.
| note | ○ The position of all pits are to be confirmed with the superintendent if ambiguity arises from the drawings.
| note | REFERENCE DOCUMENTS: Dwgs Appx 2: Cl 8.0
| note | INSPECTION/TEST METHOD: Survey Conformance Report
| note | RECORD OF CONFORMITY: Survey Report. This ITP signed off
| note | WP
| note | RESPONSIBILITY: Fulton Hogan Engineer / Superintendent
| date | Date Completed:
| checkpoint | 2.2 - Excavation
| note | FREQUENCY: Each trench
| note | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth greater than 75mm below the specified level of the invert of the pipe to allow for appropriate bedding.
| note | ○ Any trench which may have been excavated to a greater depth than necessary shall be filled into the required level with concrete 1:3:6 mix. Any loose material shall be removed.
| note | ○ Trench shall be battered, benched or shored in line with WorkSafe code of practice when required by assessment under 1.5m in depth and is mandatory over 1.5m.
| note | ○ No stockpiles within 2m of end of the trench to reduce bearing pressure.
| note | REFERENCE DOCUMENTS: Appx 2: Cl 8.0, Cl 9.0, Cl 11.0
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | IP
| note | RESPONSIBILITY: Fulton Hogan Foreman
| date | Date Completed:
| checkpoint | 2.3 - Inspection of trench base
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Base of the trench shall be inspected prior to placement of bedding.
| note | REFERENCE DOCUMENTS: Appx 2: Cl 8.0
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | IP
| note | RESPONSIBILITY: Fulton Hogan Engineer
| date | Date Completed:
| checkpoint | 2.4 - Placement of bedding material
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: A 75mm minimum layer of compacted class 3 crushed rock shall be used under base of pit
| note | REFERENCE DOCUMENTS: IDM SD415
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | IP
| note | RESPONSIBILITY: Fulton Hogan Foreman
| date | Date Completed:
| checkpoint | 2.5 - Concrete pre-pour inspection
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: The site of the concrete pour for the cast in-situ pit shall be inspected by a client supervisor before proceeding.
| note | ○ Reinforcement shall be check for correct cover & lap as per drawings
| note | REFERENCE DOCUMENTS: IDM SD415
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | WP
| note | RESPONSIBILITY: Fulton Hogan Engineer / Superintendent
| date | Date Completed:
| checkpoint | 2.6 - Concrete pour and pit construction
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: All pits are to be constructed in accordance with IDM Spec 415. Pit should also be constructed in accordance with site specific drawings.
| note | REFERENCE DOCUMENTS: IDM SD415
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | IP
| note | RESPONSIBILITY: Fulton Hogan Engineer
| date | Date Completed:
| checkpoint | 2.7 - Pit base shaped with concrete to match pipe invert
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Construct as shown on Standard Drawing 1P50318
| note | REFERENCE DOCUMENTS: IDM SD415
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: This ITP signed off
| note | IP
| note | RESPONSIBILITY: Fulton Hogan Engineer
| date | Date Completed:
| checkpoint | 2.8 - Placement of pit covers
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: All pits shall be fitted with standard City of Melbourne covers specificed on the drawings of appropriate class.
| note | REFERENCE DOCUMENTS: IDM SD415
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: This ITP signed off
| note | IP
| note | RESPONSIBILITY: Fulton Hogan Engineer
| date | Date Completed:
| checkpoint | Final Inspection
| note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| checklist | ITP-045 - Pipe Conection to Main Drain | itp | ITP-045 - Pipe Conection to Main Drain
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
| note | – using the correct and complete set of drawings
| note | – all drawings are the latest revision
| note | REFERENCE DOCUMENTS: Drawings and drawing registers
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | HP*
| note | RESPONSIBILITY: Project Engineer / Site Foreman
| date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
| note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: This ITP signed off
| note | HP*
| note | RESPONSIBILITY: Project Engineer / Site Foreman
| date | Date Completed:
| checkpoint | 1.3 - Precast Materials Inspection
| note | FREQUENCY: Each Delivery
| note | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
| note | REFERENCE DOCUMENTS: 701.04b
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
| note | IP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| checkpoint | 1.4 - Precast Pipe
| note | FREQUENCY: Prior to Commencing
| note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058
| note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619, Cl. 701.04(a), Cl. 701.04(b)(i), Cl. 705.04(d), Cl. 705.11, AS4058, AS4680
| note | INSPECTION/TEST METHOD: Document review & Site inspection
| note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
| note | IP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Excavation Permit
| note | FREQUENCY: Each lot
| note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
| note | ○ Plant and equipment shall be appropriate for the task.
| note | ○ Excavation operations shall not disturb areas outside the limit of excavation
| note | REFERENCE DOCUMENTS: Excavation permit
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP*
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| checkpoint | 2.2 - Set out drainage
| note | FREQUENCY: Prior to excavation
| note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
| note | REFERENCE DOCUMENTS: Drawings 701.10
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP
| note | RESPONSIBILITY: Engineer / Forman & Superintendent
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Excavation (pipes)
| note | FREQUENCY: Each Trench
| note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical.
| note | Depth of trench:
| note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
| note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
| note | REFERENCE DOCUMENTS: 701.15, Table 701.151
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Site Foreman
| date | Date Completed:
| checkpoint | 2.4 - Bedding & Support
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Provide mass Concrete support around branch pipe minimum 150mm thick. Concrete shall be grade S40 with a maximum water cement ratio of 0.50.
| note | REFERENCE DOCUMENTS: MELBOURNE WATER CORPORATION 7251/08/425
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Site Engineer / Site Foreman
| date | Date Completed:
| checkpoint | 2.5 - Break Into main drain
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Reinforment in main drain to be cut and formed into collar. Care should be taken to prevent damage to pipe and to enshore opening is kept to a minimum.
| note | REFERENCE DOCUMENTS: MELBOURNE WATER CORPORATION 7251/08/425
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP
| note | RESPONSIBILITY: Site Engineer / Site Foreman, Superintendent
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Pipe to Pipe Conection
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Where connection cannot be rendered from inside main drain, connection to consists of 300mm long stub to allow rendering from outside. Bonding of new to old concrete shall be sufficent to ensure no cracks or leaks form. Concrete surfaces to be scabbled, cleaned primed with parchem nitobond SBR. All reinforcement without adequite cover to be sealed with epoxy or similar.
| note | REFERENCE DOCUMENTS: MELBOURNE WATER CORPORATION 7251/08/425
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Site Engineer / Site Foreman
| date | Date Completed:
| checkpoint | 2.7 - Place & compact backfill material over pipes
| note | FREQUENCY: each lot
| note | ACCEPTANCE CRITERIA: Ordinary earth from excavation which contains no rock fragments compacted in layers no greater than 150mm. Compaction to be minimum 92% modified A.A.S.H.O. using handheld mechanical equipment. Top 100mm to be topsoil and seeded
| note | REFERENCE DOCUMENTS: RFI.01
| note | INSPECTION/TEST METHOD: Visual Inspection + Testing
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Site Engineer / Site Foreman
| date | Date Completed:
| section | 3 - Testing & Completion
| checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
| note | FREQUENCY: as required/requested
| note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort. Bedding material shall be compacted using a compaction plated to refusal.
| note | REFERENCE DOCUMENTS: 701.2
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: Test Reports
| note | TP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| checkpoint | Final Inspection
| note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| checklist | ITP-050 - Omnigrip Road Surfacing | itp | ITP-050 - Omnigrip Road Surfacing
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for Correct Documentation
| note | FREQUENCY: Prior to Commencing Activity
| note | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
| note | REFERENCE DOCUMENTS: Contract Drawings and Registers
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: This ITP Signed off
| note | HP*
| note | RESPONSIBILITY: Fulton Hogan Engineer
| date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
| note | FREQUENCY: Prior to Commencing Activity
| note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
| note | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
| note | INSPECTION/TEST METHOD: Inspection
| note | RECORD OF CONFORMITY: This ITP Signed off
| note | IP
| note | RESPONSIBILITY: Fulton Hogan Engineer
| date | Date Completed:
| checkpoint | 1.3 - Check Materials
| note | FREQUENCY: Each Delivery
| note | ACCEPTANCE CRITERIA: Ensure the correct materials have been received including:
| note | – Part A Epoxy Compound
| note | – Part B Epoxy Harderner
| note | – Coloured Aggregate Dressing
| note | REFERENCE DOCUMENTS: Receivable Inspection Checklist
| note | INSPECTION/TEST METHOD: Inspection
| note | RECORD OF CONFORMITY: This ITP Signed off
| note | IP
| note | RESPONSIBILITY: Fulton Hogan Engineer
| date | Date Completed:
| checkpoint | 1.4 - Setting out
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Alignment and location of Omnigrip road sufracing shall be marked in accordace with the appropriate design drawings.
| note | REFERENCE DOCUMENTS: Work Procedure
| note | INSPECTION/TEST METHOD: Inspection
| note | RECORD OF CONFORMITY: This ITP Signed off
| note | WP
| note | RESPONSIBILITY: Fulton Hogan Engineer, Client
| date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Monitoring Conditions
| note | FREQUENCY: Prior to start
| note | ACCEPTANCE CRITERIA: Omnigrip CST must not be applied to wet pavements under any circumstances and suspension of application should be considered:
| note | – During periods of dew, drizzle or rain
| note | – If the surface temperature exceeds 60°C
| note | – If the surface temperature drops below 10°C and is in decline.
| note | REFERENCE DOCUMENTS: Omnigrip Technical Data Sheet
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: This ITP signed off
| note | IP
| note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
| date | Date Completed:
| checkpoint | 2.2 - Asphalt Surface Preperation
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Ensure that the substrate is dry and clean of all contaminates. Asphalt pavements shall be virgourously brushed or treated with compressed air to remove dust and loose aggregate.
| note | REFERENCE DOCUMENTS: Omnigrip Technical Data Sheet
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: This ITP Signed off
| note | IP
| note | RESPONSIBILITY: Fulton Hogan Engineer
| date | Date Completed:
| checkpoint | 2.3 - Material Mixing and Installation
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: The Epoxy Part A should be added to Epoxy Part B at a ratio of 1:1 and mixed using a slow speed for 90 to 120 seconds to obtain a homegenous mix. Add pigment colouring throughout the mixing process.
| note | ○ Once mixed the resin should be immediately applied & spread evenly using a serrated squeegee or notched trowel at an average rate of 1.35 - 1.7 kg/m2.
| note | ○ The resion should self-level, however, the use of a 20mm find nap roller should be used to back roll and level the resin.
| note | ○ The applied resin should receive the aggregate dressing within 10-15 minutes of application ensuring no wet resin is left exposed.
| note | REFERENCE DOCUMENTS: Omnigrip Technical Data Sheet
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: This ITP Signed off
| note | IP
| note | RESPONSIBILITY: Fulton Hogan Engineer
| date | Date Completed:
| checkpoint | 2.3 - Curing
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: For any surface works on asphalt there must be a minimum curing period of 7-10 days.
| note | REFERENCE DOCUMENTS: Omnigrip Technical Data Sheet
| note | INSPECTION/TEST METHOD: Visual Inspection
| note | RECORD OF CONFORMITY: This ITP Signed off
| note | IP
| note | RESPONSIBILITY: Fulton Hogan Engineer
| date | Date Completed:
| checkpoint | Final Inspection
| note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| textbox | Print Name:
| textbox | Position:
| date | Date:
| checklist | ITP-068 - Construction of Trench Grate | itp | ITP-068 - Construction of Trench Grate
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
| note | – using the correct and complete set of drawings
| note | – all drawings are the latest revision
| note | REFERENCE DOCUMENTS: Drawings and drawing registers
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP*
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
| note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP*
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| checkpoint | Trench Grate Material Procurement
| note | FREQUENCY: Prior to commencing any activity
| note | ACCEPTANCE CRITERIA: Approved durham ductile heelguard trench grate and frame product NO. CHP30C or approved
| note | REFERENCE DOCUMENTS: Drawings
| note | INSPECTION/TEST METHOD: Check Material Specs
| note | RECORD OF CONFORMITY: ITP SIGNED
| note | HP
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
| note | FREQUENCY: Prior to start
| note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
| note | REFERENCE DOCUMENTS: 703.17
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP
| note | RESPONSIBILITY: Project Engineer/ Superintendent
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Temporary Drainage Provisions
| note | FREQUENCY: If Required
| note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
| note | REFERENCE DOCUMENTS: Cl 703.18
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| checkpoint | 2.3 - Bedding
| note | FREQUENCY: Each lot
| note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
| note | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
| note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted. A Slurry of low to medium slump concrete should be poured on the base of the excavated trench prior to placing the PVC in position. The Height of the slurry bed should be determined based on figure c in the intallation guildlines
| note | REFERENCE DOCUMENTS: Cl 703.21 Installation guidelines
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | WP
| note | RESPONSIBILITY: Project Engineer/ Superintendent
| date | Date Completed:
| checkpoint | 2.4 - Joining PVC sections
| note | FREQUENCY: Each lot
| note | ACCEPTANCE CRITERIA: Place each section of PVC in position under the string line. Align each end of the connecting PVC/frame sections so that they are touching. use clamp or bolts to hold the PVC/frame sections together
| note | REFERENCE DOCUMENTS: Installation Guidelines
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - 1st Pour
| note | FREQUENCY: Each lot
| note | ACCEPTANCE CRITERIA: Pour Concrete to approximately half the depth of the excavated trench. The concrete should now be compacted to remove air pockets and ensure that the grooves of the. PVC trench are sufficiently filled.
| note | REFERENCE DOCUMENTS: Installation Guidelines Drawings
| note | INSPECTION/TEST METHOD: Site Inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Final Pour
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: The final concrete pour should be completed to finish height, with the finish surface being graded towards the trench, as required.
| note | REFERENCE DOCUMENTS: Installation Guidelines Drawings
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Site Engineer/ Site Foreman
| date | Date Completed:
| checkpoint | 2 - Tie Into existing curb
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Transition from trench grate to existing curb in a neat transition
| note | REFERENCE DOCUMENTS: Drawings
| note | INSPECTION/TEST METHOD: Visual inspection
| note | RECORD OF CONFORMITY: ITP Signed
| note | HP
| note | RESPONSIBILITY: Site Engineer/ Site Foreman
| date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Joints
| note | FREQUENCY: Each joint
| note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
| note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
| note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
| note | REFERENCE DOCUMENTS: 703.26
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Project Engineer/ Site Foreman
| date | Date Completed:
| checkpoint | 2.8 - Backfilling
| note | FREQUENCY: Each Lot
| note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
| note | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
| note | ○ Layers shall not exceed 150mm compacted depth
| note | REFERENCE DOCUMENTS: 703.29
| note | INSPECTION/TEST METHOD: Verify
| note | RECORD OF CONFORMITY: ITP Signed
| note | IP
| note | RESPONSIBILITY: Project Engineer
| date | Date Completed:
| checkpoint | Final Inspection
| note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| textbox | Print Name:
| textbox | Position:
| date | Date: