## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-008
[11 empty] | Revision : 1 | 2024-07-10
Client: |  | Dandenong City Council |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Ordish Road |  | Cement Treated Layer |  | Name: | Ruby Lewis | Name: | Cam Beattie |  | Name: | Cam Beattie
Contract No: |  | 2324-12 |  | Specifications: VicRoads Specification Section 173 , 306
|  |  |  | Structure / Component: Pavement |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : | 2024-07-10 | Date : | 2024-07-10 |  | Date : | 2024-07-10
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed | HP* | Project Engineer / Site Foreman | N/A |  | N/A
1.2 | Material Mix Design |  | Prior to commencing any activity | Material proposed for import as Class 3 sub-base material meets the requirements of VR Section 812 or 820. Obtain material compliance data from the supplier and submit to VRs for approval | Cl 812.04 Section 820.04 to 820.09 RC 500.02 | Document Review | Mix Design VicRoads Approval | HP* | Project Engineer | N/A |  | N/A
1.3 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed | HP* | Project Engineer / Site Foreman | N/A |  | N/A
2 | Earthworks / Geofabric placement
2.1 | Excavation to 400mm below the existing surface levels |  | Every 20 lineal meters | Ensure the depth is 400mm depth or greater | NA | IP | This ITP signed | IP | Project Engineer / Site Foreman
| Geofabric placement |  | Every 20 lineal meters | MastaGrid GGCB440 Geofabric is placed in even layers and 300mm of overlap is achieved when joining rolls Ensure that there are no creases in the fabric | NA | IP | This ITP signed | IP | Project Engineer / Site Foreman
3 | Materials
3.1 |  |  |  | The Contractor shall supply all materials required to construct the cementitious treated pavement subbase. The supply of Cementitious Treated Crushed Rock or Cementitious Treated Crushed Concrete shall comply with the requirements of Section 815. | Cl 306.04 | Visual Inspection | This ITP signed off | IP | Project Engineer / Site Foreman | N/A |  | N/A
3.2 | Moisture Content |  |  | The moisture content of the material at the time of spreading and compaction, expressed as a percentage by mass, shall be within plus 0.5% and minus 1.0 % from the Modified optimum moisture content. | Cl 306.05 | Visual Inspection | This ITP signed off | IP | Project Engineer / Site Foreman | N/A |  | N/A
4 | Testing Requirements
4.1 | Test Rolling |  | Each lot | Test rolling may be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091. | CL 306.09 | HP | This ITP signed off; Test reports | TP | Superintendent / foreman | N/A |  | N/A
4.2 | Compaction |  | Each lot | Testing and Acceptance of Compaction The work represented by the lot will be accepted as far as compaction is concerned if the mean density ratio for the lot is not less than 96.0%. If the mean of the individual density ratio test values for the lot is less than 96.0%, but greater than or equal to 92% the work represented by the lot may be accepted but the method of rectification and/or redesign of the pavement shall be approved by the Superintendent. Alternatively, the Superintendent may accept the work at a reduced rate calculated using the formula: | CL 306.09 | TP | This ITP signed off; Test reports | TP | Project Engineer | N/A |  | N/A
4.3 | Survey Conformance |  | Each lot | Pavement subbase shall be finished to a smooth and uniform surface and shall, after compaction, conform within the following limits to the levels, lines, grades, thicknesses and cross sections as specified or shown on the drawings. (a) Width and Alignment The width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset when measured at a right angle. (b) Surface Level of Subgrade and Pavement The surface level of the subgrade and pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet requirements as specified in Clause 306.12. Surface level tolerances: Range x = +6, -12mm | Cl 306 | IP | Cl 306.12. | SCP | Project Engineer / Site Foreman | N/A |  | N/A
4.4 | Curing |  | Each lot | The subbase shall be kept in good order and condition and free from contamination. | N/A | IP | This ITP signed off; | IP | Project Engineer / Site Foreman | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.