## Table 1
| WORK AREA: |  | DESCRIPTION OF ACTIVITY: Establishment and Initial Set Out |  |  | Key: P= PERFORM (Activity) R = REVIEW (Documents & Work) W = WITNESS (Activity) H = HOLD (Point for Acceptance) |  | 2 | GvdLinde |  |  | 2024-07-10
[8 empty] | 1 | GvdLinde |  |  | 2024-06-19
| Kioreroa Road Rising Sewer Main | [6 empty] | 0 | GvdLinde |  |  | 2024-05-10
[8 empty] | Rev | Originator |  |  | Date |  | Approved |  |  | Date
Item No. |  | ITEM |  | ACTIVITY TASK | ACCEPTANCE CRITERIA |  | CERTIFING DOCUMENTATION AND FREQUENCY |  |  | Supervisor, Foreman or Subcontractor |  |  | Project Manager or Delegated Person |  |  | Engineer’s Representative
[10 empty] | Key | Sign / Date |  | Key |  | Sign / Date | Key |  | Sign / Date
1 |  | Award of Contract |  | Award of Contract | Letter of Award |  | Letter of Award | [5 empty] | R
2 |  | Management Plans |  | Project Commencement | Submission to engineer to the contract |  | ‘SSSP, EMP, QCP, TMP, JSA | [5 empty] | P |  |  | R
3 |  | Insurances |  | Project Commencement | Current certificate |  | Current certificate | [5 empty] | P |  |  | R
4 |  | Bond |  | Project Commencement | Current certificate |  | Prior to First Progress Claim | [5 empty] | P |  |  | R
5 |  | Dilapidation Survey |  | Project Commencement | Photos and description of scope of work prior to commencement of physical works. |  | Photos of footpath, Berm, pavement and individual properties. |  |  | P |  |  | R
6 |  | Notification to Residents |  | Project Commencement, Notification | Letter to be distributed to affected residents prior to commencement of work. |  | Letter to residents | [5 empty] | P |  |  | R
7 |  | Information Sign Boards |  | Project Commencement, Notification – Sign Boards to be supplied and installed | As per WDCEES |  | Photos |  |  | P |  |  | R |  |  | W
|  | Design |  | Design of vertical and horizontal alignment and locations of components | Submission of drawings to engineer for review as per T- WES0001 – Preliminary and General, Section2.4. |  | Acceptance | [5 empty] | P |  |  | H
8 |  | Initial Set out |  | Set out of manhole positions and alignment of new line, etc | As per drawings |  | Surveyor to set out |  |  | R |  |  | R |  |  | W
9 |  | Notification of Hazards |  | Working at depths greater than 1.5m | Notification to Work safe prior to commencement of work |  | Copy of Notification to Work safe | [5 empty] | P |  |  | R
|  |  |  | Working around Overhead lines | Notify Northpower prior to works starting |  | Close approach permit and Standover |  |  | p |  |  | P |  |  | R
Item No. |  | ITEM |  | ACTIVITY TASK | ACCEPTANCE CRITERIA |  | CERTIFING DOCUMENTATION AND FREQUENCY |  |  | Supervisor, Foreman or Subcontractor |  |  | Project Manager or Delegated Person |  |  | Engineer’s Representative
[10 empty] | Key | Sign / Date |  | Key |  | Sign / Date | Key |  | Sign / Date
|  |  |  | Working around Gas lines | Notify First Gas |  | Standover and permit |  |  | P |  |  | P |  |  | R
10 |  | B4UDig |  | Submit B4UDig Notification | B4UDig Submission confirmation – Mark out – Close Approach Permits |  | B4UDig Plans and sequence numbers – Mark out – Close Approach Permits |  |  | P |  |  | P
11 |  | Environmental Controls |  | Environmental Controls in Place | Environmental Controls in place as per EMP/CEMP |  | CEMP, Photos |  |  | P |  |  | P |  |  | W
12 |  | Access Permits |  | Project Commencement | Complete permits prior to commencement of works in WWTP |  | Permit to Occupy | [5 empty] | P |  |  | W
13 |  | Temporary Works |  | Set up of temporary work provisions such as: - Shoring Protection - Temporary Access provisions - Dewatering | Temporary work provisions in place as per relevant approved SWMS or JSA prior to commencement of works |  | Relevant WMS, SWMS or JSA | [5 empty] | P |  |  | R
14 |  | Stockpile Locations |  | Agree Stockpile locations with engineer | Suitable stockpile locations reviewed and agreed with engineer |  | Acceptance | [5 empty] | P |  |  | H
15 |  | Dewatering |  | Pumping water from trench | Submit Method Statement, Install temp pond, manage clean discharge, as per T-WES 00011 – Earthworks, Reinstatement and Dewatering |  | Method Statement Acceptance |  |  | P |  |  | R |  |  | H
INSPECTION & TEST PLAN
INSPECTION & TEST PLAN (ITP)
The ITP defines the required inspections during various stages of fabrication, construction & installation work. It is also a method of communicating these requirements to those doing the work & a verifying record that they have been carried out.
The ITP defines four different levels of inspection according to the following criteria:  Perform (P) The person(s) performing the work inspects his/her own work and the Foreman/Supervisor or Subcontractors Representative is to verify/check the work as correct. The Foreman/Supervisor or Subcontractors Representative is required to sign the Inspection & Test Checklist.  Review (R) – Documents When applied to documents this can indicate review & approval before fabrication commences e.g. weld procedures or after completion e.g. QC Package.  Review (R) –Work Performed Fabrication may proceed past the points indicated on the ITP. This type of inspection performed on a random basis. If corrective action is necessary, the frequency of inspections may be increased.  Witness (W) This type of inspection is performed when critical activities are undertaken & verification of work done is required by a third party, or internally by a supervisor or QA Personnel. It is the responsibility of the Foreman/Supervisor or Subcontractors Representative to notify whoever is identified as the Witness initiator that the (W) stage of inspection has been reached.  Hold (H) This type of inspection requires the Foreman/ Supervisor or Subcontractors Representative to notify the United Civil Project Manager that the (H) stage of inspection has been reached. Fabrication shall not proceed past this point unless the inspection has been carried out or approval to proceed is given in writing & signed by the Engineer’s Representative.