## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Pavement and Drainage ITP | itp |  |  |  |  | Pavement and Drainage ITP
section | Materials
checkpoint | Hardfill GAP65
label | SPECIFICATION REFERENCE - Arapohue Road RP2840 - Mechanically Stabilised Earth Wall - Technical Specification CO203.4.3
label | TEST/TASK REQUIRED - IANZ Test certificates
label | INSPECTION BY - UCCL, KDC
label | TASK TIMING OR TASK FREQUENCY - 1 test per source submitted 2 weeks prior to MSE Construction
label | ACCEPTANCE CRITERIA - GAP65 shall meet the grading from Table 203.1, a crushing resistance greater than or equal to 120kN and have a weathering resistance of AA,AB,AC,BA,BB or CA
label | UCCL - H
label | Engineer/Client - R