## Sheet1
1 | Manual Roller Blinds | Accurate site survey. | Per window. | As per ARC-9400(9) T-Schedule and NBQA-2000 V2020. | Location as per Norfolk Blinds Markup Plan and BOQ. | Refer to approved Norfolk Blinds Markup Plan and BOQ. | X | S | W | 1 - Manual Roller Blinds - Site Measure | CHARACTERISTICS: Accurate site survey. | STAGE/FREQUENCY: Per window. | RECORDS REQUIREMENT STANDARD/SPEC: As per ARC-9400(9) T-Schedule and NBQA-2000 V2020. | ACCEPTANCE CRITERIA: Location as per Norfolk Blinds Markup Plan and BOQ. | INSPECTION/TEST PROCEDURE: Refer to approved Norfolk Blinds Markup Plan and BOQ. | INSTALLER: X | SUPERVISOR: S | CLIENT: W | 1 - Manual Roller Blinds - Site Measure
| Site Measure | [17 empty] | CHARACTERISTICS: Accurate site survey.
2 | Manual Roller Blinds | Single brackets are secured & are aligned correctly. | Per Blind during installation. | As per ARC-9400(9) T-Schedule and NBQA-2000 V2020. | Bracket fixings are secure & aligned. | Once secured, brackets will be firmly in place, and unable to be moved by hand. | X | S | W | [9 empty] | STAGE/FREQUENCY: Per window.
| Bracket Fixings | [17 empty] | RECORDS REQUIREMENT STANDARD/SPEC: As per ARC-9400(9) T-Schedule and NBQA-2000 V2020.
3 | Manual Roller Blinds | Fabric cut, blind assembled and tested. | Per blind during manufacture. | As per ARC-9400(9) T-Schedule and NBQA-2000 V2020. | As per NBQA-2000 V2020. | Blinds are manufactured as per NBQA-2000 V2020 and as per ARC-9400(9) T-Schedule. | X | S | W | [9 empty] | ACCEPTANCE CRITERIA: Location as per Norfolk Blinds Markup Plan and BOQ.
| Manufacturing | [17 empty] | INSPECTION/TEST PROCEDURE: Refer to approved Norfolk Blinds Markup Plan and BOQ.
4 | Manual Roller Blinds | Standard Work for Blind Installation. | Per blind during installation. | As per ARC-9400(9) T-Schedule and NBQA-2000 V2020. | Blind installed as per Standard Work for Blind Installation. | As per ITP procedures for bracket fixings, chain fixings, fabric blemishes and operation. | X | S | W | [9 empty] | INSTALLER: X
| Install Procedure | [17 empty] | SUPERVISOR: S
CLIENT: W