## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | QMD07 ITP-001 - Installation WWMH F20525 | itp |  |  |  |  | QMD07 ITP-001 - Installation WWMH F20525
section | ITP-001 - Installation WWMH F20525
checkpoint | 1 - Manhole base Preparation (Pre-cast or in-situ)
label | Controlled By : (Position) - CR
label | Accept / Reject Criteria - Clean and dry base
label | ○ Correct bedding material and compaction
label | ○ Reinforcement and formwork inspected
label | ○ Waterproofing components in place
label | Spec. Ref, Procedure Or Method Statement - Project Drawings, D18 Construction Methodology
label | Frequency Of Inspection OR Test - Prior to placing concrete or setting precast base
label | HOLD POINT - I
checkpoint | 2 - Manhole Cyclinder Installation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct alignment and verticality
label | ○ Joints sealed with approved material
label | ○ Steps/lifting holes sealed
label | ○ Wall thickness and type verified
label | Spec. Ref, Procedure Or Method Statement - D18 – Precast Installations, Manufacturer specs NZS 3109
label | Frequency Of Inspection OR Test - Prior to backfilling
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 3 - Pipe protrusions into manhole
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Flexible joint within 1metre of the manhole
label | Spec. Ref, Procedure Or Method Statement - D18.3 INSTALLATION
label | Frequency Of Inspection OR Test - Prior to pouring corbels
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 4 - Internal Benching and Channeling
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - Smooth trowelled finish
label | ○ Accurate channel fall to spec
label | ○ Benching slope toward channel
label | ○ No honeycombing or cracks
label | Spec. Ref, Procedure Or Method Statement - D18.3 - AS/NZS 3500 - Formed finish F3 as specified in NZS 3114
label | Frequency Of Inspection OR Test - After completion of benching/invert
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 5 - Manhole Cover and Frame Installation
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - Infiltration check
label | ○ Visual condition check
label | ○ Manhole dimensions
label | ○ Functional access features
label | Spec. Ref, Procedure Or Method Statement - D15.2 MATERIALS Maestro DIMHMCFHS MH cover
label | Frequency Of Inspection OR Test - Before handover or commissioning
label | HOLD POINT - H
holdpoint | HOLD POINT
checklist | QMD07 ITP-002 - Installation WWMH F20538 | itp |  |  |  |  | QMD07 ITP-002 - Installation WWMH F20538
section | ITP-002 - Installation WWMH F20538
checkpoint | 1 - Manhole base Preparation (Pre-cast or in-situ)
label | Controlled By : (Position) - CR
label | Accept / Reject Criteria - Clean and dry base
label | ○ Correct bedding material and compaction
label | ○ Reinforcement and formwork inspected
label | ○ Waterproofing components in place
label | Spec. Ref, Procedure Or Method Statement - Project Drawings, D18 Construction Methodology
label | Frequency Of Inspection OR Test - Prior to placing concrete or setting precast base
label | HOLD POINT - I
checkpoint | 2 - Manhole Cyclinder Installation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct alignment and verticality
label | ○ Joints sealed with approved material
label | ○ Steps/lifting holes sealed
label | ○ Wall thickness and type verified
label | Spec. Ref, Procedure Or Method Statement - D18 – Precast Installations, Manufacturer specs NZS 3109
label | Frequency Of Inspection OR Test - Prior to backfilling
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 3 - Pipe protrusions into manhole
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Flexible joint within 1metre of the manhole
label | Spec. Ref, Procedure Or Method Statement - D18.3 INSTALLATION
label | Frequency Of Inspection OR Test - Prior to pouring corbels
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 4 - Internal Benching and Channeling
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - Smooth trowelled finish
label | ○ Accurate channel fall to spec
label | ○ Benching slope toward channel
label | ○ No honeycombing or cracks
label | Spec. Ref, Procedure Or Method Statement - D18.3 - AS/NZS 3500 - Formed finish F3 as specified in NZS 3114
label | Frequency Of Inspection OR Test - After completion of benching/invert
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 5 - Manhole Cover and Frame Installation
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - Infiltration check
label | ○ Visual condition check
label | ○ Manhole dimensions
label | ○ Functional access features
label | Spec. Ref, Procedure Or Method Statement - D15.2 MATERIALS Maestro DIMHMCFHS MH cover
label | Frequency Of Inspection OR Test - Before handover or commissioning
label | HOLD POINT - H
holdpoint | HOLD POINT
checklist | QMD07 ITP-003 - Installation SWMH S21358 | itp |  |  |  |  | QMD07 ITP-003 - Installation SWMH S21358
section | ITP-003 - Installation SWMH S21358
checkpoint | 1 - Manhole base Preparation (Pre-cast or in-situ)
label | Controlled By : (Position) - CR
label | Accept / Reject Criteria - Clean and dry base
label | ○ Correct bedding material and compaction
label | ○ Reinforcement and formwork inspected
label | ○ Waterproofing components in place
label | Spec. Ref, Procedure Or Method Statement - Project Drawings, D18 Construction Methodology
label | Frequency Of Inspection OR Test - Prior to placing concrete or setting precast base
label | HOLD POINT - I
checkpoint | 2 - Manhole Cyclinder Installation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct alignment and verticality
label | ○ Joints sealed with approved material
label | ○ Steps/lifting holes sealed
label | ○ Wall thickness and type verified
label | Spec. Ref, Procedure Or Method Statement - D18 – Precast Installations, Manufacturer specs NZS 3109
label | Frequency Of Inspection OR Test - Prior to backfilling
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 3 - Pipe protrusions into manhole
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Flexible joint within 1metre of the manhole
label | Spec. Ref, Procedure Or Method Statement - D18.3 INSTALLATION
label | Frequency Of Inspection OR Test - Prior to pouring corbels
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 4 - Internal Benching and Channeling
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - Smooth trowelled finish
label | ○ Accurate channel fall to spec
label | ○ Benching slope toward channel
label | ○ No honeycombing or cracks
label | Spec. Ref, Procedure Or Method Statement - D18.3 - AS/NZS 3500 - Formed finish F3 as specified in NZS 3114
label | Frequency Of Inspection OR Test - After completion of benching/invert
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 5 - Manhole Cover and Frame Installation
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - Infiltration check
label | ○ Visual condition check
label | ○ Manhole dimensions
label | ○ Functional access features
label | Spec. Ref, Procedure Or Method Statement - D15.2 MATERIALS Maestro DIMHMCFHS MH cover
label | Frequency Of Inspection OR Test - Before handover or commissioning
label | HOLD POINT - H
holdpoint | HOLD POINT
checklist | QMD07 ITP-004 - Installation SWMH S21359 | itp |  |  |  |  | QMD07 ITP-004 - Installation SWMH S21359
section | ITP-004 - Installation SWMH S21359
checkpoint | 1 - Manhole base Preparation (Pre-cast or in-situ)
label | Controlled By : (Position) - CR
label | Accept / Reject Criteria - Clean and dry base
label | ○ Correct bedding material and compaction
label | ○ Reinforcement and formwork inspected
label | ○ Waterproofing components in place
label | Spec. Ref, Procedure Or Method Statement - Project Drawings, D18 Construction Methodology
label | Frequency Of Inspection OR Test - Prior to placing concrete or setting precast base
label | HOLD POINT - I
checkpoint | 2 - Manhole Cyclinder Installation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct alignment and verticality
label | ○ Joints sealed with approved material
label | ○ Steps/lifting holes sealed
label | ○ Wall thickness and type verified
label | Spec. Ref, Procedure Or Method Statement - D18 – Precast Installations, Manufacturer specs NZS 3109
label | Frequency Of Inspection OR Test - Prior to backfilling
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 3 - Pipe protrusions into manhole
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Flexible joint within 1metre of the manhole
label | Spec. Ref, Procedure Or Method Statement - D18.3 INSTALLATION
label | Frequency Of Inspection OR Test - Prior to pouring corbels
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 4 - Internal Benching and Channeling
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - Smooth trowelled finish
label | ○ Accurate channel fall to spec
label | ○ Benching slope toward channel
label | ○ No honeycombing or cracks
label | Spec. Ref, Procedure Or Method Statement - D18.3 - AS/NZS 3500 - Formed finish F3 as specified in NZS 3114
label | Frequency Of Inspection OR Test - After completion of benching/invert
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 5 - Manhole Cover and Frame Installation
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - Infiltration check
label | ○ Visual condition check
label | ○ Manhole dimensions
label | ○ Functional access features
label | Spec. Ref, Procedure Or Method Statement - D15.2 MATERIALS Maestro DIMHMCFHS MH cover
label | Frequency Of Inspection OR Test - Before handover or commissioning
label | HOLD POINT - H
holdpoint | HOLD POINT
checklist | QMD07 ITP-005 - Installation Water main and Structures | itp |  |  |  |  | QMD07 ITP-005 - Installation Water main and Structures
section | ITP-005 - Installation Water main and Structures
checkpoint | 1 - Excavation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Excavation depth, bedding material, trench width
label | Spec. Ref, Procedure Or Method Statement - D2 Buried Pipelines NZS 4404, AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 2 - Pipe material delivery and storage
label | Controlled By : (Position) - FM/CR
label | Accept / Reject Criteria - Inspection for damage, conformity with specs
label | Spec. Ref, Procedure Or Method Statement - D1.24
label | Frequency Of Inspection OR Test - Upon arrival
label | HOLD POINT - I
checkpoint | 3 - Pipe laying (PE/ductile iron)
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Alignment, gradient, jointing method
label | Spec. Ref, Procedure Or Method Statement - D2, AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 4 - Valve and fitting installation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct location, bedding, supports
label | Spec. Ref, Procedure Or Method Statement - D5, AS/NZS 2280
label | Frequency Of Inspection OR Test - After completion of each valve and fitting installed
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 5 - Thrust blocks / anchor blocks
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Dimensions, concrete strength, curing
label | Spec. Ref, Procedure Or Method Statement - D5.7, NZS 4404
label | Frequency Of Inspection OR Test - After completion of each thrust block
label | HOLD POINT - H
holdpoint | HOLD POINT
checkpoint | 6 - Pipe bedding and backfilling
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct layer thickness, compaction testing
label | Spec. Ref, Procedure Or Method Statement - D2.7, AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 7 - Lateral Installation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Alignment, jointing method
label | Spec. Ref, Procedure Or Method Statement - D8, AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 8 - Hydrostatic pressure testing
label | Controlled By : (Position) - PM/CR
label | Accept / Reject Criteria - M7 Pressure rebound test
label | Spec. Ref, Procedure Or Method Statement - D2.9, AS/NZS 2566.2
label | Frequency Of Inspection OR Test - Prior to comission
label | HOLD POINT - I
checkpoint | 9 - Disinfection and flushing
label | Controlled By : (Position) - PM/CR
label | Accept / Reject Criteria - Chlorination to 50 mg/L, 24 hr retention, residual test
label | Spec. Ref, Procedure Or Method Statement - D2.9, AS/NZS 4020, MoH Drinking Water Standards
label | Frequency Of Inspection OR Test - Prior to comission
label | HOLD POINT - I
checkpoint | 10 - Final connections and commissioning
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Visual inspection, isolation checks, flow direction
label | Spec. Ref, Procedure Or Method Statement - D2, NZS 4404
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - H
holdpoint | HOLD POINT
checklist | QMD07 ITP-006 - Installation Foulsewer main F13717 | itp |  |  |  |  | QMD07 ITP-006 - Installation Foulsewer main F13717
section | ITP-006 - Installation Foulsewer main F13717
checkpoint | 1 - Excavation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Excavation depth, bedding material, trench width
label | Spec. Ref, Procedure Or Method Statement - D2 Buried Pipelines NZS 4404, AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 2 - Pipe material delivery and storage
label | Controlled By : (Position) - FM/CR
label | Accept / Reject Criteria - Inspection for damage, conformity with specs
label | Spec. Ref, Procedure Or Method Statement - D1.24
label | Frequency Of Inspection OR Test - Upon arrival
label | HOLD POINT - I
checkpoint | 3 - Pipe laying (uPVC)
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Alignment, gradient, jointing method
label | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 4 - Compaction of backfill material
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct aggregates, 200mm layer depth, Plateau test, clegg readings, NDM testing
label | Spec. Ref, Procedure Or Method Statement - D2.7.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - 200mm layers
label | ○ Clegg result every 6m
label | ○ NDM result every 120m
label | HOLD POINT - S
checkpoint | 5 - Lateral Installation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Alignment, gradient, jointing method, concrete around junctions and bends as required
label | Spec. Ref, Procedure Or Method Statement - D4 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 6 - Foul Sewer main pressure testing
label | Controlled By : (Position) - FM/CR
label | Accept / Reject Criteria - Leakage testing including laterals
label | Spec. Ref, Procedure Or Method Statement - D2.9 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - After completion of main and lateral installation
label | HOLD POINT - I
checkpoint | 7 - Pipe bedding and backfilling
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct layer thickness, compaction testing
label | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 8 - Cleaning and CCTV new main
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - No debris or defects
label | Spec. Ref, Procedure Or Method Statement - D2.9 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - Prior to comission
label | HOLD POINT - I
checklist | QMD07 ITP-007 - Installation Foulsewer main F13725 | itp |  |  |  |  | QMD07 ITP-007 - Installation Foulsewer main F13725
section | ITP-007 - Installation Foulsewer main F13725
checkpoint | 1 - Excavation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Excavation depth, bedding material, trench width
label | Spec. Ref, Procedure Or Method Statement - D2 Buried Pipelines NZS 4404, AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 2 - Pipe material delivery and storage
label | Controlled By : (Position) - FM/CR
label | Accept / Reject Criteria - Inspection for damage, conformity with specs
label | Spec. Ref, Procedure Or Method Statement - D1.24
label | Frequency Of Inspection OR Test - Upon arrival
label | HOLD POINT - I
checkpoint | 3 - Pipe laying (uPVC)
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Alignment, gradient, jointing method
label | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 4 - Compaction of backfill material
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct aggregates, 200mm layer depth, Plateau test, clegg readings, NDM testing
label | Spec. Ref, Procedure Or Method Statement - D2.7.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - 200mm layers
label | ○ Clegg result every 6m
label | ○ NDM result every 120m
label | HOLD POINT - S
checkpoint | 5 - Lateral Installation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Alignment, gradient, jointing method, concrete around junctions and bends as required
label | Spec. Ref, Procedure Or Method Statement - D4 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 6 - Foul Sewer main pressure testing
label | Controlled By : (Position) - FM/CR
label | Accept / Reject Criteria - Leakage testing including laterals
label | Spec. Ref, Procedure Or Method Statement - D2.9 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - After completion of main and lateral installation
label | HOLD POINT - I
checkpoint | 7 - Pipe bedding and backfilling
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct layer thickness, compaction testing
label | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 8 - Cleaning and CCTV new main
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - No debris or defects
label | Spec. Ref, Procedure Or Method Statement - D2.9 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - Prior to comission
label | HOLD POINT - I
checklist | QMD07 ITP-008 - Installation Stormwater main S13459 | itp |  |  |  |  | QMD07 ITP-008 - Installation Stormwater main S13459
section | ITP-008 - Installation Stormwater main S13459
checkpoint | 1 - Excavation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Excavation depth, bedding material, trench width
label | Spec. Ref, Procedure Or Method Statement - D2 Buried Pipelines NZS 4404, AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 2 - Pipe material delivery and storage
label | Controlled By : (Position) - FM/CR
label | Accept / Reject Criteria - Inspection for damage, conformity with specs
label | Spec. Ref, Procedure Or Method Statement - D1.24
label | Frequency Of Inspection OR Test - Upon arrival
label | HOLD POINT - I
checkpoint | 3 - Pipe laying (uPVC)
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Alignment, gradient, jointing method
label | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 4 - Compaction of backfill material
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct aggregates, 200mm layer depth, Plateau test, clegg readings, NDM testing
label | Spec. Ref, Procedure Or Method Statement - D2.7.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - 200mm layers
label | ○ Clegg result every 6m
label | ○ NDM result every 120m
label | HOLD POINT - S
checkpoint | 5 - Lateral Installation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Alignment, gradient, jointing method, concrete around junctions and bends as required
label | Spec. Ref, Procedure Or Method Statement - D4 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 6 - Pipe bedding and backfilling
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct layer thickness, compaction testing
label | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 7 - Cleaning and CCTV new main
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - No debris or defects
label | Spec. Ref, Procedure Or Method Statement - D2.9 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - Prior to comission
label | HOLD POINT - I
checklist | QMD07 ITP-009 - Installation Stormwater main S13440 | itp |  |  |  |  | QMD07 ITP-009 - Installation Stormwater main S13440
section | ITP-009 - Installation Stormwater main S13440
checkpoint | 1 - Excavation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Excavation depth, bedding material, trench width
label | Spec. Ref, Procedure Or Method Statement - D2 Buried Pipelines NZS 4404, AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 2 - Pipe material delivery and storage
label | Controlled By : (Position) - FM/CR
label | Accept / Reject Criteria - Inspection for damage, conformity with specs
label | Spec. Ref, Procedure Or Method Statement - D1.24
label | Frequency Of Inspection OR Test - Upon arrival
label | HOLD POINT - I
checkpoint | 3 - Pipe laying (uPVC)
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Alignment, gradient, jointing method
label | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 4 - Compaction of backfill material
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct aggregates, 200mm layer depth, Plateau test, clegg readings, NDM testing
label | Spec. Ref, Procedure Or Method Statement - D2.7.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - 200mm layers
label | ○ Clegg result every 6m
label | ○ NDM result every 120m
label | HOLD POINT - S
checkpoint | 5 - Lateral Installation
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Alignment, gradient, jointing method, concrete around junctions and bends as required
label | Spec. Ref, Procedure Or Method Statement - D4 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 6 - Pipe bedding and backfilling
label | Controlled By : (Position) - FM
label | Accept / Reject Criteria - Correct layer thickness, compaction testing
label | Spec. Ref, Procedure Or Method Statement - D2.7 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 7 - Cleaning and CCTV new main
label | Controlled By : (Position) - PM
label | Accept / Reject Criteria - No debris or defects
label | Spec. Ref, Procedure Or Method Statement - D2.9 - AS/NZS 2566.2
label | Frequency Of Inspection OR Test - Prior to comission
label | HOLD POINT - I
checklist | QMD07 ITP-010 - Asphalt Reinstatement | itp |  |  |  |  | QMD07 ITP-010 - Asphalt Reinstatement
section | ITP-010 - Asphalt Reinstatement
checkpoint | 1 - Saw cutting of existing pavement
label | Controlled By : (Position) - PM/CR
label | Accept / Reject Criteria - Edge alignment, depth, and cleanliness
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P40
label | Frequency Of Inspection OR Test - Prior to reinstatement
label | HOLD POINT - S
checkpoint | 2 - Placement and compaction of basecourse
label | Controlled By : (Position) - PM/CR
label | Accept / Reject Criteria - Layer thickness and compaction testing, preparation tolerance -/+5mm
label | Spec. Ref, Procedure Or Method Statement - D2.7.7.2 - NZTA B/2
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - I
checkpoint | 3 - Tack coating edges and base
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Uniform application, coverage check
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P42 – Tack Coat Application
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 4 - Placement of asphalt (AC mix)
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Correct temperature and spread rate
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA M/10 – Asphalt Mix Requirements
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 5 - Compaction of asphalt layers
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Rolling pattern, compaction
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA M/10, B2 – Asphalt Compaction
label | Frequency Of Inspection OR Test - As works progress
label | HOLD POINT - S
checkpoint | 6 - Joint sealing and finish
label | Controlled By : (Position) - SUB
label | Accept / Reject Criteria - Seam bonding and surface appearance
label | Spec. Ref, Procedure Or Method Statement - D12.4 - NZTA P40 – Joints and Finish
label | Frequency Of Inspection OR Test - Post Paving
label | HOLD POINT - S
checkpoint | 7 - Final inspection and sign-off
label | Controlled By : (Position) - PM/CR
label | Accept / Reject Criteria - All specs met, records submitted
label | Spec. Ref, Procedure Or Method Statement - Contract Conditions
label | Frequency Of Inspection OR Test - Final Walk over
label | HOLD POINT - I