## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | Cleanroom Checklist - GPL-QSE-ITP-FIT-012 (Rev00 / Level 2 - Mezzanine) |  | Cleanroom Checklist - GPL-QSE-ITP-FIT-012 (Rev00)
| section | Prior to Works
| checkpoint | Confirm sealant product to be used
5e08fb26-5fd6-5885-952d-28d12d4b8925 | textbox | Sealant brand, type, batch number, production date, shelf life:
| checkpoint | Confirm corner details to be used within cleanroom
a91db5ca-5162-5921-9ebe-81a653b21d2d | textbox | Floor to wall:
3addff85-4144-5ff4-942e-dd1a6eeeb012 | textbox | Wall to wall:
38772396-f7e0-5f61-bd7f-9aa813848ac0 | textbox | Wall to ceiling:
| checkpoint | Cleanroom material delivered clean, protected, and undamaged (plastic wrap), provide photos
3dded79a-abf5-5a93-ba12-5b25197d965b | tickbox | Sandwich panels
b3ad0c61-a7da-5010-b90b-0a1f1f5cbd85 | tickbox | Mechanical ductwork
3d3507f5-707e-53b0-a47f-787ad335c94a | tickbox | Hydraulic ipework
ff9a1d33-5802-57b5-8db6-abce14ec45e7 | tickbox | HEPA filters
7ab2b65a-877c-5919-91a4-a512e92e1492 | tickbox | Grilles
1dfe7521-a637-58db-9e27-9f787feb0888 | tickbox | Lights
f558e634-64b0-5e2c-ae8c-aac592ec3e6b | tickbox | Windows
ed2c2b35-804a-583f-8152-3178eaf30814 | tickbox | Doors
| checkpoint | Confirm relevant approved design drawing
017a1621-a748-531a-98a5-42f7cfd439e8 | textbox | Refer Shop Drawings, confirm dwg no. and revision no.
| section | During Works
| checkpoint | Cleanroom walls checklist, provide photos
a160683f-409a-5c06-9e01-cb6326add596 | tickbox | Support framing installed as specified
fa21c054-36b9-5c53-b64e-b770c8971487 | tickbox | Panel joints fully sealed
192803cc-e462-56ab-9fa0-d51f33bfdd89 | tickbox | Wall to wall joints are coved and sealed
06ca06b4-0040-5282-be00-adabe89a79b0 | tickbox | Wall to ceiling joints are coved and sealed
f44f2af8-3097-588d-a770-896650999d43 | tickbox | Wall to floor joints are coved and sealed
6944bec1-4156-5641-b35d-2f63e163fbc9 | tickbox | All penetrations fully sealed
| checkpoint | Cleanroom ceilings checklist, provide photos
f6d5411c-9a61-5b44-90d3-0767f8b303fd | tickbox | Support framing installed as specified
8477f378-8363-52c0-a49e-4c1573e13302 | tickbox | Panel joints fully sealed
97f28338-32b2-51c3-a3c1-94d4fb4825bc | tickbox | Ceiling to wall joints are coved and sealed
e6c57845-e18a-5fed-b873-f6212765385c | tickbox | All penetrations fully sealed
| checkpoint | Mechanical checklist, provide photos
51b87076-6b72-54f9-98a6-7b0414fa6925 | tickbox | Confirm ductwork flanges ae bolted & sealed
4c83fd83-48f8-5b7d-a023-f52f9aaba0b1 | tickbox | Confirm insulation installed and sealed
990b137b-3133-5e18-a058-1831fa90f4e0 | tickbox | Confirm inside of ductwork is clean
af767a96-846c-5816-9d29-37a04bb7f589 | tickbox | Pressure testing completed
f9152dfa-37cb-5e34-b23b-91051749f5b9 | tickbox | Supply & return air grilles completed
4916ca91-ea39-5f23-9870-5f1a78376acb | tickbox | HEPA factory certificates of conformity saved
d3bfecef-f1b1-594d-bb73-544c1f3de7f8 | tickbox | HEPA installation complete & test points installed either side
| checkpoint | Pass Through Hatches installed, cleaned and sealed
38e130a5-ef64-5d75-90f5-cf0af96b513b | note | Attach commissioning tests
| checkpoint | Electrical checklist, provide photos
ba81f989-933a-504c-93a3-f837b8f977e4 | tickbox | Confirm sub mains power & distribution boards are installed
a3d17c21-e37c-5459-9f75-5e0401ba447f | tickbox | All penetrations & cables sealed
4090d4db-3e77-5c91-8da2-ba09facd2ab2 | tickbox | Confirm light fittings installed and tested
| checkpoint | Compressed Air checklist, provide photos
0579643a-7276-549c-9c62-f8b0f7fbc74c | tickbox | Pipework and Isolation valves installed as per approved specification
4c624b1f-6be0-514e-bb4b-d78cbdab9dc5 | tickbox | Pipework labelled for contents and directional flow
469ea038-81d9-5157-9551-9da2ca24585e | tickbox | Backflow protection installed
e5e7ae11-9519-5696-8d91-5d874f72a9c0 | tickbox | Pressure testing completed
3d4bd1a0-3217-5642-94cf-91c16e182d12 | tickbox | Hose connections within cleanroom sealed
| checkpoint | Confirm joinery is installed and completed
c614b307-92ca-52ee-a362-ad37774cf20c | note | Confirm no wood is exposed, all must be sealed, no gaps
| checkpoint | Doors & Access Control checklist
1772844c-3436-5ffa-85ab-e9d0c7459c5b | tickbox | Glass supplied as per specification & Australian Standards
4dd0d9ee-d712-5948-aba5-c4598fe3ec71 | tickbox | Doors closing flush and sealed when in closed position
9f5fd685-4747-5981-96d3-89282634e7e1 | tickbox | Hardware fitting flush & sealed to surface
d8830554-de6e-58e3-b885-18c4ff1dcfbb | tickbox | Interlocks installed in accordance with approved design
f8956fc9-634b-502b-a02e-968384b9dddd | tickbox | Sealant to hinges, frame, glazing, and door closers all complete
| checkpoint | Windows checklist
515987f1-8c37-5596-a2fe-0c91ebfef7e9 | tickbox | Glass supplied as per specification & Australian Standards
bd087fd0-4f81-5ed1-91e0-a3104a6b3dd1 | tickbox | Window glass finishing flush and sealed
| checkpoint | Confirm sealing works are completed throughout
| checkpoint | Confirm testing & monitoring instrumentation is calibrated
5b5bebc9-3f28-57f0-8170-6c1bc2ce7998 | textbox | BMS: Make, model, serial number:
32aa883d-f1e7-5421-a163-7cbe48c23b27 | textbox | EMS: Make, model, serial number:
| checkpoint | Attach Cleanroom Consultant Inspection Report(s), and confirm all actions are closed out
| checkpoint | Confirm all ceiling tiles are sealed
| section | After Works
| checkpoint | Review panels & joints to ensure no visible damage/cracks/misalignments
| checkpoint | Confirm final cleaning completed for area
| checkpoint | Attach subcontractor ITP for Sandwich Panels
| section | Sign Offs
| checkpoint | Orwell Sign Off
f7c807cf-ca55-5f6f-ae3d-d18a5f6aecdc | note | Authorised By: DL
cd444a3f-0837-57b0-9fb3-ec5b5d60e221 | note | Issue Date: 24.06.2023
| signoff | Request Sign Off