## Sheet1
2.1 | Concrete | IFC Drawings | 32MPa concrete to be used as per IFC drawings. | Document Review | Each Mix | HP* | PE | This ITP | 2.1 - Concrete | Reference - IFC Drawings | Acceptance Criteria - 32MPa concrete to be used as per IFC drawings. | Method - Document Review | Frequency - Each Mix | Category - HP* | Responsibility - PE | Verifying Documents - This ITP | Date Completed: | 2.1 - Concrete
2.2 | Steel components | IFC Drawings AS41000 AS1163 | All Steel must comply with Australian Standards. Steel section sizes must be checked on site. Steel posts to be CHS with a grade of C250 | Document review Visual and Measure | All elements | IP | SE/Site Supervisor | Delivery Dockets | 2.2 - Steel components | Reference - IFC Drawings AS41000 AS1163 | Acceptance Criteria - All Steel must comply with Australian Standards. Steel section sizes must be checked on site. Steel posts to be CHS with a grade of C250 | Method - Document review Visual and Measure | Frequency - All elements | Category - IP | Responsibility - SE/Site Supervisor | Verifying Documents - Delivery Dockets | Date Completed: | Reference - IFC Drawings
3.1 | Excavation works | IFC Drawings L1-CHE-STD-005 | Excavation for post foundation must not undermine track and comply with PTDT requirements. Follow asset owners guidelines for work around their service. Excavation must use Non Distructive Digging in close proximity to services | Visual |  | IP | SE/Site Supervisor | This ITP | 3.1 - Excavation works | Reference - IFC Drawings L1-CHE-STD-005 | Acceptance Criteria - Excavation for post foundation must not undermine track and comply with PTDT requirements. Follow asset owners guidelines for work around their service. Excavation must use Non Distructive Digging in close proximity to services | Method - Visual | Frequency - | Category - IP | Responsibility - SE/Site Supervisor | Verifying Documents - This ITP | Date Completed: | Acceptance Criteria - 32MPa concrete to be used as per IFC drawings.
4.1 | Survey Set-out | IFC Drawings | Survey to set out the following but not limited to: existing services, post locations, refuge bays Offset checked against the running edge prior to installation of posts. Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template) Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts) | Measure Visual inspect | Each element | IP | Surveyor SE/PE/SPE | This ITP | 4.1 - Survey Set-out | Reference - IFC Drawings | Acceptance Criteria - Survey to set out the following but not limited to: existing services, post locations, refuge bays Offset checked against the running edge prior to installation of posts. Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template) Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts) | Method - Measure Visual inspect | Frequency - Each element | Category - IP | Responsibility - Surveyor SE/PE/SPE | Verifying Documents - This ITP | Date Completed: | Method - Document Review
4.2 | Vibration Monitoring | Worley vibration monitoring plan | Vibration monitors installed as required in monitoring plan. Vibration at VIVA pipelines not to exceed 10mm/s | Measure | Each element | IP | SE/PE/SPE | This ITP | 4.2 - Vibration Monitoring | Reference - Worley vibration monitoring plan | Acceptance Criteria - Vibration monitors installed as required in monitoring plan. Vibration at VIVA pipelines not to exceed 10mm/s | Method - Measure | Frequency - Each element | Category - IP | Responsibility - SE/PE/SPE | Verifying Documents - This ITP | Date Completed: | Frequency - Each Mix
5.1 | Ground Conditions | IFC Drawings | All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material. | Visual | Each post | IP | SE/Site Supervisor | This ITP | 5.1 - Ground Conditions | Reference - IFC Drawings | Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material. | Method - Visual | Frequency - Each post | Category - IP | Responsibility - SE/Site Supervisor | Verifying Documents - This ITP | Date Completed: | Category - HP*
5.2 | Post Foundation | IFC Drawings | Concrete - 300mm Dia - 800 mm Depth CHS Sleeve: - Depth 1400 - Other Dimensions as per IFC Direct Driven: - 88.9x4 CHS - Depth: 1400 Insulated fence near OLE posts: - 95x65 Truform LVL - Depth 800mm (post embedment 700mm) - 300mm diameter Spacings: Typical: 2700 max Gates: 1350 Refuge: 1200 | Measure | Each footing | IP | SE/Site Supervisor | Concrete Dockets | 5.2 - Post Foundation | Reference - IFC Drawings | Acceptance Criteria - Concrete - 300mm Dia - 800 mm Depth CHS Sleeve: - Depth 1400 - Other Dimensions as per IFC Direct Driven: - 88.9x4 CHS - Depth: 1400 Insulated fence near OLE posts: - 95x65 Truform LVL - Depth 800mm (post embedment 700mm) - 300mm diameter Spacings: Typical: 2700 max Gates: 1350 Refuge: 1200 | Method - Measure | Frequency - Each footing | Category - IP | Responsibility - SE/Site Supervisor | Verifying Documents - Concrete Dockets | Date Completed: | Responsibility - PE
5.3 | Post Installation | IFC Drawings L1-CHE-STD-005 | Minimum offset 3000mm from centreline of track. Minimum 2m offset to existing OLE structures (insulated fence required) Maximum post spacing to be 3m Two spans at 1350CTRS at the end and at Refuge bays. Max. post height 1800mm above ground level. Vertical Tolerance: ±20mm from the design line. | Measure | Each post | IP | SE/Site Supervisor | This ITP | 5.3 - Post Installation | Reference - IFC Drawings L1-CHE-STD-005 | Acceptance Criteria - Minimum offset 3000mm from centreline of track. Minimum 2m offset to existing OLE structures (insulated fence required) Maximum post spacing to be 3m Two spans at 1350CTRS at the end and at Refuge bays. Max. post height 1800mm above ground level. Vertical Tolerance: ±20mm from the design line. | Method - Measure | Frequency - Each post | Category - IP | Responsibility - SE/Site Supervisor | Verifying Documents - This ITP | Date Completed: | Verifying Documents - This ITP
5.4 | Post Installation - insulated fence near OLE structure | IFC Drawings L1-CHE-STD-005 | Minimum offset 4000mm from centreline of track. Minimum 1m offset to existing OLE structures Maximum post spacing to be 2.7m Two spans at 1350CTRS at the end and at Refuge bays. Max. post height 1800mm above ground level. Vertical Tolerance: ±20mm from the design line. | Measure | Each post | IP | SE/Site Supervisor | This ITP | 5.4 - Post Installation - insulated fence near OLE structure | Reference - IFC Drawings L1-CHE-STD-005 | Acceptance Criteria - Minimum offset 4000mm from centreline of track. Minimum 1m offset to existing OLE structures Maximum post spacing to be 2.7m Two spans at 1350CTRS at the end and at Refuge bays. Max. post height 1800mm above ground level. Vertical Tolerance: ±20mm from the design line. | Method - Measure | Frequency - Each post | Category - IP | Responsibility - SE/Site Supervisor | Verifying Documents - This ITP | Date Completed: | Date Completed:
5.5 | Chain Wire Mesh Installation | IFC Drawings | Chain-wire mesh 1800x50x2.50 to be fixed to fence post with tie wire. Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire. | Visual | Each element | IP | SE/Site Supervisor | This ITP | 5.5 - Chain Wire Mesh Installation | Reference - IFC Drawings | Acceptance Criteria - Chain-wire mesh 1800x50x2.50 to be fixed to fence post with tie wire. Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire. | Method - Visual | Frequency - Each element | Category - IP | Responsibility - SE/Site Supervisor | Verifying Documents - This ITP | Date Completed: | 2.2 - Steel components
5.6 | Bracing | IFC Drawings | 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps. Bracing to be installed on both sides of the fence at the fence corners | Visual | Each element | IP | SE/Site Supervisor | This ITP | 5.6 - Bracing | Reference - IFC Drawings | Acceptance Criteria - 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps. Bracing to be installed on both sides of the fence at the fence corners | Method - Visual | Frequency - Each element | Category - IP | Responsibility - SE/Site Supervisor | Verifying Documents - This ITP | Date Completed: | Reference - IFC Drawings AS41000 AS1163
5.7 | Wire mesh and bracing at OLE posts (insulated fence) | IFC Drawings | Mesh fence to be PVC coated Bracing with 95x65 truform LVL - fix to post with 2x12G timber batten screws Tension wires to be PVC coated Mesh fixed to posts using fence staples at max 200mm spacing | Visual | Each element | IP | SE/Site Supervisor | This ITP | 5.7 - Wire mesh and bracing at OLE posts (insulated fence) | Reference - IFC Drawings | Acceptance Criteria - Mesh fence to be PVC coated Bracing with 95x65 truform LVL - fix to post with 2x12G timber batten screws Tension wires to be PVC coated Mesh fixed to posts using fence staples at max 200mm spacing | Method - Visual | Frequency - Each element | Category - IP | Responsibility - SE/Site Supervisor | Verifying Documents - This ITP | Date Completed: | Acceptance Criteria - All Steel must comply with Australian Standards. Steel section sizes must be checked on site. Steel posts to be CHS with a grade of C250
5.8 | Refuge Installation | IFC Drawings | Refuge Access to only open from track side. No chain wire mesh to be installed at refuge access. Refuge Access to be located maximum 20m intervals 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only. | Visual | Each element | IP | SE/Site Supervisor | This ITP | 5.8 - Refuge Installation | Reference - IFC Drawings | Acceptance Criteria - Refuge Access to only open from track side. No chain wire mesh to be installed at refuge access. Refuge Access to be located maximum 20m intervals 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only. | Method - Visual | Frequency - Each element | Category - IP | Responsibility - SE/Site Supervisor | Verifying Documents - This ITP | Date Completed: | Method - Document review Visual and Measure
5.9 | Refuge Signage | IFC Drawings | Sign shall be installed on fence half way between refuges indicating distance to adjacent refuges. Max size of signage to be A3 or smaller (297mmx420mm MAX) | Visual | Each element | IP | SE/Site Supervisor | This ITP | 5.9 - Refuge Signage | Reference - IFC Drawings | Acceptance Criteria - Sign shall be installed on fence half way between refuges indicating distance to adjacent refuges. Max size of signage to be A3 or smaller (297mmx420mm MAX) | Method - Visual | Frequency - Each element | Category - IP | Responsibility - SE/Site Supervisor | Verifying Documents - This ITP | Date Completed: | Frequency - All elements
6.1 | Fence Height and Track Clearance | IFC Drawings | Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings. | Measure | Each lot | IP | SE/Site Supervisor | Survey report | 6.1 - Fence Height and Track Clearance | Reference - IFC Drawings | Acceptance Criteria - Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings. | Method - Measure | Frequency - Each lot | Category - IP | Responsibility - SE/Site Supervisor | Verifying Documents - Survey report | Date Completed: | Category - IP
Responsibility - SE/Site Supervisor
Verifying Documents - Delivery Dockets
Date Completed:
3.1 - Excavation works
Reference - IFC Drawings L1-CHE-STD-005
Acceptance Criteria - Excavation for post foundation must not undermine track and comply with PTDT requirements. Follow asset owners guidelines for work around their service. Excavation must use Non Distructive Digging in close proximity to services
Method - Visual
Frequency -
Category - IP
Responsibility - SE/Site Supervisor
Verifying Documents - This ITP
Date Completed:
4.1 - Survey Set-out
Reference - IFC Drawings
Acceptance Criteria - Survey to set out the following but not limited to: existing services, post locations, refuge bays Offset checked against the running edge prior to installation of posts. Up track: Minimum offset 2135mm from centreline of track. (1285mm outside edge of track - Engineer to verify with timber jig template) Down track: Minimum offset 3172mm from centreline of track. (Utilise existing posts - Engineer to verify with string line between posts)
Method - Measure Visual inspect
Frequency - Each element
Category - IP
Responsibility - Surveyor SE/PE/SPE
Verifying Documents - This ITP
Date Completed:
4.2 - Vibration Monitoring
Reference - Worley vibration monitoring plan
Acceptance Criteria - Vibration monitors installed as required in monitoring plan. Vibration at VIVA pipelines not to exceed 10mm/s
Method - Measure
Frequency - Each element
Category - IP
Responsibility - SE/PE/SPE
Verifying Documents - This ITP
Date Completed:
5.1 - Ground Conditions
Reference - IFC Drawings
Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
Method - Visual
Frequency - Each post
Category - IP
Responsibility - SE/Site Supervisor
Verifying Documents - This ITP
Date Completed:
5.2 - Post Foundation
Reference - IFC Drawings
Acceptance Criteria - Concrete - 300mm Dia - 800 mm Depth CHS Sleeve: - Depth 1400 - Other Dimensions as per IFC Direct Driven: - 88.9x4 CHS - Depth: 1400 Insulated fence near OLE posts: - 95x65 Truform LVL - Depth 800mm (post embedment 700mm) - 300mm diameter Spacings: Typical: 2700 max Gates: 1350 Refuge: 1200
Method - Measure
Frequency - Each footing
Category - IP
Responsibility - SE/Site Supervisor
Verifying Documents - Concrete Dockets
Date Completed:
5.3 - Post Installation
Reference - IFC Drawings L1-CHE-STD-005
Acceptance Criteria - Minimum offset 3000mm from centreline of track. Minimum 2m offset to existing OLE structures (insulated fence required) Maximum post spacing to be 3m Two spans at 1350CTRS at the end and at Refuge bays. Max. post height 1800mm above ground level. Vertical Tolerance: ±20mm from the design line.
Method - Measure
Frequency - Each post
Category - IP
Responsibility - SE/Site Supervisor
Verifying Documents - This ITP
Date Completed:
5.4 - Post Installation - insulated fence near OLE structure
Reference - IFC Drawings L1-CHE-STD-005
Acceptance Criteria - Minimum offset 4000mm from centreline of track. Minimum 1m offset to existing OLE structures Maximum post spacing to be 2.7m Two spans at 1350CTRS at the end and at Refuge bays. Max. post height 1800mm above ground level. Vertical Tolerance: ±20mm from the design line.
Method - Measure
Frequency - Each post
Category - IP
Responsibility - SE/Site Supervisor
Verifying Documents - This ITP
Date Completed:
5.5 - Chain Wire Mesh Installation
Reference - IFC Drawings
Acceptance Criteria - Chain-wire mesh 1800x50x2.50 to be fixed to fence post with tie wire. Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire.
Method - Visual
Frequency - Each element
Category - IP
Responsibility - SE/Site Supervisor
Verifying Documents - This ITP
Date Completed:
5.6 - Bracing
Reference - IFC Drawings
Acceptance Criteria - 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps. Bracing to be installed on both sides of the fence at the fence corners
Method - Visual
Frequency - Each element
Category - IP
Responsibility - SE/Site Supervisor
Verifying Documents - This ITP
Date Completed:
5.7 - Wire mesh and bracing at OLE posts (insulated fence)
Reference - IFC Drawings
Acceptance Criteria - Mesh fence to be PVC coated Bracing with 95x65 truform LVL - fix to post with 2x12G timber batten screws Tension wires to be PVC coated Mesh fixed to posts using fence staples at max 200mm spacing
Method - Visual
Frequency - Each element
Category - IP
Responsibility - SE/Site Supervisor
Verifying Documents - This ITP
Date Completed:
5.8 - Refuge Installation
Reference - IFC Drawings
Acceptance Criteria - Refuge Access to only open from track side. No chain wire mesh to be installed at refuge access. Refuge Access to be located maximum 20m intervals 50dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
Method - Visual
Frequency - Each element
Category - IP
Responsibility - SE/Site Supervisor
Verifying Documents - This ITP
Date Completed:
5.9 - Refuge Signage
Reference - IFC Drawings
Acceptance Criteria - Sign shall be installed on fence half way between refuges indicating distance to adjacent refuges. Max size of signage to be A3 or smaller (297mmx420mm MAX)
Method - Visual
Frequency - Each element
Category - IP
Responsibility - SE/Site Supervisor
Verifying Documents - This ITP
Date Completed:
6.1 - Fence Height and Track Clearance
Reference - IFC Drawings
Acceptance Criteria - Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
Method - Measure
Frequency - Each lot
Category - IP
Responsibility - SE/Site Supervisor
Verifying Documents - Survey report
Date Completed: