## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP No. PC239 - PRECAST PANEL CONSTRUCTION | itp |  |  |  |  | ITP No. PC239 - PRECAST PANEL CONSTRUCTION
section | PRECAST PANEL CONSTRUCTION
checkpoint | 1 - Ensure drawings are all ‘approved for construction’
label | Reference Documents - AS 3600 concrete structures, AS3850 Prefabricated concrete
label | ○ Document register.
label | Acceptance Criteria - Drawings & spec all ‘approved for construction’
label | Verification Activity: MP - H
label | Verification Activity: BW - H
label | Verification Activity: ADG - R
label | Remarks/Records - KEN BROWN & ASSOCIATES – Consulting Structural and Civil Engineers, RPEQ – 1514 Form-12 at completion of project
holdpoint | HOLD POINT
checkpoint | 2 - Safe Work Method Statement, Pre-Pour ITR + Post-Pour ITR in-place
label | Reference Documents - AS3600 concrete structures
label | ○ Industry Code of Practice
label | Acceptance Criteria - Complies with standard.
label | Verification Activity: MP - R
label | Verification Activity: BW - S
label | Verification Activity: ADG - S
label | Remarks/Records - MULHERIN PRECAST – Quality Management System
checkpoint | 3 - Concrete design mix approval and trial mix
label | Reference Documents - AS3600 concrete structures
label | ○ ADG Specification for Precast Concrete
label | Acceptance Criteria - No concrete shall be placed in the Works until approval of the mix design has been obtained from the Administrator.
label | Verification Activity: MP - H
label | Verification Activity: BW - H
label | Verification Activity: ADG - H
label | Remarks/Records - MULHERIN PRECAST – Quality Management System
label | ○ Supplier Concrete Mix Design and materials test reports
holdpoint | HOLD POINT
checkpoint | 4 - Reo, sheer bar, tension bar, Cast-in lifters + ferrules
label | Reference Documents - AS3600 concrete structures, AS1110 Metric bolts, AS4671 steel reinforcing materials.
label | ○ AS5216 Design of post-installed and cast-in fastenings in concrete
label | Acceptance Criteria - Complies with standard.
label | ○ The producer and the processor of reinforcing steel must be certified to a product conformity assessment scheme
label | Verification Activity: MP - R
label | Verification Activity: BW - R
label | Verification Activity: ADG - S
label | Remarks/Records - Wire Industries, ACRS accredited Certificate Number: 61203
checkpoint | 5 - Formwork assembled and inspected to drawings
label | Reference Documents - AS3610.1
label | Acceptance Criteria - Formwork shall conform to AS 3610 except as uno.
label | ○ Approved to proceed
label | Verification Activity: MP - H
label | Verification Activity: BW - H
label | Verification Activity: ADG - H
label | Remarks/Records - MULHERIN PRECAST – Quality Management System
label | ○ Y5 – Control Document Form, Pre-Pour Check Sheet
holdpoint | HOLD POINT
checkpoint | 6 - Reinforcement, cast-in plates, ferrules, lifters installed and inspected to drawings
label | Reference Documents - AS3600 concrete structures
label | ○ AS5216 Design of post-installed and cast-in fastenings in concrete
label | Acceptance Criteria - Approved to proceed
label | Verification Activity: MP - H
label | Verification Activity: BW - H
label | Verification Activity: ADG - H
label | Remarks/Records - MULHERIN PRECAST – Quality Management System
label | ○ Y5 – Y7 Control Document Form, Pre-Pour and Reinforcement Check Sheet
holdpoint | HOLD POINT
checkpoint | 7 - Concrete mix supply and concrete placement
label | Reference Documents - AS1379
label | Acceptance Criteria - Approved to proceed
label | ○ Concreting operations shall be carried out in a continuous manner for each precast item.
label | ○ Compaction of concrete shall commence immediately after deposition
label | Verification Activity: MP - H
label | Verification Activity: BW - H
label | Verification Activity: ADG - H
label | Remarks/Records - MULHERIN PRECAST – Quality Management System
label | ○ Y4 – Control Document Form, Precast Concrete Day Pour Sheet
holdpoint | HOLD POINT
checkpoint | 8 - Concrete testing - slump tests
label | Reference Documents - AS1012- Methods of testing concrete.
label | Acceptance Criteria - NATA approved supplier
label | Verification Activity: MP - W
label | Verification Activity: BW - R
label | Verification Activity: ADG - R
label | Remarks/Records - KCT Kearney`s Concrete Testing Pty Ltd
label | ○ NATA Accreditation Number - 20227
checkpoint | 9 - Panel inspection – removal of formwork, curing, dimensions, visual inspection, finish, defect inspections
label | Reference Documents - AS3850 – table 2.8.
label | Acceptance Criteria - Approved to proceed.
label | Verification Activity: MP - H
label | Verification Activity: BW - H
label | Verification Activity: ADG - H
label | Remarks/Records - MULHERIN PRECAST – Quality Management System
label | ○ Y6 – Control Document Form, Post-Pour Check Sheet
holdpoint | HOLD POINT
checkpoint | 10 - Marking, handling, storing and transporting
label | Reference Documents - Crane and Panel Storage Daily Check Sheet.
label | Acceptance Criteria - Complies
label | ○ On each precast concrete element, the information (date, ID, manufacture’s name & max mass) shall be clearly and permanently marked on a surface which shall not be on permanent display.
label | Verification Activity: MP - H
label | Verification Activity: BW - S
label | Verification Activity: ADG - S
label | Remarks/Records - MULHERIN PRECAST – Quality Management system
label | ○ Y16 – Control Document Form, Crane and Panel Storage Daily Check Sheet
holdpoint | HOLD POINT
checkpoint | 11 - Certificate of Compliance
label | Reference Documents - Precast Certificate of Compliance
label | Acceptance Criteria - Pre - Delivery
label | Verification Activity: MP - R
label | Verification Activity: BW - R
label | Verification Activity: ADG - S
label | Remarks/Records - MULHERIN PRECAST – Quality Management System
label | ○ Y3- Control Document Form, Certificate of Compliance
checkpoint | 12 - Non-Conformances all closed out.
label | Reference Documents - Non Conformance Report / register.
label | Acceptance Criteria - NCR’s closed out
label | Verification Activity: MP - H
label | Verification Activity: BW - H
label | Verification Activity: ADG - H
label | Remarks/Records - MULHERIN PRECAST – Quality Management System
label | ○ Y12 – Control Document Form, Non-Conformance Report/register
holdpoint | HOLD POINT
checkpoint | 13 - Document compilation and lot close-out
label | Acceptance Criteria - All relevant documentation
label | ○ Visibuild Construction Quality Management Software
label | Verification Activity: MP - R
label | Verification Activity: BW - R
label | Verification Activity: ADG - R
label | Remarks/Records - MULHERIN PRECAST – Quality Management System
label | ○ Visibuild Construction Quality Management Software
checkpoint | Mulherin Precast - Signoff:
signoff | Signature:
checkpoint | BW - Signoff:
signoff | Signature:
checklist | Y3 - Certificate of Compliance | [5 empty] | Y3 - Certificate of Compliance Template
section | PRECAST CERTIFICATE OF COMPLIANCE
checkpoint-no-status | To be completed and signed off by the manufacturer’s management representative – Supervisor or higher.
textbox | PRINCIPAL CONTRACTOR:
textbox | PROJECT:
textbox | SITE ADDRESS:
textbox | PANEL ERECTOR:
textbox | CONCRETE DESIGN STRENGTH FOR LIFTING (MPa):
textbox | DESIGN STRENGTH (MPa):
checkpoint | Panel
textbox | Panel No
textbox | Drawing No
textbox | Rev
textbox | Pre Pour ITR Status
textbox | Calculated Weight (t)
date | Date Cast
textbox | Field Sheet No (Batch ID)
textbox | Concrete Docket No
label | Concrete test Results (Mpa)
textbox | 7 Days
textbox | 28 Days
textbox | 28 Days
textbox | ETA on Site
date | Date Verified
checkpoint | 1. Lifters have been checked for size and location as per approved shop drawings
checkpoint | 2. Lifters have been checked to ensure that lift capacity is stamped on exposed top
checkpoint | 3. Edge lifters installed in line with the manufacturer’s recommendations
checkpoint | Final Inspection
textbox | I, |  |  | , on behalf of Mulherin Precast state that the panel/s scheduled above, have been manufactured according to the approved shop drawings, AS3850, the National Code of Practice for Precast and Tilt-up and Concrete Elements in Building Construction
textbox | Concrete strength as recorded on delivery docket:
textbox | Lifting insert manufacturer:
textbox | Type:
textbox | WLL:
label | (Lifters installed complete with tension bar, and shear bar installed in line with manufacturer’s recommendations)
label | NOTE: Panels are to be handled, transported and erected as per AS3850 and the National Code of Practice for Precast, Tilt-up and Concrete Elements in Building Construction. A copy of this Certificate and the manufacturer’s technical information about each element (including details of the correct rigging formation for each element) must be supplied to the principal contractor (and crane crew) by the erection design engineer prior to panels being unloaded on site.
holdpoint | Signature:
checklist | Y4 - Precast Concrete Pour Day Sheet | [5 empty] | Y4 - Precast Concrete Pour Day Sheet - Rev 0
section | PRECAST CONCRETE DAY POUR SHEET
checkpoint-no-status | Details
number | Day:
textbox | Time Ordered:
button | AM/PM | AM,PM
date | Date:
dropdown | Weather Conditions: | Fine,Overcast,Showery,Rain
textbox | Notes
checkpoint | Concrete Mix Confirmed
dropdown | S5026002 | 50,20,120,Other
textbox | Other:
textbox | Sample ID:
textbox | Concrete Test No: (doc No:)
checkpoint | Panel
textbox | Panel ID No
textbox | Job No
textbox | m3
textbox | Form ITP Sighted
textbox | Steel ITP Sighted
textbox | On-Site Time
textbox | Off- Site Time
holdpoint | Signature:
checklist | Y5 - Daily PRE & POST Check Sheet | [5 empty] | Y5 - Daily PRE & POST Check Sheet
section | PRODUCT DETAILS
checkpoint-no-status | Details
textbox | Product Description/Code
textbox | Cast Bed No
textbox | Drawing Revision
textbox | Other Remarks:
section | PRE-POUR CHECK LIST (ACCEPTABLE DEVIATIONS – AS 3610.1-2010 TABLE 3.3.3)
checkpoint | Mould dimensions within project tolerance
checkpoint | Mould surface cleaned
checkpoint | Sealing and rubbers in place
checkpoint | Mould oiled and excess removed
checkpoint | Correct diameter grout tubes and length
checkpoint | Correct reinforcement size & position
checkpoint | Sufficient & correct bar chairs/nibs
checkpoint | Correct lifters, type and position
checkpoint | Correct fittings & casting items installed
checkpoint | Correct Chamfer and edging tools
section | Cover Measurement AS PER IFC DRAWING
checkpoint-no-status | Cover Measurement
label | COVER: Crown
textbox | COVER: Crown - SPEC
textbox | COVER: Crown - ACT
label | COVER: Sides
textbox | COVER: Sides - SPEC
textbox | COVER: Sides - ACT
label | COVER: Top
textbox | COVER: Top - SPEC
textbox | COVER: Top - ACT
label | COVER: Bottom
textbox | COVER: Bottom - SPEC
textbox | COVER: Bottom - ACT
label | COVER: Ends
textbox | COVER: Ends - SPEC
textbox | COVER: Ends - ACT
label | COVER: Haunch
textbox | COVER: Haunch - SPEC
textbox | COVER: Haunch - ACT
label | COVER: Inner
textbox | COVER: Inner - SPEC
textbox | COVER: Inner - ACT
label | COVER: Rebate
textbox | COVER: Rebate - SPEC
textbox | COVER: Rebate - ACT
section | CASTING CHECK LIST (Sampling in accordance with AS.1012.1)
checkpoint | CASTING CHECK LIST
textbox | Casting commenced: |  |  | hrs
textbox | Casting completed: |  |  | hrs
textbox | Sample no:
textbox | Slump: |  |  | mm
textbox | Air temp: |  |  | °C
textbox | Concrete temp: |  |  | °C
textbox | Concrete mix code:
textbox | Mix strength:
textbox | No. of cylinders:
textbox | Delivery docket No.
textbox | Finish applied
section | POST POUR AND STORAGE CHECK LIST (ACCEPTABLE DEVIATIONS – AS 3610.1-2010 TABLE 3.3.3)
checkpoint-no-status | Date stripped:
date | Date:
checkpoint | Visual inspection on all faces
checkpoint | Product dimension checked (minimum 1in 10 units)
checkpoint | Any defects identified including cracks, honeycombs etc.
textbox | if Yes, Specify:
checkpoint | Any cracking visible - mark on product check drawing
checkpoint | Specified class of finish achieved
checkpoint | Any stripping, handling or storage damage
checkpoint | Product clearly labelled. (Include Code, Date, Mould No. Weight etc.)
checkpoint | NCR required:
textbox | NCR No.:
checkpoint | Checked/Approved by:
textbox | Checked by:
textbox | Approved by:
label | Position: QA Engineer
label | Position: Third Party Inspector
label | Position: Manager
date | Date:
holdpoint | Signature:
checklist | Y7 - Daily Reinforcement Check Sheet | [5 empty] | Y7 - Daily Reinforcement Check Sheet
section | DAILY REINFORCEMENT CHECK SHEET
checkpoint-no-status | Details
textbox | Product Description/Code
textbox | Schedule No.
textbox | Cast Bed No.
textbox | Bar Mark No's
textbox | Manufacturing Shop Drawing No.
textbox | Quantity.
section | Reinforcement Bar Details: Steel Reinforcing Manufacture to AS/NZS 4671:2001, ACRS Certificate No. 61203
checkpoint | Mesh SL
textbox | Mesh SL:
button | Size Acceptable | Yes,No
button | Spacing Acceptable | Yes,No
button | Lap Acceptable | Yes,No
button | Cog Acceptable | Yes,No
checkpoint | Distribution Bars
button | Size Acceptable | Yes,No
button | Spacing Acceptable | Yes,No
button | Lap Acceptable | Yes,No
button | Cog Acceptable | Yes,No
checkpoint | Other Bars
button | Size Acceptable | Yes,No
button | Spacing Acceptable | Yes,No
button | Lap Acceptable | Yes,No
button | Cog Acceptable | Yes,No
section | Reinforcement Dimensions: AS PER IFC DRAWING
checkpoint | Is reinforcement drawing(s) attached?
checkpoint | Is length acceptable +0mm -10mm
checkpoint | Is width acceptable +0mm -10mm
checkpoint | Is reinforcement square
section | Reinforcement Assembly: AS PER IFC DRAWING
checkpoint | Strength and Stiffness for lifting
checkpoint | Sufficiently Tied
checkpoint | Perimeter Bar U.N.O
section | Reinforcement Cage Setup: AS PER IFC DRAWING
checkpoint | Bar chair type
textbox | Bar chair type:
checkpoint | Bar chair size (cover)
textbox | Bar chair size (cover):
checkpoint | Number of bar chairs acceptable
section | Checked/Approved by
checkpoint | Checked/Approved by:
textbox | Checked by:
textbox | Approved by:
label | Position: QA Engineer
label | Position: Third Party Inspector
label | Position: Manager
date | Date:
holdpoint | Signature: