## Template
INSPECTION TEST REPORT (ITP)
Project Name: Cambridge St. Epping | Date: | Adaptive representative | Bloc representative | Revision # | Rectification Works To Complete | Comments
Level: 1-4 | Change Date to green when 100% completed | Place Yes if completion is confirmed, No if with actual balance of works | If No, please explain | Are there any issues Adaptive needs to rectify on this issue? | Are there any site issues that need to rectify on this issue? | Further information | Signature
Room Name & Code: RAC Apartments Bedheads
Joinery Code: B.J03
Date Installed:
Joinery Installed Level
Doors adjusted | NA | NA |  |  | NA
Benchtop installed | NA | NA |  |  | NA
Corian site measured | NA | NA |  |  | NA
Shelving installed | NA | NA |  |  | NA
Gap filled
Screws capped
Bulkhead/Filler installed (if required) | NA | NA |  |  | NA
Glass splashback measured after installation | NA | NA |  |  | NA
Power point locations on glass splashback have been confirmed prior to ordering | NA | NA |  |  | NA
Any damage to finished joinery
Setout location accurate | NA | NA |  |  | NA
Aluminium trim installed | NA | NA |  |  | NA
Pinboards installed | NA | NA |  |  | NA
Site conditions preventing completion of unit
Are we holding up any trades? Please explain what can we do to rectify this in the further information section.

## Sheet1
Project Name: | Date | Adaptive representative | Bloc representative | Revision # | Rectification Works To Complete | Comments
Level: | Change Yes to green when 100% completed | Change no to red if not finished | If No please explain | Are there any issues Adaptive needs to rectify on this issue? | Are there any site issues that need to rectify on this issue? | Further information
Room Name & Code:
Joinery Code:
Date Installed:
Joinery Installed Level
Doors adjusted
Benchtop installed
Stone site measured | NA
Adjustable shelving installed
Gap filled
Screws capped
Bulkhead required
Glass splashback measured after installation | NA
Power point locations on glass splashback have been confirmed prior to ordering | NA
Any damage to finished joinery | NA
Setout location accurate
Aluminium trim installed | NA
Pinboards installed
Site conditions preventing completion of unit | NA
Are we holding up any trades? Please explain what can we do to rectify this in the further information section. | NA