## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | RAC Bedheads | itp |  |  |  |  | ITP - RAC Bedheads
section | Details
checkpoint | Joinery Installed Level
checkpoint | Doors adjusted
checkpoint | Benchtop installed
checkpoint | Corian site measured
checkpoint | Shelving installed
checkpoint | Gap filled
checkpoint | Screws capped
checkpoint | Bulkhead/Filler installed (if required)
checkpoint | Glass splashback measured after installation
checkpoint | Power point locations on glass splashback have been confirmed prior to ordering
checkpoint | Any damage to finished joinery
checkpoint | Setout location accurate
checkpoint | Aluminium trim installed
checkpoint | Pinboards installed
checkpoint | Site conditions preventing completion of unit
checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.
checklist | RAC Memory Box | itp |  |  |  |  | ITP - RAC Memory Box
section | Details
checkpoint | Joinery Installed Level
checkpoint | Doors adjusted
checkpoint | Benchtop installed
checkpoint | Corian site measured
checkpoint | Shelving installed
checkpoint | Gap filled
checkpoint | Screws capped
checkpoint | Bulkhead required
checkpoint | Glass splashback measured after installation
checkpoint | Power point locations on glass splashback have been confirmed prior to ordering
checkpoint | Any damage to finished joinery
checkpoint | Setout location accurate
checkpoint | Aluminium trim installed
checkpoint | Pinboards installed
checkpoint | Site conditions preventing completion of unit
checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.
checklist | RAC Robes | itp |  |  |  |  | ITP - RAC Robes
section | Details
checkpoint | Joinery Installed Level
checkpoint | Doors adjusted
checkpoint | Benchtop installed
checkpoint | Corian site measured
checkpoint | Shelving installed
checkpoint | Gap filled
checkpoint | Screws capped
checkpoint | Bulkhead/Filler installed (if required)
checkpoint | Glass splashback measured after installation
checkpoint | Power point locations on glass splashback have been confirmed prior to ordering
checkpoint | Any damage to finished joinery
checkpoint | Setout location accurate
checkpoint | Aluminium trim installed
checkpoint | Pinboards installed
checkpoint | Site conditions preventing completion of unit
checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.
checklist | RAC Vanity | itp |  |  |  |  | ITP - RAC Vanity
section | Details
checkpoint | Joinery Installed Level
checkpoint | Doors adjusted
checkpoint | Benchtop installed
checkpoint | Corian site measured
checkpoint | Shelving installed
checkpoint | Gap filled
checkpoint | Screws capped
checkpoint | Bulkhead/Filler installed (if required)
checkpoint | Glass splashback measured after installation
checkpoint | Power point locations on glass splashback have been confirmed prior to ordering
checkpoint | Any damage to finished joinery
checkpoint | Setout location accurate
checkpoint | Aluminium trim installed
checkpoint | Pinboards installed
checkpoint | Site conditions preventing completion of unit
checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.
checklist | RL Bath | itp |  |  |  |  | ITP - RL Bath
section | Details
checkpoint | Joinery Installed Level
checkpoint | Doors adjusted
checkpoint | Benchtop installed
checkpoint | Corian site measured
checkpoint | Shelving installed
checkpoint | Gap filled
checkpoint | Screws capped
checkpoint | Bulkhead/Filler installed (if required)
checkpoint | Glass splashback measured after installation
checkpoint | Power point locations on glass splashback have been confirmed prior to ordering
checkpoint | Any damage to finished joinery
checkpoint | Setout location accurate
checkpoint | Aluminium trim installed
checkpoint | Pinboards installed
checkpoint | Site conditions preventing completion of unit
checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.
checklist | RL Kitchen | itp |  |  |  |  | ITP - RL Kitchen
section | Details
checkpoint | Joinery Installed Level
checkpoint | Doors adjusted
checkpoint | Benchtop installed
checkpoint | Corian site measured
checkpoint | Shelving installed
checkpoint | Gap filled
checkpoint | Screws capped
checkpoint | Bulkhead/Filler installed (if required)
checkpoint | Glass splashback measured after installation
checkpoint | Power point locations on glass splashback have been confirmed prior to ordering
checkpoint | Any damage to finished joinery
checkpoint | Setout location accurate
checkpoint | Aluminium trim installed
checkpoint | Pinboards installed
checkpoint | Site conditions preventing completion of unit
checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.
checklist | RL Laundry | itp |  |  |  |  | ITP - RL Laundry
section | Details
checkpoint | Joinery Installed Level
checkpoint | Doors adjusted
checkpoint | Benchtop installed
checkpoint | Corian site measured
checkpoint | Shelving installed
checkpoint | Gap filled
checkpoint | Screws capped
checkpoint | Bulkhead/Filler installed (if required)
checkpoint | Glass splashback measured after installation
checkpoint | Power point locations on glass splashback have been confirmed prior to ordering
checkpoint | Any damage to finished joinery
checkpoint | Setout location accurate
checkpoint | Aluminium trim installed
checkpoint | Pinboards installed
checkpoint | Site conditions preventing completion of unit
checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.
checklist | RL Robe & Storage | itp |  |  |  |  | ITP - RL Robe & Storage
section | Details
checkpoint | Joinery Installed Level
checkpoint | Doors adjusted
checkpoint | Benchtop installed
checkpoint | Corian site measured
checkpoint | Shelving installed
checkpoint | Gap filled
checkpoint | Screws capped
checkpoint | Bulkhead/Filler installed (if required)
checkpoint | Glass splashback measured after installation
checkpoint | Power point locations on glass splashback have been confirmed prior to ordering
checkpoint | Any damage to finished joinery
checkpoint | Setout location accurate
checkpoint | Aluminium trim installed
checkpoint | Pinboards installed
checkpoint | Site conditions preventing completion of unit
checkpoint | Are we holding up any trades? Please explain what can we do to rectify this in the further information section.