## Site establishment
Site establishment
ACCESS | Secure ground entry | Pass/Fail/NA | same pass/fail/na checklist for each item in column B with comment function
| Digital sign in | Pass/Fail/NA
| Stair access | Pass/Fail/NA
| Loading platform | Pass/Fail/NA
| Secure upper building entry | Pass/Fail/NA
| Carpark exclusion zones | Pass/Fail/NA
| Public building entry zone | Pass/Fail/NA
| Fire protection mainteance zone | Pass/Fail/NA
SIGNAGE | Hazard board | Pass/Fail/NA
| Site contact | Pass/Fail/NA
| Emergency evacuation plan | Pass/Fail/NA
| Wayfinding signage | Pass/Fail/NA
| Site Office | Pass/Fail/NA
| Lunchroom | Pass/Fail/NA
| Noticeboard | Pass/Fail/NA
FACILITIES | Site Office | Pass/Fail/NA
| Lunchroom | Pass/Fail/NA
| Toilet | Pass/Fail/NA
| Waste management seperation | Pass/Fail/NA
| Water connection | Pass/Fail/NA
| Waste connection | Pass/Fail/NA
| Power connection | Pass/Fail/NA
| Data connection | Pass/Fail/NA
| Printer/Scanner | Pass/Fail/NA
| Hoardings External | Pass/Fail/NA
| Hoardings Internal | Pass/Fail/NA
| Hoarding access | Pass/Fail/NA
| Acotusic Controls | Pass/Fail/NA
| Dust Controls | Pass/Fail/NA
| Sound Meter | Pass/Fail/NA
| Fire Extinguisher | Pass/Fail/NA
| First Aid Kit | Pass/Fail/NA
| Plan Table | Pass/Fail/NA
DOCUMENTATION | Approved Site Specific Safety Plan | Pass/Fail/NA
| Approved Construction Management Plan | Pass/Fail/NA
| Approved Building Consent Documents | Pass/Fail/NA
| Contact List | Pass/Fail/NA
| Procore documentation established | Pass/Fail/NA
| Procore invitations issued | Pass/Fail/NA
| CONQA checklists established | Pass/Fail/NA
Request Signoff

## Preline
Preline
2110 DEMOLITION | Redundant services | Pass/Fail/NA |  | same pass/fail/na checklist for each item in yellow columns with comment funciton
| Service capping | Pass/Fail/NA
| Mechanical controls | Pass/Fail/NA
| Bulkheads | Pass/Fail/NA
| Perimter walls | Pass/Fail/NA
| Floor | Pass/Fail/NA
| Making good | Pass/Fail/NA
| Demobilisation & cleanup | Pass/Fail/NA
3820 TIMBER FRAMING | Partition walls | DPC | Pass/Fail/NA
|  | Correct grade, size treatement | Pass/Fail/NA
|  | Correct anchor, general connectors, ctrs and embedment | Pass/Fail/NA
|  | True and level | Pass/Fail/NA
| Bulkhead walls | DPC | Pass/Fail/NA
|  | Correct grade, size treatement | Pass/Fail/NA
|  | Correct anchor, general connectors, ctrs and embedment | Pass/Fail/NA
|  | True and level | Pass/Fail/NA
| Wall strapping | DPC | Pass/Fail/NA
|  | Correct grade, size treatement | Pass/Fail/NA
|  | Correct anchor, general connectors, ctrs and embedment | Pass/Fail/NA
|  | True and level | Pass/Fail/NA
4520 ALUMINIUM WINDOWS AND DOORS | Windows | Correct opening | Pass/Fail/NA
|  | Flexible flashing, Sill Tape, Foam Tape Seal | Pass/Fail/NA
|  | Suitable DPC, packing, shims and fixing | Pass/Fail/NA
|  | Glazing blocks/seals | Pass/Fail/NA
|  | Cleaned | Pass/Fail/NA
|  | Manifestations required | Pass/Fail/NA
|  | Correct hardware & operation | Pass/Fail/NA
| Hinged Doors | Correct opening | Pass/Fail/NA
|  | Flexible flashing, Sill Tape, Foam Tape Seal | Pass/Fail/NA
|  | Suitable DPC, packing, shims and fixing | Pass/Fail/NA
|  | Glazing blocks/seals | Pass/Fail/NA
|  | Cleaned | Pass/Fail/NA
|  | Correct hardware & operation | Pass/Fail/NA
4710 INSULATION | Acoustic Walls 90mm R1.9 | Pass/Fail/NA
| Acoustic Ceilings 115mm R1.8 | Pass/Fail/NA
| Acoustic Ceiling Bafflestack 100mm R1.5 | Pass/Fail/NA
| Acoustic Floor 40mm R1.0 | Pass/Fail/NA
| Strapping Tape | Pass/Fail/NA
| Foam Sealant voids | Pass/Fail/NA
5210 STEEL STUD PARTITIONS | DPC | Pass/Fail/NA
| Stud 92x36 0.55 BMT @ 600 spacing | Pass/Fail/NA
| Deflection head track 92x50 x 1.15 BMT | Pass/Fail/NA
| Wall floor track 92x32 1.15 BMT | Pass/Fail/NA
| Nogging Track 92x32 0.70 BMT | Pass/Fail/NA
| Fixings & Ctrs | Pass/Fail/NA
| Provide 90x45 timber 3 sides of all door openings | Pass/Fail/NA
| Provide 90x45 timber blocking within walls at TV mounting locations | Pass/Fail/NA
| Sesimic Partition Tie SPT-10T (Timba) | Pass/Fail/NA
5230 INTERIOR TIMBER DOORS | Timber Doors Hinged | Install complete, level & true | Pass/Fail/NA
|  | Hardware & Operation | Pass/Fail/NA
|  | Damage and blemish free | Pass/Fail/NA
| Cavity Slider Doors | Install complete, level & true | Pass/Fail/NA
|  | Hardware & Operation | Pass/Fail/NA
|  | Damage and blemish free | Pass/Fail/NA
5310 SUSPENDED CEILINGS | Ceiling Perimter Trim | Fixed Edge | Pass/Fail/NA
|  | Floating Edge | Pass/Fail/NA
| Main Tee/Cross Tee | Pass/Fail/NA
| Concealed System | Pass/Fail/NA
| (CT1 / CT5) CEILING TILES | Pass/Fail/NA
| (CT2) CEILING TILES – 1200 X 600 (TO GR2) | Pass/Fail/NA
| (CT3 / CT4) CEILING TILES | Pass/Fail/NA
6220 TILING | Water proofing | Pass/Fail/NA
| Surface preparation | Pass/Fail/NA
| Tile product | Pass/Fail/NA
| Penetrations | Pass/Fail/NA
| Grouting | Pass/Fail/NA
SERVICES 1ST FIX | Mechanical | Pass/Fail/NA
| Plumbing | Pass/Fail/NA
| Electrical | Pass/Fail/NA
| Data | Pass/Fail/NA
| Fire Alarms | Pass/Fail/NA
| Fire Protection | Pass/Fail/NA
| Plumbing | Pass/Fail/NA
Request Signoff

## Finishes
Finishes
4610 GLAZING | Frameless Glass | Channels/Wedges | Pass/Fail/NA | same pass/fail/na checklist for each item in column B with comment funciton
|  | Hardware & Operation | Pass/Fail/NA
|  | Cleaned | Pass/Fail/NA
|  | Hardware & Operation | Pass/Fail/NA
|  | Cleaned | Pass/Fail/NA
|  | Cleaned | Pass/Fail/NA
5110 INTERIOR LININGS | Seratone Aqua | Correct product 4.5m Polar White | Pass/Fail/NA
|  | Silocone sealed 3mm wide | Pass/Fail/NA
|  | Alum End Cap Jointers | Pass/Fail/NA
|  | Clean & Blemish Free | Pass/Fail/NA
| Prime MDF FR Black | Correct product 12mm SQ Edge Unclashed | Pass/Fail/NA
|  | Expressed joints 6mm wide | Pass/Fail/NA
|  | Screw & Adhesive fixed | Pass/Fail/NA
|  | Clean & Blemish Free | Pass/Fail/NA
| VidaGroove Slats | 20mm 600 x 3000 SQ Edge Unclashed | Pass/Fail/NA
|  | 9mm Black Felt backing | Pass/Fail/NA
|  | VS7954 Smoked Oak | Pass/Fail/NA
|  | Discrete screw fixed | Pass/Fail/NA
|  | Intumescent coating | Pass/Fail/NA
|  | Clean & Blemish Free | Pass/Fail/NA
5151 INTERNAL TRIM | (PB13S) SOUND CONTROL PLASTERBOARD | Correct product location | Pass/Fail/NA
|  | Correct fixing, adhesive, screw pattern | Pass/Fail/NA
|  | Outlets and penetrations neat | Pass/Fail/NA
|  | Level & True | Pass/Fail/NA
| (PB13) STANDARD PLASTERBOARD | Correct product location | Pass/Fail/NA
|  | Correct fixing, adhesive, screw pattern | Pass/Fail/NA
|  | Outlets and penetrations neat | Pass/Fail/NA
|  | Level & True | Pass/Fail/NA
| (PB13H) SUPERIOR FINISH PLASTERBOARD | Correct product location | Pass/Fail/NA
|  | Correct fixing, adhesive, screw pattern | Pass/Fail/NA
|  | Outlets and penetrations neat | Pass/Fail/NA
|  | Level & True | Pass/Fail/NA
| (PB13W) WATER RESISTANT PLASTERBOARD | Correct product location | Pass/Fail/NA
|  | Correct fixing, adhesive, screw pattern | Pass/Fail/NA
|  | Outlets and penetrations neat | Pass/Fail/NA
|  | Level & True | Pass/Fail/NA
| (SRW1 / SRW2) SOUND RATED SYSTEM, WALL – TYPE 1 / 2 | GSS 133, STC 44, NLB Correct product location | Pass/Fail/NA
|  | Correct fixing, adhesive, screw pattern | Pass/Fail/NA
|  | Outlets and penetrations neat & treated as per GIB Noise | Pass/Fail/NA
|  | Floor to just through ceiling, 2.800m high | Pass/Fail/NA
|  | Side #1 = GIB® Standard® over GIB® Braceline® / GIB® Noiseline® Inner layer: Un-stopped | Pass/Fail/NA
|  | Side #2 = GIB® Standard® | Pass/Fail/NA
|  | Sound rated sealant all round perimeter of lining/s each layer | Pass/Fail/NA
|  | Level & True | Pass/Fail/NA
| (SRW3) SOUND RATED SYSTEM, WALL – TYPE 3 | GSS 132, STC 41, NLB Correct product location | Pass/Fail/NA
|  | Correct fixing, adhesive, screw pattern | Pass/Fail/NA
|  | Outlets and penetrations neat & treated as per GIB Noise | Pass/Fail/NA
|  | 1 x 13 mm each side - Floor to underside of ceiling | Pass/Fail/NA
|  | Sound rated sealant all round perimeter of lining/s each layer | Pass/Fail/NA
|  | Level & True | Pass/Fail/NA
| (SRW4) SOUND RATED SYSTEM, WALL – TYPE 4 | GST 132 (STC 40) / 133 (STC 43) / 134 (STC 46), NLB Correct product location | Pass/Fail/NA
|  | Correct fixing, adhesive, screw pattern | Pass/Fail/NA
|  | Outlets and penetrations neat & treated as per GIB Noise | Pass/Fail/NA
|  | 13 mm - Number of layers each side varies by location - Floor to underside of ceiling | Pass/Fail/NA
|  | Sound rated sealant all round perimeter of lining/s each layer | Pass/Fail/NA
|  | Level & True | Pass/Fail/NA
| (SRW5) SOUND RATED SYSTEM, WALL – TYPE 5 | GSS 134, STC 48, NLB Correct product location | Pass/Fail/NA
|  | Correct fixing, adhesive, screw pattern | Pass/Fail/NA
|  | Outlets and penetrations neat & treated as per GIB Noise | Pass/Fail/NA
|  | 2 x 13 mm each side only Inner layer: Unstopped - Floor to underside of floor above | Pass/Fail/NA
|  | Sound rated sealant all round perimeter of lining/s each layer | Pass/Fail/NA
|  | Level & True | Pass/Fail/NA
| CONTROL JOINTS | PEXPH30 Control Joint W-Profile | Pass/Fail/NA
| LONG LEG STOPPING ANGLES, METAL | EZ Concept EzyReveal | Pass/Fail/NA
| WALL CAPPING | EZ Concept EzyCap All freestanding vertical wall ends | Pass/Fail/NA
| (AHC) CEILING ACCESS HATCH | SRAP SB, Sound rated | Pass/Fail/NA
| SOUND RATED SEALANT | Perimeter of all sound rated wall and ceiling linings | Pass/Fail/NA
|  | Perimeter of all fire rated wall linings | Pass/Fail/NA
| (SK1) TIMBER, SKIRTING | Classic Single Bevelled Edge Size: 90 mm x 12 mm | Pass/Fail/NA
|  | Untreated, to general areas, H3.1, to semi-wet areas | Pass/Fail/NA
|  | Flush without gaps | Pass/Fail/NA
|  | Mitres and Junctions | Pass/Fail/NA
|  | Damage and blemish free | Pass/Fail/NA
| (AR1) TIMBER, ARCHITRAVES | Classic Single Bevelled Edge Size: 60 mm x 12 mm (to be confirmed) Treatment Untreated | Pass/Fail/NA
|  | Untreated, to general areas, H3.1, to semi-wet areas | Pass/Fail/NA
|  | Flush without gaps | Pass/Fail/NA
|  | Mitres and Junctions | Pass/Fail/NA
|  | Damage and blemish free | Pass/Fail/NA
5211 ALUMINIUM PARTITIONS | Review supplier schedule | Pass/Fail/NA
| Install complete, level & true | Pass/Fail/NA
| Hardware & Operation | Pass/Fail/NA
| Sealant & Trim | Pass/Fail/NA
| Sesimic Partition Tie SPT-10 (Standard) | Pass/Fail/NA
| Cleaned | Pass/Fail/NA
5310 SUSPENDED CEILINGS | (CT1 / CT5) CEILING TILES | Pass/Fail/NA
| (CT2) CEILING TILES – 1200 X 600 (TO GR2) | Pass/Fail/NA
| (CT3 / CT4) CEILING TILES | Pass/Fail/NA
5510 JOINERY FIXTURES | J2.01 | Pass/Fail/NA
| J2.02 | Pass/Fail/NA
| J2.03A | Pass/Fail/NA
| J2.03B | Pass/Fail/NA
| J2.03C | Pass/Fail/NA
| J2.04 | Pass/Fail/NA
| J2.05-1 | Pass/Fail/NA
| J2.05-2 | Pass/Fail/NA
| J2.05-3 | Pass/Fail/NA
| J2.06 | Pass/Fail/NA
| J2.07 | Pass/Fail/NA
| J2.08 | Pass/Fail/NA
| J2.09A | Pass/Fail/NA
| J2.09B | Pass/Fail/NA
| J2.10 | Pass/Fail/NA
| J2.11A | Pass/Fail/NA
| J2.11B | Pass/Fail/NA
| J2.12 | Pass/Fail/NA
| J2.13 | Pass/Fail/NA
| J2.14 | Pass/Fail/NA
| J2.15 | Pass/Fail/NA
| J2.16-1 | Pass/Fail/NA
| J216-2 | Pass/Fail/NA
| J2.17 | Pass/Fail/NA
| J4.01 | Pass/Fail/NA
| J4.02 | Pass/Fail/NA
| J41.03 | Pass/Fail/NA
| J4.04 | Pass/Fail/NA
| J4.05 | Pass/Fail/NA
| J4.06 | Pass/Fail/NA
| J4.07 | Pass/Fail/NA
| J4.08A | Pass/Fail/NA
| J4.08B | Pass/Fail/NA
| J4.09 | Pass/Fail/NA
| J4.10-1 | Pass/Fail/NA
| J4.10-2 | Pass/Fail/NA
| J4.11A | Pass/Fail/NA
| J4.11B | Pass/Fail/NA
5520 HARDWARE | Refer supplier scheudle | Pass/Fail/NA
| Electronic Operaton | Pass/Fail/NA
| Manual Operaton | Pass/Fail/NA
| Door stops | Pass/Fail/NA
| Damage & Blemish Free | Pass/Fail/NA
| Signs | Pass/Fail/NA
6410 RESILIENT SURFACING | Mositure test | Pass/Fail/NA
| Floor prep | Pass/Fail/NA
| Floor levelling | Pass/Fail/NA
| Floor waste gulleys | Pass/Fail/NA
| 100mm joinery toe kicks | Pass/Fail/NA
| 150mm coving walls | Pass/Fail/NA
| Product, Grading , Colour correct | Pass/Fail/NA
| Flooring protection | Pass/Fail/NA
6510 CARPETING | Mositure test | Pass/Fail/NA
| Floor prep | Pass/Fail/NA
| Floor levelling | Pass/Fail/NA
| Reducign / Finishign Trim | Pass/Fail/NA
| Carpet Planks Type 1 | Pass/Fail/NA
| Carpet Planks Type 2 | Pass/Fail/NA
| Carpet Planks Type 3 | Pass/Fail/NA
| Spares | Pass/Fail/NA
6700 PAINTING | Interior Doors | Pass/Fail/NA
| Interior Trims | Pass/Fail/NA
| Plasterboard Walls | Pass/Fail/NA
| Plasterboard Ceilings | Pass/Fail/NA
| Timber Veneer Wall Panel, Clear | Pass/Fail/NA
| Acoustic Panel AUTEX Cube Colour AP1 Muralla | Pass/Fail/NA
| Acoustic Panel AUTEX Cube Colour AP2 Beehive | Pass/Fail/NA
| Acoustic Panel AUTEX Cube Colour AP3 Gherkin | Pass/Fail/NA
7150 SANITARYWARE AND ACCESSORIES | (SK1) KITCHEN SINK, STAINLESS STEEL Level 2, West: - Breakout 2.1 (J2.03) Level 2, East: - Utility 2.2 (J2.11) | Pass/Fail/NA
| (SK1) KITCHEN SINK, STAINLESS STEEL Level 2, East: - Utility 2.2 (J2.11) | Pass/Fail/NA
| (SK2) KITCHEN SINK, STAINLESS STEEL Level 2, East: - Wellness/Retreat 2.1 (J2.09) | Pass/Fail/NA
| (SK2) KITCHEN SINK, STAINLESS STEEL Level 4: - Drinks Station (J4.12) | Pass/Fail/NA
| (AWC) TOILET SUITE, CLOSE COUPLED Level 2, West: - WC/Shr 2.1, Acc. WC/Shr 2.2 | Pass/Fail/NA
| (AWB) WASH BASIN Level 2, West: - WC/Shr 2.1, Acc. WC/Shr 2.2 | Pass/Fail/NA
| (BW) BASIN WASTE Pop Up Level 2, West: - WC/Shr 2.1, Acc. WC/Shr 2.2 | Pass/Fail/NA
| (BT) BOTTLE TRAP, EXPOSED Level 2, West: - WC/Shr 2.1, Acc. WC/Shr 2.2 | Pass/Fail/NA
| (RHK) ROBE HOOKS Level 2, West: - WC/Shr 2.1, Acc. WC/Shr 2.2 - 4-off | Pass/Fail/NA
| (ATRH) TOILET ROLL HOLDER Level 2, West: - WC/Shr 2.1, Acc. WC/Shr 2.2 - 1-off | Pass/Fail/NA
| (SHSH) SHOWER SHELF Level 2, West: - WC/Shr 2.1, Acc. WC/Shr 2.2 - 4-off (2-off per cubicle) | Pass/Fail/NA
| (MR1) MIRROR Vertical pill perimeter LED backlit mirror with demister pad Level 2, West: - WC/Shr 2.1, Acc. WC/Shr 2.2 450 mm wide x 900 mm high x 30 mm deep - 2-of | Pass/Fail/NA
| Stickers removed | Pass/Fail/NA
| Hygiene Sealant | Pass/Fail/NA
| Sanitary accessories – supply and install by tenant (NTSD) SOAP DISPENSER (AFF) AIR FRESH FAN (FH) FEMALE HYGIENE, FREESTANDING | Pass/Fail/NA
7151 TAPWARE | (SMX) SINK MIXER Level 2, West - Breakout 2.1 (J2.03) | Pass/Fail/NA
| (ABMX) BASIN MIXER Level 2, West - WC/Shr 2.1, Acc. WC/Shr 2.2 | Pass/Fail/NA
| (ASHMX) SHOWER MIXER Level 2, West - WC/Shr 2.1, Acc. WC/Shr 2.2 | Pass/Fail/NA
| (ASHSL) SLIDE SHOWER SET evel 2, West - WC/Shr 2.1, Acc. WC/Shr 2.2 | Pass/Fail/NA
| BOILING AND CHILLED SYSTEM Level 2, West:- Breakout 2.1 | Pass/Fail/NA
| BOILING AND CHILLED SYSTEM PLUS MIXER Level 2, East: - Wellness/Retreat 2.1, Utility 2.2 | Pass/Fail/NA
| BOILING AND CHILLED SYSTEM PLUS MIXER Level 4: - Drinks Station 4.1 | Pass/Fail/NA
| Stickers removed | Pass/Fail/NA
7760 APPLIANCES | Appliances supplied by client, insall by contractor | Pass/Fail/NA
| (CM) COFFEE MACHINE, ON BENCH Level 2, West - Breakout 2.1 (J2.03) | Pass/Fail/NA
| (MW) MICROWAVE Level 2, West - Breakout 2.1 (J2.03) | Pass/Fail/NA
| (OV) OVEN Level 2, West - Breakout 2.1 (J2.03) | Pass/Fail/NA
| (FR1) REFRIDGERATOR, GLASS FRONT Level 2, West - Breakout 2.1 (J2.03) | Pass/Fail/NA
| (FR2) BAR FRIDGE, GLASS FRONT Level 2, East - Wellness/Retreat 2.1 (J2.09) | Pass/Fail/NA
| (FR3) REFRIDGERATOR Level 2, East - Utility 2.2 (J2.11) | Pass/Fail/NA
| (DD1) DISH DRAWER, SINGLE Level 2, East: - Utility 2.2 (J2.11) | Pass/Fail/NA
| (DD1) DISH DRAWER, SINGLE Level 4: - Drinks Station 4.1 (J4.11A) | Pass/Fail/NA
| (DD2) DISH DRAWER, DOUBLE Level 2, West - Breakout 2.1 (J2.03) | Pass/Fail/NA
SERVICES 2ND FIX | Mechanical | Pass/Fail/NA
| Plumbing | Pass/Fail/NA
| Electrical | Pass/Fail/NA
| Data | Pass/Fail/NA
| Fire Alarms | Pass/Fail/NA
| Fire Protection | Pass/Fail/NA
| Plumbing | Pass/Fail/NA
Request Signoff

## Defect Clearance
Defect Clearance
LEVEL 2 EAST | 2.1 NORTH LANDING | Pass/Fail/NA | same pass/fail/na checklist for each item in column B with comment funciton
| 2.1 WELLNESS/RETREAT | Pass/Fail/NA
| 2.2 UTILITY | Pass/Fail/NA
| 2.3 UTILITY | Pass/Fail/NA
| 2.4 MEETING | Pass/Fail/NA
| 2.5 MEETING | Pass/Fail/NA
| 2.5 OPEN WORK AREA | Pass/Fail/NA
| 2.6 OPEN WORK AREA | Pass/Fail/NA
| 2.7 OPEN WORK AREA | Pass/Fail/NA
| 2.8 OPEN WORK AREA | Pass/Fail/NA
| 2.9 OPEN WORK AREA | Pass/Fail/NA
| 2.5 COLLAB | Pass/Fail/NA
| 2.10 OPEN WORK AREA | Pass/Fail/NA
| 2.6 FOCUS | Pass/Fail/NA
| 2.5 FOCUS | Pass/Fail/NA
| 2.6 MEETING | Pass/Fail/NA
| SOUTH LANDING | Pass/Fail/NA
LEVEL 4 WEST | NORTH LANDING | Pass/Fail/NA
| ENTRANCE | Pass/Fail/NA
| 4.2 COLLAB | Pass/Fail/NA
| 4.1 COLLAB | Pass/Fail/NA
| 4.3 COLLAB | Pass/Fail/NA
| 4.4 COLLAB | Pass/Fail/NA
| 4.3 MEETING | Pass/Fail/NA
| 4.1 OPEN WORK AREA | Pass/Fail/NA
| 4.2 OPEN WORK AREA | Pass/Fail/NA
| 4.3 OPEN WORK AREA | Pass/Fail/NA
| 4.4 OPEN WORK AREA CENTRE | Pass/Fail/NA
| 4.1 MEETING | Pass/Fail/NA
| 4.2 MEETING | Pass/Fail/NA
| 4.1 STORAGE | Pass/Fail/NA
| 4.1 DRINKS | Pass/Fail/NA
| 4.1 UTILITY | Pass/Fail/NA
| 4.1 FOCUS | Pass/Fail/NA
| 4.2 FOCUS | Pass/Fail/NA
| 4.2 STORAGE | Pass/Fail/NA
| SOUTH LANDING | Pass/Fail/NA
LEVEL 2 WEST | NORTH LANDING | Pass/Fail/NA
| 2.1 COLLAB | Pass/Fail/NA
| 2.2 COLLAB | Pass/Fail/NA
| 2.3 COLLAB | Pass/Fail/NA
| 2.4 COLLAB | Pass/Fail/NA
| 2.1 OPEN WORK AREA | Pass/Fail/NA
| 2.2 OPEN WORK AREA | Pass/Fail/NA
| 2.3 OPEN WORK AREA | Pass/Fail/NA
| 2.4 OPEN WORK AREA | Pass/Fail/NA
| 2.1 PROJECT | Pass/Fail/NA
| 2.1 UTILITY | Pass/Fail/NA
| 2.1 BREAKOUT | Pass/Fail/NA
| 2.1 MEETING | Pass/Fail/NA
| 2.1 STORE | Pass/Fail/NA
| 2.2 MEETING | Pass/Fail/NA
| 2.3 MEETING | Pass/Fail/NA
| 2.1 SHR | Pass/Fail/NA
| 2.2 ACC WC/SHR | Pass/Fail/NA
| SOUTH LANDING | Pass/Fail/NA
Request Signoff