## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Site Establishment | [5 empty] | Site Establishment
section | ACCESS
checkpoint | Site fencing
checkpoint | Secure Site entry
checkpoint | Sign in facilities
checkpoint | Scaffold access
checkpoint | Scaffold safe tag
checkpoint | Carpark exclusion zones
section | SIGNAGE
checkpoint | Hazard board
checkpoint | Site contact
checkpoint | Emergency evacuation plan
checkpoint | Wayfinding signage
checkpoint | Site Office
checkpoint | Lunchroom
checkpoint | Noticeboard
section | FACILITIES
checkpoint | Site Office
checkpoint | Lunchroom
checkpoint | Toilet
checkpoint | Waste management seperation
checkpoint | Water connection
checkpoint | Waste connection
checkpoint | Power connection
checkpoint | Data connection
checkpoint | Printer/Scanner
checkpoint | Fire Extinguisher
checkpoint | First Aid Kit
checkpoint | Plan Table
section | DOCUMENTATION
checkpoint | Approved Site Specific Safety Plan
checkpoint | Approved Construction Management Plan
checkpoint | Approved Quality Assurance Management Plan
checkpoint | Approved Building Consent Documents
checkpoint | Contact List
checkpoint | Procore documentation established
checkpoint | Procore invitations issued
checkpoint | CONQA checklists established
section | DILAPIDATION SURVEY
checkpoint | ROADINGS/ACCESS
checkpoint | FENCING
checkpoint | PAVING
checkpoint | EXTERIOR SEATING
checkpoint | NORTH ELEVATION
checkpoint | EAST ELEVATION
checkpoint | SOUTH ELEVATION
checkpoint | WEST ELEVATION
checkpoint | GRANDSTAND AREA
checkpoint | EXISTING ATHLETICS STORAGE
checkpoint | CHANGE ROOM 1
checkpoint | CHANGE ROOM 2 FEMALE/WC
checkpoint | CHANGE ROOM 3 MALE
checkpoint | STORAGE 1
checkpoint | STORAGE 2
checkpoint | STORAGE 3
checkpoint | SHOWERS/WC
checkpoint | ACC BATHROOM
checkpoint | CORRIDOR
checkpoint | KITCHEN
checkpoint | CLUBROOM
checkpoint | BAR/KITCHEN
checkpoint | MULTIUSE ROOM
checkpoint | ELECTRICAL STORAGE ROOM
section | COMMUNICATE
checkpoint | Salavage Football signage
checkpoint | Hoardings around stored items
checkpoint | Track lighting controls in kitchen
checkpoint | PA System Speaker cabling
checkpoint | Pedestrian walkway
checkpoint | TMP plan/signage
checkpoint | Demolition scope/marked
checkpoint | Items to protect marked
holdpoint | ALL WORKS COMPLETED, REVIEWED AND APPROVED
checklist | Structural | [5 empty] | Structural
section | EXCAVATION & FOUNDATIONS
checkpoint-no-status | GRIDS 1-4
checkpoint | Correct setout
checkpoint | Correct depth/Dim
checkpoint | DPM
checkpoint | Reinforcing Steel Cages
checkpoint | Reinforcing Steel Horizontal Starters
checkpoint | Reinforcing Steel Vertical Starters
checkpoint | Additional detail scabble/inserts/reid bar etc
checkpoint | Engineer Approval
checkpoint | Concrete strength MPA
checkpoint | Concrete finish
checkpoint-no-status | GRIDS 3-4
checkpoint | Correct setout
checkpoint | Correct depth/Dim
checkpoint | DPM
checkpoint | Reinforcing Steel Cages
checkpoint | Reinforcing Steel Horizontal Starters
checkpoint | Reinforcing Steel Vertical Starters
checkpoint | Additional detail scabble/inserts/reid bar etc
checkpoint | Engineer Approval
checkpoint | Concrete strength MPA
checkpoint | Concrete finish
checkpoint-no-status | GRIDS 5-6
checkpoint | Correct setout
checkpoint | Correct depth/Dim
checkpoint | DPM
checkpoint | Reinforcing Steel Cages
checkpoint | Reinforcing Steel Horizontal Starters
checkpoint | Reinforcing Steel Vertical Starters
checkpoint | Additional detail scabble/inserts/reid bar etc
checkpoint | Engineer Approval
checkpoint | Concrete strength MPA
checkpoint | Concrete finish
checkpoint-no-status | GRIDS 8-10
checkpoint | Correct setout
checkpoint | Correct depth/Dim
checkpoint | DPM
checkpoint | Reinforcing Steel Cages
checkpoint | Reinforcing Steel Horizontal Starters
checkpoint | Reinforcing Steel Vertical Starters
checkpoint | Additional detail scabble/inserts/reid bar etc
checkpoint | Engineer Approval
checkpoint | Concrete strength MPA
checkpoint | Concrete finish
section | EXTERIOR FOUNDS
checkpoint-no-status | WEST STAIR
checkpoint | Correct setout
checkpoint | Excavation depth/dim
checkpoint | DPM
checkpoint | Reinforcing Steel
checkpoint | Engineer Approval
checkpoint | Concrete strength MPA
checkpoint | Concrete finish
checkpoint-no-status | SHS PADS
checkpoint | Correct setout
checkpoint | Excavation depth/dim
checkpoint | DPM
checkpoint | Reinforcing Steel
checkpoint | Engineer Approval
checkpoint | Concrete strength MPA
checkpoint | Concrete finish
section | BLOCKWORK WALLS
checkpoint-no-status | GRIDS 1-4
checkpoint | Blockwork surface/edges
checkpoint | HD12 400EW central
checkpoint | Additional detail - cast in bolts
checkpoint | Engineer approval
checkpoint | Concrete strength MPA
checkpoint | Concrete finish
checkpoint-no-status | GRIDS 3-4
checkpoint | Blockwork surface/edges
checkpoint | HD12 400EW central
checkpoint | Additional detail - cast in bolts
checkpoint | Engineer approval
checkpoint | Concrete strength MPA
checkpoint | Concrete finish
checkpoint-no-status | GRIDS 5-6
checkpoint | Blockwork surface/edges
checkpoint | HD12 400EW central
checkpoint | Additional detail - cast in bolts
checkpoint | Engineer approval
checkpoint | Concrete strength MPA
checkpoint | Concrete finish
checkpoint-no-status | GRIDS 8-10
checkpoint | Blockwork surface/edges
checkpoint | HD12 400EW central
checkpoint | Additional detail - cast in bolts
checkpoint | Engineer approval
checkpoint | Concrete strength MPA
checkpoint | Concrete finish
section | EXISTING STEELWORK COATINGS
checkpoint-no-status | Grandstand Area
checkpoint | GRIDS 1-3 EAST
checkpoint | GRIDS 3-5
checkpoint | GRIDS 5-7
checkpoint | GRIDS 7-9
checkpoint | GRIDS 9-11
checkpoint | GRIDS 11-13 WEST
section | NEW STEEL WORK
checkpoint | Wall Bracing Bays 300PFC on flat
checkpoint | Block Walls 180PFC Detail 6 / S4.1
checkpoint | Block Walls existing RSJ Details 8-9 / 4.1
checkpoint | 180UB Seating Detail 11 A-D / S4.2
checkpoint | 65 SHS Post Base Detail 10 / S4.2
checkpoint | 65 SHS Post Apex Detail 17 / S4.2
checkpoint | 150 PFC West Stair Details 3-4 / S2.2
checkpoint | New Stair 02
checkpoint | New Stair 04
checkpoint-no-status | Below Seating
checkpoint | GRIDS 1-3 EAST
checkpoint | GRIDS 3-5
checkpoint | GRIDS 5-7
checkpoint | GRIDS 7-9
checkpoint | GRIDS 9-11
checkpoint | GRIDS 11-13 WEST
checkpoint-no-status | Roof Bracing Bays & Connection detailing
checkpoint | BAY 1 GRIDS 1-2 EAST
checkpoint | BAY 2 GRIDS 5-6
checkpoint | BAY 3 GRIDS 9-10
checkpoint | BAY 4 GRIDS 12-13
checkpoint-no-status | Wall Bracing Bays & Connection detailing
checkpoint | BAY 1 GRIDS 1-2 EAST
checkpoint | BAY 2 GRIDS 5-6
checkpoint | BAY 3 GRIDS 9-10
checkpoint | BAY 4 GRIDS 12-13
section | CONCRETE REPAIRS
checkpoint | Item 1
checkpoint | Item 2
checkpoint | Item 3
checkpoint | Item 4
checkpoint | Item 5
checkpoint | Item 6
checkpoint | Item 7
checkpoint | Item 8
checkpoint | Item 9
checkpoint | Item 10
checkpoint | Item 11
checkpoint | Item 12
checkpoint | Item 13
checkpoint | Item 14
checkpoint | Item 15
checkpoint | Item 16
checkpoint | Item 17
checkpoint | Item 18
checkpoint | Item 19
checkpoint | Item 20
holdpoint | ALL WORKS COMPLETED, REVIEWED AND APPROVED
checklist | Carpentry & Preline | [5 empty] | Carpentry & Preline
section | 2111 DEMOLITION
checkpoint | Demolition scope identifed
checkpoint | Elements for salvage & delivery to client
checkpoint | Elements for salavage & reuse
checkpoint | Electrical Disconnections
checkpoint | Plumbing Disconnections
checkpoint | Demolition scope disposed & tidy
checkpoint | Demolition scope complete
checkpoint | Asbestos ARCP approved plan
checkpoint | Asbestos clearance
section | 4161 UNDERLAYS, FOILF, DPC, DPM & TAPES
checkpoint | DPC Bottom plates
checkpoint | DPC Other instances
checkpoint | Correct wall underlay
checkpoint | Correct roof underlay
checkpoint | Flashing tape to openings
checkpoint | Flashing tape sill second layer
checkpoint | Flashing tape head/sill corners
checkpoint | Overlap and Joining Tapes
checkpoint | Penetration seals
section | 3821 TIMBER FRAMING
checkpoint-no-status | East Wall Grid 1
checkpoint | Correct size, grade & treatement
checkpoint | Correct framing centres
checkpoint | Correct openings, lintels & trimmers
checkpoint | Correct blocking & edges for sheet linings
checkpoint | Substrate plumb, level & true
checkpoint-no-status | West Wall Grid 13
checkpoint | Correct size, grade & treatement
checkpoint | Correct framing centres
checkpoint | Correct openings, lintels & trimmers
checkpoint | Correct blocking & edges for sheet linings
checkpoint | Substrate plumb, level & true
checkpoint-no-status | Mezzanine Storage & Stair
checkpoint | Correct size, grade & treatement
checkpoint | Correct framing centres
checkpoint | Correct openings, lintels & trimmers
checkpoint | Correct blocking & edges for sheet linings
checkpoint | Substrate plumb, level & true
checkpoint-no-status | Shower A
checkpoint | Correct size, grade & treatement
checkpoint | Correct framing centres
checkpoint | Correct openings, lintels & trimmers
checkpoint | Correct blocking & edges for sheet linings
checkpoint | Substrate plumb, level & true
section | 4711 THERMAL INSULATION
checkpoint-no-status | East Wall Grid 1
checkpoint | 90mm R2.6
checkpoint-no-status | West Wall Grid 13
checkpoint | 90mm R2.6
section | WALL LININGS
checkpoint-no-status | East Wall Grid 1
checkpoint | [TM-01] GBUW 60 2 layers 13mm Fyreline
checkpoint | Inner layer 32mm x 6g GIB® Grabber® High Thread Drywall Screws Inner layer: 600mm centres up each stud. Place fasteners 12mm from longitudinal sheet edges and 18mm from sheet ends. Place fasteners at 200mm centres along sheet end butt joints.
checkpoint | Outer layer 51mm x 6g GIB® Grabber® High Thread Drywall Screws Outer layer: 300mm centres up each stud. Place fasteners 12mm from longitudinal sheet edges and 18mm from sheet ends. Place fasteners at 200mm centres along sheet end butt joints.
checkpoint-no-status | West Wall Grid 13
checkpoint | [TM-01] GBUW 60 2 layers 13mm Fyreline
checkpoint | Inner layer 32mm x 6g GIB® Grabber® High Thread Drywall Screws Inner layer: 600mm centres up each stud. Place fasteners 12mm from longitudinal sheet edges and 18mm from sheet ends. Place fasteners at 200mm centres along sheet end butt joints.
checkpoint | Outer layer 51mm x 6g GIB® Grabber® High Thread Drywall Screws Outer layer: 300mm centres up each stud Place fasteners 12mm from longitudinal sheet edges and 18mm from sheet ends. Place fasteners at 200mm centres along sheet end butt joints.
checkpoint-no-status | Mezzanine Storage & Stair
checkpoint | [TM-02] GBUW 30a 1 Layer 16mm Fyreline both sides
checkpoint | Fastners 41mm x 6g GIB® Grabber® High Thread Drywall Screws
checkpoint | Inner layer: 600mm centres up each stud. Place fasteners 12mm from longitudinal sheet edges and 18mm from sheet ends. Place fasteners at 200mm centres along sheet end butt joints
checkpoint | [TM-02] Second layer 12mm Strandboard both sides
checkpoint-no-status | Shower A Male
checkpoint | [TM-03] 4.5mm Seratone Aqua direct fixed
checkpoint-no-status | Shower B Female
checkpoint | Duraplan Shower Partitions
section | CEILING LININGS
checkpoint-no-status | Grids 3-6 Change Areas Male/Female
checkpoint | GBFC 60 1 layer 16mm GIB Fyreline®
checkpoint | Fasteners 51mm x 7g GIB® Grabber® High Thread Drywall Screws.
checkpoint | Fastener centres 150mm centres around the perimeter of each sheet. Place fasteners at 200mm centres along each joist and at the centre of each nog. Place fasteners 12mm from longitudinal sheet edges and 18mm from sheet ends.
checkpoint-no-status | Kitchen
checkpoint | GBFC 60 1 layer 16mm GIB Fyreline®
checkpoint | Fasteners 51mm x 7g GIB® Grabber® High Thread Drywall Screws.
checkpoint | Fastener centres 150mm centres around the perimeter of each sheet. Place fasteners at 200mm centres along each joist and at the centre of each nog. Place fasteners 12mm from longitudinal sheet edges and 18mm from sheet ends.
checkpoint-no-status | Making good areas opened for the works
checkpoint | GBFC 60 1 layer 16mm GIB Fyreline®
checkpoint-no-status | Mezzanine Storage & Stair
checkpoint | GBFC 30 1 Layer 13mm Fyreline
checkpoint | Fastners 51mm x 7g GIB® Grabber® High Thread Drywall Screws.
checkpoint | Centres Place fasteners at 150mm centres around the perimeter of each sheet and at 200mm centres along each joist and at the centre of each nog. Place fasteners 12mm from longitudinal sheet edges and 18mm from sheet ends.
section | 4231 JAMES HARDIE HARDIE FLEX SHEET CLADDING (1)
checkpoint-no-status | Soffits/Spandrel
checkpoint | 6mm JH Hardie Flex Sheet
checkpoint | Correct fastner 40x2.8mm galv nail (Zone c)
checkpoint | Vertical jointer sealant
checkpoint | Horizontal jointer metal flashing
checkpoint | Internal corner joint fixing & underflashing
checkpoint | External corner joint fixing & underflashing
checkpoint | Seal edges
checkpoint | Penetrations and flashings prepared
checkpoint | Specific FRR system construction details
checkpoint | Specific Bracing system construction details
section | 4231 JAMES HARDIE HARDIE FLEX SHEET CLADDING (2)
checkpoint-no-status | Grandstand Seating area East Grid 1
checkpoint | 6mm JH Hardie Flex Sheet
checkpoint | Correct fastner 40x2.8mm galv nail (Zone c)
checkpoint | Vertical jointer sealant
checkpoint | Horizontal jointer metal flashing
checkpoint | Internal corner joint fixing & underflashing
checkpoint | External corner joint fixing & underflashing
checkpoint | Seal edges
checkpoint | Penetrations and flashings prepared
checkpoint | Specific FRR system construction details
checkpoint | Specific Bracing system construction details
section | 4231 JAMES HARDIE HARDIE FLEX SHEET CLADDING (3)
checkpoint-no-status | Grandstand Seating area West Grid 13
checkpoint | 6mm JH Hardie Flex Sheet
checkpoint | Correct fastner 40x2.8mm galv nail (Zone c)
checkpoint | Vertical jointer sealant
checkpoint | Horizontal jointer metal flashing
checkpoint | Internal corner joint fixing & underflashing
checkpoint | External corner joint fixing & underflashing
checkpoint | Seal edges
checkpoint | Penetrations and flashings prepared
checkpoint | Specific FRR system construction details
checkpoint | Specific Bracing system construction details
section | 4231 JAMES HARDIE HARDIE FLEX SHEET CLADDING (4)
checkpoint-no-status | Grandstand Seating area Grid X
checkpoint | 6mm JH Hardie Flex Sheet
checkpoint | Correct fastner 40x2.8mm galv nail (Zone c)
checkpoint | Vertical jointer sealant
checkpoint | Horizontal jointer metal flashing
checkpoint | Internal corner joint fixing & underflashing
checkpoint | External corner joint fixing & underflashing
checkpoint | Seal edges
checkpoint | Penetrations and flashings prepared
checkpoint | Specific FRR system construction details
checkpoint | Specific Bracing system construction details
section | 4241 DIMOND PROFILED CLADDING
checkpoint | Correct profile - Hi-Five
checkpoint | Correct base material & coating system - ZAM on steel, Colorcote Magnaflow
checkpoint | Correct colour - refer Finishes schedule
checkpoint | Movement joints transverse flashings max 12.0m
checkpoint | Confirm Hi Five Roof & Gutter Detail 1 / A-5000
checkpoint | Confirm Hi Five Wall Cladding to Wind Lobby Detail 2 / A-5000
checkpoint | Confirm Hi Five Roof & Barge Detail 3 / A-5000
checkpoint | Confirm Hi Five Cladding to Column/Blockwall Detail 1 / A-5001
checkpoint | Confirm Hi Five Cladding to Steel Work Detail 2 / A-5001
checkpoint | Confirm Hi Five Cladding to Foundation Detail 3 / A-5001
checkpoint | Confirm Wall Penetration Detail 4 / A-5001
checkpoint | Penetrations and flashings prepared
section | 4311 DIMOND PROFILED METAL ROOFING
checkpoint | Confirm Gutter Detail 1 / A-5000
checkpoint | Confirm Apron to Canopy Detail 2 / A-5000
checkpoint | Confirm Roof Barge Detail 3 / A-5000
checkpoint | Roofing Surfaces, plastic protection, pen marks, clean
checkpoint | Pencil Marks
checkpoint | Clean/swarf removed
checkpoint | East Elevation
checkpoint | West Elevation
checkpoint | South Elevation
section | 7411 DIMOND RAINWATER SPOUTING SYSTEMS
checkpoint | Confirm Gutter Detail 1 / A-5000
checkpoint | Bracket centres
checkpoint | Snow strap centres
checkpoint | Clean/swarf removed
section | 4521 ALUM WINDOWS & DOORS
checkpoint | Confirm Door Head Detail 4 / A-5002
checkpoint | Confirm Door Jamb Detail 5 / A-5002
checkpoint | Confirm Door Sill Detail 6 / A-5002
checkpoint | Confirm Window Head Detail 4 / A-5003
checkpoint | Confirm Window Jamb Detail 5 / A-5003
checkpoint | Confirm Window Sill Detail 6 / A-5003
checkpoint | W01
checkpoint | W02
checkpoint | W03
checkpoint | W04
checkpoint | W05
checkpoint | W06
checkpoint | W07
checkpoint | W08
checkpoint | Wind Lobby/Canopy
section | 4553 EXTERIOR DOORS
checkpoint | D01 Electrical
checkpoint | D02 Clubroom
checkpoint | D03 Multiuse
checkpoint | D04 Multiuse / Stair 5
checkpoint | D05 Storage 2
checkpoint | D06 Storage Mezz
checkpoint | D07 Corridor East
checkpoint | D08 Confirm Roller Door Head Detail 1 / A-5002
checkpoint | D08 Confirm Roller Door Jamb Detail 2 / A-5002
checkpoint | D08 Confirm Roller Door Sill Detail 3 / A-5002
checkpoint | D08 Confirm operation
section | 4611 EXTERIOR GLAZING
checkpoint | Confirm Polycarbonate Head Detail 1 / A-5003
checkpoint | Confirm Polycarbonate Jamb Detail 2 / A-5003
checkpoint | Confirm Polycarbonate Sill Detail 3 / A-5003
checkpoint | East Elevation
checkpoint | West Elevation
section | FLOOR COVERINGS
checkpoint | Kitchen Servey Area
checkpoint | Kitchen Servey Area / Clubroom Side
checkpoint | Male Shower Area
checkpoint | Female Shower Area
checkpoint | Female Shower Screed
checkpoint | Female Shower Slot Drain
checkpoint | Female Shower Waterproofing system
section | 6700 PAINTING GENERAL
checkpoint | Stopping
checkpoint | Trim
checkpoint | Doors
checkpoint | Walls
checkpoint | Ceilings
checkpoint | Blockwalls
section | 6711 PAINTING EXTERIOR
checkpoint | Fibre Cement Soffit / Spandrel
checkpoint | Fibre Cement Walls
checkpoint | Grandstand Seating Reinstatement
section | PLUMBING
checkpoint | Female WC
checkpoint | Female Showers
checkpoint | Reconnections
checkpoint | Shower Strip Drain
checkpoint | Threshold Drain & Sump
checkpoint | Other
checkpoint | Asbuilt Drainage Plan
section | ELECTRICAL
checkpoint | EM Lights
checkpoint | Iullumintaed Exit Signage
checkpoint | SWB complete
checkpoint | Outlets reinstated
checkpoint | Exterior Lighting reinstated
checkpoint | Interior Lighting reinstated
checkpoint | Appliances reinstated
checkpoint | Other
checkpoint | Electrical COC
section | FIRE ALARMS
checkpoint | Interior
checkpoint | Exterior
checkpoint | FA Panel
checkpoint | Inspection & Certification
section | MISC COMPLIANCE ITEMS
checkpoint | Yellow safety stair slip resistance strips Mezz stair
checkpoint | Domed buttons 150mm from end and top of hadrails bothsides
checkpoint | Accessibilty Signage
section | REINSTATE & CLEAN
checkpoint | Refer dlipatation survey, shelves, hooks etc
checkpoint | Remove protection
checkpoint | Builders Clean
holdpoint | ALL WORKS COMPLETED, REVIEWED AND APPROVED
checklist | Building Control Inspections | [5 empty] | Building Control Inspections
section | Building Control
checkpoint | Blockwork
checkpoint | Pre-Cladding - Wrap/Cavity/Batten
checkpoint | Preline COMBINED
checkpoint | Postline interior linings
checkpoint | Postline Fire rating
checkpoint | Wet area membrane
checkpoint | Final - Commercial
checkpoint | CPU
checkpoint | Amendment(s)
holdpoint | ALL WORKS COMPLETED, REVIEWED AND APPROVED
checklist | Defect Clearance | [5 empty] | Defect Clearance
section | EXTERIOR
checkpoint | NORTH ELEVATION
checkpoint | EAST ELEVATION
checkpoint | SOUTH ELEVATION
checkpoint | WEST ELEVATION
checkpoint | GRANDSTAND AREA
section | INTERIOR
checkpoint | ATHLETICS STORAGE
checkpoint | CHANGE ROOMS
checkpoint | SHOWERS/KITCHEN
checkpoint | CLUBROOM
checkpoint | MULTIUSE ROOM
holdpoint | ALL WORKS COMPLETED, REVIEWED AND APPROVED