## Type A
type A | name Type A - 904mm | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
tickbox | Foot Anchor - 5T | 4
tickbox | Ferrules - M-20 96mm | 18
tickbox | Ferrules - M-24 96mm | 12
tickbox | ID Plate
tickbox | 40 Pan 2 | 1
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
tickbox | All Concrete Dockets Attached
section | Delivery
checkpoint | Truck Rego and Insurance
tickbox | Truck Rego & Insurance Reviewed
checkpoint | Load Sheet
tickbox | Load Sheets Reviewed
checkpoint | Install Sheet
tickbox | Install Sheets Reviewed
checklist | Checkers Checklist
checkpoint | Overall Measurements - 904mm height
checkpoint | Lifters Correct - Position, Size, Orientation
tickbox | 5T Foot Anchors | 4
checkpoint | Ferrules - Measurement, Quantity & Location
tickbox | M-20 x 96mm | 18
tickbox | M-24 x 96mm | 12
checkpoint | Ferrules - 300mm N12 in Ferrule
checkpoint | Check Concrete cover around Reo 40mm
checkpoint | Check 40mm cover off Void Former
checkpoint | Panel Thickness as per Plans
checkpoint | Check mould is Clean - No stray wire before mould closure
checkpoint | Check bolts are secure
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Panel Thickness - As per drawing
textbox | Foot Anchor - 5T | 4
tickbox | Ferrules - M-20 96mm | 18
tickbox | Ferrules - M-24 96mm | 12
textbox | ID Plate | 1
checkpoint | Use Culvert Mould
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Check Concrete cover around reo 40mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - off Form
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix 40 Pan 2 |  | upload docket?
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | signoff?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER

## Type B
type A | name Type A - 904mm | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
tickbox | Foot Anchor - 5T | 4
tickbox | Ferrules - M-20 96mm | 7
tickbox | ID Plate | 1
tickbox | 40 Pan 2
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
tickbox | All Concrete Dockets Attached
section | Delivery
checkpoint | Truck Rego and Insurance
tickbox | Truck Rego & Insurance Reviewed
checkpoint | Load Sheet
tickbox | Load Sheets Reviewed
checkpoint | Install Sheet
tickbox | Install Sheets Reviewed
checklist | Checkers Checklist
checkpoint | Overall Measurements - 904mm height
checkpoint | Lifters Correct - Position, Size, Orientation
tickbox | 5T Foot Anchors | 4
checkpoint | Ferrules - Measurement, Quanity and Location
tickbox | M-20 x 96mm | 7
checkpoint | Check Concrete cover around Reo 40mm
checkpoint | Ferrules - 300mm N12 in Ferrule
checkpoint | Check 40mm cover off Void Former
checkpoint | Panel Thickness as per Plans
checkpoint | Check mould is Clean - No stray wire before mould closure
checkpoint | Check bolts are secure
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Panel Thickness - As per drawing
textbox | Foot Anchor - 5T | 4
tickbox | Ferrules - M-20 96mm | 7
textbox | ID Plate | 1
checkpoint | Use Culvert Mould
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Check Concrete cover around reo 40mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - off Form
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix 40 Pan 2 |  | upload docket?
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | signoff?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER