## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
05986190-61b2-45a9-b985-98858ba9d165 | checklist | Checkers Checklist (Type A) |  | Checkers Checklist
47578f42-9b18-4181-951e-7a738d83e468 | section | Details
6adf76c0-8227-45f4-a053-6a8c33b8129d | checkpoint | Overall Measurements - 904mm height
fdd1f2ff-37eb-49ac-99e4-c83f4f3e8a5e | checkpoint | Lifters Correct - Position, Size, Orientation
c4c17f06-44c9-542f-9330-cf615330c824 | tickbox | 4 x 5T Foot Anchors
7c642c1a-71b4-4320-8630-852bad6e38dc | checkpoint | Ferrules - Measurement, Quantity & Location
40ac9ba4-3a86-58f8-8d5f-8452372106d9 | tickbox | 18 x M-20 x 96mm
87a096ff-cb4c-5c65-9797-adab4a635a83 | tickbox | 12 x M-24 x 96mm
f51b6265-1d2e-4f5e-99b3-86c2dfc104fa | checkpoint | Ferrules - 300mm N12 in Ferrule
ad4cfc62-1cf7-49e4-b236-2165d68f2fdf | checkpoint | Check Concrete cover around Reo 40mm
81b22db2-fe71-4570-af1c-4a190503e6fb | checkpoint | Check 40mm cover off Void Former
ac94c009-a14b-4865-af48-f7b724768929 | checkpoint | Panel Thickness as per Plans
810f75b1-596f-4e54-b0aa-808a4e0f81c3 | checkpoint | Check mould is Clean - No stray wire before mould closure
75544143-c15c-471a-b454-ab6935820a4d | checkpoint | Check bolts are secure
4bcd2274-74da-4628-b021-cd48d3c12f4c | checkpoint | Photo Taken
529a167e-1e26-4384-9468-5642210a93dd | checklist | Checkers Checklist (Type B) |  | Checkers Checklist
bbf87bed-4d82-4896-8ac0-67292892e7ed | section | Details
a9491d66-a540-4eca-ae2e-283ca668588c | checkpoint | Overall Measurements - 904mm height
30c0f8b6-7015-44c0-94fe-e82646460991 | checkpoint | Lifters Correct - Position, Size, Orientation
06a7c5a2-10f4-5a37-b8d3-64739ad95b9a | tickbox | 4 x 5T Foot Anchors
ddfe7773-2714-4c83-923c-6105272bb41a | checkpoint | Ferrules - Measurement, Quanity and Location
b3b2694b-d4be-5013-90d0-d9216dcb529b | tickbox | 7 x M-20 x 96mm
b8ac36f6-0066-4075-8512-43d12056e64b | checkpoint | Check Concrete cover around Reo 40mm
a7a12681-d017-4e6a-8425-a93602478218 | checkpoint | Ferrules - 300mm N12 in Ferrule
a20f497d-baef-4c29-9725-28ad07bff435 | checkpoint | Check 40mm cover off Void Former
11eb2850-b60e-4831-b918-9135552b8026 | checkpoint | Panel Thickness as per Plans
8eea0a50-1630-4347-9929-aa15db37ae47 | checkpoint | Check mould is Clean - No stray wire before mould closure
bc43d0fb-2b02-4f7a-9a05-d20ecb06af58 | checkpoint | Check bolts are secure
799b7d84-8565-4b18-99a0-1fd735cdeff2 | checkpoint | Photo Taken
e3911aad-cc50-40bc-9736-648d06926c22 | checklist | Installers Checklist (Type A) |  | Installers Checklist
d1130244-b3a1-4454-929a-9d9fa756a7fa | section | Details
1bed96a3-61be-4db9-8174-f9847d2ae699 | checkpoint | Complete Material "Bucket List"
8e2f07d3-642b-560f-a1f2-77fd1d388e87 | textbox | Panel Thickness - As per drawing
eaff7c09-21da-5ef7-9515-4c3c6bf00e7a | textbox | 4 x Foot Anchor - 5T
663e2c6b-18ef-53bf-8c11-692fc6fb1bef | tickbox | 18 x Ferrules - M-20 96mm
715d58ba-3210-5291-a7fe-0b679b4fa5cd | tickbox | 12 x Ferrules - M-24 96mm
3c3b2c8e-946a-5be6-82ab-5e1e650c53ed | textbox | 1 x ID Plate
87d14e58-2a32-4672-8213-6e7ab49b3446 | checkpoint | Use Culvert Mould
540a0733-aa2a-4dab-a6a0-a6d1ac33b3d7 | checkpoint | Apply bond breaker or wax 1 2 3
e52bb980-de10-497c-a9ad-9538498402d1 | checkpoint | Install Reo as-per Shop Drawing Plan
6fb5ca8a-57aa-442d-b8b2-38ec33e1fba2 | checkpoint | Lifters to be Firm & Square against Formwork
349c381a-cb73-4fda-b033-f38b5da7009b | checkpoint | Temporary Fix ID Plate to Formwork
f03b2d37-86df-490d-afb1-fdb0f29fff5f | checkpoint | Check Concrete cover around reo 40mm
f1e12959-3e70-437c-80b4-b1fabe8da69e | checkpoint | DOUBLE CHECK EVERYTHING
a0b03543-9940-4593-875e-08672dd3e507 | checkpoint | Finish Required - off Form
d105e4e5-2a06-43b8-9bb3-007e2af0cc5d | checkpoint | QA - Final Check of ALL measurerments & Photos
da6e5a7c-243e-469a-a243-fdaac1418463 | checkpoint | QA - Concrete Mix 40 Pan 2
302380a0-3512-444a-bcc0-748761a88569 | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
9236baad-4b24-40ba-b321-75b566063f36 | checkpoint | CONCRETE TEST TAKEN
7e63ecc3-4357-5ff6-bd45-13800ecbf627 | date | Pour Date
996ef4b9-b4e7-4ce5-8f89-69062432ab92 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
9cb05846-d78c-40d1-ae73-cfcca29861fb | signoff | Request Signoff
a530a2dc-9b59-40c4-9d56-5b4f0b838b4a | checklist | Installers Checklist (Type B) |  | Installers Checklist
970cf6e7-c6d1-455c-b5d6-092fc252e0be | section | Details
10a98f78-441c-4f15-87c3-7ba984c96f64 | checkpoint | Complete Material "Bucket List"
e72a6a24-031c-5b46-8252-e779330bb178 | textbox | Panel Thickness - As per drawing
3ab3302d-f07e-5ca7-847b-14040194036d | textbox | 4 x Foot Anchor - 5T
9774bf70-cdff-57ca-9240-e754c8b31ffb | tickbox | 7 x Ferrules - M-20 96mm
72459bf3-f6d3-5c21-96cb-6b420b972596 | textbox | 1 x ID Plate
88ba4cbb-2eae-43d7-8156-0938091d10b1 | checkpoint | Use Culvert Mould
6a85ed6d-5671-4a9c-86d8-fd1433db0efa | checkpoint | Apply bond breaker or wax 1 2 3
e66f1844-9080-4e45-83b0-765ab55aa2ab | checkpoint | Install Reo as-per Shop Drawing Plan
fd5b1461-5414-409a-8966-c4445266f772 | checkpoint | Lifters to be Firm & Square against Formwork
2b29176a-cb39-4aa0-9cdc-2573412cade4 | checkpoint | Temporary Fix ID Plate to Formwork
42b43a5d-b4de-4bd1-a212-624d143e15bf | checkpoint | Check Concrete cover around reo 40mm
fa65e5f7-c673-4719-bf21-99dfa7a43f37 | checkpoint | DOUBLE CHECK EVERYTHING
2f9f3818-82a2-4ff0-a4f7-8db0831c61da | checkpoint | Finish Required - off Form
31d51ac8-7b06-4fc9-8b5a-502cffc2daa9 | checkpoint | QA - Final Check of ALL measurerments & Photos
07aa15ad-9358-4727-bd11-ac358a508806 | checkpoint | QA - Concrete Mix 40 Pan 2
3269493e-1c8c-4d3b-9f07-a9041b3268f3 | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
123ae4d7-d3a8-4297-bc7e-d6b4676da9a3 | checkpoint | CONCRETE TEST TAKEN
c1bd6491-b7b5-5cfc-9d58-ce4966786b95 | date | Pour Date
529c681e-c974-4855-98fc-0586b136ef23 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
d9d08482-2571-4b5d-b2db-9476b0081c6a | signoff | Request Signoff
8ec6aea5-2d17-45e0-a58e-77ea87cf3df0 | checklist | Precast Components ITP (Type A) |  | Precast Components ITP
1f0531f1-ce02-46e9-a254-810650bdbabd | section | Manufacturing Documents
8ad77f35-db0a-4cdf-9c40-610feeb1be16 | checkpoint | Shop drawings reviewed and updated. Issued "As For Construction"
e490aa43-de73-45ad-85af-36cd8e1229e4 | section | Pre-Pour Checks
6ff48f60-3d0e-46fd-83a4-9fca935558ed | checkpoint | Final Inspection - all placed in accordance with approved shop drawings
36f1e1d6-8d35-53ba-84e0-b0fd7621732d | tickbox | 4 x Foot Anchor - 5T
7984e937-837d-5c82-a80c-6c7728a1342b | tickbox | 18 x Ferrules - M-20 96mm
18a3b588-c774-55cf-9c92-6e3dc3324f4c | tickbox | 12 x Ferrules - M-24 96mm
91800815-a692-54fd-a0d0-15d5c9f454be | tickbox | ID Plate
481b9e60-331b-531c-9bca-307fc30206da | tickbox | 1 x 40 Pan 2
9012e075-fdfe-4b92-b210-5d820f8f08b8 | checkpoint | Upload sufficient number of photos pre pour
bcd70c9f-ae37-4751-8243-b06e511dea46 | section | Concrete Pour Checks
6cbefbac-abc9-4e61-b846-065089f26f7d | checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
c066cddc-c136-5df3-ab03-fb52067e314a | tickbox | All Concrete Dockets Attached
1691d045-590f-476f-83e8-56292b09d16e | section | Delivery
8b3ad21f-1b8b-4fb0-a265-cb5ce7e71598 | checkpoint | Truck Rego and Insurance
c24dbbdf-e2cd-5e07-89f4-cb1a770d8f21 | tickbox | Truck Rego & Insurance Reviewed
42e219aa-825b-41b3-bd08-1ad39249d807 | checkpoint | Load Sheet
648ebbcf-ef9f-5135-9dc6-ad9910295991 | tickbox | Load Sheets Reviewed
aa535b23-1cdb-402c-b815-feb7ba5bb9dd | checkpoint | Install Sheet
dbfdc9a2-4f6f-5fbb-a23e-12830301153f | tickbox | Install Sheets Reviewed
7a5f87e0-a0e5-49b7-9bf4-6c4d7f1f6058 | checklist | Precast Components ITP (Type B) |  | Precast Components ITP
ce92a1b7-e092-44b9-ae6e-afd48249b9ec | section | Manufacturing Documents
c9a372b4-2ed9-42ee-9744-4a6fc3bbcb6a | checkpoint | Shop drawings reviewed and updated. Issued "As For Construction"
d9d767ae-a66b-4bf4-a1f3-6d15eb12ffb3 | section | Pre-Pour Checks
0b8d0e71-f64c-41f0-8c81-a56fadefacd6 | checkpoint | Final Inspection - all placed in accordance with approved shop drawings
4579bb16-84c5-5fee-b5df-738b0d5d9b36 | tickbox | 4 x Foot Anchor - 5T
609d46b7-47da-5a5e-b2d9-9a993de52206 | tickbox | 7 x Ferrules - M-20 96mm
518299d2-67e5-5b83-ab3f-b94f38ce822a | tickbox | 1 x ID Plate
af6eb90d-507d-5bb6-83c0-0717313cd2a2 | tickbox | 40 Pan 2
30cad194-6ebf-4d60-b5c4-c57bd781454d | checkpoint | Upload sufficient number of photos pre pour
17ae7826-aa57-4f08-95bf-23b4672fd3a3 | section | Concrete Pour Checks
8a9a6928-4651-4be4-bf45-fbb513379955 | checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
77483fbf-3c7e-590b-a651-b374f88e1f1e | tickbox | All Concrete Dockets Attached
a20c21f8-ccfe-457c-ac5a-1265d8abdf17 | section | Delivery
a28d0a74-765d-4d78-8e32-78ec3a1c7e46 | checkpoint | Truck Rego and Insurance
8395eac5-af0e-51eb-9afb-2b3cd676f724 | tickbox | Truck Rego & Insurance Reviewed
0559704a-b4a8-40fa-a767-4bd4af077d49 | checkpoint | Load Sheet
d37d199b-7443-59e8-9524-1e6a79ce3068 | tickbox | Load Sheets Reviewed
4ebb9497-8463-4796-b3be-66aa680c0531 | checkpoint | Install Sheet
fbf3cf1a-8f83-5e8f-a408-8ea5409cfc3f | tickbox | Install Sheets Reviewed