## Project Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Checklist Template
Site QA
Site QA | 1. Civil
Site QA | 1. Civil | 1.1 Building Footprint
Site QA | 1. Civil | 1.1 Building Footprint | Drainage/Services |  |  | Civil - Drainage Checklist
Site QA | 1. Civil | 1.1 Building Footprint | Building Subgrades |  |  | Civil - Buildings Subgrade
Site QA | 1. Civil | 1.2 External Works
Site QA | 1. Civil | 1.2 External Works | Drainage/Services |  |  | Civil - Drainage Checklist
Site QA | 1. Civil | 1.2 External Works | Driveway & Pavement
Site QA | 2. Structural
Site QA | 2. Structural | 2.1 Basement
Site QA | 2. Structural | 2.1 Basement | PALISADE WALL
Site QA | 2. Structural | 2.1 Basement | PILES |  |  | Structure - Crane Piles Checklist
Site QA | 2. Structural | 2.1 Basement | FOUNDATIONS (CAPPING BEAMS & GROUND BEAMS) |  |  | Structure - Foundation Beams
Site QA | 2. Structural | 2.1 Basement | INSITU COLUMNS, BEAMS & WALLS |  |  | Insitu Beams & Cols & Walls
Site QA | 2. Structural | 2.1 Basement | SLAB ON GRADE |  |  | Structure - Slab on Grade
Site QA | 2. Structural | 2.1 Basement | PRECAST WALLS |  |  | Structure – Pre-cast Panels
Site QA | 2. Structural | 2.1 Basement | SHOTCRETE WALLS |  |  | Structure - Shotcrete Walls
Site QA | 2. Structural | 2.1 Basement | BLOCKWALLS |  |  | Structure – Retaining Wall (Concrete Block)
Site QA | 2. Structural | 2.1 Basement | TANKING |  |  | Please Load 2.1 Tanking Checklist from below tabs
Site QA | 2. Structural | 2.2 Ground Floor
Site QA | 2. Structural | 2.2 Ground Floor | FOUNDATIONS (CAPPING BEAMS & GROUND BEAMS) |  |  | Structure - Foundation Beams
Site QA | 2. Structural | 2.2 Ground Floor | PRECAST ELEMENTS |  |  | Structure - PC Walls & Planters
Site QA | 2. Structural | 2.2 Ground Floor | INSITU COLUMNS & WALLS |  |  | Structure - Insitu Columns & Walls
Site QA | 2. Structural | 2.2 Ground Floor | STEEL BEAMS & COLUMNS |  |  | Structure - Structural Steel - Column and Beams
Site QA | 2. Structural | 2.2 Ground Floor | SUSPENDED SLABS |  |  | Structure - Suspended Slab
Site QA | 2. Structural | 2.3 Level 1 | PRECAST ELEMENTS |  |  | Please Load 2.2 Precast Elements Checklist from below tabs
Site QA | 2. Structural | 2.3 Level 1 | PT SLABS |  |  | 2.3 PYT Slabs from below tabs
Site QA | 2. Structural | 2.3 Level 1 | INSITU COLUMNS & WALLS |  |  | 2.1 In-situ Elements from below tabs
Site QA | 2. Structural | 2.3 Level 1 | STEEL BEAMS AND COLUMNS |  |  | 2.2 Steel Beams & Columns
Site QA | 2. Structural | 2.4 Level 2 | PRECAST ELEMENTS |  |  | Please Load 2.2 Precast Elements Checklist from below tabs
Site QA | 2. Structural | 2.3 Level 2 | PT SLABS |  |  | 2.3 PYT Slabs from below tabs
Site QA | 2. Structural | 2.3 Level 2 | INSITU COLUMNS & WALLS |  |  | 2.1 In-situ Elements from below tabs
Site QA | 2. Structural | 2.3 Level 2 | STEEL BEAMS AND COLUMNS |  |  | 2.2 Steel Beams & Columns
Site QA | 2. Structural | 2.4 Level 3 | PRECAST ELEMENTS |  |  | Please Load 2.2 Precast Elements Checklist from below tabs
Site QA | 2. Structural | 2.4 Level 3 | PT SLABS |  |  | 2.3 PYT Slabs from below tabs
Site QA | 2. Structural | 2.4 Level 3 | INSITU COLUMNS & WALLS |  |  | 2.1 In-situ Elements from below tabs
Site QA | 2. Structural | 2.4 Level 3 | STEEL BEAMS AND COLUMNS |  |  | 2.2 Steel Beams & Columns
Site QA | 2. Structural | 2.6 Roof | PRECAST ELEMENTS |  |  | Please Load 2.2 Precast Elements Checklist from below tabs
Site QA | 2. Structural | 2.6 Roof | BLOCKWALLS |  |  | 2.2 Steel Beams & Columns
Site QA | 2. Structural | 2.6 Roof | INSITU COLUMNS & WALLS |  |  | 2.1 In-situ Elements from below tabs
Site QA | 2. Structural | 2.6 Roof | PT SLABS |  |  | 2.3 PYT Slabs from below tabs
Site QA | ITP Civil - Bore Piling |  |  |  |  | 60f6460907d757adb4a3e7717c66d3c49d14d05f4e73722491ca367475462cfc
Site QA | ITP Structure – Foundation (Pilecaps and Ground beams) |  |  |  |  | 0bd81b34cb6f23fdbd46e16b6af7c21ee1179fecd7a58eac9480eadce72089ee
Site QA | ITP Civil - Boring Piles
Site QA | ITP Civil - Boring Piles | Palisade Retaining |  |  |  | ITP Civil - Bore Piling - Palisade Retaining
Site QA | ITP Civil - Boring Piles | Driveway Piles |  |  |  | ITP Civil - Bore Piling - Driveway Piles
Site QA | ITP Civil - Boring Piles | Building Piles |  |  |  | ITP Civil - Bore Piling - Building Piles
Site QA | ITP Structure - Foundation (Pilecaps and Ground Beams)
Site QA | ITP Structure - Foundation (Pilecaps and Ground Beams) | Palisade Capping Beam |  |  |  | ITP Structure – Foundation (Pilecaps and Ground beams) - Palisade Capping Beam
Site QA | ITP Structure - Foundation (Pilecaps and Ground Beams) | Driveway Capping Beam |  |  |  | ITP Structure – Foundation (Pilecaps and Ground beams) - Driveway Capping Beam
Site QA | ITP Structure - Foundation (Pilecaps and Ground Beams) | Building Capping Beams |  |  |  | ITP Structure – Foundation (Pilecaps and Ground beams) - Building Capping Beams
Site QA | ITP Structure - Foundation (Pilecaps and Ground Beams) | Building Ground Beams |  |  |  | ITP Structure – Foundation (Pilecaps and Ground beams) - Building Ground Beams

## ITP Tree
87 SHELLY BEACH RD - ITP
| 1. CIVIL |  |  | 2. STRUCTURAL | 2.1 BASEMENT | PALISADE WALL | 3. FACADE | MEMBRANE AND INSULATION | GROUND FLOOR |  | 4. FITOUT | BASEMENT | APPARTMENT 1 GARAGE | FIRST FIX SERVICES AND LININGS
|  | 1.1 BUILDING FOOTPRINT | DRAINAGE/ SERVICES
[6 empty] | PILES |  |  | ROOF |  |  |  |  | SECOND FIX & FITOUT
BUILDING SUBGRADES
[6 empty] | FOUNDATIONS (CAPPING BEAMS & GROUND BEAMS) | [6 empty] | APPARTMENT 2 GARAGE | FIRST FIX SERVICES AND LININGS
[8 empty] | CLADDING | CURTAIN WALL | NORTH ELEVATION
|  | 1.2 EXTERNAL WORKS | DRAINAGE/ SERVICES
[6 empty] | INSITU COLUMNS, BEAMS & WALLS | [7 empty] | SECOND FIX & FITOUT
EAST ELEVATION
DRIVEWAY & PAVEMENT
[6 empty] | SLAB ON GRADE | [6 empty] | APPARTMENT 3 GARAGE | FIRST FIX SERVICES AND LININGS
SOUTH ELEVATION
[6 empty] | PRECAST WALLS | [7 empty] | SECOND FIX & FITOUT
WEST ELEVATION
[6 empty] | SHOTCRETE WALLS | [6 empty] | APPARTMENT 4 GARAGE | FIRST FIX SERVICES AND LININGS
[9 empty] | SUNSHADES | NORTH ELEVATION
[6 empty] | BLOCKWALLS | [7 empty] | SECOND FIX & FITOUT
EAST ELEVATION
[6 empty] | TANKING | [6 empty] | APPARTMENT 5 GARAGE | FIRST FIX SERVICES AND LININGS
SOUTH ELEVATION
SECOND FIX & FITOUT
[5 empty] | 2.2 GROUND FLOOR | FOUNDATIONS (CAPPING BEAMS & GROUND BEAMS)
WEST ELEVATION
[13 empty] | APPARTMENT 6 GARAGE | FIRST FIX SERVICES AND LININGS
PRECAST ELEMENTS
[9 empty] | GRC | NORTH ELEVATION |  |  |  | SECOND FIX & FITOUT
INSITU COLUMNS & WALLS
[10 empty] | EAST ELEVATION |  |  | APPARTMENT 7 GARAGE | FIRST FIX SERVICES AND LININGS
STEEL BEAMS AND COLUMNS
[10 empty] | SOUTH ELEVATION |  |  |  | SECOND FIX & FITOUT
SUSPENDED SLABS
[10 empty] | WEST ELEVATION |  |  | APPARTMENT 8 GARAGE | FIRST FIX SERVICES AND LININGS
[5 empty] | 2.3 LEVEL 1 | PRECAST ELEMENTS
SECOND FIX & FITOUT
[9 empty] | RENDER | NORTH ELEVATION
PT SLABS
[13 empty] | LOBBY/ COMMONAL AREAS | FIRST FIX SERVICES AND LININGS
EAST ELEVATION
INSITU COLUMNS & WALLS
SECOND FIX & FITOUT
SOUTH ELEVATION
STEEL BEAMS AND COLUMNS
[10 empty] | WEST ELEVATION |  | APARTMENT 1 | FIRST FIX SERVICES AND LININGS
[5 empty] | 2.4 LEVEL 2 | PRECAST ELEMENTS
SECOND FIX & FITOUT
PT SLABS
[12 empty] | APARTMENT 2 | FIRST FIX SERVICES AND LININGS
INSITU COLUMNS & WALLS
SECOND FIX & FITOUT
STEEL BEAMS AND COLUMNS
[12 empty] | APARTMENT 3 | FIRST FIX SERVICES AND LININGS
[5 empty] | 2.5 LEVEL 3 | PRECAST ELEMENTS
SECOND FIX & FITOUT
PT SLABS
[12 empty] | APARTMENT 4 | FIRST FIX SERVICES AND LININGS
INSITU COLUMNS & WALLS
SECOND FIX & FITOUT
STEEL BEAMS AND COLUMNS
[12 empty] | APARTMENT 5 | FIRST FIX SERVICES AND LININGS
[5 empty] | 2.6 ROOF | PRECAST ELEMENTS
SECOND FIX & FITOUT
BLOCKWALLS
[12 empty] | APARTMENT 6 | FIRST FIX SERVICES AND LININGS
INSITU COLUMNS & WALLS
SECOND FIX & FITOUT
PT SLABS
[12 empty] | APARTMENT 7 | FIRST FIX SERVICES AND LININGS
SECOND FIX & FITOUT
[12 empty] | APARTMENT 8 | FIRST FIX SERVICES AND LININGS
SECOND FIX & FITOUT
DEVELOP ITP
ITP READY FOR REVIEW
ITP UPLOADED

## 1.1 Drainage-Services
CIVIL - Drainage
Notes:
Pre-start
Civil Engineer - preconstruction inspection (incl. Watercare as required for waste water) |  | comments/photos/pass fail/file uplopad
Locates done on site – confirm no clash with pre-existing underground services |  | comments/photos/pass fail/file uplopad
GL and datum provided |  | comments/photos/pass fail/file uplopad
Check design drawings |  | comments/photos/pass fail/file uplopad
Clear work area
Trenching & Drilling
Delineation of area |  | comments/photos/pass fail/file uplopad
Benching appropriate for ground conditions |  | comments/photos/pass fail/file uplopad
Removal/cutting of obstruction (abandoned services, piles) |  | comments/photos/pass fail/file uplopad
Civil Eng inspection report received and close-out (incl. AT & Parks) |  | comments/photos/pass fail/file uplopad
Installation
Council inspection carried out (hold point)
Confirm correct bedding material being used and spot check RL’s |  | comments/photos/pass fail/file uplopad
Detention tank installation |  | comments/photos/pass fail/file uplopad
Pre cast manhole installation |  | comments/photos/pass fail/file uplopad
Pipes installed and correct junctions/connections |  | comments/photos/pass fail/file uplopad
Correct grade lids to manholes and pits |  | comments/photos/pass fail/file uplopad
Lid level and catchpit RL's check |  | comments/photos/pass fail/file uplopad
Civil Eng inspection report received and close-out |  | comments/photos/pass fail/file uplopad
Backfilling
Council inspection carried out IDT (hold point)
Appropriate backfill material |  | comments/photos/pass fail/file uplopad
Backfill and compact as per Civil specs |  | comments/photos/pass fail/file uplopad
Post Backfilling
Ensure all areas level and clean with no open trenches or spoil |  | comments/photos/pass fail/file uplopad
Internal manhole works |  | comments/photos/pass fail/file uplopad
i. Splitters and benching completed | (add tick box for i,ii,iii) | comments/photos/pass fail/file uplopad
ii. Civil Eng inspection |  | comments/photos/pass fail/file uplopad
iii. Council inspection report received and close-out – as-built plan required |  | comments/photos/pass fail/file uplopad
Drainage QA received and as built |  | comments/photos/pass fail/file uplopad
Civil Eng inspection report received and close-out
Drilling QA
Signoff of public connections

## 1.1 Building Subgrades
Buildings Preparation of Subgrade & Subbase |  | Should we make this a general ITP for Subgrade and Subbase that we can apply to buildings, pavings etc. |  | Agreed.
I interpret subgrade as the cut/fill level of the existing ground (bulk excavation), and subbase as the engineered layers build up for the given slab/pavement/asphalt above. Do you agree?
| Notes: | Agreed. Happy to split them as subgrade and sub-base
Pre-Start
Setout - GL and datum and mark up of excavations completed |  | Anything else prestart?
Site Clearance and clean-ups
Drainage check - ensure drainage provisions are in place to avoid subgrade saturation
Inspect for any required CBR (California Bearing Ratio) or other strength tests
Geotech design engineer's inspection (pre-work)
Subgrade base
Bulk excavation completed to correct RL and extent, QA handover provided by sub-contractor
Geotech design engineer's inspection |  | For bulk - check if needed pre/during/post | Need it for all three
Detailed excavation completed to correct RL's and widths, QA handover provided by sub-contractor |  | Included width as we do not want over/under excavated. Changed height to RL. | Agreed
Geotech design engineer's inspection |  | For detailed- check if needed pre/during/post | Yes, need it for all three for detailed too
Prompt for Compaction Testing & Survey?
Building Subbase
Council inspection carried out ISF - Sub-Grade before hard fill (Hold Point)
GL and datum and mark up of excavations completed |  | Delete per prestart item above. | Agreed
Placement of hardfill layers, compacted as per design
Drainage piping installed under foundation level |  | Where is this best placed and should it be a Services QA & sign off?
Platforms spot checks heights and location
Prompt for Compaction Testing & Survey?
Sign-off
Dockets
Subgrade QA and test results received
Subbase QA and test results received
Geotech Eng Final Inspection report received and close-out | (add tick box for i,ii,iii) | Proof rolling always required?
Survey |  | Can just state final inspecion

## 1.2 Driveway & Pavement
checklist | Driveway & Pavement
section | Pre-start
checkpoint | Site clearance
Delete? | Soil compaction testing | I would lump all of these under having the Subgrade & Subbase ITP signed off.
Delete? | Sub-grade level check | Agreed
Delete? | Geotech Eng inspection report received- and close-out
Delete? | GL and datum and mark up of excavations completed
Delete? | Detailed excavation completion to correct height and handover provided by sub-contractor
checkpoint | Review excavation as-builts
checkpoint | Drainage slope verification | Not sure
checkpoint | Pipe material and size check
section | During works
checkpoint | Base course compaction
checkpoint | Level check of base
checkpoint | Civil Eng inspection report received- and close-out
checkpoint | Concrete mix design
checkpoint | Concrete strength test
checkpoint | Trench excavation for drains
checkpoint | Pipe material and size check
checkpoint | Pipe laying and alignment
checkpoint | Pipes installed and correct junctions/connections | (add tick box for i,ii,iii)
checkpoint | Cesspit installation
checkpoint | Kerb bedding preparation
checkpoint | Kerb alignment and level
checkpoint | Kerb placement and bonding
section | Final Inspection & testing
checkpoint | Pavement thickness check
checkpoint | Pavement surface water test
checkpoint | Markings and signage
checkpoint | Surface finish quality check

## 2.1 Palisade Wall
Already on Conqa

## 2.1 Piles
Already on CONQA
Please just add a checklist for the crane piles

## 2.1 Foundation Beams (Cap & GD)
ITP Structure – Foundation Beams
Already on CONQA

## 2.1 In-situ Elements (Beams, Co
In-situ Elements (Beams, Columns & Walls)
section | 1. Pre-start
checkpoint | Clear work Area
checkpoint | QA for sub-grade and relevant services received
checkpoint | GL and datum provided
checkpoint | Review construction drawings and set-out
section | 2. Pre-pour
checkpoint | Service trade sign off/QA
checkpoint | Waterproof sign off/QA
checkpoint | Cast-in items/QA
checkpoint | Formwork signoff/QA
tickbox | i. Check RL levels and benchmarks
tickbox | ii. Check Dimentions and alignment
tickbox | iii. Check form ties and propping
tickbox | iv. Overall Cleanliness and Seals and ready to Pour
tickbox | v. Setdowns, rebates, fillets & joints
tickbox | vi. Shoring/temporary works design reviewed, inspected and approved by the design engineer
checkpoint | Reo sign off/QA
checkpoint | GN inspection
tickbox | i. Details checked
tickbox | ii. Starters/ embedment depth, cover checked
tickbox | iii. Check reinforcements size, spacing and cleanliness
checkpoint | Any CAN, Engr requirements (Reo Pull-out test)
checkpoint | Structural Eng inspection report received and close-out
checkpoint | Council inspection report received and close-out
checkpoint | Depth and RL of rebates correct (for flat slab)
section | 3. Access/Safety
checkpoint | Clear access for trucks/pump
checkpoint | Exposed reo capped
checkpoint | Safe access to all areas of pour
section | 4. Pour
checkpoint | Confirm mix
checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint | Weather recorded
section | 5. Post pour
checkpoint | Checks
checkpoint | i. Finish
checkpoint | ii. Levels
checkpoint | iii. Starters
checkpoint | iv. Scabbling
checkpoint | Pour QA received including dockets
checkpoint | Concrete Test Results

## 2.1 Slab on Grade
ITP – Structure – Slab on Grade
Note
Pre-start
Foundation Beam QA Completed
Council inspection carried - ISF (floor slab) & IPP (underslab plumbing) - (Hold Point)
Services sign-off
i. Electrical | tickbox for i.ii.iii.iv
ii. Fire
iii. Hydraulic & gas
iv. Comms and Fibre
Subgrade QA completed
i. Blinding
GL and datum provided | tickbox for i.
Clean work area
Pre-Pour
Waterproofing sign-off/QA
i. DPM including tapes and laps | tickbox for i,ii
ii. Waterstop where applicable
Formwork signoff/QA
i. Step down/ falls | tickbox for I,ii,iii
ii. Ties, propping, seal formworks
iii. Seismic gap/expansion joints
Reo sign off/QA
GN inspection
i. Details checked | tickbox for i.ii.iii.iv.v
ii. Any CANs
iii. Check starters, cover checked, thickenings
iv. Reinsforcement size, spacing, supports.
v. Clean formwork and ready to pour
Structural Eng inspection report received and close-out
Access/safety/protection
Clear access for trucks/pump
Safe access to all areas of pour
Panel and steel protection
Pour
Confirm mix
Confirm concrete is being tested (slump and cylinders)
Weather recorded
Post pour
Finish
Levels
Curing agent
Scabble
Saw cuts within 24h of pour and slurry removed
Pour QA received including concrete dockets
Concrete Test Results

## 2.1 Shotcrete Walls
ITP Structure – Shotcrete Walls
Flash Coat Stage
Pre-start
Ground beams sign-off/QA received.
Ground level (GL) and datum confirmed.
Work area cleaned and ready.
Pre-pour
Service trades sign-off/QA completed.
Mark-up attached.
Check RL levels and benchmarks.
Dimensions and alignment confirmed.
Ensure overall cleanliness and seals are in place.
Reinforcement (Reo) sign-off/QA obtained.
General inspection to confirm details.
Specific checks on:
Scabbling, starter bars, embedment depth, and cover.
Reinforcement size, spacing, and cleanliness.
Structural Engineer inspection report received and closed out.
Council inspection report received and closed out.
Pour sequence mark-up confirmed.
Access/Safety
Confirm sprayer and pump access.
Ensure safe access to all spray areas.
Exposed reinforcement capped.
Spray
Confirm mix specifications.
Confirm concrete testing (slump and cylinder tests).
Record weather conditions.
Final Coat Stage
Pre-start
Confirm that flash coat has set and meets required specifications.
Work area cleaned and prepared for final coat.
Pre-pour
Re-check levels and alignment.
Ensure structural integrity of flash coat.
Re-confirm RL levels and benchmarks for final coat.
Check that all reinforcement is securely in place.
Access/Safety
Confirm access for final spray application.
Ensure safe pathways and capped reinforcement.
Final Coat Spray
Confirm mix and consistency.
Verify concrete testing procedures (slump and cylinder tests) are being followed.
Monitor weather for optimal spraying conditions.
Post Spray / Pour
Complete finish and level checks for the final coat.
Pour QA received with concrete dockets included.

## 2.1 Blockwalls
ITP Structure – Retaining Wall (Concrete Block)
Pre-start
Foundation QA
GL and datum provided
Blocks, weep pipes
Clean work area
Structural steel connections
Pre Block work
Reinforcement - sign off/QA
Ensrure safe platform access
GN Inspection
i. detail checks.
a. Any RFI's, Authority req.
During works
Foundation works including base preparation
Check set-out
Check reo details
Bottom clean-outs for inspection
Brick Layering
Drainage pipes/ weep holes
Pre-pour (blocks infill)
Reo sign off/QA
Grout specification
GN inspection
i. Details checked
ii. Starters, cover checked
iii. Clean-outs free of debris and ready to inspect/pour
Structural Eng inspection report received and close-out
Council inspection report received and close-out
Access/Safety
Clear access for mixers
Exposed reo capped
Safe access to all areas of work
Post pour
Checks
i. Finish
ii. Levels
iii. Alignment
Documentation QA received

## 2.1 Tanking
type | name
checklist | ITP Structure – Tanking
section | Pre-start
checkpoint | Panel QA received
checkpoint | Block wall QA received
checkpoint | Subgrade QA
checkpoint | Panel joints grouted/sealed
checkpoint | Drainage QA received
checkpoint | GL and datum provided
checkpoint | Clean work area
checkpoint | Safe access
checkpoint | HOLD POINTS
section | Installation
checkpoint | Waterproofing as per architectural drawings
checkpoint | Membrane have been extended and with correct lapping (150mm ovelaps)
checkpoint | Council inspection report received and close-out
section | Post install
checkpoint | Protective layers
checkpoint | Tanking QA received

## 2.2 Steel Beams & Columns
checklist | Steel Beams & Columns
section | Pre-Start
checkpoint | Slab QA received
checkpoint | Off-site Manufacture QA
checkpoint | Protective coatings QA
checkpoint | RL for support beams/ Plinth
checkpoint | Plate support/ bolts surveyed and checked as built
checkpoint | checked tolerances, packing space
checkpoint | Area clean/clear for access equipment
checkpoint | Propping / shoring
section | Safety
checkpoint | taglines secured
checkpoint | Work space demarcation
section | Erection
checkpoint | GN inspection
tickbox | i. Welds, bolts, plumb, alignment, etc. as per design
tickbox | ii. QA test requirements such as Torque test, Welding test (NDT - UT/MPI)
checkpoint | Structural Eng inspection report received and close-out
checkpoint | Council inspection report received and close-out
section | Post erection
checkpoint | Propping where required
checkpoint | Connections completion
checkpoint | Spot check RL’s and plumb
checkpoint | Primer touch-ups
checkpoint | Steel QA received
checkpoint | Grout under columns & drypack beams
checkpoint | Grout filling columns

## 2.2 Precast Elements
checklist | Precast Elements
section | Pre-start
checkpoint | GL and datum provided
checkpoint | Timber guides installed – including spacers
checkpoint | Waterstop installed
checkpoint | Clean work area
checkpoint | Ground Beams QA received
checkpoint | Review IFC Shop Drawings & Starters
checkpoint | Off-site manufacture QA records
checkpoint | Min days/MPa since pour
checkpoint | Temporary works & propping approval by engineer
section | Delivery Inspection
checkpoint | Check for damage/defects on arrival
checkpoint | Measurement checks in line w/ IFC SD
checkpoint | Panels unloaded correctly
section | Installation
checkpoint | Installed in correct location as per Struc. Dwg
checkpoint | Check temporary bracing as per requirements
checkpoint | Sample verticality check
checkpoint | Ensure correct RLs on top of panels
checkpoint | Strcutrual engineer inspection in-place
checkpoint | Connections to PC elements check
checkpoint | Subcontractor's panel installation QA
section | Post Installation
checkpoint | As per propping design.
checkpoint | Check for damage to panels
checkpoint | Confirm all Grouting completed
checkpoint | Check on portal tubes and anchor points
checkpoint | Panel installation QA

## 2.2 Suspended Slabs
ITP Structure – Suspended Slab
Pre-start
Precast QA/ signoff
Blockwork QA/ signoff
Edge protection in place
Access provided
GL and datum provided
Clean work area
Pre-pour
Propping sign-off/QA received
Formwork sign-off/QA received
i. Check RL levels and benchmarks
ii. Check Dimentions and alignment
iii. Setdowns, rebates, fillets & joints
iv. Overall Cleanliness and Seals and ready to Pour
v. Shoring/temporary works design reviewed, inspected and approved by the design engineer
Reo sign-off/QA received
Services & Passive Fire sign-off
GN inspection
i. Details checked
ii. Stair opening checked
iii. Starters, cover, Trimmer installed, Hangers, saddle bars, Nib Reo location
iv. Penetrations set-outs and sizes confirmed & sleeves in place
v. Clean and ready to pour
Structural steel cast-in items
Structural Eng inspection report received and close-out
Council inspection report received and close-out
Access/Safety
Clear access for trucks/pump
Safe access to all areas of pour
Wash up organized
Pour
Confirm mix
Confirm concrete is being tested (slump and cylinders)
Weather recorded
Checked Screed to falls
Post pour
Finish
Levels
Curing agent and canvas protection (standby)
Scabble
Pour QA received including dockets
Concrete Test Results

## 2.2 Crane Base
ITP Structure – Foundation (Towercrane)
1. Pre-start – HOLD POINT
Clear work Area
QA for sub-grade and relevant services received
GL and datum provided
Review construction drawings and set-out
Geotechnical Eng inspection report received and closed-out
2. Pre-pour
Service trade sign off/QA
Formwork signoff/QA
i. Check RL levels and benchmarks
ii. Check Dimentions and alignment
iii. Check form ties and propping
iv. Overall Cleanliness and Seals and ready to Pour
Reo sign off/QA
GN inspection
i. Details checked
1. Any CAN, Engr requirements ( Reo Pull-out test
ii. Scabbling, Starters/ embedment depth, cover checked
iii. Check reinforcements size, spacing and cleanliness
Structural Eng inspection report received and close-out
Council inspection report received and close-out
3. Access/Safety
Clear access for trucks/pump
Exposed reo capped
Safe access to all areas of pour
4. Pour
Confirm mix
Confirm concrete is being tested (slump and cylinders)
Weather recorded
5. Post pour
Checks
i. Finish
ii. Levels
iii. Starters
Pour QA received including dockets
6. Towercrane Assembly preparation
i. ensure personell trained
ii. Verify all components
iii. Confirm to conduct trial run and check safety devices and emergency sys.
iv. Ensure load test and recorded results.
v. Confirm certification and approva and authority approvals
vi. Handing over documentations, and training certs.

## 2.3 PT Slabs
ITP – Structure – PT Slab
section | Pre-start
checkpoint | Precast QA/ signoff
checkpoint | Edge protection in place
checkpoint | Access provided
checkpoint | GL and datum provided
checkpoint | Clean work area
checkpoint | Services sign-off | tickbox for i.ii.iii.iv
tickbox | i. Electrical
tickbox | ii. Fire
tickbox | iii. Hydraulic
tickbox | iv. Comms and Fibre
section | Pre-Pour
checkpoint | Propping sign-off/QA received
checkpoint | Formwork sign-off/QA received
checkpoint | i. Check RL levels and benchmarks
checkpoint | ii. Check Dimentions and alignment
checkpoint | iii. Setdowns, rebates, fillets & joints
checkpoint | iv. Overall Cleanliness and Seals and ready to Pour
checkpoint | v. Shoring/temporary works design reviewed, inspected and approved by the design engineer
checkpoint | Reo sign-off/QA received
checkpoint | i. Bottom mat reinforcing & joints sign off/QA
checkpoint | ii. Tendons and grout vents and sockets QA including as-built locations
checkpoint | iii. Top mat reinforcing
checkpoint | Services & Passive Fire sign-off
checkpoint | GN inspection | tickbox for i.ii.iii.iv.v
tickbox | i. Details checked
tickbox | ii. Stair opening checked
tickbox | iii. Starters, cover, Trimmer installed, Hangers, saddle bars, Nib Reo location
tickbox | iv. Penetrations set-outs and sizes confirmed & sleeves in place
checkpoint | v. Clean formwork and ready to pour
checkpoint | Engineer Inspection - Edge
checkpoint | Structural Eng inspection report received and close-out
checkpoint | Council inspection report received and close-out
section | Access/safety/protection
checkpoint | Clear access for trucks/pump
checkpoint | Safe access to all areas of pour
checkpoint | Panel and steel protection
checkpoint | Wash up organized
section | Pour
checkpoint | Confirm mix
checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint | Weather recorded
section | Post pour & Tensioning
checkpoint | Finish
checkpoint | Levels
checkpoint | Scabble
checkpoint | Curing agent
checkpoint | Post tensioning inspection & concrete testing
checkpoint | i. Concrete test results followed by initial stressing, tensioning results
checkpoint | ii. Concrete test results followed by final Tensioning, tensioning results
checkpoint | Pour QA received including concrete dockets
checkpoint | Stressing and elongation QA
checkpoint | Cutting strands & filling sockets with mortars
checkpoint | Grouting the isolated penetrations
checkpoint | Sign off process for the PT tensioning by the design engineer
checkpoint | Bleeding air into vents and grout-filling
checkpoint | Slab flatness testing
checkpoint | Depropping and clean-ups