## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Structure - Tanking
section | Pre-start
checkpoint | Panel QA received
checkpoint | Block wall QA received
checkpoint | Subgrade QA
checkpoint | Panel joints grouted/sealed
checkpoint | Drainage QA received
checkpoint | GL and datum provided
checkpoint | Clean work area
checkpoint | Safe access
checkpoint | HOLD POINTS
section | Installation
checkpoint | Waterproofing as per architectural drawings
checkpoint | Membrane have been extended and with correct lapping (150mm ovelaps)
checkpoint | Council inspection report received and close-out
section | Post install
checkpoint | Protective layers
checkpoint | Tanking QA received
checklist | Precast Elements
section | Pre-start
checkpoint | GL and datum provided
checkpoint | Timber guides installed – including spacers
checkpoint | Waterstop installed
checkpoint | Clean work area
checkpoint | Ground Beams QA received
checkpoint | Review IFC Shop Drawings & Starters
checkpoint | Off-site manufacture QA records
checkpoint | Min days/MPa since pour
checkpoint | Temporary works & propping approval by engineer
section | Delivery Inspection
checkpoint | Check for damage/defects on arrival
checkpoint | Measurement checks in line w/ IFC SD
checkpoint | Panels unloaded correctly
section | Installation
checkpoint | Installed in correct location as per Struc. Dwg
checkpoint | Check temporary bracing as per requirements
checkpoint | Sample verticality check
checkpoint | Ensure correct RLs on top of panels
checkpoint | Strcutrual engineer inspection in-place
checkpoint | Connections to PC elements check
checkpoint | Subcontractor's panel installation QA
section | Post Installation
checkpoint | As per propping design.
checkpoint | Check for damage to panels
checkpoint | Confirm all Grouting completed
checkpoint | Check on portal tubes and anchor points
checkpoint | Panel installation QA
checklist | Structure - PT Slab
section | Pre-start
checkpoint | Precast QA/ signoff
checkpoint | Edge protection in place
checkpoint | Access provided
checkpoint | GL and datum provided
checkpoint | Clean work area
checkpoint | Services sign-off
bool | i. Electrical
bool | ii. Fire
bool | iii. Hydraulic
bool | iv. Comms and Fibre
section | Pre-Pour
checkpoint | Propping sign-off/QA received
checkpoint | Formwork sign-off/QA received
checkpoint | i. Check RL levels and benchmarks
checkpoint | ii. Check Dimentions and alignment
checkpoint | iii. Setdowns, rebates, fillets & joints
checkpoint | iv. Overall Cleanliness and Seals and ready to Pour
checkpoint | v. Shoring/temporary works design reviewed, inspected and approved by the design engineer
checkpoint | Reo sign-off/QA received
checkpoint | i. Bottom mat reinforcing & joints sign off/QA
checkpoint | ii. Tendons and grout vents and sockets QA including as-built locations
checkpoint | iii. Top mat reinforcing
checkpoint | Services & Passive Fire sign-off
checkpoint | GN inspection
bool | i. Details checked
bool | ii. Stair opening checked
bool | iii. Starters, cover, Trimmer installed, Hangers, saddle bars, Nib Reo location
bool | iv. Penetrations set-outs and sizes confirmed & sleeves in place
checkpoint | v. Clean formwork and ready to pour
checkpoint | Engineer Inspection - Edge
checkpoint | Structural Eng inspection report received and close-out
checkpoint | Council inspection report received and close-out
section | Access/safety/protection
checkpoint | Clear access for trucks/pump
checkpoint | Safe access to all areas of pour
checkpoint | Panel and steel protection
checkpoint | Wash up organized
section | Pour
checkpoint | Confirm mix
checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint | Weather recorded
section | Post pour & Tensioning
checkpoint | Finish
checkpoint | Levels
checkpoint | Scabble
checkpoint | Curing agent
checkpoint | Post tensioning inspection & concrete testing
checkpoint | i. Concrete test results followed by initial stressing, tensioning results
checkpoint | ii. Concrete test results followed by final Tensioning, tensioning results
checkpoint | Pour QA received including concrete dockets
checkpoint | Stressing and elongation QA
checkpoint | Cutting strands & filling sockets with mortars
checkpoint | Grouting the isolated penetrations
checkpoint | Sign off process for the PT tensioning by the design engineer
checkpoint | Bleeding air into vents and grout-filling
checkpoint | Slab flatness testing
checkpoint | Depropping and clean-ups
checklist | Structure - Steel Beams & Columns
section | Pre-Start
checkpoint | Slab QA received
checkpoint | Off-site Manufacture QA
checkpoint | Protective coatings QA
checkpoint | RL for support beams/ Plinth
checkpoint | Plate support/ bolts surveyed and checked as built
checkpoint | Checked tolerances, packing space
checkpoint | Area clean/clear for access equipment
checkpoint | Propping / shoring
section | Safety
checkpoint | taglines secured
checkpoint | Work space demarcation
section | Erection
checkpoint | GN inspection
bool | i. Welds, bolts, plumb, alignment, etc. as per design
bool | ii. QA test requirements such as Torque test, Welding test (NDT - UT/MPI)
checkpoint | Structural Eng inspection report received and close-out
checkpoint | Council inspection report received and close-out
section | Post erection
checkpoint | Propping where required
checkpoint | Connections completion
checkpoint | Spot check RL’s and plumb
checkpoint | Primer touch-ups
checkpoint | Steel QA received
checkpoint | Grout under columns & drypack beams
checkpoint | Grout filling columns