## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Structure - In-situ Elements (Beams, Columns & Walls)
section | 1. Pre-start
checkpoint | Clear work Area
checkpoint | QA for sub-grade and relevant services received
checkpoint | GL and datum provided
checkpoint | Review construction drawings and set-out
section | 2. Pre-pour
checkpoint | Service trade sign off/QA
checkpoint | Waterproof sign off/QA
checkpoint | Cast-in items/QA
checkpoint | Formwork signoff/QA
bool | i. Check RL levels and benchmarks
bool | ii. Check Dimentions and alignment
bool | iii. Check form ties and propping
bool | iv. Overall Cleanliness and Seals and ready to Pour
bool | v. Setdowns, rebates, fillets & joints
bool | vi. Shoring/temporary works design reviewed, inspected and approved by the design engineer
checkpoint | Reo sign off/QA
checkpoint | GN inspection
bool | i. Details checked
bool | ii. Starters/ embedment depth, cover checked
bool | iii. Check reinforcements size, spacing and cleanliness
checkpoint | Any CAN, Engr requirements (Reo Pull-out test)
checkpoint | Structural Eng inspection report received and close-out
checkpoint | Council inspection report received and close-out
checkpoint | Depth and RL of rebates correct (for flat slab)
section | 3. Access/Safety
checkpoint | Clear access for trucks/pump
checkpoint | Exposed reo capped
checkpoint | Safe access to all areas of pour
section | 4. Pour
checkpoint | Confirm mix
checkpoint | Confirm concrete is being tested (slump and cylinders)
checkpoint | Weather recorded
section | 5. Post pour
checkpoint | Checks
checkpoint | i. Finish
checkpoint | ii. Levels
checkpoint | iii. Starters
checkpoint | iv. Scabbling
checkpoint | Pour QA received including dockets
checkpoint | Concrete Test Results