## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Precast Install QA |  |  |  |  | Yes | Precast Install QA | a8ee41a7-da47-4390-894e-4f5c154f5683
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Complete
text | 7550b3e1-b030-5a0d-acf5-2cf1aebf6c54 |  | textbox | Watpac supervisor
text | facc2d68-b395-51dd-a314-74416f8c7bdf |  | textbox | Precast Supplier
text | 23949769-b9f8-556f-b7b6-4fed5468a0cf |  | textbox | Rigging Company
text | cfdbee6a-d376-5bed-b6e3-4816e7606a39 |  | textbox | Riggin Supervisor
text | 38e51bdf-1569-537e-8266-935a090e86dc |  | textbox | Crane Supplier
checkpoint-group |  |  | section | Lifting and Quality Checks
checkpoint-status |  |  | checkpoint | Birth Cert (QA) Provided
checkpoint-status |  |  | checkpoint | Panel Visual inspection (any damage, check coulour and quality) take photo
checkpoint-status |  |  | checkpoint | Can the panel be lifted as per rigging details provided in shop drawing?
checkpoint-status |  |  | checkpoint | Do strongbacks, fall protection need to be installed prior to lift?
checkpoint-group |  |  | section | Post install check
checkpoint-status |  |  | checkpoint | Set out check - Grid / level / plumb
checkpoint-status |  |  | checkpoint | All Bracekts installed with correct number of fixings, washers, packing shims etc
checkpoint-status |  |  | checkpoint | Grouting
checkpoint-status |  |  | checkpoint | Propping signed off temp works engineer
checkpoint-status |  |  | checkpoint | Grouting
checkpoint-status |  |  | checkpoint | Ready/OK to pour upper level
checklist-flat |  |  | checklist | Job Details |  |  |  |  | Yes | Job Details Checklist | ef3643f2-75a6-4723-9ae3-8e0292cc22b3
checkpoint-status |  |  | checkpoint | Project details entered below
text | a05d1768-7d54-5aa0-a796-3b2baa6a6245 |  | textbox | Job File Number
text | 9f0a64fa-879f-5a3e-9e0e-ae266ce79dc2 |  | textbox | Project Name
text | 7ab2284e-c170-5c27-bccc-7b2e8f8d21a8 |  | textbox | Site Address
text | 488c684c-14dc-540a-a855-543c974281ca |  | textbox | Main Contractor
text | 06674a40-8ec8-516d-a939-95e6012b1569 |  | textbox | Main Contractor POC
text | 6481cf4c-6f7d-5711-b225-56cb4758aa22 |  | textbox | Structural Engineer
text | 5e4d939d-c89a-5df3-9b2e-e7ce5369f4bf |  | textbox | Architect
checklist-sectioned |  |  | checklist | Precast Panel QA |  |  |  |  | Yes | Precast Panel QA (V1) | f1bca21c-60a7-4490-9414-07d49883e237
checkpoint-group |  |  | section | Precast Element Details
checkpoint-status |  |  | checkpoint | Concrete Details Complete
text | 25c36033-72a3-5b0b-8d7c-43f3fd7b1772 |  | textbox | Concrete Volume
text | efb3eb6e-1802-575b-a43c-87d0bf0f06ad |  | textbox | Concrete Strength
text | 4bb266a6-4a6f-50f6-9b99-a0b353cdd04c |  | textbox | Enter Drawing Revision Number
text | 1f5f8c2a-e160-55dc-91b2-3b82f47280ff |  | textbox | Cast Date
text | a2483b76-cf31-5173-b4e8-e02bd6e288f0 |  | textbox | Admixture Required
checkpoint-group |  |  | section | Formwork Set Up Checks
checkpoint-status |  |  | checkpoint | Length/Width/Thickness/Cutouts/Diagonals
checkpoint-status |  |  | checkpoint | Edge Details & Rebates
checkpoint-status |  |  | checkpoint | Inserts on MF (Weld plates, RB's, TIM's, Penetrations, DB Bottoms)
checkpoint-status |  |  | checkpoint | MF roughening's
checkpoint-status |  |  | checkpoint | Sides Straight & Magnets Fastened
checkpoint-status |  |  | checkpoint | Mould Face Clean
checkpoint-group |  |  | section | Prepour Checks
checkpoint-status |  |  | checkpoint | Mould Cleaned & Oiled
checkpoint-status |  |  | checkpoint | Reinforcing details checked/highlighted off against shop drawing (Bar sizes, grades and spacings)
checkpoint-status |  |  | checkpoint | Check covers on all sides, MF and TF
checkpoint-status |  |  | checkpoint | There is sufficient cover to rebates around openings or weatherproofing details
checkpoint-status |  |  | checkpoint | Starters (Size, Grade, Setout and Length)
checkpoint-status |  |  | checkpoint | Inserts on TF (Weld plates, RB's, TIM's, Penetrations, DB's, Rebates)
checkpoint-status |  |  | checkpoint | Lifters
checkpoint-status |  |  | checkpoint | Tie wire Trimmed
checkpoint-status |  |  | checkpoint | Panel fully clean
checkpoint-status |  |  | checkpoint | General Photos Attached
checkpoint-status |  |  | checkpoint | Shop Drawing Checked Off (attach photo)
checkpoint-group |  |  | section | Demould Inspection
checkpoint-status |  |  | checkpoint | Demould Inspection complete
checkpoint-group |  |  | section | Loading Out
checkpoint-status |  |  | checkpoint | Photo take of Panel on Truck
checkpoint-status |  |  | checkpoint | No remedial work required on site
checkpoint-group |  |  | section | Test Results, Certificates and Documentation
checkpoint-status |  |  | checkpoint | Upload reinforcing detail sheets
checkpoint-status |  |  | checkpoint | Concrete Docket Attached
checkpoint-status |  |  | checkpoint | Upload Concrete test results
checkpoint-status |  |  | checkpoint | Upload Photo of Reinforcing Cast # Tracking
checkpoint-status |  |  | checkpoint | Upload Lift Designs