## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Precast Install QA |  |  |  |  | Yes | Precast Install QA | d01a6781-caaa-4d02-a1bb-6dfe74201f27
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Details Complete
text | d56d27d8-fe45-5a16-8e6c-531d0e78462b |  | textbox | Watpac supervisor
text | 4ec7fdd0-bd55-50dd-a70b-90c8df8ab033 |  | textbox | Precast Supplier
text | 2de04007-82a8-5ad5-a55b-aedf152bef3b |  | textbox | Rigging Company
text | bf5459c5-f79d-58bd-9618-7bcef3aa2a5f |  | textbox | Riggin Supervisor
text | 226c272e-0eff-518b-826a-72e2bd1fa688 |  | textbox | Crane Supplier
checkpoint-group |  |  | section | Lifting and Quality Checks
checkpoint-status |  |  | checkpoint | Birth Cert (QA) Provided
checkpoint-status |  |  | checkpoint | Panel Visual inspection (any damage, check coulour and quality) take photo
checkpoint-status |  |  | checkpoint | Can the panel be lifted as per rigging details provided in shop drawing?
checkpoint-status |  |  | checkpoint | Do strongbacks, fall protection need to be installed prior to lift?
checkpoint-group |  |  | section | Post install check
checkpoint-status |  |  | checkpoint | Set out check - Grid / level / plumb
checkpoint-status |  |  | checkpoint | All Bracekts installed with correct number of fixings, washers, packing shims etc
checkpoint-status |  |  | checkpoint | Grouting
checkpoint-status |  |  | checkpoint | Propping signed off temp works engineer
checkpoint-status |  |  | checkpoint | Grouting
checkpoint-status |  |  | checkpoint | Ready/OK to pour upper level
checklist-sectioned |  |  | checklist | Precast Panel QA |  |  |  |  | Yes | Precast Panel QA (V1) | e6bb37e7-fda9-4337-aa66-fdeb62373b02
checkpoint-group |  |  | section | Precast Element Details
checkpoint-status |  |  | checkpoint | Concrete Details Complete
text | 1e686c64-6cd8-53e7-935f-87ea53a25d04 |  | textbox | Concrete Volume
text | 65ed450a-b4ca-5f23-8d64-be2235f03f37 |  | textbox | Concrete Strength
text | a8f4d790-b8f8-5972-88ac-ea1ef58d2ce2 |  | textbox | Enter Drawing Revision Number
text | 545b9746-b62c-5ba4-9b20-fbb8291c14a9 |  | textbox | Cast Date
text | a57e571b-98f9-5080-b861-c27e580d3ecc |  | textbox | Admixture Required
checkpoint-group |  |  | section | Formwork Set Up Checks
checkpoint-status |  |  | checkpoint | Length/Width/Thickness/Cutouts/Diagonals
checkpoint-status |  |  | checkpoint | Edge Details & Rebates
checkpoint-status |  |  | checkpoint | Inserts on MF (Weld plates, RB's, TIM's, Penetrations, DB Bottoms)
checkpoint-status |  |  | checkpoint | MF roughening's
checkpoint-status |  |  | checkpoint | Sides Straight & Magnets Fastened
checkpoint-status |  |  | checkpoint | Mould Face Clean
checkpoint-group |  |  | section | Prepour Checks
checkpoint-status |  |  | checkpoint | Mould Cleaned & Oiled
checkpoint-status |  |  | checkpoint | Reinforcing details checked/highlighted off against shop drawing (Bar sizes, grades and spacings)
checkpoint-status |  |  | checkpoint | Check covers on all sides, MF and TF
checkpoint-status |  |  | checkpoint | There is sufficient cover to rebates around openings or weatherproofing details
checkpoint-status |  |  | checkpoint | Starters (Size, Grade, Setout and Length)
checkpoint-status |  |  | checkpoint | Inserts on TF (Weld plates, RB's, TIM's, Penetrations, DB's, Rebates)
checkpoint-status |  |  | checkpoint | Lifters
checkpoint-status |  |  | checkpoint | Tie wire Trimmed
checkpoint-status |  |  | checkpoint | Panel fully clean
checkpoint-status |  |  | checkpoint | General Photos Attached
checkpoint-status |  |  | checkpoint | Shop Drawing Checked Off (attach photo)
checkpoint-group |  |  | section | Demould Inspection
checkpoint-status |  |  | checkpoint | Demould Inspection complete
checkpoint-group |  |  | section | Loading Out
checkpoint-status |  |  | checkpoint | Photo take of Panel on Truck
checkpoint-status |  |  | checkpoint | No remedial work required on site
checkpoint-group |  |  | section | Test Results, Certificates and Documentation
checkpoint-status |  |  | checkpoint | Upload reinforcing detail sheets
checkpoint-status |  |  | checkpoint | Concrete Docket Attached
checkpoint-status |  |  | checkpoint | Upload Concrete test results
checkpoint-status |  |  | checkpoint | Upload Photo of Reinforcing Cast # Tracking
checkpoint-status |  |  | checkpoint | Upload Lift Designs
checklist-flat |  |  | checklist | Job Details |  |  |  |  | Yes | Job Details Checklist | f90c0df6-9c5d-44cd-b172-06cd58caba50
checkpoint-status |  |  | checkpoint | Project details entered below
text | 5eba2bfb-bb3c-51c1-8b2c-ef0e0d19feb6 |  | textbox | Job File Number
text | 341296d8-4d62-501a-86be-f7645d742966 |  | textbox | Project Name
text | cab9d395-dd50-5bb5-8232-8dde4f336faa |  | textbox | Site Address
text | 70fe4f5d-7068-5b00-9c3f-8fd95d4c6333 |  | textbox | Main Contractor
text | 91a8ab3c-af61-5e6c-9963-bc6d562c5be6 |  | textbox | Main Contractor POC
text | 6e088d2f-d6d6-57ef-9235-4a1c8128a854 |  | textbox | Structural Engineer
text | 1df700e5-8057-55c8-9325-db3535bf5899 |  | textbox | Architect