## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-031 - MCC Stormwater Drainage | itp |  |  |  |  | ITP-031 - MCC Stormwater Drainage | 7e263036-4a7f-4589-b81a-474fe5b3840f
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 1.3 Precast Materials acceptance
label | FREQUENCY: Each Delivery
label | ACCEPTANCE CRITERIA: Precast reinforced concrete pipes shall be accepted on the basis of full compliance with the requirements of this section and AS/NZS 4058.
label | REFERENCE DOCUMENTS: Cl. 701.05e
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.4 Precast Pipe & Culvert Compliance
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Box Culverts to comply with requirements of VicRoads Section 619.
label | ○ Precast Reinforced Concrete (Portland) Pipes shall comply with requirements of AS 4058.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619, Cl. 701.04, Cl. 701.05(a), AS4058, AS4680
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.5 Precast Drainage Pit Compliance
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 610.
label | ○ Pits to manufactured as per the City of Melbourne Standard drawings 1P 50301, 1P 50318
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.610, Cl. 705.04, AS5100, City of Melbourne Standard Drawings 1P50301, 1P50318
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.6 Bedding material classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Materials used for bedding and selected backfill shall be free from perishable matter and lumps and shall conform with the requirements of Table 701.091 and Table 701.092.
label | REFERENCE DOCUMENTS: 701.09(d), 701.091, 701.092
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.7 Backfill material Classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Ordinary backfill shall be free from perishable matter and shall conform with the requirements of Table 701.091.
label | REFERENCE DOCUMENTS: 701.09(d), 701.091
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 1.8 Mortar material classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
label | REFERENCE DOCUMENTS: 610.33
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.2 Set out drainage
label | FREQUENCY: Prior to backfilling
label | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
label | REFERENCE DOCUMENTS: Drawings 701.10
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Excavation (pipes)
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical
label | Depth of trench:
label | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
label | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
label | REFERENCE DOCUMENTS: 701.151, 701.15
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
textbox | Date Completed:
checkpoint | 2.4 Excavation (pits)
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: A minimum clearance of 400mm is required around the external faces of precast pits.
label | REFERENCE DOCUMENTS: 705.05b
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
textbox | Date Completed:
checkpoint | 2.5 Compact base of trench
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
label | REFERENCE DOCUMENTS: 701.15
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.6 Place bedding material & compact
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | REFERENCE DOCUMENTS: 701.20, 701.20a
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed:
checkpoint | 2.7 Place pipes & precast pits
label | FREQUENCY: Each Line/Pit
label | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.8 Installation of In-Situ Cast Pits
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: In-situ cast pits to be installed as per the City of Melbourne Standard Drawings 1P50301, 1P50318
label | ○ Pre-Pour inspection to be completed
label | REFERENCE DOCUMENTS: City of Melbourne Standard Drawings 1P50301, 1P50318
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.9 Jointing pipe sections
label | FREQUENCY: Each Line
label | ACCEPTANCE CRITERIA: All interlocking (flush) joint reinforced concrete pipes shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
label | REFERENCE DOCUMENTS: 701.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.10 Sealing - for joining culvert sections and pipe penetrations in pits
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: Contact areas between top and bottom sections of box culverts to be mortared. The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of Clause 610.32.
label | REFERENCE DOCUMENTS: 610.32, 701.17c
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.11 Survey of laid pipe or pit
label | FREQUENCY: Prior to backfilling
label | ACCEPTANCE CRITERIA: The location of each run of drainage has been verified prior to backfilling and conforms to the following tolerances:
label | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | (c) invert level of pipes at pits ±50 mm
label | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | REFERENCE DOCUMENTS: 701.1
label | INSPECTION/TEST METHOD: Survey Conformance Point
label | RECORD OF CONFORMITY: ITP Signed
label | SCP
label | RESPONSIBILITY: Site Engineer/ Surveyor
textbox | Date Completed:
checkpoint | 2.12 Haunching & compaction of bedding material
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Height of additional bedding material = 30% of nominal pipe diameter or culvert height.
label | ○ Loose layer thickness <=150mm
label | ○ Compacted to refusal using hand held mechanical equipment.
label | ○ 1 lot = 150mm layer
label | REFERENCE DOCUMENTS: 701.16, 701.20
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.13 Place & compact backfill material over pipes
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
label | Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
label | ○ Loose layer thickness <= 150mm.
label | ○ 1 lot = 150mm layer
label | REFERENCE DOCUMENTS: 701.19, 701.20
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
checkpoint | 2.14 Place & compact backfill material around pits
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: Loose layer thickness <= 300mm.
label | ○ Compacted to refusal using hand held mechanical equipment.
label | REFERENCE DOCUMENTS: 705.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Enginer
textbox | Date Completed:
checkpoint | 2.15 Install step irons
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: For pits > 1m deep.
label | REFERENCE DOCUMENTS: 705.12
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Enginer
textbox | Date Completed:
checkpoint | 2.16 Pit base shaped with concrete to match pipe invert
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: As shown on Standard VicRoads drawing - Pit & Pipe Invert levels SD 1002
label | REFERENCE DOCUMENTS: Standard VicRoads drawing SD 1002
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Enginer
textbox | Date Completed:
checkpoint | 2.17 Place pit covers
label | FREQUENCY: Each Pit
label | ACCEPTANCE CRITERIA: Covers must be set to within ±10mm of the design levels shown on the drawings
label | REFERENCE DOCUMENTS: 705.17 CoM Standard Pit Lid Drawing
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
textbox | Date Completed:
section | Testing & Completion
checkpoint | 3.1 CCTV inspection
label | FREQUENCY: each lot
label | ACCEPTANCE CRITERIA: All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | REFERENCE DOCUMENTS: 701.3
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: CCTV Report
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 Flushing of pipes
label | FREQUENCY: Each line
label | ACCEPTANCE CRITERIA: All pipes to be flushed clean upon completion
label | REFERENCE DOCUMENTS: 701.28
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer
textbox | Date Completed: