## Table 1
Inspection and test plan – Site Clearing
Project no. |  | CC0408 |  |  | Project name: |  | MREH BESS |  | Date |  |  |  | SGJV Approval |  |  |  | SAMSUNG-GCOR-000121
ITP no. |  | CC0408-ITP-002 |  |  | Revision date: |  | 3.05.2024 (C) |  | Plant and equipment used: |  |  |  | Excavator, Dozer, Moxy
Lot no. |  |  |  |  | Location (chainages, detailed description or marked up plan): | [7 empty] | Lot map attached.
SGJV ITP no. |  | MRH00B00-QAITP0001
[12 empty] | Verification of acceptance by | [6 empty] | Remarks / record (eg. test reports, certificates, checklist etc)
[12 empty] | Symal |  |  |  | SGJV |  | Principal
Item no. | Activity |  |  | Ref docs |  | Acceptance criteria |  | Acceptance |  |  | Freq | Key | Resp | Initial/ date |  | Key | Sign/ date | Sign/date
1.0 Pre-start activities
1.1 | Determine Lot Size |  |  | N/A |  | What is the lot size? |  | m2 |  |  | Once | S | SE |  |  | S |  |  | Work Lot Map
1.2 | Safety Ensure that the following items have been actioned: - SWMS if applicable - Plant Pre-start Inspection - Service locations identified - Traffic Management Plans (if req’d) - All staff inducted |  |  | SWMS TMPS Plant prestart inspection form |  | SWMS submitted reviewed and accepted if required. Personnel inducted to SGJV requirements. Plant inspections completed and entered. Pre-work briefings completed. Service diagrams available and services located. |  | Yes ☐ No ☐ N/A ☐ |  |  | Once (Pre-Start) | W | SS |  |  | S |  |  | Hard copy of the SWMS (if required)
1.3 | Excavation Permit |  |  | Excavation permit template |  | All identified underground services marked and potholed to confirm location and depth. No machine excavation within 1m of underground services. Permit available and signed. |  | Yes ☐ No ☐ N/A ☐ |  |  | Prior to start of works | H | SS |  |  | W |  |  | Signed Excavation Permit (if required)
1.4 | Check Survey Set-out |  |  | N/A |  | Survey setout extend of works |  | Yes ☐ No ☐ N/A ☐ |  |  | Prior to start of Works | H | SV, SS |  |  | W |  |  | N/A
2.0 Clearing And Grubbing
2.1 | Clearing and Grubbing |  |  | MRH/00/P/ 00- PM/SPC/0 003 (Rev 3) Page 53 |  | Have the identified areas been cleared of all vegetation, refuse, unsuitable material and obstructions down to natural surface? In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed. Unsuitable material and topsoil is to be stockpiled in the designated location and is not to be used as fill material. |  | Yes ☐ No ☐ N/A ☐ |  |  | Once | W | SS |  |  | W |  |  | Visual Check Photos (if required)
3.0 Topsoil Stripping
3.1 | Stripping |  |  | IFC Constructio n MRH/A0/B/ 00- CV/DWG/0 008 |  | Has the area been stripped and stockpiled to an appropriate depth (minimum top 50mm) removing surface topsoil and unsuitable material in a way to leave the surface evenly graded and free- draining? |  | Yes ☐ No ☐ N/A ☐ |  |  | Once | W | SS |  |  | H |  |  | Visual Check Photos (if required)
3.2 | Topsoil export / stockpiling |  |  | IFC constructio n drawing MRH/A0/B/ 00- CV/DWG/0 021 |  | Has the topsoil being stockpiled been approved by SGJV (where applicable) and silt fence around the stockpile present? Have the environmental controls as per CHMP &CEMP and Enviro/Biodiversity Assessment been adhered to. Dispose material as per CHMP and Enviro/Biodiversity requirements |  | Yes ☐ No ☐ N/A ☐ |  |  | Once | W | SS |  |  | H |  |  | Stockpile Plan Photos
Comments:
Works complete (signer SS) |  |  | Date works complete
Lot conforms (signer SE) |  |  | Date lot closed | [6 empty] | NCR/s no. raised |  |  |  |  | Date NCR closed for this lot
SGJV / Client Representative signoff: Name Company Signature Date
Name Company Signature Date
Responsibility (Resp.) Key: PM-Project Manager, PE-Project Engineer, SE- Site Engineer, CS-Civil Superintendent, SS-Site Supervisor, SV-Surveyor, CR-Client Representative Inspection Key : W – Witness, H – Hold Point, S - Surveillance