## Table 1
Inspection and test plan – Bulk Earthworks
Project no. |  | CC0408 |  |  | Project name |  | MREH BESS | [5 empty] | Date |  |  |  | SGJV Approval |  |  | SAMSUNG-GCOR-000121
ITP no. |  | CC0408-ITP-003 |  |  | Revision no. |  | C | Revision date |  | 03.05.2024 |  |  | Layer thickness
Plant and equipment used |  |  |  |  | Excavator, Dozer, Moxy, Stabiliser, Grader, Roller, Tandems, Trucks & Trailers, Dozer
Lot no. |  |  |  |  | Location (chainages, detailed description or marked up plan)
SGJV ITP no. |  | MRH00B00-QAITP0002
[14 empty] | Verify of acceptance by | [8 empty] | Remarks / record (eg. test reports, certificates, checklist etc)
[14 empty] | Symal Infrastructure |  |  |  |  | SGJV |  |  | Principal
Item no. | Activity |  | Ref docs |  |  | Acceptance criteria |  |  | Acceptance |  |  | Frequency |  | Key |  | Resp |  | Sign/ date | Key |  | Sign/ date | Sign/ date
1.0 Preliminaries
1.1 | Determine lot size |  | N/A |  |  | What is the lot size? |  |  | m2 |  |  | Prior to start of Works |  | S |  | SE |  |  | S |  |  |  | Lot Map
1.2 | Survey set-out |  | N/A |  |  | Is the most current survey file what the team is working to and has the work area been set out for line and level? |  |  | ☐ Yes ☐ No ☐ N/A |  |  | Each lot & Each possession |  | W |  | SE |  |  | S |  |  |  | N/A
1.3 | Water management |  | EMP |  |  | Where necessary, have batters been rounded and catch drains constructed to allow for potential surface runoff during the course of excavation? Are environmental controls set up as per the site EMP? |  |  | ☐ Yes ☐ No ☐ N/A |  |  | Each lot & Each possession |  | S |  | SE |  |  | S |  |  |  | N/A
1.4 | Clearing |  | CC0408- ITP- 002 or MRH00B00- QAITP0001 |  |  | Has the area been cleared and grubbed in accordance with CC0408- ITP-002 or MRH00B00-QAITP0001? |  |  | ☐ Yes ☐ No ☐ N/A |  |  | Prior to start of Works |  | W |  | SE |  |  | S |  |  |  | N/A
Is the area in cut / fill / both? If in cut proceed to step 2.0 and strike out section 3.0. If in fill please strike out section 2.0 and proceed to section 3.0 If in both proceed to step 2.0 as well as section 3.0
2.0 Bulk earthworks – Cut
[14 empty] | Verify of acceptance by | [8 empty] | Remarks / record (eg. test reports, certificates, checklist etc)
[14 empty] | Symal Infrastructure |  |  |  |  | SGJV |  |  | Principal
Item no. | Activity |  | Ref docs |  |  | Acceptance criteria |  |  | Acceptance |  |  | Frequency |  | Key |  | Resp |  | Sign/ date | Key |  | Sign/ date | Sign/ date
2.1 | Excavation material classification |  | MRH/00/P/00- PM/SPC/0003 Rev 3; Page 53 |  |  | Has the material being excavated been inspected with category agreed upon by Superintendent? Tick category below: ☐ Topsoil ☐ Unsuitable material ☐ Fill material ☐ Other: |  |  | ☐ Yes ☐ No ☐ N/A |  |  | Prior to start of Works |  | W |  | SE |  |  | S |  |  |  | Test reports
2.2 | Stockpile |  | N/A |  |  | Has the stockpile location been approved by SGJV. |  |  | ☐ Yes ☐ No ☐ N/A |  |  | Prior to start of Works |  | H |  | SE |  |  | H |  |  |  | SGJV approved stockpile plan
2.3 | Subgrade preparation or scarification |  | MRH/A0/B/00- CV/DWG/0040 |  |  | Has the cut surface been trimmed to an even surface free from lose material or scarified/ripped? Have surface levels been checked to avoid over excavation? |  |  | ☐ Yes ☐ No ☐ N/A |  |  | Each lot & Each possession |  | S |  | SE |  |  | H |  |  |  | Test reports/as- built survey
2.4 | Lime mix |  | MRH/A0/B/00- CV/DWG/0040 |  |  | Has lime demand testing been completed and submitted? |  |  | ☐ Yes ☐ No ☐ N/A |  |  | Prior to starting |  | H |  | SE |  |  | H |  |  |  | ☐ Test reports No longer applicable.
2.5 | Lime stabilisation |  | MRH/A0/B/00- CV/DWG/0040 |  |  | Has the prepared subgrade been lime stabilised as per the IFC design? |  |  | ☐ Yes ☐ No ☐ N/A |  |  | Each lot & Each possession |  | S |  | SE |  |  | W |  |  |  | Photos/As-built report No longer applicable.
Compaction Scale: minimum 3
|  |  | AS3798 Table |  |  | tests per lot, or 1 test per
|  |  | 8.1 |  |  | 1000m2 | [5 empty] | Each lot
&
2.6 | Compaction |  | MRH/00/P/00- PM/SPC/0003 |  |  | Has the subgrade been adequately compacted achieving 100% SDD? |  |  | ☐ Yes ☐ No ☐ N/A |  |  | Each possession |  | W |  | SE |  |  | S |  |  |  | ☐ Test reports
|  |  | MRH/A0/B00- |  |  | Is the subgrade material within
|  |  | CV/DWG/0008 |  |  | +/- 2% of the optimum
moisture content.
[14 empty] | Verify of acceptance by | [8 empty] | Remarks / record (eg. test reports, certificates, checklist etc)
[14 empty] | Symal Infrastructure |  |  |  |  | SGJV |  |  | Principal
Item no. | Activity |  | Ref docs |  |  | Acceptance criteria |  |  | Acceptance |  |  | Frequency |  | Key |  | Resp |  | Sign/ date | Key |  | Sign/ date | Sign/ date
Has the layer thickness conformed with Item No. 4.2 ‘Acceptance criteria’ ?
Does the layer withstand test rolling without visible deformation or springing? List Attendees:
2.7 | Test Rolling |  | MRH/A0/B/00- CV/DWG/0040 |  |  | Type of equipment used: |  |  | ☐ Yes ☐ No ☐ N/A If ‘no’ please see below. If ‘yes’ please proceed. |  |  | Each lot & Each possession |  | H |  | SE |  |  | H |  |  |  | ☐ Proof Roll Inspection Checklist
☐ Water cart
☐ Tandem
☐ Others:
Identification of soft wet or unstable material |  |  | N/A |  |  | What quantity of soft, wet, or unstable material is present? |  |  | … m2 … m3 |  |  | As required |  | W |  | SE |  |  | S |  |  |  | Photos (if required)
Treatment of unsuitable material |  |  | N/A |  |  | Has rectification process been submitted to SGJV for review. What was the rectification process used. |  |  | ☐ Yes ☐ No ☐ N/A |  |  | As required |  | W |  | SE |  |  | S |  |  |  | Aconex Correspondence
3.0 Bulk earthworks - Fill
3.1 | Fill material classification |  | MRH/00/P/00- PM/SPC/0003 page 53 |  |  | Has the material to be used as fill been approved for use? Material Type: |  |  | ☐ Yes ☐ No ☐ N/A |  |  | Prior to start of Works |  | S |  | SE |  |  | H |  |  |  | Material Acceptance correspondence/C ertificate
3.2 | Stripped surface - test rolling (If applicable) |  | MRH/A0/B/00- CV/DWG/0040 |  |  | Does the stripped surface to be filled withstand test rolling without visible deformation or springing? |  |  | ☐ Yes ☐ No ☐ N/A If ‘no’ please see below. |  |  | Each lot & Each possession |  | H |  | SE |  |  | H |  |  |  | ☐ Proof roll checklist
[14 empty] | Verify of acceptance by | [8 empty] | Remarks / record (eg. test reports, certificates, checklist etc)
[14 empty] | Symal Infrastructure |  |  |  |  | SGJV |  |  | Principal
Item no. | Activity |  | Ref docs |  |  | Acceptance criteria |  |  | Acceptance |  |  | Frequency |  | Key |  | Resp |  | Sign/ date | Key |  | Sign/ date | Sign/ date
[6 empty] | List Attendees: |  |  | If ‘yes’ please proceed to item 3.3
Identification of soft wet or unstable material |  |  | N/A |  |  | What quantity of soft, wet or unstable material is present? |  |  | … m2 … m3 |  |  |  |  | H |  | SE |  |  | S |  |  |  | Photos / Visual inspection
Treatment of unsuitable material |  |  | N/A |  |  | What rectification process is to be undertaken |  |  | ☐ Yes ☐ No ☐ N/A |  |  | As required |  | S |  | SE |  |  | S |  |  |  | Aconex Correspondence /Approval from SGJV
3.3 | Preparation of surface |  | MRH/A0/B/00- CV/DWG/0040 |  |  | Has adequate water been added to the stripped surface to ensure adhesion to the next layer? |  |  | ☐ Yes ☐ No ☐ N/A |  |  | Each lot & Each possession |  | S |  | SE |  |  | S |  |  |  | Photos (if required)
Has fill been placed in
maximum 200mm and
|  |  | MRH/00/P/00- PM/SPC/0003 |  |  | minimum 100mm compacted layer thickness? | [5 empty] | Each lot &
3.4 | Fill Placement |  | MRH/A0/B00- CV/DWG/0008 |  |  | Rock in the fill should be less than 75 mm. |  |  | ☐ Yes ☐ No ☐ N/A |  |  | Each possession |  | S |  | SE |  |  | S |  |  |  | Photos (if required)
Fill should be free of clay and
free from organic.
3.5 | Moisture |  | AS 3798 |  |  | Has the material maintained at optimum moisture content (within +/- 2% of optimum moisture), with additional water being added if required during compaction? |  |  | ☒ Yes ☐ No ☐ N/A |  |  | As required |  | S |  | SE |  |  | S |  |  |  | Test Reports
3.6 | Lime mix |  | MRH/A0/B/00- CV/DWG/0040 |  |  | Has mix demand testing been completed and submitted? |  |  | ☐ Yes ☐ No ☐ N/A |  |  | Once |  | H |  | SE |  |  | H |  |  |  | ☐ Test reports No longer applicable.
[14 empty] | Verify of acceptance by | [8 empty] | Remarks / record (eg. test reports, certificates, checklist etc)
[14 empty] | Symal Infrastructure |  |  |  |  | SGJV |  |  | Principal
Item no. | Activity |  | Ref docs |  |  | Acceptance criteria |  |  | Acceptance |  |  | Frequency |  | Key |  | Resp |  | Sign/ date | Key |  | Sign/ date | Sign/ date
3.7 | Lime stabilisation |  | MRH/A0/B/00- CV/DWG/0040 |  |  | Has the prepared subgrade been lime stabilised as per the IFC design? |  |  | ☐ Yes ☐ No ☐ N/A |  |  | Each lot & Each possession |  | S |  | SE |  |  | W |  |  |  | Photos/As-built report No longer applicable.
3.8 | Compaction |  | MRH/A0/B00- CV/DWG/0008 |  |  | Compaction Scale: minimum 3 tests per lot, or 1 test per 1000m2 Has the subgrade been adequately compacted achieving 100% SDD? Is the subgrade material within +/- 2% of the optimum moisture content. |  |  | ☐ Yes ☐ No ☐ N/A |  |  | Each lot & Each possession |  | W |  | SE |  |  | S |  |  |  | ☐ Test reports
Does the layer withstand test rolling without visible deformation or springing? List Attendees:
3.9 | Test Rolling |  | MRH/A0/B/00- CV/DWG/0040 |  |  | Type of equipment used: ☐ Water cart |  |  | ☐ Yes ☐ No ☐ N/A If ‘no’ please see below. If ‘yes’ please proceed |  |  | Each lot & Each possession |  | H |  | SE |  |  | H |  |  |  | ☐ Proof Roll Inspection Checklist
☐ Tandem
☐ Other:
Identification of soft wet or unstable material |  |  | N/A |  |  | What quantity of soft, wet or unstable material is present? |  |  | … m2 … m3 |  |  | As required |  | S |  | SE |  |  | S |  |  |  | Photos (if required)
[14 empty] | Verify of acceptance by | [8 empty] | Remarks / record (eg. test reports, certificates, checklist etc)
[14 empty] | Symal Infrastructure |  |  |  |  | SGJV |  |  | Principal
Item no. | Activity |  | Ref docs |  |  | Acceptance criteria |  |  | Acceptance |  |  | Frequency |  | Key |  | Resp |  | Sign/ date | Key |  | Sign/ date | Sign/ date
Treatment of unsuitable material |  |  | N/A |  |  | Has rectification process been submitted to SGJV for Review? What was the rectification process used? |  |  | ☐ Yes ☐ No ☐ N/A |  |  | As required |  | H |  | SE |  |  | S |  |  |  | Photos (if required)
4.0 Conformance check
4.1 | Width and alignment |  | IFC Drawings |  |  | Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings? |  |  | ☐ Yes ☐ No ☐ N/A |  |  | Once |  | W |  | SE |  |  | H |  |  |  | ☐ As built report
4.2 | Subgrade level and shape |  | IFC Drawings |  |  | Has the prepared subgrade been surveyed in accordance with and verifying specified requirements? Is the subgrade within +/- 20mm of design surface. |  |  | ☐ Yes ☐ No ☐ N/A |  |  | As required |  | W |  | SE |  |  | H |  |  |  | ☐ As built report
Comments:
Works complete (signer SS) |  |  |  | Date works complete
Lot conforms (signer SE) |  |  |  | Date lot closed | [6 empty] | NCR/s no. raised |  |  |  | Date NCR closed for this lot
SGJV / Client Representative signoff: Name Company Signature Date
Name Company Signature Date
Responsibility (Resp.) Key: PM - Project Manager, PE-Project Engineer, SE- Site Engineer, CS-Civil Superintendent, SS-Site Supervisor, SV-Surveyor, CR-Client Representative Inspection key: W – Witness, H – Hold Point, S - Surveillance