## Table 1
Inspection and test plan – Pavement Construction
Project no. |  |  |  | CC0408 |  |  |  | Project name |  |  | MREH BESS |  |  |  | Date | [5 empty] | SGJV Approval |  |  |  |  | SAMSUNG-GCOR-000121
ITP no. |  |  |  | CC0408-ITP-005 |  |  |  | Revision date |  |  | 03.05.2024 (C) |  |  |  | Plant and equipment used | [5 empty] | Excavator, Tandems, Rollers, Watercart, Posi-Track
Lot no. | [7 empty] | Location (chainages, detailed description or marked up plan) | [12 empty] | See lot map attached.
SGJV ITP no. |  |  |  | MRH00B00-QAITP0004
[19 empty] | Verification of acceptance by | [9 empty] | Remarks/record (e.g. Test frequency reports, certificates, checklist etc.)
[19 empty] | Symal |  |  |  |  | SGJV |  |  |  | Principal
|  | Item no. | Activity |  |  |  | Ref docs |  | Acceptance criteria |  |  |  | Acceptance |  |  |  | Freq |  | Key | Resp |  |  | Initial/ date | Key | Sign/ date |  |  | Sign/ date
1.0 Pre-start activities
|  | 1.1 | Determine Lot Size |  |  |  | N/A |  | What is the lot size? |  |  | m2 |  |  |  |  | N/A |  | S | SE |  |  |  | S |  |  |  |  | ☐ Work Lot Map
|  | 1.2 | Survey Setout |  |  |  | N/A |  | Has the work area been set out for line and level? |  |  | Yes ☐ No ☐ N/A ☐ |  |  |  |  | Prior to start of Works |  | W | SE |  |  |  | S |  |  |  |  | N/A
|  | 1.3 | Material Classification & Source |  |  |  | MRH/00/P/ 00- PM/SPC/0 003 Rev 3, Page 55 |  | Is the correct material being used? |  |  | Yes ☐ No ☐ N/A ☐ Please tick appropriate Box: Site Won ☐ 20mm Class 2 ☐ 20mm Class 3 ☐ 20mm Class 4 ☐ Other |  |  |  |  | Prior to start of Works |  | W | SE |  |  |  | H |  |  |  |  |  Test Report/Material certificate
2.0 Previous pavement conformance
2.1 | Conformance of Previous Layer |  |  | MRH/A0/B /00- CV/DWG0 040 | Has the previous layer passed acceptance criteria? |  |  |  |  | Yes ☐ No ☐ N/A ☐ |  |  |  | Each Lot |  |  | W | SE |  |  | S | [5 empty] |  Refer to ITP for previous layer
3.0 Placement of pavement
3.1 | Placement |  |  | IFC Drawings MRH/A0/B/ 00- CV/DWG0 040 | Has the fill been placed in a maximum compacted layer as outlined below? Maximum Layer Depth: 200mm |  |  |  |  | Yes ☐ No ☐ N/A ☐ |  |  |  | Each Lot |  |  | S | SE |  |  | S | [5 empty] | ☐ Photo (if required)
3.2 | Moisture |  |  | MRH/A0/B/ 00- CV/DWG0 008 | Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction? |  |  |  |  | Yes ☐ No ☐ N/A ☐ |  |  |  | Each Lot |  |  | S | SE |  |  | S | [5 empty] | ☐ Photo (if required)
|  |  |  | MRH/A0/B/ | Has the layer been adequately compacted achieving a mean value density ratio of: Pavement Type 1:  “Granular Surface” Top Layer: 98% MOD Bottom Layer: 97% MOD  “Low Permeability Capping Layer” Both Layers: 98% STD Pavement Type 2:  “Granular Surface” One Layer: 98% MOD  “Low Permeability Capping Layer” Both Layers: 98% STD 3 x tests to be conducted per compacted layer per approved lot map.
00-
CV/DWG0
8
3.3 | Compaction | [8 empty] | Yes ☐ No ☐ N/A ☐ |  |  |  | Each Lot |  |  | W | SE |  |  | S | [5 empty] | ☐ Compaction test results
AS3798
Table 8.1
3.4 | Test Rolling |  |  | MRH/A0/B/ 00- CV/DWG0 040 | Does the layer withstand test rolling without visible deformation of springing? |  |  |  |  | Yes ☐ No ☐ N/A ☐ If ‘no’, please see sections 3.5 and 3.6. |  |  |  | Each Lot |  |  | W | SE |  |  | H | [5 empty] | ☐ Photo (if required)
[5 empty] | List attendees: |  |  |  |  | If ‘yes’, proceed to section 4.0.
3.5 | Identification of soft, wet or unstable material |  |  | N/A | What quantity of soft, wet or unstable material is present? |  |  |  |  | m |  |  |  | As required |  |  |  | SE |  |  | S | [5 empty] | ☐ Photo (if required)
3.6 | Treatment of unsuitable material |  |  | IFC Drawings | Has rectification process been submitted for review? What was the rectification process used? SGJV approval acquired before proceeding with the above process? |  |  |  |  | Yes ☐ No ☐ N/A ☐ Process Used: |  |  |  | As required |  |  | S | SE |  |  | H | [5 empty] | ☐ Photo (if required) Aconex Correspondence:
4.0 Pavement conformance
4.1 | Pavement Finish |  |  | IFC Drawings | Has the pavement course been finished to a smooth and uniform surface? |  |  |  |  | Yes ☐ No ☐ N/A ☐ |  |  |  | Once |  |  | W | SE |  |  | H | [5 empty] | ☐ Photo (if required)
4.2 | Width & Alignment |  |  | IFC Drawings | Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings? |  |  |  |  | Yes ☐ No ☐ N/A ☐ |  |  |  | Each Lot |  |  | W | SE |  |  | S | [5 empty] | ☐ Photo (if required)
4.3 | Surface Level of Pavement Courses |  |  | IFC Drawings | Has the prepared layer been surveyed in accordance with and verifying specified requirements? All crushed rock layers: Mean Range: +10mm to - 10mm |  |  |  |  | Yes ☐ No ☐ N/A ☐ |  |  |  | Each Lot |  |  | H | SE |  |  | H | [5 empty] | ☐ As-Built Reports
Comments:
Works complete (signer SS) | [5 empty] | Date works complete
Lot conforms (signer SE) | [5 empty] | Date lot closed | [9 empty] | NCR/s no. raised | [5 empty] | Date NCR closed for this lot
SGJV / Client Representative signoff:
Name Company Signature Date
Name Company Signature Date
Responsibility (Resp.) Key: PM-Project Manager, PE-Project Engineer, SE- Site Engineer, CS-Civil Superintendent, SS-Site Supervisor, SV-Surveyor, CR-Client Representative Inspection Key : W – Witness, H – Hold Point, S - Surveillance