## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | ITP - Foam Bitumen Stabilisation Rev 0 | itp | ITP - Foam Bitumen Stabilisation | 4216c747-4808-4716-ab13-9261e9574f94
| section | 1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING / DESIGN and DRAWINGS
| checkpoint | 1.01 - AP40 Basecourse Aggregates used for overlay (if applicable)
18f80137-e68d-5f5c-8e3c-ca8dd218f646 | note | Notes:
63f62e1a-54de-5249-8342-5bfc793549b4 | note | ○ H = Hold point up to approval of Optimisation Testing
e515b63a-06f1-5a2a-819a-21de548e0da6 | note | ○ M = Monitor during production
8ba08741-6723-598e-8a1d-6729427c1e68 | note | Detail of Activity / Test - Crushing Resistance
b7e509d1-a886-5812-a8f7-42034fc3db88 | note | Action (Hold, Monitor, Witness) - H
a7590362-aa7b-5de6-948e-b44b1989843c | note | Minimum Test Frequency - 1 per 10,000 m3
32c71017-990a-5bf5-9de7-a9d04804cf76 | note | Inspection / Test method - NZS4407:3.10
f7475d00-f999-571b-8ab6-29815cf4cdfc | note | Acceptance Criteria - < 10% passing 2.36mm sieve at 130kN
4bf3096c-f23b-548c-846d-4e08d38db8c2 | note | Record documents (QCP - Quality Control Portal) - IANZ report
09355c40-6154-535d-a995-37d28d98a948 | note | Responsibility - Contractor
9fd4437d-7613-5dc7-b9ac-2bf6e2e15efb | note | Designer - A
093dff5c-00af-559a-9a8e-5ddecae5949a | note | Eng. Rep - I
319d3c42-ecf9-55be-8851-48d2ab8ad5ad | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.02 - AP40 Basecourse Aggregates used for overlay (if applicable)
bf1c6484-4b5e-599c-aff6-4722bd752707 | note | Detail of Activity / Test - Weathering Quality Index
cdf1b233-2a1d-5c1a-b9c7-dd1bcb655c44 | note | Action (Hold, Monitor, Witness) - H
d838f44e-9a10-5cb5-b979-fd669fb2bab8 | note | Minimum Test Frequency - 1 per 10,000 m3
98a45d6b-e562-5ecd-8240-2dbf96931769 | note | Inspection / Test method - NZS4407:3.11
4d534a52-1dc6-57b6-950e-bad9018476bc | note | Acceptance Criteria - AA, AB, AC, BA, BB, CA
8786e057-2936-5946-b99d-128744a666e4 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
c1c867d9-57ac-5da8-8439-1f5e91066b83 | note | Responsibility - Contractor
91eb24c6-8534-57ff-b400-7787c152518a | note | Designer - A
04bdeb91-8204-5121-a78c-9fd9e57f7678 | note | Eng. Rep - I
c8c8c6d2-2d9a-5978-87e0-392a05228f96 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.03 - AP40 Basecourse Aggregates used for overlay (if applicable)
9255db96-2df0-5fc4-919a-6424bfc78c63 | note | Detail of Activity / Test - Calfornia Bearing Ratio (CBR)
f22f8524-43dd-5f8f-b417-136e8ffa5aab | note | Action (Hold, Monitor, Witness) - H
f6234824-4928-5d75-aedf-7c99101bfe98 | note | Minimum Test Frequency - 1 per 10,000 m3
e262af5f-9d8d-5b2d-ada6-ebcb322dca50 | note | Inspection / Test method - NZS4402:4.1.3, NZS4407:3.15
5e3fbcac-d352-59fe-b537-6d9b4966cef5 | note | Acceptance Criteria - Compaceted using NZ Vibe Hammer. 4-day soaked CBR ≥ 80%
1d78ceb9-6e31-5c53-89ff-cdbb31a7db45 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
5aef50e8-cbb7-5a16-a362-1d1db4d9b89d | note | Responsibility - Contractor
97770fd8-30f1-5601-a5f9-153470d59368 | note | Designer - A
5c6b9215-5943-5ccd-acb7-57ba5020552b | note | Eng. Rep - I
28355262-de83-5a0d-b325-40df4aacdeeb | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.04 - AP40 Basecourse Aggregates used for overlay (if applicable)
3b794877-a84b-54cf-86fd-87a89688ddbd | note | Detail of Activity / Test - Quality of Fines, either PI or SE or CI
26b4d3f9-9704-5640-809b-7c837883e26a | note | Action (Hold, Monitor, Witness) - H
e4dd5ad0-7a3f-58a2-9707-2d02a96332e5 | note | Minimum Test Frequency - 1 per 1,000 m3
7bf939e6-39e4-53a9-8246-e21f9ccc898f | note | Inspection / Test method - NZS4407:3.4 - PI, NZS4407:3.5 - CI
c62bca29-645b-569f-96ba-3bd3961f6e0e | note | Acceptance Criteria - PI ≤ 5, CI ≤ 3
26a6ec8d-2d6c-5ffa-96a7-65dd831857a3 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
c3084073-454a-5df3-b6c1-ed5878fb6d32 | note | Responsibility - Contractor
7c1a7ddd-ce91-5097-8355-e0884688f705 | note | Project Specific Notes / Instructions - NZTA M04: 2024
21c67299-4991-5c32-b249-dc198fba966f | note | ○ AP40 - Class 2
2399a71f-aec1-5630-b5c3-98c8fe71bbb5 | note | ○ PI and CI applies
2360a319-9a02-526e-a154-e55782c1fb31 | note | Designer - A
1be1bff7-974f-53e6-a650-aee76e365e8d | note | Eng. Rep - I
ba052500-e2ac-5b67-8310-32039e554e1e | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.05 - AP40 Basecourse Aggregates used for overlay (if applicable)
ac012d0f-bb6d-5169-83a2-b0b2697666db | note | Detail of Activity / Test - Broken Faces Content
e1443abc-af96-511e-be52-d2836221060e | note | Action (Hold, Monitor, Witness) - H
77224abf-986a-5b72-b5bf-f69505300d0e | note | Minimum Test Frequency - 1 per 1,000 m3
f26257c9-178c-5f01-9457-a072cf4425f9 | note | Inspection / Test method - NZS4407:3.14
0a0e3602-94e2-5d9e-b763-12297219ae7d | note | Acceptance Criteria - ≥ 70% more than two broken faces on aggregates between 37.5mm and 4.75mm
7574459d-092f-5a22-ba4d-29708eee3e85 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
0e0304e3-d493-5a75-ad79-5b12cdcdabcb | note | Responsibility - Contractor
d5374282-76f1-59a4-bdd6-335179be4766 | note | Project Specific Notes / Instructions - Waived if aggregate is from crushed hard rock quarry
e8659cf5-25dc-50ec-bedb-f450048094f6 | note | Designer - A
86a9969f-f5cc-534a-ba0c-fae22a39a84d | note | Eng. Rep - I
37863e21-fde0-5c47-8476-b74a51eb51f9 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.06 - AP40 Basecourse Aggregates used for overlay (if applicable)
57ef5a5f-ab5c-588e-b27b-80f51be2dc01 | note | Detail of Activity / Test - Particle Size Distribution
9096ced6-64c6-5b6f-9575-25131ca6e6b9 | note | Action (Hold, Monitor, Witness) - H
25a6395a-c35a-5f75-9680-e5b9a3cdd15c | note | Minimum Test Frequency - 1 per 1,000 m3
27010c02-9c84-5dab-9661-64ebadcbf27b | note | Inspection / Test method - NZS4407:3.8.1
eb97da68-39c0-50b3-afbc-b6d59a4d8224 | note | Acceptance Criteria - NZTA M04:2024-Class 2
0fdc453b-3b12-5ee2-a5bd-eec4e5b79cdd | note | ○ Class 2 in Table 12 for PSD
33bd8979-8bcf-5fd9-bbd1-75a043292645 | note | ○ Table 13 for shape control
670e0309-9409-5ea3-8f65-682ea97b4fde | note | Record documents (QCP - Quality Control Portal) - IANZ report
a8b69bd1-2bae-5440-9692-db15d5c5e051 | note | Responsibility - Contractor
332ae894-bb5b-5ac5-bc24-8357d5082de6 | note | Designer - A
ade5fb37-bf02-58e3-99d3-6d6af4522170 | note | Eng. Rep - I
39faaba5-6cde-5529-b619-614246175c6a | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.07 - Optimisation of Stabilising Agent(s)
4788fa12-5a60-5fb7-a6d2-064b9fcfcbe3 | note | Detail of Activity / Test - Blend Particle Size Distribution
7fb8e18c-949c-51ad-8d22-e78b78c8ec45 | note | Action (Hold, Monitor, Witness) - H
163cb6c7-e495-565a-9481-8c9ad5beed16 | note | Minimum Test Frequency - 1 per 1,000 m3
7ba0e458-8ec0-5f01-bea9-97d47ef6f5e1 | note | Inspection / Test method - NZS4407:3.8.1
523e76e3-a4db-5cdd-b1ed-0e226b960d90 | note | Acceptance Criteria - Check if average of existing (from TPs) and any overlay will meet the ideal FBS / BE grading.
f45f8321-7e38-5e03-b1bb-fdbba563ac7b | note | Record documents (QCP - Quality Control Portal) - Report using IANZ Reports for AP40 and TP PSDs
c44ee264-6945-5ad7-a465-b15c9b41e725 | note | Responsibility - Designer
ab299b4d-b18d-5b50-9a5e-b1f8cdefcee1 | note | Project Specific Notes / Instructions - Designer to advise if "average" blend is acceptable.
ec1d330a-2c28-501f-a77f-8c317478100a | note | Designer - R
2e1f689d-e116-534a-8de0-dbf7c83486db | note | Eng. Rep - A
5284631c-3d67-5cab-aa53-bbe60fb14be4 | note | Contractor - I
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.08 - Optimisation of Stabilising Agent(s)
ebdb1c69-d01e-542a-af29-cd00411caf01 | note | Detail of Activity / Test - Indirect Tensile Strength, ITS
665587d1-b012-5647-8432-1169cb2afaf7 | note | Action (Hold, Monitor, Witness) - H
8533d432-e1b2-5c15-b878-ef3a8320e208 | note | Minimum Test Frequency - 1 Optimisation test per aggregate type
9cef32df-05e5-5425-9134-7f9fd809a187 | note | Inspection / Test method - NZTA T/19: 2020
aee8a673-c0dc-59b5-b3f8-bb8c5cbb09b1 | note | Acceptance Criteria - Testing at 1mm/min:
83e4c2fc-c068-5a10-b192-d0ac196c3388 | note | – BSM Dry ITS: 175 kPa to 400 kPa
89ceb06f-fee8-5bb4-86c0-307e7d9a6b2e | note | – BSM Soaked ITS: 150 kPa to 350 kPa
93f088f5-fc9c-5369-a12c-1751ae58df14 | note | Testing at 50.8mm/min:
29cd1974-c2da-5922-baa2-88a4cbc5bac9 | note | – BSM Dry ITS: 210 kPa to 480 kPa
c7f4d48b-4d9a-5019-b34b-d5df5e927170 | note | – BSM Soaked ITS: 180 kPa to 450 kPa
10701e9b-4f55-5051-a90f-e0ac4b568bd8 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
60da5b29-93a5-5fd4-ad2a-50b37eaf9563 | note | Responsibility - Designer
bcde9021-98e3-5671-8fc5-f03d357a8502 | note | Project Specific Notes / Instructions - Designer to advise on binder content(s)
3099dab8-2269-5c01-b6a6-93baf5f52ba5 | note | ○ Note that the min.design ITS is as per T/19 Notes + 25kPa to ensure that the min.ITS values are obtained in the field
4977ef22-2307-5a9e-941b-61e061656386 | note | Designer - R
6cd28c56-679b-5bea-bbab-56309ae50f81 | note | Eng. Rep - A
598789f9-63c4-5992-a9a4-eed0e68c131f | note | Contractor - I
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.09 - Optimisation of Stabilising Agent(s)
721b9694-e710-5062-a80a-2c1a80b7e893 | note | Detail of Activity / Test - Unconfined Compressive Strength, UCS
39bdd341-c01e-55b9-afeb-4829d9188ed0 | note | Action (Hold, Monitor, Witness) - H
898403a8-f1ab-5ede-b6b3-be8830b07c14 | note | Minimum Test Frequency - 1 Optimisation test per aggregate type
cd0ea3a3-dc21-5660-94b5-e5700441918e | note | Inspection / Test method - CCNZ / NPTG / CETANZ Industry Guide
eb69fde7-e6dd-5ded-9fa7-6a546d982673 | note | Acceptance Criteria - UCS limits set by the design engineeer
ce11192f-f779-5859-8e34-89eb156ba096 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
f007fd1b-4641-5084-ae1a-e95076be6a89 | note | Responsibility - Designer
42802bee-c58c-5872-a616-2f19e1393d2a | note | Designer - R
9dae86dc-7376-5177-8d7f-5f509797a55f | note | Eng. Rep - A
58ed924f-d949-5ef1-8aa7-c5bbfe1fdaff | note | Contractor - I
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.10 - Optimisation of Stabilising Agent(s)
940f8bac-e707-5c09-921d-bfc2384abc8c | note | Detail of Activity / Test - Modified Maximum Dry Density
cbc6c9a2-98ec-5d4a-9fcc-c8405a95e72c | note | Action (Hold, Monitor, Witness) - H
ba0a952b-8b1e-5900-b5d8-c96c58f6f379 | note | Minimum Test Frequency - At Optimised Binder selection
612965e8-1945-55f3-bbbe-1bd8f3e3f032 | note | Inspection / Test method - NZS 4402.4.1.3
f1bae931-f2bb-5e7a-8290-8f5e3f8b6929 | note | Acceptance Criteria - To determine target density
3dae57ad-629a-57de-8d75-41d373c95675 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
330630e0-7f68-5251-b816-28e36f0f854e | note | Responsibility - Designer
a092c365-e7e3-5f3d-8b5a-2e4183ebdebf | note | Project Specific Notes / Instructions - Required before Stabilisation comences
b54dc74d-7779-5a9c-9438-9cc5cc5bf1b8 | note | Designer - R
b6370a95-48c9-50fd-bbcb-9b46560931af | note | Eng. Rep - A
2ca0aa22-3040-5e37-b75f-e429cd9a6bd1 | note | Contractor - I
| signoff | AUTHORITY HOLDPOINT
| section | 1.1. CREW PACK
| checkpoint | 1.10 - Design Report and IFC Drawings issued
5503c545-236c-5086-9a2a-9ef8d175585a | note | Detail of Activity / Test - Confirmation by Design Lead
4cda2e35-5625-549c-b4fc-12ac2e38420a | note | Action (Hold, Monitor, Witness) - H
05c24fd8-63d0-51ea-b750-f41ea2aff2ae | note | Minimum Test Frequency - 2 weeks before works start
cf4e5707-f2b2-54a6-9074-2e298233362c | note | Inspection / Test method - N/A
dc58bba4-4e49-59d6-80c9-ca31437f9093 | note | Acceptance Criteria - PDR and Drawings approved by NZTA-SME
4948c31e-6e15-59b6-b3b5-dc80229427ec | note | Record documents (QCP - Quality Control Portal) - PDR and IFC Drawings
94af590f-f1d6-53d3-adeb-80ed6538f71a | note | Responsibility - Design Lead
ebe24c54-1388-5b5b-8d9e-d8bed8aba77c | note | Project Specific Notes / Instructions - Due to the nature of the acceleration works the 2 weeks may be the Rev.B "For Construction Review". IFC may be 1 week ebfore works starts
54c00f0d-938f-5c09-a706-695444bd1d50 | note | Designer - R
a2d57149-155f-5242-aa8d-82689d49c37e | note | Eng. Rep - A
2753f7cf-9e9f-5718-8ff0-d7c74bbcfacf | note | Contractor - I
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.11 - Approved TMP
9f467806-3159-5af2-b225-c579ce379a68 | note | Detail of Activity / Test - TDS
9175d3c1-8949-512c-87ba-fbc4f3ac627a | note | Action (Hold, Monitor, Witness) - H
6d81d04d-d8d1-5ae3-8178-e344ab519238 | note | Minimum Test Frequency - 1 week before works start
a928c16f-72fb-511c-8e2d-3a187494bb99 | note | Responsibility - Contractor
768404a0-9738-58ad-8d7a-aeb13cef32b0 | note | Eng. Rep - I
f78d0855-d955-55f5-a61d-56dbe1bc4a35 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.12 - Service Location plans in supervisior's vehicle and marked out on site
9b17c858-2b0e-5253-8e3e-02053ecac89a | note | Detail of Activity / Test - TDS
74d6f143-a04f-5c09-bc9c-3dd499e230c3 | note | Action (Hold, Monitor, Witness) - H
3b1bde94-58f1-5a3b-8af3-d126da6fa12e | note | Minimum Test Frequency - 1 week before works start
6d8c2097-96f6-5aaa-919c-7fc3f6bed7ae | note | Responsibility - Contractor
350d29a6-b7fa-5249-80ee-43765a6d66c1 | note | Eng. Rep - I
b123970f-69ac-59a1-a25c-91ebefca937e | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.13 - Approved RQP
b0ab40e4-4565-5e9d-9eb6-1571909bf054 | note | Detail of Activity / Test - TDS
9b7edd25-1cf8-5d8d-aef5-4d7d34ece52c | note | Action (Hold, Monitor, Witness) - H
e9c0e512-e822-51fc-b723-ca0c152525ed | note | Minimum Test Frequency - 1 week before works start
83e44b87-989c-541d-828c-3302cb775602 | note | Responsibility - Contractor
41f5c28b-80a2-5b0f-aa84-bb9dba3a1f30 | note | Eng. Rep - I
f1275cb9-7ba3-56e4-a3ad-c94a93c08b4d | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.14 - Approved ITP
c88f46f4-9b2f-50a6-9868-444a3ece7114 | note | Detail of Activity / Test - Confirmation by Design Lead
b9993c6e-7ac2-5ed4-b9b1-353d3af51dc3 | note | Action (Hold, Monitor, Witness) - H
6270319b-f55b-524e-af90-242ba3c28197 | note | Minimum Test Frequency - 2 weeks before works start
67514f1c-8ab9-5984-bb72-f2823bec332d | note | Inspection / Test method - N/A
0b27e45f-6a65-524a-a258-9810d5ec6f8c | note | Acceptance Criteria - CW-AWP-ITP
5e35123e-a6a0-55e8-9e2c-1535e238505a | note | Record documents (QCP - Quality Control Portal) - PDR and IFC Drawings
e69c4322-5ca0-57a1-ac7f-eb500f102545 | note | Responsibility - Design Lead
656d98c3-2a77-5b4d-a56f-3bd921583878 | note | Designer - R
18816b2d-b703-5d7e-9726-f2243c11a783 | note | Eng. Rep - A
ba87b00b-acb6-5be4-b167-934694441ab4 | note | Contractor - I
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.15 - Daily Crew biefing Plan
10225b80-000f-5530-9255-23ebbe603d0c | note | Detail of Activity / Test - TDS
38077387-444c-5543-9605-6a236b33550e | note | Action (Hold, Monitor, Witness) - H
6ecc0ac6-61e1-5b71-98e1-227183f6dd3a | note | Minimum Test Frequency - 1 week before works start
4a74b284-763c-56d4-a765-d5a515d45dc3 | note | Responsibility - Contractor / Stabilising Contractor
45dd7a92-e691-5c8e-b9c9-c239abea42a6 | note | Eng. Rep - I
39b00969-aa55-5a84-b424-9c92c32d019c | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| section | 2.0. BEFORE BITUMEN STABILISATION STARTS
| checkpoint | 2.01 - Setout section
0dbff9f2-390e-5e5c-ae14-28fa66830360 | note | Detail of Activity / Test - Install offset pegs / check geometric model; record centreline, edge line or mark out stabilisation extents from existing line marking
fc7ac0fe-7a88-53f9-b954-1038fb8f93c7 | note | Action (Hold, Monitor, Witness) - H
c700c526-fd80-51d3-b34f-372683c2e32e | note | Minimum Test Frequency - Prior to each section
fbd49f1f-77ac-5d0e-9665-40e55ac532b5 | note | Inspection / Test method - Survey
48e06446-e385-5192-86fd-2a9cf603fc7c | note | Acceptance Criteria - Document existing furniture
a2b6b9e3-4e65-57f6-ae09-cb18f5a18ed5 | note | Record documents (QCP - Quality Control Portal) - Electronic survey files
6ea0c2bf-b92c-5759-9d5f-39211aec11ad | note | Responsibility - Contractor
512e470b-4707-565c-a86e-fd6c9c75e240 | note | Eng. Rep - I
b06d9329-25ee-58b6-abda-6c7c196afb2f | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.02 - Pre-hoe, shape and proof roll
402421b5-2308-5d65-9cb9-f984203b6534 | note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
95f01f37-0ec2-5512-a941-0ce45dc89dc7 | note | Action (Hold, Monitor, Witness) - H
2f72053d-5143-569c-a3e4-cfe42e383cef | note | Minimum Test Frequency - Prior to stabilisation per section
e0b4c527-5ebf-551a-b504-c5d4fdb3de1f | note | Inspection / Test method - Use grader's machine control and inspect shape
263ae599-8acb-5480-9680-809fcdd5cea2 | note | Record documents (QCP - Quality Control Portal) - N/A
be594c3c-d332-5708-8ce0-1b9cc6766a36 | note | Responsibility - Stabilising Contractor
957498a6-7989-5738-9641-0cddc905d031 | note | Project Specific Notes / Instructions - Intention is to carry out only minor correction (eg.2% to 3%). Any major shape corrections to be identified prior to site establishment and included in the site specific methodology statement
7b5aaaa1-89f9-5167-b5df-3ce461fd93e6 | note | Eng. Rep - A
d8f731ad-7423-59f3-bd20-e0f92f45a86a | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.03 - Pre-hoe, shape and proof roll
a3fbcd5b-a232-52c1-9056-7fe1c7bf441f | note | Detail of Activity / Test - Pre-hoe to depth specified and shape as instructed in the site spcific methodology statement and/or IFC drawings and proof roll while compacting
e38cf73d-65ac-5107-a777-aa81c16f700e | note | Action (Hold, Monitor, Witness) - H
010c6124-a937-57c5-ac00-4238e7bb0912 | note | Minimum Test Frequency - Prior to stabilisation per section
0dd0fd40-43ba-5d2b-a5c3-5d81b5d590a9 | note | Inspection / Test method - Visual check or Vibratory Roller's response meter
5fce98c4-3384-5021-8f49-965660edc5e6 | note | Record documents (QCP - Quality Control Portal) - Stabilising Contractor confirm no obvious soft areas found
5d4010a6-b442-5d1c-8eb0-8310a88c0beb | note | Responsibility - Stabiliisng Contractor
662c91b4-0b69-55d3-a4ab-edfa71bc1f24 | note | Project Specific Notes / Instructions - Any soft spots identified by visual means or that show up as significantly different to be raised with the ER for further instructions
378f092b-243d-54e8-a61a-75adc453b3f3 | note | Eng. Rep - A
ee1dc0c2-8309-5ae6-a089-36b4f72005c4 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.04 - Overlay and check levels
838c7956-7499-5ce4-9cb6-7a1cc11bde35 | note | Detail of Activity / Test - Supply, pre-compact and trim to line and level with NZTA M/4 AP40
2d0d9dbd-ca0d-579c-9cc4-ac82d69739d4 | note | Action (Hold, Monitor, Witness) - H
e6e7c339-5c76-50b2-9912-42d7893b973d | note | Minimum Test Frequency - Prior to stabilisation per section
976b9fc3-5a84-57dc-8729-cf15f5f8891f | note | Inspection / Test method - Survey
5a6c0b0b-2937-510f-b543-7d3e3cf6f1e1 | note | Acceptance Criteria - As per NZTA Z/16
f596977a-2c38-5946-b18c-e87bb99db33d | note | Record documents (QCP - Quality Control Portal) - Check with Grader and visual inspection
095aa0db-9e50-55ae-bd4d-bc714e0f54cf | note | Responsibility - Stabilising Contractor with Main Contractor
8cc65c3c-081f-5992-8f60-b942f06880f5 | note | Project Specific Notes / Instructions - This is the last opportunity to check items before adding the FB. Assess items such as (but not limited to):
12412c0d-6cd2-5d34-972d-4a638ed03f67 | note | – overlay aggregate quality / consistency
d56a7cdc-17c9-50be-bbec-67c64dc6bdb8 | note | – moisture content
70f37098-afb4-5a33-bca8-6ab0b70c9649 | note | – any concerns with shape and tie in
921cec00-fbae-53fd-9bdb-2844e443539a | note | – etc.
8b670e4f-f16a-5e39-b6ec-0ab7e82419cc | note | Eng. Rep - I
765f9f45-d3b4-5e33-a623-b75202d28347 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.05 - Production Plan
49d65c49-264b-5cc9-87fd-19518739a642 | note | Detail of Activity / Test - Plan showing cut lines and sequencing of works
0043d545-ecb5-5d69-9e9f-99cc3f136896 | note | Action (Hold, Monitor, Witness) - M
e1d47ff8-3304-5811-8258-7151d076cd04 | note | Minimum Test Frequency - Prior to each section
6c67a253-1f51-59e7-92ea-540cbe70f5aa | note | Inspection / Test method - Daily Report
cf727e2e-07a3-54b9-88aa-8e6adc658792 | note | Acceptance Criteria - Points covered in NZTA B/5
e013f3bc-804f-5690-91bd-29c5e4c537ee | note | Record documents (QCP - Quality Control Portal) - Daily Production Plan
4fc522d8-7deb-5a0b-9227-7fd1b4d4d222 | note | Responsibility - Stabilising Contractor
56801c39-85a7-502a-b965-d5b9b093233c | note | Eng. Rep - I
166f3b7f-bacf-5010-8d5e-498822b73bbd | note | Contractor - R
| checkpoint | 2.06 - Weather conditions
2663b87f-4d5d-50cd-b3e7-102e48276da4 | note | Detail of Activity / Test - Material behind stabiliser
22e3a961-8940-5b56-991e-ffb0badb382b | note | Action (Hold, Monitor, Witness) - M
6d333c2f-c0af-50b4-8e19-819d50993299 | note | Minimum Test Frequency - Prior to spreading
a6b8573e-4edb-5f56-9623-81d09acceb81 | note | Inspection / Test method - Measurement
96ee3487-c38e-577d-bef2-d2ecb1d62cf9 | note | Acceptance Criteria - Material after stabilisation:
bd58cbcb-1da1-559c-961a-41ca2227d12e | note | ○ BE: > 20°C, FB: > 20°C and Ambient: >5 deg.C
6f481e4d-d648-5ecf-9fc3-556df64e3fed | note | Record documents (QCP - Quality Control Portal) - Daily work Log
1b9b237a-927d-5e06-9566-e4a631b806d9 | note | Responsibility - Stabilsing Contractor
923adf05-7ffb-52cf-b9e5-bca5c1fae2b2 | note | Eng. Rep - I
6247681b-6f87-5748-8404-ddb53ada6a60 | note | Contractor - R
| checkpoint | 2.07 - Weather conditions
9563956e-0fe0-5762-a384-90ac0a045f99 | note | Detail of Activity / Test - Wind
95e1caa9-ae5b-5a86-83f9-db39182a9989 | note | Action (Hold, Monitor, Witness) - M
f218d500-f698-5992-bbdf-689dfab17957 | note | Minimum Test Frequency - Prior to spreading cement or lime
4d296803-dff7-57b1-9bf2-0c31a1d7757b | note | Inspection / Test method - Local weather stations
0d4874d3-f009-5a6e-a4ac-f4e01fcbcd61 | note | Acceptance Criteria - Wind speed < 25 km/hr
81aa49cd-bf34-584d-a618-81cd56c9890a | note | Record documents (QCP - Quality Control Portal) - Daily work Log
0aba85e3-d363-50a7-b23d-a1f7375c62ac | note | Responsibility - Stabilsing Contractor
ce04b340-fde8-5911-afde-5909831b85ca | note | Eng. Rep - I
4653041e-03db-5f2d-878a-1a2fde7af1af | note | Contractor - R
| checkpoint | 2.08 - Weather conditions
ea1e3f9c-6f80-5b3b-9bf2-183306c39e98 | note | Detail of Activity / Test - Rain
3136168d-bdf9-56e3-84bd-eef7f5e0a86d | note | Action (Hold, Monitor, Witness) - M
271e6c91-5ccb-5823-981e-120418c740c8 | note | Minimum Test Frequency - Prior to spreading cement or lime
0fd699ba-bbe0-5592-aacf-25a5f47b6a44 | note | Inspection / Test method - Local weather stations
15fdf81f-439c-5095-b851-1442f765a758 | note | Acceptance Criteria - No spreading of cement / lime if it is raining or likely to rain before these can be mixed in with the material
34c5afad-c61c-5477-9de6-38a93cded489 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
c7db969c-6876-5e1d-8ac2-95a62365d73d | note | Responsibility - Stabilsing Contractor
35fa5507-9f93-511d-a089-62448048f9eb | note | Eng. Rep - I
9df9aa7e-c806-5392-8b1c-a3bc2d315a7d | note | Contractor - R
| section | 3.0. BITUMEN STABILISATION OPERATION
| checkpoint | 3.01 - Stabilising Agents
80ec0980-9deb-5626-9672-574a6e0b15a7 | note | Detail of Activity / Test - Lime (if applicable - check PI delete otherwise)
4c127c3e-e5cd-5c2a-944e-9abf5f515cd6 | note | Action (Hold, Monitor, Witness) - M
0a11c16b-b254-53e3-9c95-2bcd9bcfee64 | note | Minimum Test Frequency - Per Batch
0b43d063-9c96-5b00-98b0-84ba61fe9709 | note | Inspection / Test method - TNZ M/15
d22615be-c504-5adb-9813-ee4beb742799 | note | Acceptance Criteria - Conform to Specification
3341189e-61d4-57f9-97ed-c4528d237757 | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
e718f248-ee0f-5879-a277-4cbd07196665 | note | Responsibility - Stabilising Contractor
1fdb5e7b-6238-577e-8edb-c5263e2b1b49 | note | Eng. Rep - I
c902081b-0b2d-5767-8a3c-e016c2950a59 | note | Contractor - R
| checkpoint | 3.02 - Stabilising Agents
51c5894b-0254-58dc-b42c-22059e3ab49a | note | Detail of Activity / Test - Cement, GP
0bb7c6a9-fae5-5c02-8c8c-b187d8be4f89 | note | Action (Hold, Monitor, Witness) - M
6b96f722-aad5-5751-93ca-e419d2573a53 | note | Minimum Test Frequency - Per Batch
4783e56c-34c7-57fd-9ecb-37423a55c3c8 | note | Inspection / Test method - NZS 3122
8ca825cd-f03e-5cb0-99b7-146accdf6530 | note | Acceptance Criteria - Conform to Specification
8cca7fa6-53e3-5f85-914a-600a7a282d0b | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
0acda1e1-a79a-5940-a36f-44e9b0abcf40 | note | Responsibility - Stabilising Contractor
99cc58fc-8b7b-5874-8890-ab7db502e36a | note | Eng. Rep - I
5c375b39-3370-5f0c-9888-ed73ca9ba29f | note | Contractor - R
| checkpoint | 3.03 - Stabilising Agents
d42d78bd-e52e-5378-8ef2-d8eb7850d33c | note | Detail of Activity / Test - Bitumen (130/150)
33c9f1ff-ff44-57ed-ad9d-d665643f3a63 | note | Action (Hold, Monitor, Witness) - M
3dd0bd95-4040-543b-b2f7-c89837edb81c | note | Minimum Test Frequency - Per Batch
dcbef890-2069-5f35-8b10-8430fbdb7bdc | note | Inspection / Test method - M/1
54d7cca4-8d56-572e-8ddb-b5cb1b9841e0 | note | Acceptance Criteria - Conform to Specification
4cb970ac-7b18-5da1-8d03-8ebcd6f75bda | note | Record documents (QCP - Quality Control Portal) - Certificate in contractor's site folder
779dbf98-36df-51f9-ac34-d262d084c0a6 | note | Responsibility - Stabilising Contractor
9677bb4d-0039-58d5-b016-a0dfc5712b1d | note | Eng. Rep - I
e390d0db-3da4-5d66-879e-4e94d714a075 | note | Contractor - R
| checkpoint | 3.04 - Spreading of powdered stabilising agent (Cement / Lime)
ca53ae61-d148-5518-b6a1-855c008e13ed | note | Detail of Activity / Test - Place 1m2 canvas or 0.5m x 0.5m trays along spreader run
725acaab-a773-586a-98aa-7c2cd64595fa | note | Action (Hold, Monitor, Witness) - M
00339805-4c74-5e72-a6a6-d2e4e0ffaf9e | note | Minimum Test Frequency - every 400 m2, every 150m for a 2.4m width
c30c0a37-e778-5f61-9641-c1b15f893330 | note | Inspection / Test method - Weigh mat or tray
00e8e12f-118b-5516-b70d-dd85575eb191 | note | Acceptance Criteria - ± 0.5kg/m2 of specified rate
9d4211c0-352c-5b48-9fde-ca32018e5eb1 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
39a32729-269c-5ed2-9d68-fcfa2935955a | note | Responsibility - Stabilising Contractor
ac2c00ca-10cb-51a1-a1ea-f65f295df1a6 | note | Eng. Rep - I
c0b46075-542d-5631-9a28-50714511776f | note | Contractor - R
| checkpoint | 3.05 - Spreading of powdered stabilising agent (Cement / Lime)
7cf7225b-f607-5cbb-94c7-f48cdb979918 | note | Detail of Activity / Test - Compare area spread with weight used for each spreader load
91f38495-f877-57ed-af03-cfa07fe54c84 | note | Action (Hold, Monitor, Witness) - M
4088e1c6-24ba-5558-a06a-b211e9285128 | note | Minimum Test Frequency - On-going measurement by computer/load cells
133da87e-54d7-5108-b837-c48c04ebbfe5 | note | Inspection / Test method - Measurement each run
24ce8686-d6f3-513f-b6d8-0691ba5e100a | note | Acceptance Criteria - ± 2.5% of specified rate
14666f4c-b608-59b0-a103-5ee7f6e6b1f8 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
dc21e9ad-ea6a-58fd-ac75-9d3f1f12048c | note | Responsibility - Stabilising Contractor
d039a6d6-9648-5632-a6d8-d0f3c8b1a9b0 | note | Eng. Rep - I
31fb1831-3873-5dd4-8c5b-32530b603087 | note | Contractor - R
| checkpoint | 3.06 - Injection of bituminous stabilising agent (FBS or BE)
b8679352-82c8-5fb1-87a2-00ec72e375e2 | note | Detail of Activity / Test - Flow meter and operator's display readings
999de91f-8ceb-5744-a9df-d331393a58ec | note | Action (Hold, Monitor, Witness) - M
dfb45a6c-1392-5468-93ae-591724101e62 | note | Minimum Test Frequency - Continous monitoring by the operator and the grounds person
65ef9279-275f-5254-b60f-67c24f281272 | note | Inspection / Test method - Visual display reading
08a34080-08d5-5c6a-8504-2cea3116c900 | note | Acceptance Criteria - ± 5% of specified rate
58d5cc78-3e05-5935-877f-0cbdc770c4c4 | note | Record documents (QCP - Quality Control Portal) - N/A
e278918b-3198-5659-8d29-19a93e774fb2 | note | Responsibility - Stabilising Contractor
8ae57fa4-8722-5c3f-9606-1f05799a384e | note | Eng. Rep - I
1dd6c462-d72c-57f9-9350-4912b9b88337 | note | Contractor - R
| checkpoint | 3.07 - Injection of bituminous stabilising agent (FBS or BE)
9d69f787-1161-5116-b9e0-f16c4a1b0e7a | note | Detail of Activity / Test - Compare tonnes used (from the stabiiser's PCU) with the measured area
27f26676-ca58-59c7-b5e4-581fb58b1190 | note | Action (Hold, Monitor, Witness) - M
6f2008c8-59d7-58ca-bc7b-c0677c5fbc19 | note | Minimum Test Frequency - Record usage from PCU at the end of each run
4511f13a-5bd1-57e0-84af-39b5d0cced4a | note | Inspection / Test method - Record readings at the end of each run
5b84a9a7-76bd-5be3-a9ce-2f2457f10fd4 | note | Acceptance Criteria - ± 3% of specified rate
cab883fd-b432-5784-a4c2-acd3c37cad67 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
13392ee7-71ed-525e-af4a-38282bed8dd4 | note | Responsibility - Stabilising Contractor
b76c5f04-ee08-52e6-9ff6-19548a1570e1 | note | Eng. Rep - I
12da839e-c8fb-5d2a-95eb-2a241580fb80 | note | Contractor - R
| checkpoint | 3.08 - Injection of bituminous stabilising agent (FBS or BE)
c82453a2-f00e-5e02-b42a-d76452c57008 | note | Detail of Activity / Test - Compare tonnes used (from delivery docket) with measured area
62fe8e27-d58c-55f7-b160-8d53a8981092 | note | Action (Hold, Monitor, Witness) - M
205c65b6-218b-56f3-8836-e5041f5d877e | note | Minimum Test Frequency - For each bitumen tanker load
4edf933c-b8a5-57de-9f31-25baf14d5704 | note | Inspection / Test method - Dip bitumen tanker before and after
26142db5-d591-5af3-b0bd-e0ca299c3539 | note | Acceptance Criteria - ± 2.5% of specified rate
90af0b53-3912-5a2d-a63e-7c73bc313cb0 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
5d18f4e2-1d5a-5a77-b433-09b1859bb2e4 | note | Responsibility - Stabilising Contractor
c7b86ee6-498a-5661-a52f-a8504c3adddf | note | Eng. Rep - I
ef2f3aa0-4555-5b94-aac9-ad48c0898dc6 | note | Contractor - R
| checkpoint | 3.09 - Injection & Mixing of Water
c1900c7e-062c-5c44-b913-24f65d0e5540 | note | Detail of Activity / Test - In-situ Stabilisation process
2d38fb89-1419-5e0a-8c25-411b1bc6634d | note | Action (Hold, Monitor, Witness) - M
737c8b43-ca6f-5f69-a2ae-38a5980fc46d | note | Minimum Test Frequency - On-going visual assessment
14486130-e9c5-58ea-9bc8-76e865013550 | note | Inspection / Test method - Visual and hand squeeze test
7e982c05-5894-5a45-9f1a-57b80a0ce4a9 | note | Acceptance Criteria - Mixed material free of pockets or streaks. Overlaps minimum of 150mm
aa936270-31ce-5792-a635-565f345f50a3 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
71789ec3-cbbd-5ee7-b147-9412c853df9a | note | Responsibility - Stabilising Contractor
c446985c-94a7-58d1-a14f-f78f9dbb8909 | note | Eng. Rep - I
20f24a66-c491-5077-b2cf-30fc0d890a8e | note | Contractor - R
| checkpoint | 3.10 - Depth of stabilisation
3141b0f4-2655-52a6-a1e5-496067de13b8 | note | Detail of Activity / Test - Depth of stabilisation
2ff7c912-5ad5-5de1-8af3-d40cfee7ab23 | note | Action (Hold, Monitor, Witness) - M
e87536f7-3332-5dd0-8d6b-e135c31ce10a | note | Minimum Test Frequency - Every 200m
5ae96c7c-24bd-52ad-8a8e-563229f4136f | note | Inspection / Test method - Measurement
2a8422f6-a9d8-5a2c-8fbc-e7280541c40a | note | Acceptance Criteria - +15mm / -5mm from specified depth
5818d298-df63-5be2-8240-3767c6b39705 | note | Record documents (QCP - Quality Control Portal) - Daily work Log
74e892e3-b2f7-540a-abaf-edf468e0c296 | note | Responsibility - Stabilising Contractor
9290dfca-a473-5aca-9215-e3e82665d107 | note | Eng. Rep - I
4fb66193-a01d-569a-85d4-c5639e9f9c0a | note | Contractor - R
| checkpoint | 3.11 - FBS material
749a4c15-833d-5d54-bee9-8f5d5db8f401 | note | Detail of Activity / Test - Stabilised material strength - ITS
e98e541e-2087-51f7-94d5-6af4dac58f0d | note | Action (Hold, Monitor, Witness) - M
21859f99-6ae6-5110-9383-ee5e78117154 | note | Minimum Test Frequency - 3 soaked ITS + 3 dry ITS per Lot or when the material changes
13dffcc0-80eb-53e6-988a-eb9ac30f199f | note | Inspection / Test method - NZTA T/19N: 2020
8f42db1d-78ac-55e9-a3e1-948ac74a902f | note | Acceptance Criteria - Testing at 1mm/min:
d77db120-1624-5ebb-a252-5ce3bd098f1a | note | – BSM Dry ITS: 150 kPa to 400 kPa
ab36866f-7c69-58d9-8616-b53d8a41ed35 | note | – BSM Soaked ITS: 120 kPa to 350 kPa
eee75f91-085b-5261-9df5-91cb407fbe92 | note | Testing at 50.8mm/min:
0117bd5f-90d6-51f9-ac74-cf9bf13dd1f0 | note | – BSM Dry ITS: 180 kPa to 450 kPa
4d41ce67-cd6e-5fb1-82ae-9bfb644cb4b4 | note | – BSM Soaked ITS: 150 kPa to 420 kPa
693967ee-eaf7-5f7c-a72e-150e1c1af251 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
035c3097-2e55-5303-befe-aeb1a672b4d1 | note | Responsibility - Stabilising Contractor
12a2b8b0-d8a0-534f-a5fa-33fe0057ce7e | note | Project Specific Notes / Instructions - ITS briquettes to be produced on site if travel time to lab > 30 minutes.
b4caadc9-3ecd-5acf-99d5-12fd6954c64e | note | Designer - I
9a3e5477-ba54-58bd-aeaf-72f4fffdb551 | note | Eng. Rep - A
eea998a8-7dc9-56b3-8d29-0dffe5c57412 | note | Contractor - R
| checkpoint | 3.12 - Compaction
8151ca3c-7b12-54e0-86e7-86e67075a467 | note | Detail of Activity / Test - Plateau Density Test
f3b1872e-7e04-523b-9134-8bb9449ffc98 | note | Action (Hold, Monitor, Witness) - H
945be50a-1952-5092-8b85-cfdd1e61e553 | note | Minimum Test Frequency - On first day per site and then 1 per 10,000m2 unless material or anvil conditions change
40ec1008-ac91-5214-b623-26cbcb2cf922 | note | Inspection / Test method - Draft NZTA T/24 (Aug-2024)
2957020d-bc4e-541c-b2c6-20dd42f14331 | note | Acceptance Criteria - To establish suitability of rollers and compaction mode / pattern to achieve FBS-MDD
7ac11a80-a46f-54fb-9f37-94d22f8bf9ab | note | Record documents (QCP - Quality Control Portal) - Field PDT sheet photos into ConQA for ER and Pavement designer to assess. IANZ report when processed.
e017369d-d680-573b-977e-68f15fa30122 | note | Responsibility - Stabilising Contractor
c7bac0f2-55d8-5b4a-88a0-f174fea7e3a1 | note | Project Specific Notes / Instructions - If FBS-MDD can't be achieved then the PDT-MDD must be approved by the ER
dd7da7b0-fcc4-5df0-b15b-9843dde92bd8 | note | Designer - I
598974eb-0c9d-5e0b-8d95-ae2cbb780bb7 | note | Eng. Rep - A
a1844855-0225-5299-ada1-4dedbce1f532 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.13 - Compaction
48c99337-430b-553a-aeb3-8c831c0292aa | note | Detail of Activity / Test - Maximum Dry Density
5358390d-0906-580e-8853-bc0f1e2703ba | note | Action (Hold, Monitor, Witness) - M
a134d446-92f1-50ff-b7ad-ef23b1a8569b | note | Minimum Test Frequency - On the first day on a new treatment section, then 1 per 10,000m2 unless the material changes
f0bdee3c-4fb1-558e-8c28-38526ff71c15 | note | Inspection / Test method - NZS 4402.4.1.3
86bb6348-4e39-5a53-9ec3-fd983239e746 | note | Acceptance Criteria - For analysis of DoC. To be done at the sampled MC, at hand squeze test MC and 1% above the hand squueze test on site.
0c05b386-f225-50f0-a631-90ad1bb24b7a | note | Record documents (QCP - Quality Control Portal) - IANZ Report
30517d53-793c-5c75-a918-6d2453179191 | note | Responsibility - Stabilising Contractor
f45ebd07-a5bd-5d65-8e66-a0d514686407 | note | Project Specific Notes / Instructions - MDD briqutte to be produced on site if travel time to lab > 30 minutes. Note that if the Stabilising Contractor notices changes in material then another one point DD at the hand squeeze test moisture content shall be carried out.
f92c386f-2b4b-5c3d-9327-aa87b52e9c9b | note | Designer - I
79c03412-1dea-5684-894b-d15c9e6bb727 | note | Eng. Rep - A
755e2729-d5cd-5841-962f-92c29981d721 | note | Contractor - R
| checkpoint | 3.14 - Compaction
56c7628d-37d4-5212-9923-124979305093 | note | Detail of Activity / Test - Degree of Compaction (DoC)
259fe430-69dd-52e5-8a7a-a3c3466ee64e | note | Action (Hold, Monitor, Witness) - H
2dc5a5e6-7bef-5b03-807b-1479656a8e74 | note | Minimum Test Frequency - 5 per 1,000m2
55c275d2-72be-55b8-bc5e-ec93a8a0ff81 | note | Inspection / Test method - NZS 4407.4.2.1 (DT full stabilising depth)
4d823151-5a62-5132-8f7b-4aef7decc854 | note | Acceptance Criteria - Average DoC ≥ 98%, Minimum DoC ≥ 95%
4d011f6e-7667-5778-845b-1ac86a441a78 | note | Record documents (QCP - Quality Control Portal) - IANZ Report
7dcf4b69-48a0-531b-ba3c-2bcbf54b2d1b | note | Responsibility - Stabilising Contractor
4fdbad26-4619-5c78-81c4-6deb6468488f | note | Designer - I
7939fe38-9676-5bd8-9563-129b7e0fcf68 | note | Eng. Rep - A
4796d8d4-3c89-54d8-a445-6709679bc869 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.15 - Finished Pavement
39ae77e8-168c-5402-988a-f47e93dff702 | note | Detail of Activity / Test - Crossfall
239320c3-9be2-58c8-b38e-edc4832df94b | note | Action (Hold, Monitor, Witness) - H
2f7feb26-88cf-5705-b8aa-8e0626ca73bd | note | Minimum Test Frequency - every 20m
277bf509-3e30-5bae-8163-6ccc69c962bd | note | Inspection / Test method - Measurement
9fdd6742-9e2c-5249-9c46-8f399b1b6ad8 | note | Acceptance Criteria - ± 0.5% of specified crossfall measure, 2m apart
133907ec-f3b3-52c0-848d-3a4759096c7f | note | Record documents (QCP - Quality Control Portal) - Survey
01d18fca-1713-56a6-8dc5-61e0c5e14d09 | note | Responsibility - Stabilising Contractor
2137e37c-6fd6-5bd6-8746-b8acd976fc4d | note | Eng. Rep - A
431063b4-68a0-5e08-b15f-e89fcc2707e3 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.16 - Finished Pavement
a7ce0724-1c6d-5e3a-a645-5a397276186c | note | Detail of Activity / Test - Stabilised width
c203ee22-730d-5d52-9a20-add681de2317 | note | Action (Hold, Monitor, Witness) - H
38b3844c-4a38-5ff5-aebb-6de4551e393a | note | Minimum Test Frequency - 1 every 20m
94f37080-4808-5b6d-901c-6511a608ebcc | note | Inspection / Test method - Measurement
54fa1675-2104-510f-8461-437b2f1ada15 | note | Acceptance Criteria - -20mm, +100mm
06b8568b-681c-5769-996e-90144fed54c3 | note | Record documents (QCP - Quality Control Portal) - Survey
e03f27a6-4ba0-52ea-b54e-c7d2ca4ea89f | note | Responsibility - Stabilising Contractor
98485c72-6706-5e44-8da3-65866ace868c | note | Eng. Rep - A
43e54208-2efb-5587-96e2-445451c900b1 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.17 - Finished Pavement
467133d4-4615-5fa0-b428-7886e80d8581 | note | Detail of Activity / Test - Surface Shape
20558fcd-ca40-5ca5-92c8-4e39cf746bc5 | note | Action (Hold, Monitor, Witness) - H
ac3835eb-3437-5600-88c7-431769298a8c | note | Minimum Test Frequency - every 20m
3d5f7e4f-af3b-5d99-b3e9-82c2376b25c7 | note | Inspection / Test method - Measurement
b2ecf7d5-b0b8-57d4-a995-1a6e84a36586 | note | Acceptance Criteria - < 10mm using 3m straight edge
73213fed-94d9-5f91-8691-2b58621393af | note | Record documents (QCP - Quality Control Portal) - Survey
1a2198a0-c192-57d8-b2b1-7cb8285f618a | note | Responsibility - Stabilising Contractor
98bccd1a-afcb-5cf5-9cb0-c3f3fa844be3 | note | Project Specific Notes / Instructions - Only required if the visual inspection appears unsatisfactory
a416368d-15ce-59af-a4bf-090d2d0d9e49 | note | Eng. Rep - A
60cf051e-1c6a-53cb-a4e9-a17d5ff8dc77 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.18 - Finished Pavement
61ff4436-da54-5922-9d88-d495b350fefd | note | Detail of Activity / Test - Surface Levels
1fa8a5e2-30bb-5013-bcc1-2c0f41515f2a | note | Action (Hold, Monitor, Witness) - H
5679dda0-6ec7-508c-925e-5223185afa90 | note | Minimum Test Frequency - every 20m
b96bac66-79cf-58d6-a55c-ce2fee7fd4c9 | note | Inspection / Test method - Measurement
80ee9d99-07e4-59c6-8646-7254896b3ab4 | note | Acceptance Criteria - -5mm, +15mm
7845f2f6-c612-5da2-aa69-a05b78e93b24 | note | Record documents (QCP - Quality Control Portal) - Survey
a404ccb6-2a8c-535d-928b-ed48a4239b1d | note | Responsibility - Stabilising Contractor
aa89d069-47fb-5933-9188-9618a0a522ae | note | Eng. Rep - A
dd82ba3b-c80c-5087-b3c6-d44605e93426 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.19 - Finished Pavement (1)
039f76a2-6238-5168-9de5-7d8b27988d09 | note | Detail of Activity / Test - Surface Finish
6c38363a-8722-5712-94ff-a3c756c6e952 | note | Action (Hold, Monitor, Witness) - H
96b61b58-e1f1-579a-b12e-ee4f482b48d4 | note | Minimum Test Frequency - Per Lot
b466d6c4-8c4b-5c8c-b531-56c8d178ae8b | note | Inspection / Test method - Visual
f0a73847-e0d3-5161-a1f4-f84bcd604eb8 | note | Acceptance Criteria - 1. Larger aggregate held in pace with a matrix of smaller aggregate
6a7c82b8-b24b-5fd9-89e4-dee4a0a9e2f0 | note | 2. Smaller aggregate held in place by fine material
8fb55cb1-d2c3-5f1a-90a1-c7c6a060ecde | note | 3. matrix does not displace under normal trafficking and/or sweeping
409b868b-5d3b-5fcf-996b-b1f16058d51c | note | Record documents (QCP - Quality Control Portal) - Survey
1d040787-1e24-516d-b68a-f6e7432af6ff | note | Responsibility - Stabilising Contractor
dc1c2aef-2098-5ec7-8b8c-c9b30ef0c675 | note | Project Specific Notes / Instructions - ER to be present at pre-seal inspection
51064c4c-6113-534f-9cdd-13c6689c1260 | note | Eng. Rep - A
b53af3c6-d381-55b5-b7ed-f22dcd092520 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.19 - Finished Pavement (2)
e76a0468-3dba-5c7d-a0f1-a6f89229a9fc | note | Detail of Activity / Test - Roughness
2ac19967-fcf3-5a46-927b-cf487b47d224 | note | Action (Hold, Monitor, Witness) - H
d2e389db-f26b-5fe7-87a6-caaf55c12df8 | note | Minimum Test Frequency - Before Sealing
db20c071-afb4-5f48-8f0d-493e9a9a29d3 | note | Inspection / Test method - TNZ TM 7003 v1
bff9ac0b-3842-53f5-a344-fa3d790a5492 | note | Acceptance Criteria - 100m rolling average ≤ 75 counts/km
615ea099-acd3-5cd4-a9a6-6e2d492c03fd | note | Record documents (QCP - Quality Control Portal) - Test Certificate
9e50d33e-47e4-5c4a-b056-005e63884ce2 | note | Responsibility - Contractor
148a1ae3-8e14-5e62-bdb1-cb92776e88ce | note | Eng. Rep - A
2e1347f9-4014-51e2-bbce-9c867666069a | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.20 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
1d04bacf-e728-5e2a-9975-1b9e4b7b200c | note | Detail of Activity / Test - Clegg Impact Value
1d6425bf-7cfa-5522-82a8-d82bbecbfd19 | note | Action (Hold, Monitor, Witness) - H
15e2d3aa-9052-5ba5-86b8-836bcd06a4a7 | note | Minimum Test Frequency - 5 per 1000m2
857ca237-d034-57ae-a864-42cfed3dc192 | note | Acceptance Criteria - CIV ≥ 50
053aad16-0bf9-5137-a424-f8cbd2fcc2b8 | note | Record documents (QCP - Quality Control Portal) - CIV form - ConQA
51e5905c-6cdd-538c-9c31-c2d3b22ebe49 | note | Responsibility - Stabilising Contractor
1b541593-23fa-5893-928d-933d6a59d125 | note | Designer - I
17dd12ba-2b8f-576a-883e-791c1e84d067 | note | Eng. Rep - A
cd71f8ea-681f-50ec-b745-fcd1a7ccae2b | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.21 - Part of Pre-Seal Inspection (left in here and repeated in the Chipseal as it is part of the Pavement to Surfacing handover)
c7b5f0e6-d01a-59f8-b596-76f265376940 | note | Detail of Activity / Test - Degree of Saturation, DOS
b37db144-ba14-5037-968c-95a02aa5cab5 | note | Action (Hold, Monitor, Witness) - M
29f5de12-8708-5d34-8f16-076af4d1f8b6 | note | Minimum Test Frequency - 5 per 1000m2
d3c5e608-07f8-5aa2-89e1-0b08bce7e636 | note | Inspection / Test method - NZS 4407.4.2.2 and DOS calculation in NZTA B/5
3ce39a38-0c90-5f40-8c13-39568fc8ccb9 | note | Acceptance Criteria - aim for DOS ≤ 80%
551bc92b-dcfc-54db-b6ee-3e19ff090f35 | note | Record documents (QCP - Quality Control Portal) - IANZ report
e135872f-95dd-527a-a74e-31c05ac5ffc9 | note | Responsibility - Contractor
631a3e31-d78c-5194-99e7-2cfb3982af84 | note | Project Specific Notes / Instructions - Report only
ef6d3c34-2571-526b-a8b0-fdb9ed911587 | note | Designer - I
96d3256c-8fae-5c59-8fd0-716a3b6bfa3e | note | Eng. Rep - A
d2627d8c-4c1e-55f2-a574-83fd93041ac9 | note | Contractor - R
| section | 4.0. FINAL SIGN OFF
| checkpoint | 4.01 - Pavement Layer Signoff
eb606170-296a-5170-a0b7-bfecca475758 | note | Detail of Activity / Test - Assessment of all test results for conformity
b3019603-b77a-5fae-bc16-46fe083bbcd1 | note | Action (Hold, Monitor, Witness) - H
9f27dca9-5ed2-5728-9a4b-84cca5e8a090 | note | Minimum Test Frequency - Each Lot
567fd32b-fefe-57c5-9c19-ed36cf4f7bf5 | note | Inspection / Test method - Site Inspection
86d96cd3-92b1-5cac-8e42-73129b636a48 | note | Acceptance Criteria - Reporting of any non-conforming results to Designer via NCR
5edb096b-3473-52b2-ab88-2e5adabc1f80 | note | Record documents (QCP - Quality Control Portal) - NCR
31a20b08-4dde-55e4-a15c-b88308b6a60f | note | Responsibility - Engineers Representative
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
d47cd496-04e3-57f6-a7d6-0d699e9d6775 | textbox | Contractor's Rep Name:
6f6e8b94-691c-5a40-8dbf-7d968a920848 | textbox | Engineer's Rep. Name:
33fa4f07-f37d-5308-a95f-4c5c9b7eff37 | date | Date:
| signoff | Add Signature
| checklist | ITP - Kerb and Channel Rev 0 | itp | ITP - Kerb and Channel | 923c7ed0-3b8e-4515-ae41-9ae903e76b87
| section | 1.0. AGGREGATE AND CONCRETE TESTING
| checkpoint | 1.01 - Concrete
c28dba65-dbc6-5e52-89c0-9fb7ea64c649 | note | Detail of Activity / Test - Concrete Supply
5f12d43f-3dff-5c08-bfa1-2342d2edc07d | note | Action (Hold, Monitor, Witness) - H
2351f1e3-82c8-5225-b768-59d4b42c8b08 | note | Minimum Test Frequency - 1 Test per material per source
7641424e-9196-54bf-821f-27c62b241939 | note | Inspection / Test method - NZS4407:3.10
056e1e39-2a06-5e9d-afc0-c56e3c60cdef | note | Acceptance Criteria - 20Mpa Minmum Strength after 28 Day
3041d1b1-8824-5b4a-baf8-3578504b58e5 | note | Record documents (QCP - Quality Control Portal) - IANZ report
27ebaebf-6d5f-5ff9-94f2-58e217253a84 | note | Responsibility - Contractor
e07f0d09-1ff5-5105-863d-c81c012b1b2d | note | Designer - A
29226a34-2ce8-5c8b-a1ce-fc2ae13a409e | note | Eng. Rep / NZTA - I
0eaa195f-a12a-5d36-83eb-424df7bd7c58 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.02 - NZTA M04
f4ab533c-1954-53c5-93d0-3e6b74e0b758 | note | Detail of Activity / Test - Crushing Resistance
cb00372a-cfba-5ff6-b291-ef5171be99fe | note | Minimum Test Frequency - 1 Test per material per source
4db60482-e034-57aa-87a0-2d97e68bc313 | note | Inspection / Test method - NZS4407:2.4.7
4ce8848b-6a40-53c9-81e2-8936d6eedafd | note | Acceptance Criteria - > 130KN
52179bef-1b1e-5132-9c57-b15233c67c6c | note | Record documents (QCP - Quality Control Portal) - IANZ report
5e81b707-77b3-5400-9d04-f3c5edf1fec3 | note | Responsibility - Contractor
cca007ec-b3ed-5851-99f0-e840665257ca | note | Designer - A
bd5b413a-d3ea-5e5e-89a4-2f809ff2a745 | note | Eng. Rep / NZTA - I
bb322f82-90fa-55ef-8ed0-51e3a4677e57 | note | Contractor - R
| checkpoint | 1.03 - NZTA M04
98e8f66f-9c88-5d84-9e9e-2bc26eca8cc8 | note | Detail of Activity / Test - Particle size distribution
a55fab7b-aa80-513a-9d44-f56d17d327d4 | note | Action (Hold, Monitor, Witness) - H
06612d8b-7922-5bae-88ec-ad70233077ed | note | Minimum Test Frequency - 1 Test per material per source
0d0e10a4-140b-52af-828a-f6897761ea5f | note | Inspection / Test method - NZS4407:2.4.7
e2e280fb-e315-526c-bdec-77cc1e93288f | note | Acceptance Criteria - As per NZTA M04 Specfication
632af8fd-4fa4-53ef-bbc9-2c80ac647cc3 | note | Record documents (QCP - Quality Control Portal) - IANZ report
53c4cc40-2b74-50d5-911b-c5f09e6cc645 | note | Responsibility - Contractor
de152650-e28c-5911-8c0c-e1595f940ff2 | note | Designer - A
b29ecef5-52be-521d-be40-843ff5ba9fa2 | note | Eng. Rep / NZTA - I
58b11fa7-b2aa-52fd-9d11-05f30f5cae34 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| section | 2.0. CONSTUCTION
| checkpoint | 2.01 - Earthworks
31780bbb-abb0-5b51-90fa-3992953f49dc | note | Detail of Activity / Test - Cut to Waste Existing Kerb and Channel
5c3124cd-c33b-53e9-baba-cc5de0eab82c | note | Action (Hold, Monitor, Witness) - M
f2e00d79-2fc3-58a1-81cd-f8633e8164b6 | note | Minimum Test Frequency - As per IFC drawings
b4521da3-d58e-5acf-9c69-99dac85808bd | note | Inspection / Test method - Visual / Photo
532fe4a3-0840-58a0-a9fb-eb9220469b0e | note | Acceptance Criteria - Site Engineers Approval
0baab63a-7ccf-5fd9-a3d6-f58ff3959e41 | note | Record documents (QCP - Quality Control Portal) - Checksheet
633c9b59-f2a0-5d05-821b-b731176e5989 | note | Responsibility - Contractor
09ac1f10-e8dc-5aed-9f14-64540d73d20a | note | Designer - A
3bbe3dff-ba77-540e-baf7-a40ed238e4f0 | note | Eng. Rep / NZTA - I
7b9487b4-a878-504f-ac73-3ae61da7047c | note | Contractor - R
| checkpoint | 2.02 - Prepare Subgrade
5152414b-b2f5-5232-b128-3b60c79cc8a6 | note | Detail of Activity / Test - Subgrade further compacted or excavate the unsuitable material and replace
6b333cae-6cb0-5dfb-a6ec-3486575f3146 | note | Action (Hold, Monitor, Witness) - M
d6d09cd5-c181-512c-9fe4-3f816cfc57d7 | note | Minimum Test Frequency - Test Every 10m
ad8c76ae-aaa5-52d3-8590-a71eafb7d211 | note | Inspection / Test method - Visual / Photo
8e4deab2-8dbb-52ae-8967-31f7318b0489 | note | Acceptance Criteria - Clegg Result >15
24729b58-04b7-566a-bbaa-d475abf12fb0 | note | Record documents (QCP - Quality Control Portal) - Checksheet
5553241d-5988-57f0-b520-facad70fd49d | note | Responsibility - Contractor
3c677786-259a-5ccc-acd9-dae2add4874a | note | Designer - A
44c7348c-8f4a-57a8-9fcb-e8e9de5964b0 | note | Eng. Rep / NZTA - I
270b20e4-c90e-56c2-9f35-d60b3f5c5ac8 | note | Contractor - R
| checkpoint | 2.03 - M4 Palcement
e930e4e7-e60b-5cdd-8dd6-7929e36f0b00 | note | Detail of Activity / Test - Compacted layer of GAP40 as required to adjust height of new K&C shall be placed over subgrade. (75mm Min)
67fbe963-46c0-5eac-9bba-de301fe7e56a | note | Action (Hold, Monitor, Witness) - H
5c98f86e-3ab6-5605-8418-05ec76a996bf | note | Minimum Test Frequency - Test Every 10m
c2b78627-cee3-51d2-bae7-71b3a040416c | note | Inspection / Test method - Clegg Test
7c94625a-28cd-5827-b209-cc2d6a66d064 | note | Acceptance Criteria - Clegg Result >30
bb54384a-3abe-5caf-8003-c7c2e176967f | note | Record documents (QCP - Quality Control Portal) - Checksheet
056043cf-c2eb-50dc-9a87-687092a36ae2 | note | Responsibility - Contractor
12147659-47fd-5fa9-befb-756659d510dd | note | Designer - I
ba2ef4ea-4e67-5430-b9df-9d75bf1aa80f | note | Eng. Rep / NZTA - A
423d42b5-d442-5ed0-9323-f883a49633f9 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.04 - Kerb and Channel Placement, Line and Level
331465c0-e040-5992-b3df-50d1cba9972a | note | Detail of Activity / Test - Construction of Kerb as per profile setout in IFC drawing
6c244b7a-4746-56ef-bb36-0bf6ad4eae3e | note | Action (Hold, Monitor, Witness) - M
ce4d77bb-f258-53fc-a5a9-4b59a2d43635 | note | Minimum Test Frequency - Throughout the activity
9d0cf89d-6b16-5084-8b61-220d5c3d7738 | note | Inspection / Test method - Meausre off Survey Pegs
c30b0585-385d-53f5-ba92-dd8db5b35cb5 | note | Acceptance Criteria - Check Sheet of Survey Pegs Versus Actual
8328c7b2-928b-5eb9-8adc-9f9339a43ad9 | note | Record documents (QCP - Quality Control Portal) - Checksheet
5ff24f96-f738-5815-8681-baf77732bfe6 | note | Responsibility - Contractor
ad9fd77f-9315-5780-875c-f33472bee601 | note | Designer - A
dfde453d-1cc5-5129-b72d-d52850109bf0 | note | Eng. Rep / NZTA - I
1d8957da-0904-56c3-a938-229dbd7ea404 | note | Contractor - R
| checkpoint | 2.05 - Contraction/Expansion Joints
5163d854-182e-5029-906e-78cdccf48483 | note | Detail of Activity / Test - Maximum spacing of 3m and minimum 50mm deep
172215c3-8d26-5308-9a2d-b79507a4df41 | note | Action (Hold, Monitor, Witness) - M
5cfaa435-fb95-535c-8220-8df1fceee4e8 | note | Minimum Test Frequency - Once
f5723d9d-a969-5a31-a22e-4d89e055789a | note | Inspection / Test method - Visual / Photo
f691f8a6-c050-53bf-9b1a-48994da3eb9b | note | Acceptance Criteria - Measure Cut Spacings
79232ae0-6bfd-50c2-977c-a13c231a483d | note | Record documents (QCP - Quality Control Portal) - Checksheet
2f07e8da-b154-5d4c-bcf2-3d0a32b8002f | note | Responsibility - Contractor
b1a8bf03-b862-5b66-86bd-c2e2167fa507 | note | Designer - A
98425e34-65fc-5ea1-94c0-50e9794bf192 | note | Eng. Rep / NZTA - I
775220d6-84d8-506a-a55a-600ea569039d | note | Contractor - R
| checkpoint | 2.06 - Curing of Concrete
d0f86cdf-a10f-5ff4-a961-bd3fcc055cad | note | Detail of Activity / Test - Curing period shall not be less than 1 day OR 36 hours
2ced8da0-95cc-56bf-a8fa-e1435a3b3f28 | note | Action (Hold, Monitor, Witness) - M
db7433eb-0cfa-5107-91b4-6cfcc2b67e7f | note | Minimum Test Frequency - Throughout the activity
bacb5928-9a52-5ac5-a141-a3c7342dc032 | note | Inspection / Test method - Visual / Photo
e0745b69-e3ef-5376-8521-91709ed8326b | note | Acceptance Criteria - Visual Inspection
4e93f544-166f-568e-815f-b931cb93e4af | note | Record documents (QCP - Quality Control Portal) - Checksheet
4fff75df-2ca5-55ab-a253-ca2e12eac5ec | note | Responsibility - Contractor
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
def521a5-19bc-57be-92d7-dbc032333c2a | textbox | Contractor's Rep Name:
2553d783-fc64-52ee-8c82-d2fb5be12e4f | textbox | Engineer's Rep. Name:
5264cd35-dfb2-525b-ab33-0067722a9d78 | date | Date:
| signoff | Add Signature
| checklist | ITP - Shoulder Construction Rev 0 | itp | ITP - Shoulder Construction | 25d21760-671c-46ff-a05b-ba49fc8158d4
| section | 1.0. AGGREGATE ACCEPTANCE TESTING
| checkpoint | 1.01 - AP65
35e57379-9b88-5f0d-9726-151f6267832c | note | Detail of Activity / Test - Crushing Resistance
1096744a-15aa-58d7-9ab1-70159ef03235 | note | Action (Hold, Monitor, Witness) - H
3938bc9e-a39d-5cdb-af61-f6c4fce3a908 | note | Minimum Test Frequency - 1 Test per material per source
3bba8581-9c0e-59c3-b17e-e937f33b9142 | note | Inspection / Test method - NZS4407:3.10
a6b737df-58e0-5384-b75c-d4d5dbd36ef0 | note | Acceptance Criteria - > 100KN
bcc8e6aa-3581-5054-aca3-69e9e553df1f | note | Record documents (QCP - Quality Control Portal) - IANZ report
8009b0da-dce5-5c67-a2e7-9c953693f0c6 | note | Responsibility - Contractor
3cb7bf7d-2863-556a-8d96-f63466479884 | note | Designer - A
837a181b-9571-5a55-9d08-15c1d16fa5a8 | note | Eng. Rep / NZTA - I
194c03c2-1e67-5464-aad4-ccfd2f18bd34 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.02 - AP65
3bb4ff76-e5df-5843-8bc5-3022912db289 | note | Detail of Activity / Test - Particle size distribution
ba2bae6a-93bb-5a10-8afb-93b8ffc8ed9b | note | Action (Hold, Monitor, Witness) - H
efe53eee-29c5-5973-abb1-a1969d5b31bb | note | Minimum Test Frequency - 1 Test per material per source
20042b9f-023f-58b6-bd2b-9f7a0bfaf07f | note | Inspection / Test method - NZS4407:3.8.1
17313f64-7cf6-51de-bec0-98fe0d434bf5 | note | Acceptance Criteria - As per NZTA M03 Specfication
5055d394-8d14-5ed8-9a56-d9c44a8b1dfb | note | Record documents (QCP - Quality Control Portal) - IANZ report
bc6c2611-62e0-5bb0-ba69-1173fdf5215e | note | Responsibility - Contractor
821cdb63-90de-50bf-ad5c-d92b82eed4fa | note | Designer - A
44f573e8-85d9-5866-9efd-10953d3c183c | note | Eng. Rep / NZTA - I
346523aa-14c1-5b38-b0c3-b2ac5b005b3a | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.03 - NZTA M04
68820bbd-afd5-5cad-880e-795f725f4a2d | note | Detail of Activity / Test - Crushing Resistance
ba456ba0-f434-5faf-b396-ae6d48bb8808 | note | Minimum Test Frequency - 1 Test per material per source
537f8eb0-6d6b-52f2-8ea4-05826d635919 | note | Inspection / Test method - NZS4407:2.4.7
d77e25f7-90b5-5865-8bb8-e14bcb2b52a9 | note | Acceptance Criteria - > 130KN
311a69ef-e279-5279-a017-a2079a2ebb5d | note | Record documents (QCP - Quality Control Portal) - IANZ report
bba1042d-6ada-5cef-8f7d-8cab188e7f9a | note | Responsibility - Contractor
8068d621-c464-5a6f-95fc-9cdfe52caa2c | note | Designer - A
7a9f4a90-b0d5-58e2-ab09-fbc6f5ceca12 | note | Eng. Rep / NZTA - I
0d816ef7-8056-50e8-ad1f-7498d6a46b79 | note | Contractor - R
| checkpoint | 1.04 - NZTA M04
f734e22d-647b-5fa2-831a-28dda86e6f9a | note | Detail of Activity / Test - Particle size distribution
2b48542e-5737-55b6-b565-9ed53fef28c6 | note | Action (Hold, Monitor, Witness) - H
c9d4f870-b5b8-558b-baf7-0023b3e9fca3 | note | Minimum Test Frequency - 1 Test per material per source
60097ba6-2fbb-51a3-a246-13361c159c75 | note | Inspection / Test method - NZS4407:2.4.7
788a29fc-6bc7-5fc9-93b6-6b840eea0a74 | note | Acceptance Criteria - As per NZTA M04 Specfication
9916145b-72a4-54a0-b139-9da64ec56b04 | note | Record documents (QCP - Quality Control Portal) - IANZ report
41324a53-1986-5995-aef2-826004648167 | note | Responsibility - Contractor
f2b3d62c-a149-53d8-938a-e052dfc37d9e | note | Designer - A
3e7d7ecc-78eb-5412-8add-2bf5f62ddeb9 | note | Eng. Rep / NZTA - I
c9e70f47-7ae6-5988-8057-72731abfb9fd | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| section | 2.0. CONSTUCTION
| checkpoint | 2.01 - Earthworks
b61e58c2-cc9c-5b35-90eb-2c40aaed6e5f | note | Detail of Activity / Test - Cut to Waste Insitu Shoulder
5d5d59b9-dd36-5543-a511-93418ac916d9 | note | Action (Hold, Monitor, Witness) - M
d5391111-a4fc-5224-823c-a9ca4e2f8bb9 | note | Minimum Test Frequency - As per design drawings
c29d8b4a-87d2-54f1-977a-f6d9b195acf4 | note | Inspection / Test method - Visual / Photo
4422d707-9e84-5db7-b49a-0d4564f919dd | note | Acceptance Criteria - Site Engineers Approval
d0b39179-1c91-5845-8268-28c75a4b99d0 | note | Record documents (QCP - Quality Control Portal) - Checksheet
559b55e9-d6cd-5282-956d-99ed63e9e40c | note | Responsibility - Contractor
cffadae0-de1f-5bc7-9414-e703e6d7c9e2 | note | Designer - A
fa63a1e3-cb09-5714-8e9a-b9d2981d5829 | note | Eng. Rep / NZTA - I
b24d30da-3c00-55be-935c-d4ee735dada1 | note | Contractor - R
| checkpoint | 2.02 - AP65 Placement
c4abc028-8aee-59f8-b927-9fbb7df8dd63 | note | Detail of Activity / Test - Gap 65 Placed in Accordance with Design and Survey
ee8958d7-a48c-5862-89c9-f15d5a5d7de7 | note | Action (Hold, Monitor, Witness) - M
d5075a69-4eed-5dc1-bd32-2477b41aef97 | note | Minimum Test Frequency - As per design drawings
459bdb0d-be26-52f8-ba75-d7346de03fbb | note | Inspection / Test method - Visual / Photo
67a4880a-685d-5674-86cd-e39b17507c6c | note | Acceptance Criteria - Site Engineers Approval
9c41f0d6-a996-58e8-b970-7c47aaaf8ced | note | Record documents (QCP - Quality Control Portal) - Checksheet
16db2f2c-2dcc-56a2-bc40-f7ab90d4f8ae | note | Responsibility - Contractor
d0deac72-dbd8-5a8c-9f57-140a4099f835 | note | Designer - A
45ea1efa-e37e-5b08-8847-be3c62defa0e | note | Eng. Rep / NZTA - I
3defcf44-2ff4-55db-adfc-a9034ea12277 | note | Contractor - R
| checkpoint | 2.03 - AP65 Compaction
1614fb7d-4e3d-53a5-b5ce-afde2cb34db0 | note | Detail of Activity / Test - Compact in Layers no greater than 200mm.
d05046d1-5be4-567b-81e7-44958069d048 | note | Action (Hold, Monitor, Witness) - H
fce7cf4d-b95b-5465-be02-fde96a3171bf | note | Minimum Test Frequency - 1 MDD Test per 50m
3fc660e5-07f3-5683-a165-2733938eb5ed | note | Inspection / Test method - Nuclear Densometer MDD Test
2af0169c-3963-51c0-8cb7-76a08d92199d | note | Acceptance Criteria - 95% MDD Achieved
961ea53e-17a3-5bec-a86c-27cc2c17dcfb | note | Record documents (QCP - Quality Control Portal) - IANZ report
b1b1df2a-886f-5fe1-8e2e-18f3c86145cb | note | Responsibility - Contractor
e45a41a5-817f-50bc-8983-7c3105dcb4ea | note | Designer - I
671d6270-4a90-5783-9d79-f70b5538934f | note | Eng. Rep / NZTA - A
17820d7b-c13c-577e-ae97-668df2e97395 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.04 - M4 Placement
f317e8fd-83e0-58f9-b6d1-f956fcc2d23c | note | Detail of Activity / Test - M4 Placed in Accordance with Design Drawing and Survey
2b9abca4-feea-503b-a0a3-de3ff7798540 | note | Action (Hold, Monitor, Witness) - M
0bfa817f-61ee-5fa8-a86b-e46c5e5d461c | note | Minimum Test Frequency - As per design drawings
591338a7-c1a2-5a44-b8c9-779aab333a15 | note | Inspection / Test method - Visual / Photo
fd5c0053-1cb1-50a2-9228-9478d82a3ce7 | note | Acceptance Criteria - Minimum Width 300mm.
723f53cb-ad4e-540e-8d2a-d4082357eaa3 | note | Record documents (QCP - Quality Control Portal) - Checksheet
71fb81c9-7a64-5437-a492-81ea3e6bd88f | note | Responsibility - Contractor
b128e269-c5a9-55ad-a435-98a89c5f32b2 | note | Designer - A
70804076-5b39-5600-8f06-30d8559a1beb | note | Eng. Rep / NZTA - I
b0f8acb0-6cae-5513-a27e-64a851a89397 | note | Contractor - R
| checkpoint | 2.05 - M4 Compaction
c647409c-f85c-52e9-ac6f-5ca999997459 | note | Detail of Activity / Test - Compact in Layers no greater than 150mm.
13f6bf66-2f9b-561a-8b59-8c56ae6417d7 | note | Action (Hold, Monitor, Witness) - H
8613a141-d1fe-54c0-b494-1627c2439b93 | note | Minimum Test Frequency - 1MDD Test per 50m
a0a2f320-23b8-5049-831b-d182c746c5ae | note | Inspection / Test method - Nuclear Densometer MDD Test
ffa3fdd3-2db3-521a-9786-49828baca648 | note | Acceptance Criteria - 98% MDD Achieved
267e30f7-415e-5abc-bcf7-d74096ac494c | note | Record documents (QCP - Quality Control Portal) - IANZ report
dd624d14-d62b-5e18-abc8-ed27a6dff1d4 | note | Responsibility - Contractor
9bcd581a-f1b8-5c91-aef0-f766f39a87ad | note | Designer - I
8193c8f2-ab15-50d0-8508-5c8c438b0f7c | note | Eng. Rep / NZTA - A
c9b70a26-f2f7-55c7-82dd-cbd939a89d85 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
53af85ce-03f6-585b-82a7-92cf0e32c471 | textbox | Contractor's Rep Name:
ce81b22d-8330-5659-8c3b-d70eb55b7eef | textbox | Engineer's Rep. Name:
460765d8-ad50-5b2d-ae5d-9ec641989812 | date | Date:
| signoff | Add Signature
| checklist | ITP - Subsoil Drainage Rev 1 | itp | ITP - Subsoil Drainage | 48c57658-3f65-4f95-9cd8-70a467d2e7ac
| section | 1.0. AGGREGATE AND BINDER OPTIMISATION / ACCEPTANCE TESTING
| checkpoint | 1.01 - Drainage aggregate
892bd164-7761-51df-8e27-7490f12610c1 | note | Detail of Activity / Test - Crushing Resistance
f34fe5e5-f850-5a41-ad7d-4c19f3207e77 | note | Action (Hold, Monitor, Witness) - H
0f482f64-9d69-596b-9dc1-aab3b0f19226 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
0cc2c27b-fc73-5ea4-ad39-7021495c136a | note | Inspection / Test method - NZS4407:3.10
72e1e5d1-24aa-5b72-a70c-aa9ac0bf7175 | note | Acceptance Criteria - > 100KN
a3f954bb-aa6d-526e-847a-2b8394d4c523 | note | Record documents (QCP - Quality Control Portal) - IANZ report
b85e7d7c-df5e-5fe7-9e27-e8d606d98895 | note | Responsibility - Contractor
c1d2251b-6dd0-54c0-bdfc-3e5b5989687e | note | Designer / PTG - A
91887811-8daf-59e9-8d6b-f1648e47d21f | note | Eng. Rep / NZTA - I
6255aca9-f902-59b8-afec-477d240bbdfe | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.02 - Drainage aggregate
a39be7b9-56b8-5f0a-9df8-f444f0f1ba4f | note | Detail of Activity / Test - Particle size distribution
95bf18d8-24eb-52de-a2c3-b590ef0b04a6 | note | Action (Hold, Monitor, Witness) - H
15c684ee-a28f-5cca-9c3d-07b6c2d8ebae | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - 1 Test per material per source
2f2e6f30-5519-5827-8fb7-252c3e84ef60 | note | Inspection / Test method - NZS4407:3.8.1
9aafa1ad-1738-5017-aa47-e1f31f7f0123 | note | Acceptance Criteria - as per IFC drawing
f0a83ad7-2ba9-52be-9a3a-fa3a59b0c5a5 | note | Record documents (QCP - Quality Control Portal) - IANZ report
b3e1d23f-72bf-5798-be46-12cf64e5cdc4 | note | Responsibility - Contractor
2ed164a7-a063-5cf5-8ad3-af4649b8a005 | note | Designer / PTG - A
9e7e174e-b7b0-5481-b880-ab8db2a84266 | note | Eng. Rep / NZTA - I
b9a195c4-2fad-5057-86c0-2a0211178461 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.03 - Pipe
043a4a1e-ad56-5d42-8fb6-1226ff2f83ad | note | Detail of Activity / Test - Subsoil Pipe Material
a5c212f6-676f-5130-a012-1859e28901bf | note | Action (Hold, Monitor, Witness) - H
81c98f48-df8f-590c-8a30-f6da899a610d | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - each delivery
c3f67e42-4975-5789-b7b3-3f892fb8d9e2 | note | Inspection / Test method - Dockets for each delivery
ad7b8bb5-35f5-5cee-87b5-59192a179345 | note | Acceptance Criteria - Compliance with TNZ F/2
72aa4e63-78e5-5f11-bc18-3a97a02dc777 | note | Record documents (QCP - Quality Control Portal) - Delivery Docket
77323653-8901-55d8-a8ce-09a1151f1bb6 | note | Responsibility - Contractor
b3ef01d4-5905-5c51-a9fd-b170d911a526 | note | Designer / PTG - A
21dbf408-3b0c-5dae-973f-d9a9427b8da1 | note | Eng. Rep / NZTA - I
dd8956b8-b4da-5615-bd99-e7d12cc8ff50 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| section | 2.0. CONSTUCTION
| checkpoint | 3.12 - Alignment
225b9fb8-1b4a-5cbb-a2e3-0d594a5c06b6 | note | Detail of Activity / Test - Subsoils to be placed behind the Kerb line or as instructed by Engineer
98b368a8-6c55-5105-b15a-67e58eee75a6 | note | Action (Hold, Monitor, Witness) - H
0afc5726-144e-5ee7-9769-e778a43deffa | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
3967d193-d43f-5725-b6ca-0cd961f6c630 | note | Acceptance Criteria - Engineers Approval
5e026732-6372-5e92-9a56-66e13674fd57 | note | Responsibility - Engineers Representative
41974f8b-875d-5194-bb01-fa11dcfddaf8 | note | Designer / PTG - A
1071ea6c-b3a8-5a30-9eb3-5212c6bb5811 | note | Eng. Rep / NZTA - I
321a7003-cbd6-5197-818c-1a77261ce656 | note | Contractor - R
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.13 - Excavation
3010a6e6-b323-5d74-bc62-f8eb21293df0 | note | Detail of Activity / Test - Excavtion of Trench should be within tolerances.
df3ddbbd-71e7-5bd9-ac0e-121fc0c2acb0 | note | Action (Hold, Monitor, Witness) - M
1992c47c-36af-5815-95fc-1baa0e291559 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
bfe43eb5-d0c7-594b-ae0f-1b71d06ba224 | note | Inspection / Test method - Visual / Photo
53e12fe7-038a-53b0-a118-4c1245242f0a | note | Acceptance Criteria - Trench width should be 300mm minimum. Trench height should be 800mm Min from top of the kerb OR Top of road level where Kerb is not present or as IFC drawing if detail specified
a63e362b-7adc-5674-95de-e0a9a8205384 | note | Record documents (QCP - Quality Control Portal) - Checksheet
f73563de-d3f5-5b64-b4a8-4a0632ba7434 | note | Responsibility - Contractor
b7e2b953-19c9-5826-be95-708e61151b82 | note | Designer / PTG - A
0e7235c6-411f-53a1-b018-0f5def003cfa | note | Eng. Rep / NZTA - I
934d1e6c-df2c-50fb-bdec-05a2b3356454 | note | Contractor - R
| checkpoint | 3.14 - Trench Lining
4ce4f9dd-6818-59c3-b6ad-28289ebd7dc6 | note | Detail of Activity / Test - A29 or other approved Bidim to be placed and wrapped around Trench.
5a1243fe-cfdc-5b70-a5f1-a92406dfc141 | note | Action (Hold, Monitor, Witness) - M
fe07117b-979e-5db8-afd7-ba84e9f1261f | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
474083fc-76ee-5d21-9407-2a55f3e95a93 | note | Inspection / Test method - Visual / Photo
98b53697-48e3-5cc0-8c1e-675044c4e7aa | note | Acceptance Criteria - Minimum Width 300mm.
e87bdc9f-4a27-5015-8ea8-3f1ab71bd97f | note | Record documents (QCP - Quality Control Portal) - Checksheet
92d1cab1-d48f-532b-bb4a-b0f3215e9991 | note | Responsibility - Contractor
817c4db7-b05f-5f87-98b5-0ada0b95ca61 | note | Designer / PTG - A
3eb79f8f-e01a-5870-95fb-abb268e186e7 | note | Eng. Rep / NZTA - I
50ba3960-a3dc-57c7-8c34-0b942f09d818 | note | Contractor - R
| checkpoint | 3.15 - Pipe laying
dd05e586-b285-56ea-994f-c14a98cbf6dd | note | Detail of Activity / Test - Pipe must have 100mm of Cushion. Drainage 60:40 Material to be used.
994498ea-7c04-5e2d-803d-1da114ba5051 | note | Action (Hold, Monitor, Witness) - M
acfc6bf2-11cd-5794-ad03-d79c0637a5e8 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
4721141c-1830-5215-961c-2b3ba8c31f6f | note | Inspection / Test method - Visual / Photo
686ba410-5ef3-5823-a7d9-0761795b6caa | note | Acceptance Criteria - Minimum 100mm
acc4caa1-34d0-59cc-8fb0-b65caf60fd0f | note | Record documents (QCP - Quality Control Portal) - Checksheet
74cca688-9e98-574b-ba83-cfb86dcf0045 | note | Responsibility - Contractor
e26fdafa-62b5-5b5f-ac96-cebe5a45e7d5 | note | Designer / PTG - A
40587998-de58-5bce-bce7-342eb4a6130f | note | Eng. Rep / NZTA - I
88b97cf2-4ac2-50d2-a66c-58ab5b4ae729 | note | Contractor - R
| checkpoint | 3.16 - Pipe laying
34a97d49-6834-56d8-8abb-1479047c71f3 | note | Detail of Activity / Test - 110mm Perforated Pipe to be laid to a gradient not less than 1:200 to discharge
798e7c27-9a3e-5182-9d4b-aa774cb413a1 | note | Action (Hold, Monitor, Witness) - M
dac1bfc2-a633-5c02-8ca6-826c0857e0da | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
669ff28b-7aa5-59ec-9d19-19456949b44d | note | Inspection / Test method - Visual / Photo
4f0ef388-6f90-5ed4-b62d-91923b3436b4 | note | Acceptance Criteria - As Per IFC Drawings
af3508cc-387c-5394-b5be-e8a9ece99ec6 | note | Record documents (QCP - Quality Control Portal) - Checksheet
518de268-3038-503e-8907-f5318d5e0d4f | note | Responsibility - Contractor
900ba9b0-d336-5861-9fba-2784f3c90f40 | note | Designer / PTG - A
36b74398-9edc-56dd-a3bd-34e6f2662c15 | note | Eng. Rep / NZTA - I
6fce5f99-e748-54be-b7a2-0f9e9f304a78 | note | Contractor - R
| checkpoint | 3.17 - Backfill
0f0349b7-83d2-55d5-90bc-09859ecdf12f | note | Detail of Activity / Test - Drainage 60:40 Material to be used.
d1c9ee56-f318-5585-9173-fd2246960aa2 | note | Action (Hold, Monitor, Witness) - M
097c5c97-59d8-5edd-b816-db96a8f21189 | note | Minimum Test Frequency (Lot = 1 day’s production or 1,500m2) - For each site where subsoil is required
d4026709-5a4b-57fc-b383-ce1ddc4b98bc | note | Inspection / Test method - Visual / Photo
af59712c-7bbf-50d8-9b71-55afbec36e81 | note | Acceptance Criteria - As Per IFC Drawings
6d1fb1a1-d590-53a7-9d87-5a2c33892e58 | note | Record documents (QCP - Quality Control Portal) - Checksheet
26cbdde5-6cef-5aae-a5f5-725870b27ed0 | note | Responsibility - Contractor
2da8a0ec-6810-5313-900d-9659becd20ac | note | Designer / PTG - A
2d587657-a17a-51cf-9a24-0a1c3f3d6e1f | note | Eng. Rep / NZTA - I
603ef748-a5fa-56bc-ba37-1c4e3691e06b | note | Contractor - R
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
039e84e0-dc07-5a3f-92dd-579192f38cab | textbox | Contractor's Rep Name:
15d42ad8-6804-55da-afef-962a10ebd38b | textbox | Engineer's Rep. Name:
cf3ae769-fb0e-549a-81b6-251edb874eee | date | Date:
| signoff | Add Signature
| checklist | Shoulder Clearing Checklist | itp | Shoulder Clearing Checklist | 6bbfb255-b493-4437-b829-9a352584fbf3
| section | Pre-site checks for the following
| checkpoint | Photos taken @ Pre start of works
31f33bbd-b990-58c9-8b9d-cc285d03fdb9 | note | Responsibility - FP/Su
f8a85bed-dcec-5d78-a485-fa951ca62bd8 | note | Comment - Field evidence for ITP
| checkpoint | Check culverts in vicinty of work inlet/outlets
33ca181a-550a-5984-b965-e85fb5d2de8b | note | Responsibility - FP/Su
89e19212-9364-5f6b-8da2-1cf5d168e948 | note | Comment - Field evidence for ITP
| checkpoint | Edge Delineators - offset position to re-instate if required
fcf70c19-6229-509d-8d08-222fc744504c | note | Responsibility - FP/Su
ac60b28b-00d3-58d0-8842-51662efa6209 | note | Comment - Field evidence for ITP
| checkpoint | Permanent Roadside Signage - Offset position to re-instate if required
ff28d3da-8737-5e5d-9079-8732e62388da | note | Responsibility - FP/Su
24b5329e-5718-56e3-9ea6-2ee18fcb9644 | note | Comment - Field evidence for ITP
| checkpoint | Photos - Post completion of works
9404eeba-5ce8-5a5c-a782-4b0e1a108e33 | note | Responsibility - FP/Su
08d6ecf5-a0b7-56fb-b83a-285aa90dbcd4 | note | Comment - Field evidence for ITP