## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Chipseal | itp |  |  |  |  | ITP - Chipseal Rev 0
section | Design
checkpoint | 1 - Treatment Selection
label | Verification Activity - Physical / Site video/photographic record
label | Methods or Reference - Asset Team - Base Preservation
label | Frequency - Annually Pre-reseal
label | Acceptance Criteria - Documented approval from at time of Tender -Team/Client
label | Hold / Witness Point - Mandatory HOLD POINT - Client Approval
label | Records - Approved Seal Designs
label | Responsible Person - Sealing Contract Manager / Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Chipseal Design
label | Verification Activity - Peer review by Authorised Seal Design Approver
label | Methods or Reference - Chipsealing in NZ
label | Frequency - One per design prior to commencing onsite
label | Acceptance Criteria - Design meets requirements of P17
label | Hold / Witness Point - Mandatory HOLD POINT - Seal Design peer Reviwer - Client Approval
label | Records - Peer Reviewed Seal Designs
label | Responsible Person - Sealing Contract Manager / Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials Testing
checkpoint | 1 - Size (Grades 2-5) & Shape (Grades 2-4)
label | Verification Activity - Lab Test
label | Methods or Reference - NZTA M/6
label | Frequency - 1/500m3
label | Acceptance Criteria - Size (ald mm)
label | ○ G2 9.5-12.0
label | ○ G3 7.5-10.0
label | ○ G4 5.5-8.0
label | ○ G5 Report
label | Hold / Witness Point - Witness Point
label | Records - IANZ Lab Reports
label | Responsible Person - Sealing Contract Manager / Engineer
checkpoint | 2 - Size (Grades 2-5) & Shape (Grades 2-4)
label | Verification Activity - Lab Test
label | Methods or Reference - NZTA M/6
label | Frequency - 1/500m3
label | Acceptance Criteria - Shape
label | ○ AGD/ALD Ratio G2,3,4 = 2.25 max
label | ○ G2,3,4 = min 98% with 2+ broken faces
label | Hold / Witness Point - Witness Point
label | Records - IANZ Lab Reports
label | Responsible Person - Sealing Contract Manager / Engineer
checkpoint | 3 - Cleanliness (Grades 2-6)
label | Verification Activity - Lab Test
label | Methods or Reference - NZTA M/6
label | Frequency - 1/500m3
label | Acceptance Criteria - Cleanness value
label | ○ G2 = 89
label | ○ G3 = 87
label | ○ G4 = 85
label | ○ G5 & G6 Report only
label | Hold / Witness Point - Witness Point
label | Records - IANZ Lab Reports
label | Responsible Person - Sealing Contract Manager / Engineer
checkpoint | 4 - Compatibility (Multi Layered seals)
label | Verification Activity - Comparison Of Chip ALD
label | Methods or Reference - Chipsealing in New Zealand NZTA (NZTA 2005)
label | Frequency - 11.5
label | Acceptance Criteria - Two Coat Seal Aggregate Compatibility
label | – – – – – – – – – – – – – –
label | Upper Limit (x ¦ y) ¦¦¦ Lower Limit (x ¦ y)
label | – – – – – – – – – – – – – –
label | 0 ¦ -0.44 ¦¦¦ 0 ¦ -1.42
label | 1 ¦ 0.27 ¦¦¦ 1 ¦ -0.84
label | 2 ¦ 0.98 ¦¦¦ 2 ¦ -0.26
label | 3 ¦ 1.69 ¦¦¦ 3 ¦ 0.32
label | 4 ¦ 2.4 ¦¦¦ 4 ¦ 0.9
label | 5 ¦ 3.11 ¦¦¦ 5 ¦ 1.48
label | 6 ¦ 3.82 ¦¦¦ 6 ¦ 2.06
label | 7 ¦ 4.53 ¦¦¦ 7 ¦ 2.64
label | 8 ¦ 5.24 ¦¦¦ 8 ¦ 3.22
label | 9 ¦ 5.95 ¦¦¦ 9 ¦ 3.8
label | 10 ¦ 6.66 ¦¦¦ 10 ¦ 4.38
label | 11 ¦ 7.37 ¦¦¦ 11 ¦ 4.96
label | 12 ¦ 8.08 ¦¦¦ 12 ¦ 5.54
label | 13 ¦ 8.79 ¦¦¦ 13 ¦ 6.12
label | 14 ¦ 9.5 ¦¦¦ 14 ¦ 6.7
label | 15 ¦ 10.21 ¦¦¦ 15 ¦ 7.28
label | 16 ¦ 10.92 ¦¦¦ 16 ¦ 7.86
label | – – – – – – – – – – – – – –
label | Compatibility Point
label | x ¦ y
label | 11.5 ¦ 7.2
label | – – – – – – – – – – – – – –
label | Hold / Witness Point - Witness Point
label | Records - IANZ Lab Reports
label | Responsible Person - Sealing Contract Manager / Engineer
checkpoint | 5 - Compatibility (Multi Layered seals)
label | Verification Activity - Comparison Of Chip ALD
label | Methods or Reference - Chipsealing in New Zealand NZTA (NZTA 2005)
label | Frequency - 7.2
label | Acceptance Criteria - Two Coat Seal Aggregate Compatibility
label | – – – – – – – – – – – – – –
label | Upper Limit (x ¦ y) ¦¦¦ Lower Limit (x ¦ y)
label | – – – – – – – – – – – – – –
label | 0 ¦ -0.44 ¦¦¦ 0 ¦ -1.42
label | 1 ¦ 0.27 ¦¦¦ 1 ¦ -0.84
label | 2 ¦ 0.98 ¦¦¦ 2 ¦ -0.26
label | 3 ¦ 1.69 ¦¦¦ 3 ¦ 0.32
label | 4 ¦ 2.4 ¦¦¦ 4 ¦ 0.9
label | 5 ¦ 3.11 ¦¦¦ 5 ¦ 1.48
label | 6 ¦ 3.82 ¦¦¦ 6 ¦ 2.06
label | 7 ¦ 4.53 ¦¦¦ 7 ¦ 2.64
label | 8 ¦ 5.24 ¦¦¦ 8 ¦ 3.22
label | 9 ¦ 5.95 ¦¦¦ 9 ¦ 3.8
label | 10 ¦ 6.66 ¦¦¦ 10 ¦ 4.38
label | 11 ¦ 7.37 ¦¦¦ 11 ¦ 4.96
label | 12 ¦ 8.08 ¦¦¦ 12 ¦ 5.54
label | 13 ¦ 8.79 ¦¦¦ 13 ¦ 6.12
label | 14 ¦ 9.5 ¦¦¦ 14 ¦ 6.7
label | 15 ¦ 10.21 ¦¦¦ 15 ¦ 7.28
label | 16 ¦ 10.92 ¦¦¦ 16 ¦ 7.86
label | – – – – – – – – – – – – – –
label | Compatibility Point
label | x ¦ y
label | 11.5 ¦ 7.2
label | – – – – – – – – – – – – – –
label | Hold / Witness Point - Witness Point
label | Records - IANZ Lab Reports
label | Responsible Person - Sealing Contract Manager / Engineer
checkpoint | 6 - Bitumen Distributor
label | Verification Activity - IANZ Lab E/2 Results
label | Methods or Reference - Code of Compliance
label | Frequency - Annual
label | Acceptance Criteria - Speed Test(+-3% over 100m), Dipstick Test (+-50L over 2000L), Matt Test (app rate within 0.10L/m2, longitudinal within 10%, thirds within 5%, transverse within 20%)
label | Hold / Witness Point - Mandatory HOLD POINT - Client - Engineer Witness
label | Records - RNZ E2 Certificate
label | Responsible Person - Sealing Contract Manager / Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Emulsion/PME Testing
label | Verification Activity - Lab Testing
label | Methods or Reference - Manufacture Specification
label | Frequency - Per Emulsion/Bitumen Production Batch
label | Acceptance Criteria - Bitumen Content, ITM 11-01, Viscosity, ITM 10-02, PH ITM-08-02
label | Hold / Witness Point - Witness Point
label | Records - IANZ Lab Reports
label | Responsible Person - Road Science
section | Surface Inspection
checkpoint | 1 - Surface Texture - Measurement
label | Verification Activity - Sandcircle Measurement
label | Methods or Reference - NZTA T/3
label | Frequency - At time of Seal Inspection
label | Acceptance Criteria - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture
label | Hold / Witness Point - Witness Point
label | Records - Sandcircle Data
label | Responsible Person - Sealing Contract Manager / Engineer
checkpoint | 2 - Surface Texture - Measurement
label | Verification Activity - ARRB Hawkeye or
label | Methods or Reference - NZTA T/3
label | Frequency - At time of Seal Inspection
label | Acceptance Criteria - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture
label | Hold / Witness Point - Witness Point
label | Records - Hawkeye Data
label | Responsible Person - Sealing Contract Manager / Engineer
checkpoint | 3 - Surface Texture - Measurement
label | Verification Activity - NZTA HSD
label | Methods or Reference - NZTA T/3
label | Frequency - At time of Seal Inspection
label | Acceptance Criteria - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture
label | Hold / Witness Point - Witness Point
label | Records - High Speed Data
label | Responsible Person - Sealing Contract Manager / Engineer
checkpoint | 4 - Pre Seal Survey
label | Verification Activity - Downer Survey or MS Forms Pre Reseal Inspection
label | Methods or Reference - Downer Survey or MS Forms Pre Reseal Inspection
label | Frequency - At time of Seal Inspection
label | Acceptance Criteria - Record & any noted issues / Client
label | Hold / Witness Point - Witness Point
label | Records - Lucidity
label | Responsible Person - Sealing Contract Manager / Engineer
checkpoint | 5 - Construction Compliance testing
label | Frequency - 24 hours in advance of seal construction commencement
label | Acceptance Criteria - Confirmation from renewals manager all testing has met requirements
label | Hold / Witness Point - Hold Point
label | Records - Email Confirmation
label | Responsible Person - Sealing Contract Manager / Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Seal Construction
checkpoint | 1 - Go/No Go Survey
label | Verification Activity - Visual, Zeus, Iris
label | Methods or Reference - Downer Survey Sealing Go / No Go, Road Science Zeus app & Downer Iris app
label | Frequency - Prior to sealing on each site
label | Acceptance Criteria - Pass on Go / No Go, Marginal & discussion with Contract Manager or written approval from Rehab Manager
label | Hold / Witness Point - Witness Point
label | Records - Lucidity
label | Responsible Person - Supervisor / Foreperson / QA
checkpoint | 2 - Pavement Markings/RRPMs
label | Verification Activity - Tagging of existing Pavement Markings, Removal of RRPMs
label | Methods or Reference - Pavement Marking Set Out Sheet, CBP
label | Frequency - Prior to sealing on each site
label | Acceptance Criteria - All raised pavement markers to be removed (1st & 2nd Coat Seal surfaces excluded) and existing line marking "tagged". Check for any new markings required
label | Hold / Witness Point - Witness Point
label | Records - None
label | Responsible Person - Foreperson / QA
checkpoint | 3 - Road Furniture & Sumps protected
label | Verification Activity - Visual Inspection
label | Methods or Reference - Crew Breifing Plan / Visual
label | Frequency - Prior to sealing on each site
label | Acceptance Criteria - Protect all road furniture in accordance with Crew Breifing Plan. Fabric & protect all sumps.
label | Hold / Witness Point - Witness Point
label | Records - None
label | Responsible Person - Foreperson
checkpoint | 4 - Surface Condition/Temp
label | Verification Activity - Physical / Visual Inspection
label | Methods or Reference - Visual / NZTA T/3
label | Frequency - Prior to sealing on each site
label | Acceptance Criteria - Surface area shall be dry and free from any loose chip, dust, dirt, vegetation. Temperature recorded on site prior to sealing commencing
label | Hold / Witness Point - Witness Point
label | Records - None
label | Responsible Person - Foreperson / QA
checkpoint | 5 - Stockpiles
label | Verification Activity - Visual Inspection
label | Methods or Reference - CBP
label | Frequency - Each Stockpile
label | Acceptance Criteria - Correct Source, Grade and quantity. Uniquely Identified.
label | Hold / Witness Point - Witness Point
label | Records - Sealing Data Docket
label | Responsible Person - Foreperson
checkpoint | 6 - Spraying
label | Verification Activity - Paper Start and Finish all runs
label | Methods or Reference - Spray Runs
label | Frequency - All Runs
label | Acceptance Criteria - Mark out start / Finish
label | Hold / Witness Point - Witness Point
label | Responsible Person - Sealing Contract Engineer / QA
checkpoint | 7 - Sealing
label | Verification Activity - Longitudinal Joints out side of wheel tracks
label | Methods or Reference - Spray Runs
label | Frequency - All Runs
label | Acceptance Criteria - Mark out lane lines by construction team
label | Hold / Witness Point - Witness Point
label | Responsible Person - Sealing Contract Engineer / QA
checkpoint | 8 - Binder Application Rate
label | Verification Activity - Tank Level dips prior to and after spray run
label | Methods or Reference - Dipstick
label | Frequency - At Beginning of the day After 1st spray run of site After last spray run of site At end of tank prior to loading
label | Acceptance Criteria - Quantities used to be within the desired tolerance of design Spray Rate
label | Hold / Witness Point - Mandatory HOLD POINT
label | Records - Spray Sheets
label | Responsible Person - QA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Chip Spread Rate
label | Verification Activity - Visual
label | Methods or Reference - Crew Briefing Plan/Visual
label | Frequency - On going whilst seal being constructed
label | Acceptance Criteria - Chip is applied in accordance with the appropriate coverage as specified in the Crew Briefing Plan
label | Hold / Witness Point - Witness Point
label | Records - Data Docket
label | Responsible Person - QA/Foreperson
checkpoint | 10 - Removal of Surplus Chip
label | Verification Activity - Physical / Visual
label | Methods or Reference - Front Mounted Broom / Suction Truck, Downer Survey or MS Forms Post Seal Inspection
label | Frequency - At conclusion of positive traffication within 48 hours
label | Acceptance Criteria - All sump and road furniture protection removed. Meets requirements of P/17 Table 2.
label | Hold / Witness Point - Witness Point
label | Records - Post Seal Inspection
label | Responsible Person - Sealing Contract Engineer / QA
section | Post Seal Construction
checkpoint | 1 - Post Seal Traffic Management
label | Verification Activity - Physical / Visual
label | Methods or Reference - As per TMP
label | Frequency - Full length and width of carriageway
label | Acceptance Criteria - Minimum of 48 hours under normal traffic flow. If rain forecast within 48 hours, traffication recommences until clear weather window of at least 48 hours
label | Hold / Witness Point - Hold Point
label | Records - Zeus or suitable recorded weather data
label | Responsible Person - Sealing Contract Manager / Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Post Seal Inspection
label | Verification Activity - On Site Visual
label | Methods or Reference - Lucidity Post Seal Inpsection
label | Frequency - After sealing is complete
label | Acceptance Criteria - Engineers requirements. Any defects identified, repairs programmed and costs estimated
label | Hold / Witness Point - Witness Point
label | Records - Post Seal Inpsection
label | Responsible Person - Sealing Contract Engineer / Manager / QA
checkpoint | 3 - Asbuilts and RAMM data
label | Verification Activity - RAMM Update Sheet
label | Methods or Reference - RAMM Database
label | Frequency - After sealing is complete
label | Acceptance Criteria - RAMM update sheet 100% complete and accurate, note data provided for RAMM update to be uploaded by others. As Built Drawing Complete.
label | Hold / Witness Point - Witness Point
label | Records - As built information / RAMM Update Sheet
label | Responsible Person - Sealing Contract Manager/ QA/QE
checkpoint | Quality Record Close Out:
textbox | Name:
date | Date:
signoff | Add Signature