## Metropolitan Roads Program Alli
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4
d5c2bc44-51db-4338-9449-f2f1c00d7337 |  | work-in-progress |  | folder | TRUE | FALSE | Civil
8546c26e-969a-4c13-96dd-47b3ccd8659c |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements
3ff6c343-3cbd-4730-ac1a-17231ed40d82 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St
21bc061f-2a49-4b62-ae49-23249e563405 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Capping
3d2d082d-4194-4955-8136-26ff62db37e4 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Capping | 080-0003-ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1
e87d5894-4865-41b5-94f9-c495865c3b77 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Subbase
b050398c-b1ff-4329-bfe6-df93086e7a55 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Subbase | 080-0004-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
d88c6e26-1353-4e01-a2fb-0d1d4d059ac6 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Asphalt BC
46133938-b71a-47c0-ab37-4c6e01405d22 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Asphalt BC | 080-0005-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
85c64563-9286-425b-8c7d-3f3ea95130d9 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Asphalt IC Layer 1
4843eed7-9a2b-4ac3-97e7-576a02d55929 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Asphalt IC Layer 1 | 080-0006-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
658716f0-e5fd-4116-b2f7-6d269e92b9e0 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Asphalt IC Layer 2
efe475ae-5799-41d4-8d69-b7476669c175 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Asphalt IC Layer 2 | 080-0066-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
e44b782e-06ec-452f-8b45-2aff636acaf0 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Asphalt WC
c8ea6720-91b2-4cc6-b677-f3c2bbb9d5df |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 1A: Asphalt WC | 080-0067-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
e9ef12eb-2f8f-4e39-ac2c-d43076290524 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 3: Capping Layer 1
8fae866f-e647-44ae-bf1e-7ca268a951e1 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 3: Capping Layer 1 | 080-0068-ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1
92a19739-1f82-47e9-8835-b5134a38d094 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 3: Capping Layer 2
7f4aa2da-90fd-42fa-bf75-9556bdbeadf6 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 3: Capping Layer 2 | 080-0069-ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1
a02a9573-3da2-46d3-b841-b5e227a54e32 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 3: Upper Subbase
36947375-b9fc-4481-b34f-0928365fe24c |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 3: Upper Subbase | 080-0070-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
e7a26e4a-5230-4461-9b96-6e1d36bbc676 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 3: Base
7a297896-4c65-4424-bdf6-a7674cf6e766 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Pavement 3: Base | 080-0071-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
07b96cab-1f63-4548-8941-ba4720cda3cb |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Victoria St | Contingency lots
9602928c-1cd4-41ca-a0c3-983fc8c39a2d |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South)
0992416b-688d-48f2-9e16-1a13570fdc65 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Capping
0566280b-53c9-4753-b15f-02b9b63699e9 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Capping | 080-0072-ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1
a4179c22-c805-4632-bee8-7a47fc5617ec |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Capping | 080-0073-ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1
f323a421-653d-4cfd-94c2-3c2a83c79080 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Subbase
f3dd72b9-eb56-4b0a-a9ea-3f30a5d848ce |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Subbase | 080-0074-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
68cc3fee-21a9-45cb-8e58-92730067000b |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Subbase | 080-0075-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
0bf5b4b1-124a-48be-ad7e-0a48a3c5dcc2 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Asphalt BC
cb451a4d-ae3d-48a1-87ab-c05264d8b87f |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Asphalt BC | 080-0076-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
a6e9ae36-9fe4-4039-9c0c-f310b99fddff |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Asphalt IC Layer 1
6e17e1ce-4d5d-4d10-868c-449bd596e0a9 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Asphalt IC Layer 1 | 080-0077-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
b10178c4-f2f5-4531-a783-6cac32d895f7 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Asphalt IC Layer 2
c16a6759-3f33-42e6-97d3-9286c2e0245f |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Asphalt IC Layer 2 | 080-0078-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
32c5b62e-48a6-4d31-90aa-b9185c443391 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Asphalt WC
04a04657-87dd-4003-a111-94f0c262fb3d |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A: Asphalt WC | 080-0079-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
777c480e-6a6a-4891-9450-c183b926c0c5 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 2: Subbase
54714752-0df2-4713-899d-d6fdd11dced0 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 2: Subbase | 080-0080-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
00a937cb-312d-47ed-9e86-f4d6a9c5f136 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 2: Asphalt BC
4870d3b1-8eb3-42f9-ad79-5d5bd33c8eb0 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 2: Asphalt BC | 080-0081-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
f90ff9a1-b370-4f2f-8d7a-c263ee624b9d |  | not-started | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 2: Asphalt BC | 080-0081-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install)
3d3c02fd-68d2-4489-8f54-ce07fd05eba2 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 2: Asphalt IC Layer 1
7f9135d1-226c-4b9a-9f1c-2a336c950fcd |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 2: Asphalt IC Layer 1 | 080-0082-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
247262b7-4b65-47ee-b56f-ebe11962a297 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 2: Asphalt IC Layer 2
aee59b80-7466-4a06-9665-934602573507 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 2: Asphalt IC Layer 2 | 080-0083-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
87743d1c-f061-4a99-a1a2-002ee1e42b74 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 2: Asphalt WC
e53db0c7-41aa-4228-a8b6-ddb84ae85a1b |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 2: Asphalt WC | 080-0084-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
26028743-db2d-4451-bcc2-ee851d10a9b6 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 6A: Capping
e494eaad-3a85-4499-884a-b768c5c46ddd |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 6A: Capping | 080-0085-ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1
06d65faf-3717-43bb-9901-c44cb0b2c41e |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 6A: Subbase
207ade29-b201-416c-917f-9a27a263e7c2 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 6A: Subbase | 080-0086-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
7f8970cd-b9a5-4c9e-939c-80b0545ef722 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 6A: Base
76badee2-f786-43d2-a24c-f6a0b8a9b103 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 6A: Base | 080-0087-ITP-CIV-Footpaths & Shared User Paths - 1 (Set-out & Bedding) Rev 1
7e159999-94d3-4d48-ab7a-adba892b950f |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 6A: Base | 080-0088-ITP-CIV-Footpaths & Shared User Paths - 2 (Concreting & Back-filling) Rev 1
eaecec49-c046-4ee9-9472-63dc4460a95e |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 7: Capping
f1839ae1-74fc-4d71-9582-521d7c28621f |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 7: Capping | 080-0089-ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1
101693aa-3d6d-4483-9c4a-56c50aa62456 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 7: Subbase
657c15c2-ddba-4d67-bbb9-d6e6169f6abe |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 7: Subbase | 080-0090-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
47e4d181-839e-4514-9f27-2833b0428467 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 7: Base
56c3a39e-5210-4112-9889-511a23ec284c |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Contingency lots
aae30515-821e-48da-8d2c-71207493b4bd |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 6C: Subgrade
f1d6a71a-40da-48e0-bbbf-4dbcad1f3b66 |  | not-started | ITP-045-CIV-CPD-Subgrade Preparation - Road Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 6C: Subgrade | ITP-045-CIV-CPD-Subgrade Preparation - Road - STH - 6C
86cfa522-dee6-43da-9bcd-f33f4b04df57 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 6C: Capping
cab6d11b-cdcf-402c-bbf0-a17f8f67984b |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 6C: Subbase
116f4769-f88f-44e4-9a7a-406b23f48688 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 6C: Base course
d93f5a30-1e9a-44a7-8730-de9f79341755 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A & 2: Under side of Subgrade - STH-1A/2-USG-1-001
326781b6-e679-4eed-8832-31177390306e |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (South) | Pavement 1A & 2: Under side of Subgrade - STH-1A/2-USG-1-001 | ITP-047-CIV-CPD-Type B FIll - Road
713f330e-268e-4fb2-b3ed-b43200f096cd |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (Bridge Deck)
de29eb7d-f737-410a-b671-34fb8411355b |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (Bridge Deck) | Pavement 4: Asphalt RC
7b2e7ad3-940a-4f43-9a7b-ed9065bc4f9c |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (Bridge Deck) | Pavement 4: Asphalt RC | 080-0092-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
4dad006b-f797-43ac-b535-48ea79478f84 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (Bridge Deck) | Pavement 4: Asphalt WC
fb8e787a-62fd-449c-8367-585934ec59dd |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (Bridge Deck) | Pavement 4: Asphalt WC | 080-0093-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
43996524-0c0c-4a12-90fb-23b424e783ee |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive
dc844f9c-3918-435d-b9f5-152520e10fa0 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive | Contingency lots
c78f20f6-1e1b-4e18-9ae3-873081c392ea |  | not-started | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive | Contingency lots | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install)
684cb676-7132-4061-bc55-2e85b51c3b60 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North)
8b0e914b-3e80-4b9d-baff-e65be31e6719 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Capping Layer 1
f5003dc9-8de5-4730-bb29-d9d465c65f19 |  | not-started | ITP-046-CIV-CPD-Type A Fill - Road Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Capping Layer 1 | 080-0094-ITP-046-CIV-CPD-Type A Fill - Road
7ed74b52-f50b-4151-97cb-0e19977d9765 |  | not-started | ITP-046-CIV-CPD-Type A Fill - Road Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Capping Layer 1 | ITP-046-CIV-CPD-Type A Fill - Road
5b48c6c1-af15-4253-811f-9783d838b968 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Capping Layer 2
d2d51a6f-ae3c-4912-abae-ce5ae8096214 |  | not-started | ITP-046-CIV-CPD-Type A Fill - Road Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Capping Layer 2 | 080-0095-ITP-046-CIV-CPD-Type A Fill - Road
37a09a97-017d-413b-bd2f-e74459cae6a9 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Subbase
12db561b-bc32-49e3-b7ad-71284bea7210 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Subbase | 080-0096-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
59e6910b-f560-4f1d-8ef9-d9790b332869 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt BC
dc325df1-8538-4627-8d82-520ddb77ab02 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt BC | 080-0097-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
24fea7b8-fab0-4b05-bf94-a66578c84bb5 |  | not-started | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt BC | 080-0097-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install)
60eaa53f-1e80-4bb6-a965-d82e478db688 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt IC Layer 1
5f352cb8-bdb2-42dc-aefe-566c7abe60ed |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt IC Layer 1 | 080-0098-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
82f1113f-b13e-478b-9c32-1f75ac7c766b |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt IC Layer 2
5065bba3-4736-4a8f-8db6-1d029bf33a01 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt IC Layer 2 | 080-0099-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
7c2a45c4-f8b9-4e22-84a8-04301f56abcc |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt WC
68ada81d-c302-4575-b984-21538c1ab1f8 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt WC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
9c30a5a7-814d-4cee-a3e8-17a8d725ddb8 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Capping Layer 1
5644882c-caca-4950-98c1-fc60f6837eed |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Capping Layer 1 | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1
3b7a7667-4a11-4826-8fe7-f6626953b491 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Capping Layer 2
10893f09-dc46-4b26-b551-bc0954bdffdc |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Capping Layer 2 | ITP-CIV-Type A Fill - Road (Supply and Install) Rev 1
e9b9d196-96e2-4d20-a9a6-36e0d46739c9 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Subbase
6595257d-a84f-4152-9556-0d03f2eac733 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Subbase | 080-0100-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
7e75475f-5662-4aad-bf67-53815f31d1c6 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Subbase | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
6341f493-fca0-47b3-8dc9-4cb4f460e385 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt BC
ec4fb4e9-6b68-4268-9a00-21c044d05013 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt BC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
a90f2612-5ee4-4e1a-8545-a943451762f9 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt IC Layer 1
b459e155-9dba-4411-8600-2a4d2ae75ba9 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt IC Layer 1 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
48a5c6d0-c611-46f1-8359-e57afc5510b9 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt IC Layer 2
8e3dcf2c-f85a-427f-9590-a390c5c6172a |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt IC Layer 2 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
54aad929-27b0-4be9-94f6-71793b0f8d8e |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt WC
06d5a206-5d2e-4b77-a5fe-5e5da6f5efb8 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 1B: Asphalt WC | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
bb4f5a2c-ea83-4c12-98e0-9fa4835cb462 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Underside of Subgrade - 0042-NTH-2-USG-01-001
c567c961-88f4-4f6c-8bc7-bcb0f1368ef6 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Underside of Subgrade - 0042-NTH-2-USG-01-001 | ITP-047-CIV-CPD-Type B FIll - Road
77095033-3d11-484f-94d5-fff21a81cdc8 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Subbase Layer 1
80285257-2f73-449c-b0a3-199a852724e3 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Subbase Layer 1 | 080-0108-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
39009f95-2407-4837-8673-efb671eb8226 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Subbase Layer 2
4c3ffa6f-747f-4791-b727-4ffed4f1bd89 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Subbase Layer 2 | 080-0109-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
6ce35dab-4352-4f41-b251-5e3f5083dece |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Subbase Layer 1
cad29c60-c1ce-4138-a4fc-2f4d94ec93ce |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Subbase Layer 1 | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
97f5fe3e-fe1f-418c-a55e-4013fb2b1d81 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Subbase Layer 2
085abccf-a6c7-4d5f-b4c4-09210d945a1c |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Subbase Layer 2 | ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
8de51953-c718-47d6-8d98-0fa9c3d14aa4 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Asphalt BC
1477d3de-55a8-41fc-bb37-10ba41f83370 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Asphalt BC | 080-0112-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
f61f5cc4-995d-4e2a-931b-4913541de73d |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Asphalt IC Layer 1
0a0c2cbd-038a-4472-87ad-a5c711a56f21 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Asphalt IC Layer 1 | 080-0113-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
fbd83109-c298-4c98-adfb-bdf244bf9e48 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Asphalt IC Layer 2
815df0f8-66fe-470d-b13f-6bb4af5ede41 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Asphalt IC Layer 2 | 080-0114-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
959ec947-5f8f-40d8-bc37-4906df4af248 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Asphalt WC
07f4c31d-092e-4d2a-ad5c-faa09915de71 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Asphalt WC | 080-0115-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
35d9d01c-1f6e-4a7f-b94d-b54dba8c4296 |  | not-started | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Asphalt WC | 080-0115-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install)
f31105ae-05a5-4ff5-bb75-06977f42367b |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Subgrade (East)
2c55d400-fe79-467d-bc05-19cd191c1bc2 |  | work-in-progress | ITP-045-CIV-CPD-Subgrade Preparation - Road Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Subgrade (East) | ITP-045-CIV-CPD-Subgrade Preparation - Road
1ca5c770-8e8b-4409-b946-01d82e964bc2 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Subbase (West)
12ccc01f-b9b7-4971-850f-3a94110eecf1 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Subbase (West) | 080-0120-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
34559e76-db0b-49ed-9255-04ad78ceaccb |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Base Layer 1 (West)
0776df9d-dfc4-4344-bf12-9ef4f3554649 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Base Layer 1 (West) | 080-0121-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
1c13e020-cbcc-4787-a4a9-db52b7614c14 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Base Layer 2 (West)
97ef58e9-e307-4a86-9ad8-8496f32b3bd6 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Base Layer 2 (West) | 080-0122-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
59b36579-90e8-4e5c-8733-9d3f9eaa5a99 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Asphalt WC (West)
18222dc6-5122-4b18-b9d7-68864d4defd5 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Asphalt WC (West) | 080-0123-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
eaf89f80-99ad-49ac-bddd-387b7d4f7077 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Subbase (East)
fdad43b6-8a5a-47d3-8966-12f83c59670c |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Subbase (East) | 080-0124-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
7e0e43c7-5dea-48f5-a06e-90ba040271e9 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Base Layer 1 (East)
4a9eea64-09c1-42ac-a607-8b51d9682223 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Base Layer 1 (East) | 080-0125-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
c1d72410-b36b-4765-8b3c-54e82f65d820 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Base Layer 2 (East)
028a96c8-2b8d-49b8-8d40-db3ee34d7b81 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Base Layer 2 (East) | 080-0126-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
195a3210-04bd-40a4-b68a-8a8de1690f92 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Asphalt WC (East)
bfb0ba55-d4e3-4c0b-8ed3-03852966f718 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Asphalt WC (East) | 080-0127-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
333f960b-08a6-4890-9367-d31ef4131a07 |  | not-started | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5B: Asphalt WC (East) | 080-0127-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3 | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install)
e4a485a2-6ed3-4b50-8858-1e02957ceb2d |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 6B: Subbase
05e3a191-2a1f-48b5-9686-199723921eb3 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 6B: Subbase | 080-0128-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
a1cd30cd-cd6a-4fc1-a9bb-171f1302924f |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 6B: Base
2acec004-b0fd-4788-94b2-d78d9bca8005 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 6B: Base | 080-0129-ITP-CIV-Footpaths & Shared User Paths - 1 (Set-out & Bedding) Rev 1
eeeefc2b-0206-4ec5-8583-4ebcf2f94721 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 6B: Base | 080-0130-ITP-CIV-Footpaths & Shared User Paths - 2 (Concreting & Back-filling) Rev 1
a026ebac-69a4-4f94-ac66-ecff4149f675 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 8: Asphalt BC
50feff37-ffd6-49bb-9f1b-ab7068f49bd3 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 8: Asphalt BC | 080-0131-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
a0d969fb-121d-486b-aff3-c8af5f8aa32d |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 8: Asphalt IC Layer 1
1312748a-4948-471f-945b-269d819f8b9f |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 8: Asphalt IC Layer 1 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
5ac6745c-0559-4e41-ab8c-011c32d55080 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 8: Asphalt IC Layer 2
e903428b-c374-42ae-bdbd-3a3a7d4c9f16 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 8: Asphalt IC Layer 2 | ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
6609a330-90d7-44ef-aec7-79866ccfeb10 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 8: Asphalt WC
257c40ce-01b3-40bd-8473-187bffee95ca |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 8: Asphalt WC | 080-0132-ITP-CIV-Hot Mix Asphalt (Supply and Install) Rev 3
eb276b38-5963-4aa9-bd02-ba526237478f |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Contingency lots
7d5fc456-96da-4047-8810-df9f5f1e164a |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Subgrade (West) 01
67d8563d-34df-4d6e-9ecd-40e3cd76fac7 |  | work-in-progress | ITP-045-CIV-CPD-Subgrade Preparation - Road Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Subgrade (West) 01 | 080-0272-NTH-5A-SG-001 (CH 1400 - CH 1550)
ce5c3141-1083-47f8-9f6a-1115e0ec5ae2 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Subgrade (West) 02
7fd54237-299f-4479-937f-3ad500decb8d |  | pass | ITP-045-CIV-CPD-Subgrade Preparation - Road Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Subgrade (West) 02 | 080-0273-NTH-5A-SG-002 (CH 1550 - CH 1610)
83f1dcb5-68b2-4928-a24d-7c2c49ddcc71 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Subbase (West) 080-0274-NTH-5A-SB-001 ( CH1400 - CH 1550)
28730624-7ad9-4a05-91d5-fd882d1fa0fc |  | work-in-progress | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Subbase (West) 080-0274-NTH-5A-SB-001 ( CH1400 - CH 1550) | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction
54d0e0e4-126c-455d-ac2f-fc5b7c143c4d |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Subbase (East)
1d720dc5-8a99-447e-b680-93e21ea3d87e |  | work-in-progress | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Subbase (East) | 080-xxx-NTH-5A-SB-003 Ch 1550-1640
4283dedc-c77a-413f-bc2c-8c4dffc7a7eb |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Subbase (West) 2
cfadba23-4f1e-4f5f-bc92-85c8aa6fd005 |  | work-in-progress | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Subbase (West) 2 | 080-0275-NTH-5A-SB-002 ( CH 1550 - CH 1610)
42ebdae5-3ad3-4131-8f9e-65d8f2be9ce7 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Subgrade (East)
64be2370-2e70-42b0-b71c-6b03854353a6 |  | work-in-progress | ITP-045-CIV-CPD-Subgrade Preparation - Road Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Subgrade (East) | ITP-045-CIV-CPD-Subgrade Preparation - Road - Pavement - Type 5A
9c12020e-c776-4c8d-94c4-328f4b220e19 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Subgrade (East) 02
d9b1548e-b8ca-498f-9657-2c026ef79cb4 |  | work-in-progress | ITP-045-CIV-CPD-Subgrade Preparation - Road Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Subgrade (East) 02 | ITP-045-CIV-CPD-Subgrade Preparation - Road - 5A - 004
5c6b3ca7-166a-4168-a75d-47eec9af1607 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Base (East)
26c0a85a-8681-4f2b-84d1-ae8a4ed4412a |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Base (East) | 080-0119-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2
6ec148cc-1883-43b7-8727-9b1e05176c0f |  | work-in-progress | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Base (East) | 080-0119-ITP-CIV-Unbound Flexible Pavement (Supply and Install) Rev 2 | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction
0d3bbd4a-f00c-4204-a0d1-bec1b091e562 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Base (West)
d2a2b264-7602-450f-92b5-b4744302ed8c |  | work-in-progress | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Base (West) | 080-0276-NTH-5A-BC-001 ( CH 1400 - CH 1550)
60abc893-8f72-4622-b37e-a2a655214289 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Base (West) 2
7c038a5a-53a1-4d09-980e-418e66ceedc0 |  | work-in-progress | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 5A: Base (West) 2 | 080-0277-NTH-5A-BC-002 (CH 1550 - CH 1610)
a6fc8d84-e373-45cc-bd21-6efc4b8dec1f |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Underside of Subgrade - 00XX-NTH-2-USG-02-001
f760b51e-a2ef-4144-8791-35422c15ac3d |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Subgrade - 00XX-NTH-2-SG-01-001
f5a15e12-ab88-486f-9a21-722b0c946a2e |  | not-started | ITP-045-CIV-CPD-Subgrade Preparation - Road Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CPT-0012-0 - Road Pavements | Calder Park Drive (North) | Pavement 2: Subgrade - 00XX-NTH-2-SG-01-001 | ITP-045-CIV-CPD-Subgrade Preparation - Road
23243534-097f-46d0-b5db-8411de3ec2fc |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage
288a9f15-ba99-4a7f-9a04-b7d59a697883 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation
f97fa96b-816a-493e-8ee2-817d0c794514 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0133-L-1/1 - Stormwater - Pit Installation
f1db54aa-4b60-4bae-ab00-bf09efc197ec |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0133-L-1/1 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
139b1264-b1e5-45f5-9c44-d6e40df05252 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0135-L-1/13 - Stormwater - Pit Installation
364435a1-9c60-4eb9-9443-a03e4aa6b4cd |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0135-L-1/13 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
ed51c305-8860-4a66-9c05-e35d79aa656a |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0136-L-1/15 - Stormwater - Pit Installation
7c1601f0-47d3-497c-b0df-2c3fb2e6dc2a |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0136-L-1/15 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
3bdb438a-89d1-4bb3-ad49-dd526c09a8dd |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0137-L-1/16 - Stormwater - Pit Installation
e935f90e-5b1a-4948-a33b-50cf9b7c3f78 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0137-L-1/16 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
f76fbf04-78a1-4e6f-adb0-0b89a53ebefc |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0138-L-1/16C - Stormwater - Pit Installation
b1143e00-b9b4-43f2-8dbb-790c446eda46 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0138-L-1/16C - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
9bc90394-88c4-4f0e-b15b-dc2923d0cfb1 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0139-L-1/17 - Stormwater - Pit Installation
4182dd00-388f-45c8-9a53-afff89b4c6af |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0139-L-1/17 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
c94ca82e-3c2e-4ce7-8bcb-16ceab99e483 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0140-L-1/1A - Stormwater - Pit Installation
5df769f1-e4e2-4b77-a53b-70b39572feb6 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0140-L-1/1A - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
4ed3be3c-d468-4cd6-bd98-86133d935430 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0142-L-1/21 - Stormwater - Pit Installation
50f9020d-f92f-4c41-9e00-31aa440b5487 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0142-L-1/21 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
f344a544-f66f-4848-a89e-ee0dd9cdd37d |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0143-L-1/22 - Stormwater - Pit Installation
0f72a2d5-2b72-4917-9e2d-08b834a6dcb8 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0143-L-1/22 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
3bce2de8-45bf-4e42-9fc6-02174ccc529b |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0144-L-1/23 - Stormwater - Pit Installation
a0180454-f2da-4fa6-9ccf-830f381a0427 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0144-L-1/23 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
05df271b-1093-4f98-a27d-35fc23f0da92 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0145-L-1/24 - Stormwater - Pit Installation
700a1acd-e35c-42de-865b-1e7c046e600a |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0145-L-1/24 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
edb2d25b-467a-49e6-8e3a-6ac40dcd2fb7 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0146-L-1/25 - Stormwater - Pit Installation
c852e132-88d9-4530-8932-13f518fc99f9 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0146-L-1/25 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
022f33e7-25b8-4232-ab9c-94130b158899 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0147-L-1/27 - Stormwater - Pit Installation
88868fe1-8a5e-46f6-baf0-f0b6091bd64a |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0147-L-1/27 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
bd651e1a-4cd2-47d3-a38b-c82620baa6ee |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0148-L-1/28 - Stormwater - Pit Installation
360b4ab9-8da7-4175-b409-ee0d96e0e647 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0148-L-1/28 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
d689f457-f5ad-4670-96f1-4719af079711 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0149-L-1/29 - Stormwater - Pit Installation
514f000e-ae5e-415e-862d-6f04d55a668b |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0149-L-1/29 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
47182fcd-e5c2-4878-be16-3e7b883e18da |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0150-L-1/3 - Stormwater - Pit Installation
d7045b63-f451-46e0-bf46-dadfcda06f8b |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0150-L-1/3 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
4f0dcb7f-7581-48d7-8046-b981af6169ba |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0158-L-2/21 - Stormwater - Pit Installation
6d0e2e0a-a73a-458a-b4a0-64bdecb5de17 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0158-L-2/21 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
bf1e26d5-57af-46a5-a2a1-85f331043fb5 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0151-L-1/4 - Stormwater - Pit Installation
dd8d93bb-f7ad-45cc-88d3-c11d47b54a10 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0151-L-1/4 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
03425c04-7079-4171-8ede-d4a455a81c0f |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0152-L-1/6 - Stormwater - Pit Installation
303becc5-7fe1-4c30-a89e-cf7be81cd22c |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0152-L-1/6 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
c223c297-3e08-4e2f-b9ec-db87d2bf1070 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0153-L-1/7 - Stormwater - Pit Installation
d96ee80b-6ed7-4c03-b7b6-6a6c8a8f1622 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0153-L-1/7 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
2638af94-a976-4a32-a140-37768c51fb03 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0156-L-2/15 - Stormwater - Pit Installation
c4717e63-f0c6-41cc-8fce-86d06adf5d81 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0156-L-2/15 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
007102c9-cd72-4de3-b833-c4f6921ea8b2 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0159-L-2/22 - Stormwater - Pit Installation
7d5acd56-c558-43da-b353-cba954e860b7 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0159-L-2/22 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
0a3a9311-d66d-4b91-b510-b2ef21eab25d |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-160-L-2/23 - Stormwater - Pit Installation
c9a10a67-cb61-467b-baff-bec70eb38940 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-160-L-2/23 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
9dec7af2-3fad-44d7-b626-761802c5bf4a |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0161-L-2/24 - Stormwater - Pit Installation
3801f861-0b1e-4e40-a236-3895e51c0282 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0161-L-2/24 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
5a9de141-9de6-4870-aea8-c56433774fcf |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0162-L-2/25 - Stormwater - Pit Installation
efe08098-aa8e-4d04-9eb2-c31ba0f6de99 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0162-L-2/25 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
9852e618-c78a-488f-9c7a-ef40dbb985c6 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0163-L-2/27 - Stormwater - Pit Installation
4a106cc1-f20a-4091-8e19-6a3f821823d8 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0163-L-2/27 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
19244ec8-0e77-4c25-8087-d957c262a3b9 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0163-L-2/29 - Stormwater - Pit Installation
aedff94a-02e9-44cf-bcce-a59d482096ba |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0163-L-2/29 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
c6199a0c-6d56-4975-b5cb-49195e52fd14 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0164-L-2/3 - Stormwater - Pit Installation
c67b084f-6721-489c-b63d-9052413a5683 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0164-L-2/3 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
a6cd1a77-3583-4f6d-a2e4-c34f1731633c |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0165-L-2/6 - Stormwater - Pit Installation
bc812212-3ef4-470c-82ba-e738955ca505 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0165-L-2/6 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
736fd02b-d7f2-4cdb-8f81-709b1ed3fa2f |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0166-L-2/7 - Stormwater - Pit Installation
12f81de9-16b3-4bf0-a3a5-ad34eae5d432 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0166-L-2/7 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
b92b44b7-fc04-4be7-a50c-d5793866a4c8 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0154-L-2/1 - Stormwater - Pit Installation
4eeffc47-964a-498f-a14d-30ae2b5935e8 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0154-L-2/1 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
29a72e66-7858-43ef-8338-b963e867515f |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0167-L-3/1 - Stormwater - Pit Installation
6869d1af-15af-4235-b4b5-1dc2e0098fb3 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0167-L-3/1 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
4d0627fd-feda-4ab9-b081-faf8c6a53656 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0175-L-4/1 - Stormwater - Pit Installation
93c0b08c-8960-445f-972a-7e284a1c4119 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0175-L-4/1 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
645e7462-739e-4092-83c5-868995b4e0d8 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0169-L-3/18 - Stormwater - Pit Installation
75827b16-493d-4562-aba6-e12c066171db |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0169-L-3/18 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
3c424441-d56d-45e5-80f8-a55926341582 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0171-L-3/23 - Stormwater - Pit Installation
61041f55-4ddf-4508-8e80-288d6b2ce7a5 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0171-L-3/23 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
af446fcd-25a9-43bb-b5f4-165eba6b6a5d |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0172-L-3/29 - Stormwater - Pit Installation
3df9db46-9b71-40e3-812d-2ccc416b976b |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0172-L-3/29 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
222dd234-b729-4996-84db-b8452cf107c5 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0173-L-3/3 - Stormwater - Pit Installation
5529e5c5-9430-4b82-8d20-89e940af7c29 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0173-L-3/3 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
ca5e51aa-48f3-4744-8c4b-38f0ae441bbb |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0174-L-3/6 - Stormwater - Pit Installation
6df5b74e-a2ca-4082-aa35-142ac896cad7 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0174-L-3/6 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
e3d78c18-487a-47d6-aeeb-895d453cbaf1 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0177-L-4/16 - Stormwater - Pit Installation
5269b963-8313-4142-8604-0f4c230d76b9 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0177-L-4/16 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
596c548a-75d1-4ec4-ab52-66c5145dc0b9 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0179-L-4/23 - Stormwater - Pit Installation
8cb6df02-93a9-486a-b80e-d33820434f72 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0179-L-4/23 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
2b1f623e-029c-469c-82c1-1f5d90b8b99d |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0180-L-4/3 - Stormwater - Pit Installation
92b8edd2-48c3-4717-9bd2-602d3df0a87a |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0180-L-4/3 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
87e110f5-777f-4d46-8815-7d12fa469c80 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0182-L-4/6 - Stormwater - Pit Installation
ef0e178d-ae6b-411a-a23f-7d8c5b814887 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0182-L-4/6 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
f2d0770b-c274-4f00-88da-cefa4869961c |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0193-L-3/5 - Stormwater - Pit Installation
4815ac86-61d0-4e5a-a72a-1504ec02661d |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0193-L-3/5 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
8b911488-6231-44c4-adff-f291e10a8fbe |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0181-L-4/5 - Stormwater - Pit Installation
de44442f-97a2-4032-9f57-7754e5572f75 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0181-L-4/5 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
6e3f5bbb-83da-4ad8-8abe-8a579ddb0d8e |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0186 - L-5/5 - Stormwater - Pit Installation
1076f2e1-9a98-4337-a501-f9a7a7f3e46d |  | pass | ITP-076-CIV-CPD-Pit 5.5 Installation Melbourne Water Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0186 - L-5/5 - Stormwater - Pit Installation | ITP-076-CIV-CPD-Pit 5.5 Installation_Melbourne Water
b2f9afab-e1e3-409b-8fc9-f798b200ba90 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0187-L-5/6 - Stormwater - Pit Installation
e6e31cc8-380c-482c-9489-3aaf27bb7d9a |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0187-L-5/6 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
69b31ccd-04ad-43f2-b1a2-9e693898c7cc |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0183-L-5/1 - Stormwater - Pit Installation
c52a6be0-3e08-41c7-973c-703d01f342b7 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0183-L-5/1 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
67ce652e-28ee-4b7c-b1f2-bda8b042f021 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0188-L-6/1 - Stormwater - Pit Installation
00930ebd-9454-4656-b81e-13a03cc9dec9 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0188-L-6/1 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
b5f0c5e3-c2d0-4ef8-b9ac-81e4c5d12dc5 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0191-L-6/6 - Stormwater - Pit Installation
b000c814-d57b-4f1c-bf14-7566f715a81f |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0191-L-6/6 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
8b2c8ee1-5039-41d2-9330-9cf604548ed5 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0141-L-1/20 - Stormwater - Pit Installation
e5360811-93b0-4398-8292-6ca19cc16eb8 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0141-L-1/20 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
a0f68fc2-572f-4fce-87a0-5677efcfa54e |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0157-L-2/20 - Stormwater - Pit Installation
8e3d2074-88f9-47ca-8651-dd22d01bc7e3 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0157-L-2/20 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
3366c9af-1a2f-449c-af13-baf4e7476b91 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0170-L-3/20 - Stormwater - Pit Installation
a9ba822b-f62c-4930-929c-453ea5d39d88 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0170-L-3/20 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
c9a5e799-dd02-4d9c-9969-82d92af737a3 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0178-L-4/20 - Stormwater - Pit Installation
995dc033-2045-4241-a5d9-bd8e777523d2 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0178-L-4/20 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
0b351173-f3fe-4ab5-9d44-8805848ebb39 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0185-L-5/20 - Stormwater - Pit Installation
54c3b275-aa16-4590-942e-fd3f144fb9fd |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0185-L-5/20 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
47da7fbf-ab1e-4fde-a555-abd20030939a |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0190-L-6/20 - Stormwater - Pit Installation
a65d7895-5d90-47c4-8a4b-906f51132ce5 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0190-L-6/20 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
e1081dd3-2ad0-459f-bdd4-c869843ee49f |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0192-L-7/20 - Stormwater - Pit Installation
2dbd47cd-c522-4fde-b5c8-1be1c328b6ff |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0192-L-7/20 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
a9b06f5f-f6ea-4a86-8e88-13faa65a967d |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0134-L-1/10-Stormwater - Pit Installation
5f7877b5-5bcf-4ab1-a6ca-9ae911a7ea17 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0134-L-1/10-Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
dd127a96-c89b-4d8e-8dc6-4c315908d614 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0155-L-2/10 - Stormwater - Pit Installation
9f0f346a-4bec-4af0-9e22-97d38f1c9acf |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0155-L-2/10 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
4b95c2ed-541b-409b-a35c-2c21da5faf6b |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0168-L-3/10 - Stormwater - Pit Installation
da25869b-53de-4916-a21a-4b8b546a7f6d |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0168-L-3/10 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
25a0c057-5cc5-4a08-81fa-b39e1c9b836d |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0176-L-4/10 - Stormwater - Pit Installation
7a123831-ed6c-43c9-8337-2287365be978 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0176-L-4/10 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
d656c8ab-49a5-4a1d-b80d-bf95a7c263c5 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0184-L-5/10 - Stormwater - Pit Installation
f7208272-64bb-458d-b0b6-e84f16dc433c |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0184-L-5/10 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
2741dabe-ec4e-4a93-afc2-96e2b510d729 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0189-L-6/10 - Stormwater - Pit Installation
e1ec1101-8a1e-4bf2-bd2a-e6eac6d047c0 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0189-L-6/10 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
2f1c7f30-20cb-4c5f-968a-4617c2a29fda |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0194-L-7/10 - Stormwater - Pit Installation
d11bcc19-fea1-4a18-9937-2f9004a1f68f |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0194-L-7/10 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
333cf4b9-56c9-4b58-b45a-5a8c4e335962 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0769-L-7/1 - Stormwater - Pit Installation
29cada2c-1071-43e9-bc8f-a38d380b510a |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0769-L-7/1 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
963ceaf4-392d-42f0-93fb-840f70a985ef |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0775-L-5/18 - Stormwater - Pit Installation
d4261e31-0ac3-4490-bd0a-7fa3af998d67 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater - Pit Installation | 080-0775-L-5/18 - Stormwater - Pit Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
4ab66292-6c30-48e3-9629-7579c4f9d70d |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe
f5bcfcc5-4dd4-4d6e-b0f4-6a613d3eccf6 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0195-L-1/1 to L-6/1 Pipe Installation
086ab5f9-892a-491f-b559-efd8577b4cea |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0195-L-1/1 to L-6/1 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
6e5765ea-38fa-47ad-9606-4c4c0ee7477e |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0196-L-7/1 to L-3/1 Pipe Installation - spare
9b2861b2-e80d-4c29-b577-0fa17f4cb25a |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0196-L-7/1 to L-3/1 Pipe Installation - spare | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
611db6eb-b2ea-4c7e-b511-36e4961de0e0 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0197-L-3/1 to L-4/1 Pipe Installation - spare
842d37c3-8a9f-4cce-84e1-714a0f7a6ce8 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0197-L-3/1 to L-4/1 Pipe Installation - spare | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
dbcf5f11-2a5d-4a99-8afe-e20f3538ddd3 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0198-L-4/1 to L-5/1 Pipe Installation - spare
1bdc7585-14a5-4489-a1f4-903488274002 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0198-L-4/1 to L-5/1 Pipe Installation - spare | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
aa0feccf-5d3d-4db8-b6d6-d7ed77952518 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0199-L-5/1 to L-6/1 Pipe Installation - spare
2e457a71-d8d0-4d84-8bef-a1bbea279ba4 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0199-L-5/1 to L-6/1 Pipe Installation - spare | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
e0736670-805f-4645-9701-2d5fa6bdeeb0 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0200-L-6/1 to L-6/20 Pipe Installation
89b2053c-3271-4551-9841-c1a1428768a3 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0200-L-6/1 to L-6/20 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
23e3f6b3-c077-4fdd-a3c8-0c1911f9fa47 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0201- L-1/1A to L-1/1 Pipe Installation
e3f1bb7b-1be1-4297-b748-d88c31e258ad |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0201- L-1/1A to L-1/1 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
c692b566-7875-42fc-934c-12bfbb8cfea9 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0202 - L-1/3 to L-2/3 Pipe Installation
a82b1b17-0916-437d-ab34-8da33526d248 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0202 - L-1/3 to L-2/3 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
25040d38-7eeb-4a44-a5c6-c3599458b160 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0463 - L-2/3 to L-3/3 Pipe Installation
fe9988ae-83da-467e-a35d-60c1cde9a3c9 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0463 - L-2/3 to L-3/3 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
34c17a9f-343c-4682-9a67-cf969f08a1a2 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0203 - L-3/3 to L-4/3 Pipe Installation
4e8ae120-9e83-43c3-b758-9a7a39ce6d0e |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0203 - L-3/3 to L-4/3 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
09f318d0-fda0-4f45-b695-0714a44178a1 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0204-L-4/3 to L-5/5 Pipe Installation
1244f2a3-fc48-461a-9f65-73ae4583124a |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0204-L-4/3 to L-5/5 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
2d7ece8c-f0c9-49bf-8c98-1a06549fe0b2 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0205-L-1/4 to L-4/5 Pipe Installation
a7c0fc8e-8600-4084-9faa-b6efc965f788 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0205-L-1/4 to L-4/5 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
a28b6d3a-0a62-4d31-ab3b-9aece59eaf60 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0206-L-4/5 to L-5/5 Pipe Installation
7d0336e8-c99b-4e3a-8a71-463074500063 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0206-L-4/5 to L-5/5 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
3fb42eda-ee06-46de-82ab-874fc45f2dd0 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0207-L-5/5 to L-6/5 Pipe Installation
75325953-e8ff-4fcd-876d-7c4e4abf45c1 |  | work-in-progress | ITP-075-CIV-CPD-General Concrete Melbourne Water Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0207-L-5/5 to L-6/5 Pipe Installation | ITP-075-CIV-CPD-General Concrete Melbourne Water
8113175f-0c84-44b2-b021-664462591aad |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0208-L-1/6 to L-2/6 Pipe Installation
91b1b302-855b-4b85-b08e-29f0b44d714e |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0208-L-1/6 to L-2/6 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
0cf9ba82-54da-470f-8cee-44ddcf052129 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0209-L-2/6 to L-3/6 Pipe Installation
141a7d2c-06e9-4e1e-9f8c-a689fa7c4f63 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0209-L-2/6 to L-3/6 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
28fdc305-2ddc-41bc-b79b-5bd5dd99b3db |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0210-L-3/6 to L-4/6 Pipe Installation
63f5ea22-dc25-4b25-afb9-57f76a344cec |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0210-L-3/6 to L-4/6 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
9f182c72-4333-46e5-bea4-b699c888d64c |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0211-L-4/6 to L-5/6 Pipe Installation
2bcda234-a569-4f79-bed6-d9aad13ee04e |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0211-L-4/6 to L-5/6 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
52a8a5d0-48b7-4d20-b9e9-8caaf8b76b34 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0212-L-5/6 to L-6/6 Pipe Installation
bb3f23ec-9484-402f-8af2-d986e8a10d0d |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0212-L-5/6 to L-6/6 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
df4a3314-1c32-4e3f-b694-f3039bcfb330 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0213-L-6/6 to L-7/6 Pipe Installation
7a4d2635-f138-484c-afce-2290fe2b1b64 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0213-L-6/6 to L-7/6 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
aa801978-9223-43db-9388-fff557a4d6a1 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0214-L-1/7 to L-2/7 Pipe Installation
86e1e95f-dd25-44b2-81eb-01941ea9af72 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0214-L-1/7 to L-2/7 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
f7509988-5629-409f-9aef-79202a9c7b25 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0215-L-1/10 to L-2/10 Pipe Installation
cb2af39e-3c95-4947-8bd5-e5da241be074 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0215-L-1/10 to L-2/10 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
e12cedb2-29bb-4bab-9eea-af125aecbf81 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0216-L-2/10 to L-3/10 Pipe Installation
6120cb64-d041-4744-9d69-ea88aee287ae |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0216-L-2/10 to L-3/10 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
5389aa96-1e3e-463c-92d8-111adae6bced |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0217 - L-3/10 to L-4/10 Pipe Installation
04633f38-0339-486e-9d0c-9f2ed626e9c9 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0217 - L-3/10 to L-4/10 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation Rev 0
c6eea030-b1be-4aeb-818c-263e9ba4f295 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0218 - L-4/10 to L-5/10 Pipe Installation
70ceb709-1b47-4290-bd78-ac7a29d9d972 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0218 - L-4/10 to L-5/10 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation Rev 0
3d32931e-1fec-4e50-a03a-f960f89c2fb1 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0219 - L-5/10 to L-6/10 Pipe Installation
453e595d-447c-4f89-8d82-f913ec762680 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0219 - L-5/10 to L-6/10 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation Rev0
389d20d5-97ae-429b-88f1-5a8e935e09ac |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0220 - L-6/10 to L-7/10 Pipe Installation
6ff4427e-803b-46b3-9244-66cb95f6b53f |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0220 - L-6/10 to L-7/10 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
e1c47165-328f-45b2-81ac-feaa130b3bc4 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0221 - L-1/13 to L-2/3 Pipe Installation
056fa8df-4c07-4fd6-b728-ca50753ffd4a |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0221 - L-1/13 to L-2/3 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
c8b83c72-5cd1-45b8-9dfb-88a1c3e37548 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0222 - L-1/15 to L-2/15 Pipe Installation
3eb0ca7c-f977-4bea-bb8a-832cb171a866 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0222 - L-1/15 to L-2/15 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
b2e27395-51af-4250-b004-5f670b806773 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0223 - L-1/16 to L-2/16 Pipe Installation
399fe4b9-3c57-4a7c-815f-043be1ae41f7 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0223 - L-1/16 to L-2/16 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
99b5f725-3623-441a-a92b-16614bc14f34 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0224 - L-2/16 to L-3/16 Pipe Installation
12afcead-8af0-43a1-afcb-9648bc30bd2d |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0224 - L-2/16 to L-3/16 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
f5cf707a-38bc-480a-9bbc-cce45a252133 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0225 - L-3/16 to L-4/16 Pipe Installation
a706ce19-f6b6-464f-9065-c8959acdf683 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0225 - L-3/16 to L-4/16 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
b3760cbb-10e4-4af9-b447-63519d0bf359 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0226 - L-3/16 to L-1/6 Pipe Installation
ec68ccb6-491c-4b2d-b44b-ef00a4c5e4e5 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0226 - L-3/16 to L-1/6 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
cd3fdcf5-f385-4503-87af-05430a93f809 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0227 - L-1/16A to L-2/16A Pipe Installtion
e9271228-92e4-4c05-aa16-50bff349bec8 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0227 - L-1/16A to L-2/16A Pipe Installtion | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
7b7a8bdd-9602-4246-9049-1cc1112d596f |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0228 - L-2/16A to L-2/16 Pipe Installation
aa904f3b-f2e4-4f00-a706-c9678609d1d2 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0228 - L-2/16A to L-2/16 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
59d33d1e-4252-44da-9627-81e97a3c0e70 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0229 - L-1/16C to L-4/16 Pipe Installation
ed3e2e75-fc80-49dd-974c-4b35bba7f898 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0229 - L-1/16C to L-4/16 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
4b1cc137-699d-4fc3-b82d-1c6c904699da |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0230 - L-1/17 to L-2/17 Pipe Installation
6765b3ec-7dc8-4ce5-82cd-8a22c4ec3bd7 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0230 - L-1/17 to L-2/17 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
2af1125d-0ef8-4578-adb5-8a26ab483dd3 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0231 - L-3/17 to L-1/1 Pipe Installation
9dae2f76-0f95-4720-8951-77ef7dd57eac |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0231 - L-3/17 to L-1/1 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
bc212018-a2b0-4a72-963d-9c96d55e226c |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0232 - L-1/1A to L-2/17A Pipe Installation
8c5fe86e-30c0-49ea-830e-6291eb8a2733 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0232 - L-1/1A to L-2/17A Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
174d0678-cb8e-42d5-a893-417f1a113489 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0233 - L-2/17A to L-2/17 Pipe Installation
9b24744d-af53-4791-93fa-e108906bcb88 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0233 - L-2/17A to L-2/17 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
81bf4226-6b60-4135-af30-22afc7b4b996 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0234 - L-1/18 to L-2/18 Pipe Installation
7aa28cf3-d6ff-4690-a601-2d6b2f8ca951 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0234 - L-1/18 to L-2/18 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
c9cd6cc5-dad7-4bfc-8618-089a3b88a53a |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0235 - L-2/18 to L-3/18 Pipe Installation
7fe7a9f1-fae8-46ea-8a3e-942c64770a91 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0235 - L-2/18 to L-3/18 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
6062c42b-c3b1-4c72-9212-471e603ed976 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0236 - L-3/18 to L-2/1 Pipe Installation
e65e2a85-b78f-41e1-b6f7-f60816a571e4 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0236 - L-3/18 to L-2/1 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
2f9a155b-f740-47b5-9d4b-fd8652008440 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0237 - L-1/18 to L-1/18A Pipe Installation
41ad77d9-e926-4d98-b455-8d058a335b22 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0237 - L-1/18 to L-1/18A Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
ac10c314-fb75-45b0-b486-2016dbd2d07c |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0238 - L-1/18B to L-2/18B Pipe Installation
6ee86bb2-d0ca-4990-9c07-f07cec24b1cc |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0238 - L-1/18B to L-2/18B Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
39954182-3df2-4207-8726-8887dace2368 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0239 - L-1/18C to L-3/18 Pipe Installation
fa5795a4-5adc-4540-a733-5d133e2dc997 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0239 - L-1/18C to L-3/18 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
0747fb4b-1f15-4574-af69-38cdde9a60a4 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0240 - L-1/20 to L-2/20 Pipe Installation
54afe039-ef3e-463d-8e87-baa3fe08ee5a |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0240 - L-1/20 to L-2/20 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
8aa8bdbc-9cab-4024-be02-4dca7b720f87 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0241 - L-2/20 to L-3/20 Pipe Installation
e79b9f75-437e-4215-aa98-5fa467fdd8dd |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0241 - L-2/20 to L-3/20 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
6034fbab-b2a7-42a9-8b0c-76a75ecc6fbd |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0242 - L-3/20 to L-4/20 Pipe Installation
be20379d-4f2f-4f57-9d16-eb98c9138863 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0242 - L-3/20 to L-4/20 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
ba77dbbd-595e-4b88-a65f-e6fd1bc22c31 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0243 - L-4/20 to L-5/20 Pipe Installation
ddcf4cf6-8f8d-496a-84ae-02025fcb57ea |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0243 - L-4/20 to L-5/20 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
cfde95a5-ba71-479a-be37-840ce8b82b18 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0244 - L-5/20 to L-6/20 Pipe Installation
66c59066-283b-41d4-8294-4c6d9e9570e7 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0244 - L-5/20 to L-6/20 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
87c5934a-0b42-4132-8f25-aee7e4e695b1 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0245 - L-6/20 to L-7/20 Pipe Installation
b513f959-8a78-4054-bbe6-729856985fb6 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0245 - L-6/20 to L-7/20 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
04421a77-d399-4c71-8355-d813f1cc535e |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0246 - L-7/20 to L-5/5 Pipe Installation
37188c8b-50ef-4f7b-9b5d-67930d4ebe51 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0246 - L-7/20 to L-5/5 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
f81f2a58-924f-46c6-b8d5-40aab669ac56 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0247 - L-1/21 to L-2/21 Pipe Installation
598312bc-6c51-454a-9201-acf8a9cf098b |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0247 - L-1/21 to L-2/21 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
cb48d9ec-1ca3-4d6a-b8b1-096bceab00d4 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0248 - L-2/21 to L-3/3 Pipe Installation
40ca2c2c-a623-447e-af8b-c03194521489 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0248 - L-2/21 to L-3/3 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
8daee7fe-7846-4ed3-8136-7751337d036b |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0249 - L-1/22 to L-2/22 Pipe Installation
242f96dc-a060-4e06-a720-e176421f5dd3 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0249 - L-1/22 to L-2/22 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
c38e5453-8aa6-4e90-bc39-ed67ba073594 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0250 - L-1/23 to L-2/23 Pipe Installation
b84128c4-1725-4a11-803f-8383c2a869c4 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0250 - L-1/23 to L-2/23 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
4183475e-e5d4-45fe-bbe1-9ef1df41a4d3 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0251 - L-2/23 to L-3/23 Pipe Installation
68322794-6dfd-4472-9ec2-f324aee9d6b2 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0251 - L-2/23 to L-3/23 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
eeca0d41-9e08-4a94-b710-31484eba307a |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0252 - L-3/23 to L-4/23 Pipe Installation
25c815a6-c94c-4117-9766-61774a9edc23 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0252 - L-3/23 to L-4/23 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
9c86b483-a10b-4829-b635-48baf6065851 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0253 - L-4/23 to L-3/5 Pipe Installation
78e473eb-a0df-47ba-a5ab-3b6a9e4a64c1 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0253 - L-4/23 to L-3/5 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
695d6dbd-9833-4111-b128-805433e6936b |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0254 - L-1/24 to L-2/24 Pipe Installation
27f54c14-e483-48e2-8915-b682acff9f69 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0254 - L-1/24 to L-2/24 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
9aa4f2fb-9ce1-462e-9bea-266b174fbd91 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0255 - L-1/25 to L-2/25 Pipe Installation
9c9019d0-f945-41be-83f8-b073aba28e75 |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0255 - L-1/25 to L-2/25 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
1d26aafd-2400-48df-9543-7357cfd31560 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0256 - L-1/27 to L-2/27 Pipe Installation
e2621eb7-5621-44bb-a867-a3f7530c4b0b |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0256 - L-1/27 to L-2/27 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
333653ee-ceac-42be-91e9-ed1c0454ee95 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0257 - L-1/28 to L-2/29 Pipe Installation
549c527d-0b9d-4588-9661-1b1518657f68 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0257 - L-1/28 to L-2/29 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
aa8c1f9c-d92d-4bc2-896d-b8ffbfaf3a8c |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0258 - L-1/29 to L-2/29 Pipe Installation
8dc92903-3813-41ad-a478-07ab2d7f3811 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0258 - L-1/29 to L-2/29 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
1b3a71e5-1c80-476c-8429-b931846715bd |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0259 - L-2/29 to L-3/29 Pipe Installation
b08021e8-748f-4200-87d0-60135d54b321 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0259 - L-2/29 to L-3/29 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
cf1a340a-7a15-4af3-84c5-5013722a0fd5 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0260 - L-1/30 to L-2/30 Pipe Installation
a34214f3-7aab-4747-a743-c1610ddcd9e8 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0260 - L-1/30 to L-2/30 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
f394d819-e1c8-4ae6-a3cf-519c489b5fc6 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0261 - L-2/30 to L-3/30 Pipe Installation
351d9088-c91a-4896-a43d-1e273af98a89 |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0261 - L-2/30 to L-3/30 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
4a0c4688-d897-442c-a929-61de5f56e6fe |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0262 - L-1/31 to L-2/31 Pipe Installation
2ef5e80a-a40e-4900-bdb2-426329e5d8de |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0262 - L-1/31 to L-2/31 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
3820053c-674b-45ba-8510-7c8dd99d6640 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0263 - L-2/31 to L-3/31 Pipe Installation
ba6a9d39-8ce4-4cb4-bfd8-02119241110e |  | not-started | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0263 - L-2/31 to L-3/31 Pipe Installation | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
07bc48a3-4529-40b4-9acf-b8e055a17fec |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0533- L-5/5 to L-6/5 Pipe Installation
239c6dfc-7b5c-4371-a70d-72d6c5d8aa8d |  | pass | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0533- L-5/5 to L-6/5 Pipe Installation | 080-0533-ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation (Splay install)
ce77029c-81d6-4732-98df-1967e238c1ca |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0768-L-2/1 to L-7/1 Pipe Installation - spare
f60371fa-87f3-40cb-9011-c70a00a3e635 |  | work-in-progress | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Stormwater Pipe | 080-0768-L-2/1 to L-7/1 Pipe Installation - spare | ITP-048-CIV-CPD - Stormwater Drainage Supply & Installation
0d14d220-2b51-591e-b8ce-12d937cc7d3e |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection
616e242a-e9b7-4cc9-a50c-cf75a824f65b |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | 080-0552 - Materials Inspection - Concrete Pipes 1200 mm - 16/03/2023
5e620f33-fa43-44b2-8477-ed1c1a785094 |  | pass | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | 080-0552 - Materials Inspection - Concrete Pipes 1200 mm - 16/03/2023 | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
122f770c-2e2d-4e33-8021-c5ef5f3ab493 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 1200 mm - 17/03/2023
b1466c9e-4253-5204-a0bc-7318bb7f28bb |  | work-in-progress | 6b4260dbe84110816b723c9ad858b7f7155f0a9e658637f442f1c6892d729929 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 1200 mm - 17/03/2023 | Materials Inspection Checklist - Concrete Pipes 1200 mm - Load 2
075b4db7-7f8e-4689-acf1-d0476b982288 |  | pass | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 1200 mm - 17/03/2023 | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
b1b36aac-85cc-4a9d-82d7-164ab487f982 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 1200 mm - 11/05/2023
e15fe6b6-437d-5bad-9ccd-988fbf2cf1c0 |  | work-in-progress | 6b4260dbe84110816b723c9ad858b7f7155f0a9e658637f442f1c6892d729929 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 1200 mm - 11/05/2023 | Materials Inspection Checklist - Concrete Pipes 1200 mm - Load 3
8dc65039-5f4c-4b45-8a82-3da600fdd4d9 |  | pass | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 1200 mm - 11/05/2023 | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
e141d8fa-103d-4c11-8766-dffe6447e9df |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 1200 mm - 12/05/2023
d2e4bc1f-b9ed-5792-ba62-d32821009d31 |  | work-in-progress | 6b4260dbe84110816b723c9ad858b7f7155f0a9e658637f442f1c6892d729929 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 1200 mm - 12/05/2023 | Materials Inspection Checklist - Concrete Pipes 1200 mm - Load 4
10ba022b-40cf-453d-9603-010430e95adb |  | work-in-progress | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 1200 mm - 12/05/2023 | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
f587c78b-2fe1-48e3-9466-56d6fb6f1f2d |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | 080-0553 - Calder - Materials Inspection - Concrete Pipes 900 mm - 11/05/2023
b766cf0d-f3c1-4442-8beb-87b5774ad2b1 |  | pass | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | 080-0553 - Calder - Materials Inspection - Concrete Pipes 900 mm - 11/05/2023 | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
323536dd-53f2-4241-80ea-a13254a90ef6 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | 080-0663 - Calder - Materials Inspection - Concrete Pipes 900 mm - 23/05/2023
639f3284-715e-44d3-8cba-c8cb1476e467 |  | pass | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | 080-0663 - Calder - Materials Inspection - Concrete Pipes 900 mm - 23/05/2023 | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
dc87a599-9316-4045-a921-3d0e0932f1f5 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 900 mm - 23/05/2023 - Load 2
1598e169-bdbb-5766-ad4d-162f28a0199b |  | work-in-progress | 6b4260dbe84110816b723c9ad858b7f7155f0a9e658637f442f1c6892d729929 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 900 mm - 23/05/2023 - Load 2 | Materials Inspection Checklist - Concrete Pipes 900 mm - Load 4
87c73328-5598-40d6-b4db-b27530f7206e |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 900 mm - 23/05/2023 - Load 3
4467f874-3d41-549f-b005-6934be7c6f4b |  | work-in-progress | 6b4260dbe84110816b723c9ad858b7f7155f0a9e658637f442f1c6892d729929 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 900 mm - 23/05/2023 - Load 3 | Materials Inspection Checklist - Concrete Pipes 900 mm - 23/05/2023 - Load 3
9ea911bd-9819-42dd-8a6f-e2df2faf1922 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 900 mm - 23/05/2023 - Load 4
057f2fb3-90c7-58d3-ba4a-3793c4247606 |  | work-in-progress | 6b4260dbe84110816b723c9ad858b7f7155f0a9e658637f442f1c6892d729929 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 900 mm - 23/05/2023 - Load 4 | Materials Inspection Checklist - Concrete Pipes 900 mm - 23/05/2023 - Load 4
8d332a82-10d1-4447-8b3c-d294b8aa9b5e |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 900 mm - 23/05/2023 - Load 5
4cf5d3b3-08f0-5a9c-886a-81c42e46d63e |  | work-in-progress | 6b4260dbe84110816b723c9ad858b7f7155f0a9e658637f442f1c6892d729929 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 900 mm - 23/05/2023 - Load 5 | Materials Inspection Checklist - Concrete Pipes 900 mm - 23/05/2023 - Load 5
5f95135b-f3ee-498d-8b67-43bf9aae00e0 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | 080-0664 - Calder - Materials Inspection - Concrete Pipes 900 mm - 24/05/2023
39d804e1-d5b4-46d3-a180-779ba007c4d0 |  | pass | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | 080-0664 - Calder - Materials Inspection - Concrete Pipes 900 mm - 24/05/2023 | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
cb99ee0b-d440-4836-ab67-06c0d67ff039 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 900 mm - 24/05/2023 - Load 2
81b0b860-b4ca-59e6-a011-2250b028be40 |  | work-in-progress | 6b4260dbe84110816b723c9ad858b7f7155f0a9e658637f442f1c6892d729929 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 900 mm - 24/05/2023 - Load 2 | Materials Inspection Checklist - Concrete Pipes 900 mm - 24/05/2023 - Load 2
b6c51231-5d5b-4513-8c82-f2122304de71 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 900 mm - 24/05/2023 - Load 3
c911ed96-8fc5-570a-a061-4326c7db6247 |  | work-in-progress | 6b4260dbe84110816b723c9ad858b7f7155f0a9e658637f442f1c6892d729929 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 900 mm - 24/05/2023 - Load 3 | Materials Inspection Checklist - Concrete Pipes 900 mm - 24/05/2023 - Load 3
26795c52-597f-4147-b288-e2ec39d98208 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 900 mm - 24/05/2023 - Load 4
45c82782-c395-526b-87ea-4a0ea003ce4f |  | work-in-progress | 6b4260dbe84110816b723c9ad858b7f7155f0a9e658637f442f1c6892d729929 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 900 mm - 24/05/2023 - Load 4 | Materials Inspection Checklist - Concrete Pipes 900 mm - 24/05/2023 - Load 4
1360e43d-1044-4b1d-8c0b-1d4218ef616b |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 900 mm - 24/05/2023 - Load 5
1121ffb1-723c-5c4e-9b57-0d597e7acbb7 |  | work-in-progress | 6b4260dbe84110816b723c9ad858b7f7155f0a9e658637f442f1c6892d729929 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | Materials Inspection Checklist - Concrete Pipes 900 mm - 24/05/2023 - Load 5 | Materials Inspection Checklist - Concrete Pipes 900 mm - 24/05/2023 - Load 5
3b368d05-907e-4358-a627-9064eae85345 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | 080-0556 - Calder - Materials Inspection Checklist - Precast pit 4/5
68caf26c-ac5b-4c1e-99d1-510ed5ce44a9 |  | pass | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | 080-0556 - Calder - Materials Inspection Checklist - Precast pit 4/5 | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
325cbcc5-440f-44f7-b568-f0eead7e6781 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | 080-0557 - Calder - Materials Inspection Checklist - Precast pit 5/5
3352974c-754f-48ec-9428-7c735f394d5c |  | pass | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | 080-0557 - Calder - Materials Inspection Checklist - Precast pit 5/5 | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection
996dada8-0aa0-4d8f-b1ad-b62a11baea99 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | 080 - 0555 - Calder - Materials Inspection - Precast pit delivery 15/04/2024
0d6c216a-832e-4154-a72d-a6f67fb55430 |  | pass | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | 080 - 0555 - Calder - Materials Inspection - Precast pit delivery 15/04/2024 | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection Rev 1
f4a0bb5c-09fc-440e-b5af-f814142a6ab8 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | 080-0554 - Calder - Materials Inspection - Precast pit delivery 07/09/2023
876198e6-dc83-42f6-9dee-ec84458cbfcb |  | pass | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Road Drainage - Material Inspection | 080-0554 - Calder - Materials Inspection - Precast pit delivery 07/09/2023 | CHK-003-CIV-Precast Reinforced Concrete Pipes & Pits - Material Delivery Inspection Rev 1
d9aa67b0-3a68-46d2-82a9-2010059cb9b5 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Subsoils
d8584ec9-9193-4eb0-85bd-2d9935bcf0ba |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Subsoils | South Main Alignment Subsoil
9332770d-cd78-4dbe-947d-f632f5c31955 |  | not-started | ITP-054-CPD-Subsurface Drainage (Supply and Install) - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Subsoils | South Main Alignment Subsoil | ITP-054-CPD-Subsurface Drainage (Supply and Install)
d2703b7c-2245-413f-8f22-e975bca4a79e |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Subsoils | North Main Alignment Subsoil
88461aaa-85d4-4487-a873-559c8bb80ae7 |  | not-started | ITP-054-CPD-Subsurface Drainage (Supply and Install) - Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CDR-0013-0 - Road Drainage | Subsoils | North Main Alignment Subsoil | ITP-054-CPD-Subsurface Drainage (Supply and Install)
ce934808-ad1e-4c22-affa-f15f503754fb |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0020-0 - Permanent Lighting Design
08a6a0da-b0ad-4104-b6eb-ef138ee5b1dd |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0020-0 - Permanent Lighting Design | Site Wide
050609bb-038e-4cd9-bf1e-fa6bda1aefc5 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0020-0 - Permanent Lighting Design | Site Wide | Calder Park Drive (North)
e7f04739-95e1-4403-ab62-a41f3e26d227 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0020-0 - Permanent Lighting Design | Site Wide | Calder Park Drive (North) | ITP-CIV-Conduit and Pit - Roads (Supply and Install) Rev 2
be693c85-8155-47d1-89e9-eff980d9a2cd |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0020-0 - Permanent Lighting Design | Site Wide | Calder Park Drive (South)
0a6f3478-52f1-4cd7-a733-8eaaf6273784 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0020-0 - Permanent Lighting Design | Site Wide | Calder Park Drive (South) | ITP-CIV-Conduit and Pit - Roads (Supply and Install) Rev 2
2b52a0c1-2aa3-4353-89b9-4ca94a7cef0e |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0020-0 - Permanent Lighting Design | Site Wide | Calder Park Drive (North)
d2ee0c24-0a0e-4077-9cf0-437810de2a1c |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0020-0 - Permanent Lighting Design | Site Wide | Calder Park Drive (North) | ITP-CIV-Supply & Installation of Street Lighting (Vic Road) Rev 1
e1aeb880-d466-4145-a2c9-751560b4dc15 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0020-0 - Permanent Lighting Design | Site Wide | Calder Park Drive (South)
df39b0e0-1e2c-4644-80bd-c92f8b69aa7d |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0020-0 - Permanent Lighting Design | Site Wide | Calder Park Drive (South) | ITP-CIV-Supply & Installation of Street Lighting (Vic Road) Rev 1
beb565ec-0cb4-4e53-be4a-dc00e1e13374 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0020-0 - Permanent Lighting Design | Site Wide | Contingency lots
0e6e107e-b281-4033-ad2f-8e1ce09c812e |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0021-0 - Greater Western Water - Water and Sewer
3a57b0ca-7595-4660-8f38-5a3b9ad71559 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0021-0 - Greater Western Water - Water and Sewer | Water Main Relocation (Subcontractor ITP)
31538a07-f4a0-466e-a5a8-0683558e38e2 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0021-0 - Greater Western Water - Water and Sewer | Water Main Relocation (Subcontractor ITP) | 080-0672 - Calder - GWW Combined Trench
410ec27f-e578-4bcb-ab52-7657429bb153 |  | pass | ITP-148-CIV-CPD-Chadoak Water Main Relocation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CUT-0021-0 - Greater Western Water - Water and Sewer | Water Main Relocation (Subcontractor ITP) | 080-0672 - Calder - GWW Combined Trench | ITP-148-CIV-CPD-Chadoak Water Main Relocation
3e33e378-3b2a-4f2c-ad0c-10ba4ce157f1 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0021-0 - Greater Western Water - Water and Sewer | Water Main Relocation (Subcontractor ITP) | 080-0673 - Calder - GWW - North and South Connection
8f7f5c0e-1cb7-4f9c-b343-8d52d302cde7 |  | pass | ITP-148-CIV-CPD-Chadoak Water Main Relocation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CUT-0021-0 - Greater Western Water - Water and Sewer | Water Main Relocation (Subcontractor ITP) | 080-0673 - Calder - GWW - North and South Connection | ITP-148-CIV-CPD-Chadoak Water Main Relocation
1b8a14e3-d7e2-4cf2-9c31-345fb0129ec9 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0021-0 - Greater Western Water - Water and Sewer | Water Main Relocation (Subcontractor ITP) | 080-0674 - Calder - GWW - Valve Installation
af090b9b-b531-468f-8f53-01d25e72c830 |  | pass | ITP-148-CIV-CPD-Chadoak Water Main Relocation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CUT-0021-0 - Greater Western Water - Water and Sewer | Water Main Relocation (Subcontractor ITP) | 080-0674 - Calder - GWW - Valve Installation | ITP-148-CIV-CPD-Chadoak Water Main Relocation
a0178daa-c3f6-4f80-a43e-09686c9d02af |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0021-0 - Greater Western Water - Water and Sewer | GWW Sewer Manhole Riser
94bd0563-894e-47d3-9de8-4c0c2b409a30 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0021-0 - Greater Western Water - Water and Sewer | GWW Sewer Manhole Riser | 080-0675 - Calder - GWW Sewer Manhole Riser
73edf201-0f3e-4702-ab60-cb4c661111b3 |  | pass | ITP-149-CIV-CPD-Chadoak Manhole Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CUT-0021-0 - Greater Western Water - Water and Sewer | GWW Sewer Manhole Riser | 080-0675 - Calder - GWW Sewer Manhole Riser | ITP-149-CIV-CPD-Chadoak Manhole
0cdb4792-3cd8-49d7-8fa5-d171268ef998 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0022-0 - Combined Utility Coordination - Jemena/NBN
23689bfe-f2b9-44de-8325-5fbf1d74fda7 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0022-0 - Combined Utility Coordination - Jemena/NBN | Contingency
f974caa0-810d-428c-92f1-90cd23d447e2 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0022-0 - Combined Utility Coordination - Jemena/NBN | Jemena HV
54621fd2-31f3-40b7-b644-cf506a4ffc73 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0022-0 - Combined Utility Coordination - Jemena/NBN | Jemena UG conduit
690dac33-2367-4ca5-b8f4-da546c3a874f |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0022-0 - Combined Utility Coordination - Jemena/NBN | Jemena UG conduit | 080-0311 - Jemena UG conduit installation - All locations
48199520-1663-4839-8579-b487254b1473 |  | pass | ITP-113-CIV-CPD- Jemena Conduit & Pits (Supply & Install) Rev1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CUT-0022-0 - Combined Utility Coordination - Jemena/NBN | Jemena UG conduit | 080-0311 - Jemena UG conduit installation - All locations | ITP-113-CIV-CPD- Jemena Conduit & Pits (Supply & Install) Rev1
0e51b08f-0e58-42b2-8869-f193dfe20e0b |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0022-0 - Combined Utility Coordination - Jemena/NBN | Jemena UG Bore
15b4330a-53d7-45af-81ff-f56f601914e6 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CUT-0022-0 - Combined Utility Coordination - Jemena/NBN | Jemena UG Bore | 080-0312 - Jelmac - Underboring
57357f14-6086-4f33-9039-bd159f14f769 |  | pass | ITP-114-CIV-CPD -Jemena Conduit Bore Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CUT-0022-0 - Combined Utility Coordination - Jemena/NBN | Jemena UG Bore | 080-0312 - Jelmac - Underboring | ITP-114-CIV-CPD -Jemena Conduit Bore Rev 1
ef695e6d-24de-4463-bc57-9f26db63f02d |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall
87af9288-d1a2-4a0d-8481-4d406690699a |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01
dfbbf567-e8d9-4c7d-a164-d88ad5e57834 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0426 - Calder - Wire Wall Installation Main - RW01
ad3f28fd-b448-408e-ab9c-ccb9d138b464 |  | not-started | ITP-126-CIV-RSS Wire Facing Wall Main Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0426 - Calder - Wire Wall Installation Main - RW01 | ITP-126-CIV-CPD-Wire Facing Wall Main Rev 0
276124fe-4b63-41ec-a84a-c108a0c53e04 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0677- Calder - Wire Wall - RW01 - Row 1
eeb785ef-0a61-4b3b-8f17-871afe54e7db |  | work-in-progress | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0677- Calder - Wire Wall - RW01 - Row 1 | CHK-010-CIV-CPD-Wire faced wall Installation
43fccd18-d7cc-4ca6-985e-d34e8d923a03 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0678 - Calder - Wire Wall - RW01 - Row 2 - 01
7f3c1fe6-5f46-45bb-8ee4-4f7cea26ad41 |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0678 - Calder - Wire Wall - RW01 - Row 2 - 01 | CHK-010-CIV-CPD-Wire faced wall Installation
6279a9d9-d6ba-4f3c-badb-ed80330c53a5 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0683 - Calder - Wire Wall - RW01 - Row 2 - 02
015f2a1b-b313-41c3-8c67-bf9158489ae5 |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0683 - Calder - Wire Wall - RW01 - Row 2 - 02 | CHK-010-CIV-CPD-Wire faced wall Installation
add4a4db-57e6-4855-8ca5-a1420e052164 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0684 - Calder - Wire Wall - RW011 - Row 3 - 01
653b2b92-e1b3-4e38-b3fa-27840f35f61c |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0684 - Calder - Wire Wall - RW011 - Row 3 - 01 | CHK-010-CIV-CPD-Wire faced wall Installation
b563be30-f0f1-4d00-b7e8-a7f1dd6c7a46 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0685 - Calder - Wire Wall - RW01 - Row 3 - 02
184c0695-678a-4f8b-a4c4-2dea136ff830 |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0685 - Calder - Wire Wall - RW01 - Row 3 - 02 | CHK-010-CIV-CPD-Wire faced wall Installation
c65eac4f-8821-4fe2-baf8-0cbb512edcfe |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0686 - Calder - Wire Wall - RW01 - Row 4 - 01
6709b7ab-6347-49a5-97c1-1fed3cb483bb |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0686 - Calder - Wire Wall - RW01 - Row 4 - 01 | CHK-010-CIV-CPD-Wire faced wall Installation
18f54926-e8cc-4bc5-a669-3bf95925dd6f |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0687 - Calder - Wire Wall - RW01 - Row 4 - 02
3906d033-2ec0-41f3-9948-f07821db6a46 |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0687 - Calder - Wire Wall - RW01 - Row 4 - 02 | CHK-010-CIV-CPD-Wire faced wall Installation
33f8a07d-e577-41be-976c-9b0157ad659f |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0688 - Calder - Wire Wall - RW01 - Row 5
cb75b887-a25a-4ccd-94c0-c52d023f0775 |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0688 - Calder - Wire Wall - RW01 - Row 5 | CHK-010-CIV-CPD-Wire faced wall Installation
7afd2802-d5ff-4cbe-8347-2da16a8165c4 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0689 - Calder - Wire Wall - RW01 - Row 6
eca350c7-f6c6-4803-80b5-4fe85ca56447 |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0689 - Calder - Wire Wall - RW01 - Row 6 | CHK-010-CIV-CPD-Wire faced wall Installation
a65b28c8-0ee8-4bf3-9c27-d4b4d17eab40 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0690 - Calder - Wire Wall - RW01 - Row 7
14a8617a-1599-4e2e-a6e3-ce05853d230f |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0690 - Calder - Wire Wall - RW01 - Row 7 | CHK-010-CIV-CPD-Wire faced wall Installation
f13ac93c-fbc9-4553-8914-0ea6470e55ad |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0691 - Calder - Wire Wall - RW01 - Row 8
d7a32ce7-a877-4e7b-bd1c-5c883dc3cdf5 |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0691 - Calder - Wire Wall - RW01 - Row 8 | CHK-010-CIV-CPD-Wire faced wall Installation
4f068201-3992-45ef-a03d-86aca576f8fa |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0692 - Calder - Wire Wall - RW01 - Row 9 - 01
5aeb3253-2f12-40f0-9f9e-83771ffe96ca |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0692 - Calder - Wire Wall - RW01 - Row 9 - 01 | CHK-010-CIV-CPD-Wire faced wall Installation
4b808d5b-ed08-495f-9c8e-2727d1b50a1a |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0693 - Calder - Wire Wall - RW01 - Row 9 - 02
46fbd595-632b-44e7-803d-853e6b46323b |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0693 - Calder - Wire Wall - RW01 - Row 9 - 02 | CHK-010-CIV-CPD-Wire faced wall Installation
b5a1fe74-8670-4667-8642-a9c68dbef2a6 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0715 - Calder - Wire Wall - RW01 - Row 10
e4599aeb-dbe9-458d-a1e1-3f39ef2bdd95 |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0715 - Calder - Wire Wall - RW01 - Row 10 | CHK-010-CIV-CPD-Wire faced wall Installation
6a3023b5-d434-43af-893c-81a7cd48edb9 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0747- Calder - Wire Wall - RW01 - Row 11
5e7a6bcd-5d67-4a4e-b3b0-6a786de9764b |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0747- Calder - Wire Wall - RW01 - Row 11 | CHK-010-CIV-CPD-Wire faced wall Installation
ceaf8b5d-a537-4eb4-9540-d0cba04d0d15 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0748 - Calder - Wire Wall - RW01 - Row 12
4d308c62-d739-4930-8786-609be00afd35 |  | work-in-progress | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW01 | 080-0748 - Calder - Wire Wall - RW01 - Row 12 | CHK-010-CIV-CPD-Wire faced wall Installation
9047bcb0-3cec-4a50-aa7a-6b56b9be1005 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02
806255b8-338a-47a2-aef2-2288e535349b |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | 080-0427 - Calder - RSS Wall Main - RW02
9c1b4d99-d481-4337-b0bb-5ee897698956 |  | work-in-progress | ITP-102-STR-RSS Wall Main Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | 080-0427 - Calder - RSS Wall Main - RW02 | ITP-102-STR-CPD-RSS Wall Main Rev 0
927eb783-869c-4c3a-af36-dab4b83a41c1 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | 080-0432 - Calder - RSS Precast Panels - RW02 - Lift 1.1 - (C01 - C27)
5e3802ea-fc66-4647-bd2c-00dc3437e71d |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | 080-0432 - Calder - RSS Precast Panels - RW02 - Lift 1.1 - (C01 - C27) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
0627bc23-fdee-4a08-94fc-84c461fc2dbd |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | 080-0433 - Calder - RSS Precast Panels - RW02 Lift 1.2 (C28 - C46)
1a86475e-fd95-4744-9e8e-d8ce815931d1 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | 080-0433 - Calder - RSS Precast Panels - RW02 Lift 1.2 (C28 - C46) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
a1c0f45e-7de2-4a8c-aa29-6e893753d9ae |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | 080-0435 - Calder - RSS Precast Panels - RW02 Lift 2 (C1-C25)
2b110b79-1bb8-423a-ad20-3e1937542900 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | 080-0435 - Calder - RSS Precast Panels - RW02 Lift 2 (C1-C25) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
4fcec17c-d5b3-4ed7-ae22-52d58a3e9b43 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | 080-0436 - Calder - RSS Precast Panels - RW02 Lift 3 (C1-C22)
000cce21-f9bd-4c95-9c47-7a67ee371184 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | 080-0436 - Calder - RSS Precast Panels - RW02 Lift 3 (C1-C22) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
a108947b-55fa-4385-952d-e354746c6411 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | 080-0437 - Calder - RSS Precast Panels - RW02 Lift 4 (C01 - C11)
92a868d9-2afd-4867-b3a9-bf5890b3c2da |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | 080-0437 - Calder - RSS Precast Panels - RW02 Lift 4 (C01 - C11) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
6a3d3831-727b-4d9e-95b4-68fe0b346dce |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | 080-0438 - Calder - RSS Precast Panels - RW02 Lift 5 (C2)
417343b2-0f8d-40b6-9884-09450f9e08c5 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | 080-0438 - Calder - RSS Precast Panels - RW02 Lift 5 (C2) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
dc227ace-7ebc-486f-b937-d107218a9394 |  | not-started | ITP-112-STR Precast L-shape Wall Rev1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW02 | ITP-112-STR Precast L-shape Wall Rev1
c4b6ee4b-1050-4800-b2c6-d26be66b59e5 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03
5195c5f4-4d6e-462e-81ee-93e911ca98de |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-428 - RW03 - RSS Wall Main
4f56546a-d164-427f-ab3e-97538e6b82d6 |  | work-in-progress | ITP-102-STR-RSS Wall Main Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-428 - RW03 - RSS Wall Main | ITP-102-STR-CPD-RSS Wall Main Rev 0
40b07f4a-1237-46fd-adbf-e8ad79960d65 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0439 - Calder - RSS Precast Panels - RW03 Lift 1 (C1-C16)
65f4823a-5945-462e-80d9-f562c906a68f |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0439 - Calder - RSS Precast Panels - RW03 Lift 1 (C1-C16) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev0
7061735c-6307-4cce-86ce-47c49e8655f5 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0440 - Calder - RSS Precast Panels - RW03 Lift 1.2 (C17-C24)
9d79994b-dbcb-45d5-9f33-e6141d2014c9 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0440 - Calder - RSS Precast Panels - RW03 Lift 1.2 (C17-C24) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
e5875209-e417-466f-9fef-edbcbd200ec7 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0441 - Calder - RSS Precast Panels - RW03 Lift 2 (C1-C24)
ab60fe3e-22e1-46d2-a988-ea3a3559f6b6 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0441 - Calder - RSS Precast Panels - RW03 Lift 2 (C1-C24) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev0
e601c041-5333-4e2b-9023-8a39ff92b626 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0442 - Calder - RSS Precast Panels - RW03 Lift 3 (C1-C23)
9bb88067-8986-41de-86c0-3245896d7ed9 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0442 - Calder - RSS Precast Panels - RW03 Lift 3 (C1-C23) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev0
745f3acb-b3a8-4bc7-b27e-934606e8c285 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0443 - Calder - RSS Precast Panels - RW03 Lift 4 (C2-C24)
e9c45509-3dac-4d64-8543-3554fd275b88 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0443 - Calder - RSS Precast Panels - RW03 Lift 4 (C2-C24) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev0
962691c9-6780-4ef4-8fd8-57c47b500e5e |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0444 - Calder - RSS Precast Panels - RW03 Lift 5 (C1-C23)
c62b7f91-3833-42a2-869c-710306cb1ece |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0444 - Calder - RSS Precast Panels - RW03 Lift 5 (C1-C23) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev0
b47cddd8-9008-4f62-8e4b-c0c67e6e143d |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0445 - Calder - RSS Precast Panels - RW03 Lift 6 (C2-C16)
390a8047-d2b8-402c-92cf-689c64ec6b55 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0445 - Calder - RSS Precast Panels - RW03 Lift 6 (C2-C16) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev0
cb6336ea-3594-4e6f-944e-49523b886238 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0446 - Calder - RSS Precast Panels - RW03 Lift 7
22e8ee4a-c86c-411f-9af4-405dfa334d37 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0446 - Calder - RSS Precast Panels - RW03 Lift 7 | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev0
52cf5af3-c647-4b43-947d-3e1ea0a6ce54 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0749 - Calder - RSS Precast Panels - RW03 Lift 8
a4dd9a05-a281-4334-a706-f373bc06a848 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0749 - Calder - RSS Precast Panels - RW03 Lift 8 | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev0
7c3448de-d23c-4db3-9aed-94c38cc1de10 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0735 - TSL-301 Panel Installation
74b40586-a436-4992-9081-3890adfcce83 |  | work-in-progress | ITP-123-STR-CPD-Steel Structures Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0735 - TSL-301 Panel Installation | ITP-123-STR-CPD-Steel Structures Installation
ea3993f5-f579-417a-b372-6b37b2c08ab5 |  | not-started | ITP-121-STR-CPD-Grout Pedestals & Bearings Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW03 | 080-0735 - TSL-301 Panel Installation | ITP-121-STR-CPD-Grout Pedestals & Bearings
0a2ca76e-af4a-4a26-8193-dd1fb47943fc |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04
8492a7ac-23ea-47a2-87aa-14262bbd2e3b |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | 080-429 - RW04 - RSS Wall Main
39a4b80c-4419-4af1-9456-3b425ceb5a84 |  | work-in-progress | ITP-102-STR-RSS Wall Main Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | 080-429 - RW04 - RSS Wall Main | ITP-102-STR-CPD-RSS Wall Main Rev 0
1e31e54c-242f-4c50-94b7-964624b82578 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | 080-0447 - Calder - RSS Precast Panels - RW04 Lift 1 (C4-C10)
8ebbfdb2-fd3e-4f8c-a66d-62f74884c7bd |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | 080-0447 - Calder - RSS Precast Panels - RW04 Lift 1 (C4-C10) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
6f6eed53-75bc-4270-bb7e-4bab01466b5e |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | 080-0448 - Calder - RSS Precast Panels - RW04 Lift 2 (C1-C10)
f619da93-c518-4cdf-95ba-209accdb5e1a |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | 080-0448 - Calder - RSS Precast Panels - RW04 Lift 2 (C1-C10) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
e3873dfc-a5f5-49e3-a4a7-3d1be36ec729 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | 080-0449 - Calder - RSS Precast Panels - RW04 Lift 3 (C1-C9)
ab23fbb6-a63c-462e-adcc-0f73caba2793 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | 080-0449 - Calder - RSS Precast Panels - RW04 Lift 3 (C1-C9) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
cdb61d72-2050-41b8-bd14-fcfe7973844a |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | 080-0450 - Calder - RSS Precast Panels - RW04 Lift 4 (C2-C10)
b5de7aa0-2336-47eb-8e94-9f2c21c8ed28 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | 080-0450 - Calder - RSS Precast Panels - RW04 Lift 4 (C2-C10) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
9272f741-69a7-412a-a25a-228df00af4b9 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | 080-0451 - Calder - RSS Precast Panels - RW04 Lift 5 (C1-C7)
6bb6e116-3bae-4573-9269-e0c04e9ee088 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW04 | 080-0451 - Calder - RSS Precast Panels - RW04 Lift 5 (C1-C7) | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
397ebde7-241a-436a-93e4-ac33170d1212 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05
43f791a9-ca81-48bc-8685-701b6cbd3682 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-428 - RW05 - RSS Wall Main
3977f5c8-33af-4d0f-924d-de8c2d1d54a6 |  | work-in-progress | ITP-102-STR-RSS Wall Main Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-428 - RW05 - RSS Wall Main | 080-430-ITP-102-STR-RSS Wall Main
563ad3e3-bb35-4a71-9d35-79952a79e2a2 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0452 - Calder - RSS Precast Panels - RW05 - Base Lift (C6-C23) - 10/04/2024
65a84b95-364d-4b9f-acd2-c2c8b8c7f508 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0452 - Calder - RSS Precast Panels - RW05 - Base Lift (C6-C23) - 10/04/2024 | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0
5ddb9d03-c4d1-40e6-b7f3-e8ef2e338ea0 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0453 - Calder - RSS Precast Panels - RW05 Lift 2 (C1-C19) -15/04/2024
75c6d349-91ce-4d9f-bb79-298e2c8d457b |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0453 - Calder - RSS Precast Panels - RW05 Lift 2 (C1-C19) -15/04/2024 | CHK-CIV-RSS Walls-Pre-cast Panel Installation Rev 0
d06a13c8-04ce-4889-990e-aaba518c25b7 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0454 - Calder - RSS Precast Panels - RW05 Lift 3 (C2-C18) - 02/05/2024
989b3762-b5b7-4331-8259-0ad60d49744a |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0454 - Calder - RSS Precast Panels - RW05 Lift 3 (C2-C18) - 02/05/2024 | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0
cae43c83-e4ed-4930-b32d-5da4744cf522 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0455 - Calder - RSS Precast Panels - RW05 Lift 4 (C1-C15) - 16/05/2024
c262f69e-df8a-4335-992a-967c849dfb77 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0455 - Calder - RSS Precast Panels - RW05 Lift 4 (C1-C15) - 16/05/2024 | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0
b44015b2-c5fa-4916-ba70-bf07d4be0b6a |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0456 Calder - RSS Precast Panels - RW05 Lift 5 (C2-C14) - 29/05/2024
19d47548-54e3-435b-969c-511a20316b6a |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0456 Calder - RSS Precast Panels - RW05 Lift 5 (C2-C14) - 29/05/2024 | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0
e047174f-71e7-4efa-938e-cc7a35881342 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0457 - Calder - RSS Precast Panels - RW05 Lift 6 (C1-C11) - 14/06/2024
3a0a4b47-5799-45a1-bae9-69bd222419cf |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0457 - Calder - RSS Precast Panels - RW05 Lift 6 (C1-C11) - 14/06/2024 | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
b2944ebb-494f-470c-a22c-ef25ebfd03bf |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0458 - Calder - RSS Precast Panels - RW05 Lift 7 (C2-C10) - 26/06/2024
828293aa-3d49-4208-9298-be2d45681505 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0458 - Calder - RSS Precast Panels - RW05 Lift 7 (C2-C10) - 26/06/2024 | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
61b1c7ae-daf1-4e30-b906-7926d05de97c |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0459 - Calder - RSS Precast Panels - RW05 Lift 8 (C1-7) - 05/07/2024
5b167627-883c-4279-990d-78a225bb629a |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0459 - Calder - RSS Precast Panels - RW05 Lift 8 (C1-7) - 05/07/2024 | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
b236dba0-bf38-4d93-80a5-23adf8644905 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0460 - Calder - RSS Precast Panels - RW05 Lift 9 (C2-C6) - 18/07/2024
9697e542-4349-447f-ae7f-8124a4858144 |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0460 - Calder - RSS Precast Panels - RW05 Lift 9 (C2-C6) - 18/07/2024 | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
b16ff781-3520-4238-a2d9-0c9d58b48a16 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0461 - Calder - RSS Precast Panels - RW05 Lift 10 (C1-C3) - 23/07/2024
611df54f-9f79-4ca6-80d5-03644a7ccc9d |  | pass | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW05 | 080-0461 - Calder - RSS Precast Panels - RW05 Lift 10 (C1-C3) - 23/07/2024 | CHK-008-CIV-CPD-RSS Walls-Pre-cast Panel Installation
7b10d274-8d32-410e-8d9c-fdb54282f520 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06
035c3fb3-8066-4dd6-ae20-4e3cb7f09f47 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0464 - Calder - Wire Wall Installation Main - RW06
93d137ca-7aa0-4f4d-b23a-7f011e1eeac1 |  | work-in-progress | ITP-126-CIV-RSS Wire Facing Wall Main Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0464 - Calder - Wire Wall Installation Main - RW06 | ITP-126-CIV-RSS Wire Facing Wall Main
59e2f48c-b7d8-41ab-9d7f-31c6e1eccebd |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0561 - Calder - Wire Wall - RW06 - Row 01 - C19-C21
98ee4d2f-f988-4da3-a90c-03c364532d9d |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0561 - Calder - Wire Wall - RW06 - Row 01 - C19-C21 | CHK-010-CIV-CPD-Wire faced wall Installation
4ba1bdd0-1cd9-4576-9ece-12ff7e4bb3a8 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0562 - Calder - Wire Wall - RW06 - Row 02
65654dcb-4a7d-4c79-a5f5-be970ac96926 |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0562 - Calder - Wire Wall - RW06 - Row 02 | CHK-010-CIV-CPD-Wire faced wall Installation
055b5521-ebf9-43bf-bb0c-8d7a0811cd26 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0572 - Calder - Wire Wall - RW06 - Row 03
ea01fa31-48d9-48b0-9650-5a0d3eedcb6b |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0572 - Calder - Wire Wall - RW06 - Row 03 | CHK-010-CIV-CPD-Wire faced wall Installation
643180d4-9f7b-47a1-a8d3-ad90936f07c3 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0694 - Calder - Wire Wall - RW06 - Row 04
fc61ac55-fdc5-43ea-b13d-af58bcc1f0b5 |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0694 - Calder - Wire Wall - RW06 - Row 04 | CHK-010-CIV-CPD-Wire faced wall Installation
c85e1724-6ef3-42b7-babd-5f56ed90cd7e |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0695 - Calder - Wire Wall - RW06 - Row 05
5f13ea47-ff43-4e8c-b19b-52283b4d81db |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0695 - Calder - Wire Wall - RW06 - Row 05 | CHK-010-CIV-CPD-Wire faced wall Installation
0892a095-e18a-40a3-b3a6-3eef9ab20c75 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0561 - Calder - Wire Wall - RW06 - Row 06
d8057cc3-6fc8-4b7f-836a-052d317371c4 |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0561 - Calder - Wire Wall - RW06 - Row 06 | CHK-010-CIV-CPD-Wire faced wall Installation
a7fd50ba-15e8-4510-a6b1-8998f0c83a3e |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0736 - Calder - Wire Wall - RW06 - Row 07
38594225-9526-4059-aad8-e8ff4c5b22d5 |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0736 - Calder - Wire Wall - RW06 - Row 07 | CHK-010-CIV-CPD-Wire faced wall Installation
010e7615-3280-4711-9ef0-2af976e0f053 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0737 - Calder - Wire Wall - RW06 - Row 08
feb1fa52-2352-4096-9dce-90531af95fe4 |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0737 - Calder - Wire Wall - RW06 - Row 08 | CHK-010-CIV-CPD-Wire faced wall Installation
2ef43be0-6ecc-40f8-909f-80d098b1308c |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0738 - Calder - Wire Wall - RW06 - Row 09
c859b124-c953-4342-a56b-6a8b64d1d6f0 |  | pass | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0738 - Calder - Wire Wall - RW06 - Row 09 | CHK-010-CIV-CPD-Wire faced wall Installation
4ec93097-3bd7-4486-b33e-c2e48b5923c0 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0739 - Calder - Wire Wall - RW06 - Row 10
6ebfbec2-d328-4a84-8d6d-d11b97facb2d |  | work-in-progress | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0739 - Calder - Wire Wall - RW06 - Row 10 | CHK-010-CIV-CPD-Wire faced wall Installation
a5441bca-3f29-4635-a8ab-3d748c2ff04c |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0740 - Calder - Wire Wall - RW06 - Row 11
807b5f09-3036-49ec-8f7f-7e64f1dbdd6f |  | work-in-progress | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0740 - Calder - Wire Wall - RW06 - Row 11 | CHK-010-CIV-CPD-Wire faced wall Installation
b01e5c0f-1753-4559-a2b6-cd57630b8935 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0741 - Calder - Wire Wall - RW06 - Row 12
739248e5-59f8-4c7e-b5f9-e94e6b293edd |  | work-in-progress | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0741 - Calder - Wire Wall - RW06 - Row 12 | CHK-010-CIV-CPD-Wire faced wall Installation
3cf7a6e3-3ad2-4aec-ba3c-a8dd70500526 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0742 - Calder - Wire Wall - RW06 - Row 13
534c039d-9e70-4c17-ac94-2b8626b932a3 |  | work-in-progress | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0742 - Calder - Wire Wall - RW06 - Row 13 | CHK-010-CIV-CPD-Wire faced wall Installation
3bf94a1f-e965-4897-aa94-dc879f74cf6a |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0743 - Calder - Wire Wall - RW06 - Row 14
14a9e418-cace-4757-972c-25c4e8adb133 |  | work-in-progress | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0743 - Calder - Wire Wall - RW06 - Row 14 | CHK-010-CIV-CPD-Wire faced wall Installation
a1827cc4-4b08-4ed5-a351-c13a76241dde |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0744 - Calder - Wire Wall - RW06 - Row 15
389dfdfa-be9e-4a5a-a92a-ce8e5b69caf1 |  | work-in-progress | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0744 - Calder - Wire Wall - RW06 - Row 15 | CHK-010-CIV-CPD-Wire faced wall Installation
7398aab1-fa55-4b41-9f5c-a0f75e5b93ad |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0745 - Calder - Wire Wall - RW06 - Row 16
8d3f6439-5896-4a50-a797-1d51e143e120 |  | not-started | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0745 - Calder - Wire Wall - RW06 - Row 16 | CHK-010-CIV-CPD-Wire faced wall Installation
b6f03d02-2fb6-4d45-b189-914c3f9106d1 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0746 - Calder - Wire Wall - RW06 - Row 17
5741012b-d396-430a-9bf8-1dc567402d45 |  | not-started | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RW06 | 080-0746 - Calder - Wire Wall - RW06 - Row 17 | CHK-010-CIV-CPD-Wire faced wall Installation
48cb5526-caac-45e5-948a-fe8ca4bbeec5 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South
e8c939f2-52c6-47eb-855e-7339ca605683 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0375 - Calder - RSS Fill - South - Foundation - Layer 0 - CH 1142-1190 - RW01
fe979c74-d6c8-4f82-92f0-75c39357fde2 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0375 - Calder - RSS Fill - South - Foundation - Layer 0 - CH 1142-1190 - RW01 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
6e182027-c79b-4fce-acad-72eab0456dca |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0377 - Calder - RSS Fill - South - Foundation - Layer 0 - CH 1190-1250 - West RW01
497c7d61-211c-48e8-bc0e-5f176335b0a1 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0377 - Calder - RSS Fill - South - Foundation - Layer 0 - CH 1190-1250 - West RW01 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
d0209b68-48a8-4b95-8f77-34f30cad9092 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0384 - Calder - RSS Fill - South - Layer 01 - CH 1142-1190 - RW01
a6e82353-4daa-4a4f-adcb-903f2a4eb173 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0384 - Calder - RSS Fill - South - Layer 01 - CH 1142-1190 - RW01 | CHK-009-STR-CPD-RSS Walls-Fill Placement Rev1
5c58d988-5064-4ec6-8ef2-88a3c139fc4d |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0387- Calder - RSS Fill - South - Layer 02 - CH 1142-1190 - RW01
acd72f8f-e190-4261-9da9-6f50c455a44f |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0387- Calder - RSS Fill - South - Layer 02 - CH 1142-1190 - RW01 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
3cafd008-2554-40f1-bc28-54219803e8eb |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0388 - Calder - RSS Fill - South - Layer 03 - CH 1142-1190 - RW01
05dde6ee-c22a-41ea-b8eb-32edb6bd2e79 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0388 - Calder - RSS Fill - South - Layer 03 - CH 1142-1190 - RW01 | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 1
f220323b-0ab5-484a-9136-9e588b10fb21 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0391 - Calder - RSS FILL - South - 014 (Layer 4, CH 1142 - CH 1250) RW01
ec3b97e0-92e0-45b9-b11b-b37db113a1f0 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0391 - Calder - RSS FILL - South - 014 (Layer 4, CH 1142 - CH 1250) RW01 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
a0067815-954d-4064-b6ff-85e7beb23ed0 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0383 - Calder - RSS FILL - South - 006 (Layer 5, CH 1200 - 1250) RW03/RW01
f94693b7-3045-4f1c-832e-6f86855693ab |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0383 - Calder - RSS FILL - South - 006 (Layer 5, CH 1200 - 1250) RW03/RW01 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
f06ff2c8-f73c-48fb-8e2a-e898b73350bf |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0374 - Calder - RSS Fill - South - Foundation - Layer 0 - CH 1100-1200 - RW02
e6fc2bea-28ae-434f-96b4-6282e44206fb |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0374 - Calder - RSS Fill - South - Foundation - Layer 0 - CH 1100-1200 - RW02 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
571124e0-9ae2-46f7-894e-1b960adac090 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0379 - Calder - RSS Fill - South - Layer 01 - CH 1140-1200 - RW02
87ec4a8e-6b74-417a-8ea3-b000562d9362 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0379 - Calder - RSS Fill - South - Layer 01 - CH 1140-1200 - RW02 | CHK-009-STR-CPD-RSS Walls-Fill Placement Rev1
a3ff441b-5641-46bb-9e6c-fd778f046d08 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0385 - Calder - RSS FILL - South - 008 (Layer 2, CH 1140 - 1200) RW02
c4fbac42-a068-46b2-9f50-4591e680bb10 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0385 - Calder - RSS FILL - South - 008 (Layer 2, CH 1140 - 1200) RW02 | CHK-009-STR-CPD-RSS Walls-Fill Placement Rev1
c71bf5de-7845-42ae-b006-ee387437c82c |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0386 - Calder - RSS FILL - South -009 (Layer 3, CH 1140 - 1200) RW02
1d07ff11-b6ae-449c-a61e-005ad9f395c6 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0386 - Calder - RSS FILL - South -009 (Layer 3, CH 1140 - 1200) RW02 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
d0cc5009-47f4-4404-963b-7424a1e0a383 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0389 - Calder - RSS Fill - South - 012 (Layer 4, CH 1140 - CH 1200) RW02
5f2a59e8-134a-4f62-b79c-2b1ff8bdc281 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0389 - Calder - RSS Fill - South - 012 (Layer 4, CH 1140 - CH 1200) RW02 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
f81874a2-8755-4bda-aad3-37d29fce586d |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0390 - Calder - RSS FILL - South - 013 (Layer 5, CH 1140 - CH 1200) RW02
7b309240-af70-4021-99e0-0d76d5b70b20 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0390 - Calder - RSS FILL - South - 013 (Layer 5, CH 1140 - CH 1200) RW02 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
c6dd9c2b-56ed-44de-97fc-5ae3cd2ecc89 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0392 - Calder - RSS FILL - South - 015 (Layer 1, CH 1100 - CH 1140) RW02
84d73d16-d00e-47b6-b7d5-bf92950522ba |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0392 - Calder - RSS FILL - South - 015 (Layer 1, CH 1100 - CH 1140) RW02 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
c2d9df25-59da-473b-8776-eb1c6836d3b1 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0393 - Calder - RSS FILL - South - 016 - (Layer 2, CH 1100 - CH 1140) RW02
99d1768c-5945-4345-8e10-cb49db41319e |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0393 - Calder - RSS FILL - South - 016 - (Layer 2, CH 1100 - CH 1140) RW02 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
d3f5873c-063e-4bf3-a2b2-e373735a160c |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0394- Calder - RSS FILL - South - 017 - (Layer 3, CH 1100 - CH 1140) RW02
b360761c-bb8a-4083-b976-1fd7959b3eba |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0394- Calder - RSS FILL - South - 017 - (Layer 3, CH 1100 - CH 1140) RW02 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
b4fc56e5-320a-4ef2-a4cd-ede91728cc92 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0395 - Calder - RSS FILL - South - 018 - (Layer 4, CH 1100 - CH 1140) RW02
21d4fc2b-37cb-4d9f-b129-ce2d94b87ed7 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0395 - Calder - RSS FILL - South - 018 - (Layer 4, CH 1100 - CH 1140) RW02 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
144c74af-279b-4a9a-bd89-9bf2046463fb |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0396 - Calder - RSS FILL - South - 019 - (Layer 5, CH 1100 - CH 1140) RW02
ab5051d3-a472-4dff-8afa-004384ed45a7 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0396 - Calder - RSS FILL - South - 019 - (Layer 5, CH 1100 - CH 1140) RW02 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
657af5a7-cba4-47ff-959f-c3190fe8ee98 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0376 - Calder - RSS Fill - South - Foundation - Layer 0 - CH 1200-1250 - East RW03
91be9c04-d7c1-4e42-8071-35eea3894ea9 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0376 - Calder - RSS Fill - South - Foundation - Layer 0 - CH 1200-1250 - East RW03 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
aec2a3b2-b4bd-40f4-b764-ca575ccb1d80 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0378 - Calder - RSS Fill - South - Layer 01 - CH 1200-1250 - RW03
3b1894dd-816c-477e-9351-cc435bf68f39 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0378 - Calder - RSS Fill - South - Layer 01 - CH 1200-1250 - RW03 | CHK-009-STR-CPD-RSS Walls-Fill Placement Rev1
708c10e1-0a45-43fc-93a9-750442452724 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0380 - Calder - RSS Fill - South - Layer 02 - CH 1200-1250 - RW03
b622838b-f97d-4a1f-8321-c5bb6e9dfd35 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0380 - Calder - RSS Fill - South - Layer 02 - CH 1200-1250 - RW03 | CHK-009-STR-CPD-RSS Walls-Fill Placement Rev1
e0f993be-6ee7-4d09-bc24-801b01860449 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0381 - Calder - RSS FILL - South - 004 (Layer 3, CH 1200 - 1250) RW03
aae183ee-2cbb-4db3-b372-f49d8f31a710 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0381 - Calder - RSS FILL - South - 004 (Layer 3, CH 1200 - 1250) RW03 | CHK-009-STR-CPD-RSS Walls-Fill Placement Rev1
a8a1b523-4207-4d41-a799-64394bd03b05 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0382 - Calder - RSS FILL - South - 005 (Layer 4, CH 1200 - 1250) RW03
17edd4b4-1caa-4c49-9bf5-41f6dee7aee8 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0382 - Calder - RSS FILL - South - 005 (Layer 4, CH 1200 - 1250) RW03 | CHK-009-STR-CPD-RSS Walls-Fill Placement Rev1
e38c5c8e-7e3a-47b2-8463-f304c7ea46eb |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0397 - Calder - RSS FILL - South - 020 - Layer 6 ( CH 1100 - CH 1250) S.A.W
307ffae3-a231-49c7-b2a6-0d91913bc604 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0397 - Calder - RSS FILL - South - 020 - Layer 6 ( CH 1100 - CH 1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
7d9f957a-f922-46a5-aa28-e68dbe83ab09 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0398 - Calder - RSS FILL - South - 021 - (Layer 7, CH 1100 - 1250) S.A.W
15697d46-5578-43e0-aec0-ba8599e24c06 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0398 - Calder - RSS FILL - South - 021 - (Layer 7, CH 1100 - 1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
f8ee69cb-a696-4be5-b48b-d5de6695a387 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0399 - Calder - RSS FILL - South - 022 - (Layer 8, CH 1100 - CH 1250) S.A.W
32a8e97d-6557-4301-8e9a-716eb39d912f |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0399 - Calder - RSS FILL - South - 022 - (Layer 8, CH 1100 - CH 1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
30854f41-60b1-4252-a495-a87497bec726 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0400 - Calder - RSS FILL - South -023 - (Layer 9, CH 1100 - 1250) S.A.W
110a9f33-40b4-4cb9-bf88-b49947c92650 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0400 - Calder - RSS FILL - South -023 - (Layer 9, CH 1100 - 1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
04a4fadb-f9b0-4b48-9961-8d57283a7332 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0401 - Calder - RSS FILL - South - 024 - (Layer 10, CH 1100 - 1250) S.A.W
15d6808d-264d-4340-81a5-45c0f3bd4ed4 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0401 - Calder - RSS FILL - South - 024 - (Layer 10, CH 1100 - 1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
a8ba14dd-59f1-42c1-9aeb-b60191786906 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0402 - Calder - RSS FILL - South - Layer 11 ( CH 1100-1250) S.A.W
43aec61c-7731-4f37-8b3d-398434ed4f8a |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0402 - Calder - RSS FILL - South - Layer 11 ( CH 1100-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
02721c33-2f68-4920-9de4-2a46811223c9 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0403 - Calder - RSS FILL - South - Layer 12 ( CH 1100-1250) S.A.W
6d0b6c3e-b612-48f6-8339-e85a2983b458 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0403 - Calder - RSS FILL - South - Layer 12 ( CH 1100-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
2b023103-23c4-42f7-b7f7-06ccf3aa8423 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0404-Calder - RSS Fill - South - Layer 13 ( CH 1100-1250) S.A.W
bd8d3ca3-7364-4b9a-96eb-559bd9d1976d |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0404-Calder - RSS Fill - South - Layer 13 ( CH 1100-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
ce19e432-ef72-4e69-9021-87c4633572a3 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0405- Calder - RSS Fill - South - Layer 14 - CH 1100-1250 - S.A.W
14ca4f59-315e-4da7-834d-bc7658013cf9 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0405- Calder - RSS Fill - South - Layer 14 - CH 1100-1250 - S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
fa99e4e9-383b-4548-9ec3-f264c867ce9f |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0406 - Calder - RSS FILL - South - Layer 15 ( CH 1150-1250) S.A.W
19a08848-74db-466f-9ac4-6b9aafcbb17e |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0406 - Calder - RSS FILL - South - Layer 15 ( CH 1150-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
74b379c9-0aa7-406e-833b-95a62edf41d5 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0407-Calder - RSS Fill - South - Layer 16 ( CH 1150-1250) S.A.W
ea051cde-235e-450f-b785-53dfb25dbf98 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0407-Calder - RSS Fill - South - Layer 16 ( CH 1150-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
e973731c-13b7-45a0-ba3d-ec006024dae1 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0408-Calder - RSS Fill - South - Layer 17 ( CH 1150-1250) S.A.W
f5e0866b-b888-4db3-9fc7-51e0a84ce7bc |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0408-Calder - RSS Fill - South - Layer 17 ( CH 1150-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
b54a9f75-9e15-40d3-a19e-547e126c5653 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0409-Calder - RSS Fill - South - Layer 18 ( CH 1156-1250) S.A.W
401d5962-6219-44b2-8780-aae4b0746c8a |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0409-Calder - RSS Fill - South - Layer 18 ( CH 1156-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
467109fe-0266-4b95-9065-0235c54513dc |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0410-Calder - RSS Fill - South - Layer 19 ( CH 1156-1250) S.A.W
fdc48097-00ba-43a9-b282-30da3376b4b4 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0410-Calder - RSS Fill - South - Layer 19 ( CH 1156-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
a0c924f9-923b-4516-83a8-0938ebe59a4f |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0411- Calder - RSS Fill - South - Layer 20 ( CH 1168-1250) S.A.W
0fa1dceb-0844-419c-9444-a249b740b234 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0411- Calder - RSS Fill - South - Layer 20 ( CH 1168-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
73b5f0e6-e03f-411e-91bf-7a67edd97e96 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0412-Calder - RSS Fill - South - Layer 21 ( CH 1168-1250) S.A.W
1432bf35-2191-46a5-9fce-14818931eb89 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0412-Calder - RSS Fill - South - Layer 21 ( CH 1168-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
e46cfa1b-4da1-4443-b02d-d6f6676fd4e6 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0413-Calder - RSS Fill - South - Layer 22 ( CH 1168-1250) S.A.W
585d9bf1-0160-4980-a5a0-b5fc00a19db8 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0413-Calder - RSS Fill - South - Layer 22 ( CH 1168-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
7e1207f3-cf92-4f05-a665-b58f70043234 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0414-Calder - RSS Fill - South - Layer 23 ( CH 1180-1250) S.A.W
6919224a-b9c3-4fb7-97e5-2beecf004afd |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0414-Calder - RSS Fill - South - Layer 23 ( CH 1180-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
1f5f0710-67c3-4f61-9296-84452f641080 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0415-Calder - RSS Fill - South - Layer 24 ( CH 1180-1250) S.A.W
554d6578-2a45-4fbf-a089-9e36b229f938 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0415-Calder - RSS Fill - South - Layer 24 ( CH 1180-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
25216f4b-c0d0-4e05-820a-843b4e455496 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-4016-Calder - RSS Fill - South - Layer 25 ( CH 1180-1250) S.A.W
ce49f266-73fe-4f50-b7d5-e57a7bbe94a6 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-4016-Calder - RSS Fill - South - Layer 25 ( CH 1180-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
0d9d1f95-06bd-4c0b-8be5-979d592676d4 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0417-Calder - RSS Fill - South - Layer 26 ( CH 1192-1250) S.A.W
3c8f4466-df3b-42c2-9c57-54a58dcf07cc |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0417-Calder - RSS Fill - South - Layer 26 ( CH 1192-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
ac5f73da-559c-4567-a36a-aae937776246 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-679-Calder - RSS Fill - South - Layer 27 ( CH 1192-1250) S.A.W
a4beb3aa-a679-4d16-9650-c6ba7fcc7c3d |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-679-Calder - RSS Fill - South - Layer 27 ( CH 1192-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
230c5d7e-ec4a-44ae-b277-8c1030be8f0e |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0680-Calder - RSS Fill - South - Layer 28 ( CH 1192-1250) S.A.W
a5f2e1bb-80fb-431c-889b-175756241c79 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0680-Calder - RSS Fill - South - Layer 28 ( CH 1192-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
22f5728e-3224-4279-a94d-1d78f9a1a174 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0681-Calder - RSS Fill - South - Layer 29 ( CH 1197-1250) RW01
fbb3abdd-ab98-4ad7-b3f2-f7fd09669fc9 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0681-Calder - RSS Fill - South - Layer 29 ( CH 1197-1250) RW01 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
64599a8d-2521-4203-9db5-255fc4dcbba3 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0682 - Calder - RSS Fill - South - Layer 30 ( CH 1197-1250) RW03
b1d4539e-e882-4b2e-992f-6327bb4d2d72 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0682 - Calder - RSS Fill - South - Layer 30 ( CH 1197-1250) RW03 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
f821ee5c-3a2a-4809-8ffb-9e295719c9bf |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0718- Calder - RSS Fill - South - Layer 31 ( CH 1197-1250) S.A.W
de52affa-8da0-48e3-b85d-bd4cc51c20bb |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0718- Calder - RSS Fill - South - Layer 31 ( CH 1197-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
0179993a-4234-4231-b6ce-9b1aa5e0af8c |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0722 - Calder - RSS Fill - South - Layer 32 (CH1197-1250) S.A.W
5c115eab-3263-4df4-96ac-16cb2c3e21fc |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0722 - Calder - RSS Fill - South - Layer 32 (CH1197-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
9fe02a6c-925d-4154-9ce9-ec9f15509bd0 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0725-Calder-RSS Fill- South - Layer 33 (CH1197-1250) S.A.W
4849e2e5-3eed-4c2a-8fd8-93522c56b339 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0725-Calder-RSS Fill- South - Layer 33 (CH1197-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
e05652ff-8dcf-43e5-bb35-ad361a976354 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0726-Calder-RSS Fill - South - Layer 34 (CH1197-1250) S.A.W
2c98590e-ef39-4d10-9040-24e20010e1f1 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0726-Calder-RSS Fill - South - Layer 34 (CH1197-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
fa4f107b-755c-4d61-b8d8-4ba8b3670e2b |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-727-Calder-RSS Fill- South - Layer 35 (CH1210-1250) S.A.W
58b422f2-5ce8-4dae-bcc2-43373d3ee005 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-727-Calder-RSS Fill- South - Layer 35 (CH1210-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
704d7692-bf40-4559-bfc0-e0625b3b27ae |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-752-Calder - RSS Fill - South - Layer 36 (CH1220-1250) S.A.W
6f513920-4995-456a-8230-53d793183a40 |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-752-Calder - RSS Fill - South - Layer 36 (CH1220-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
e7959202-9387-4a1c-b050-6addb3edd508 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0761- Calder - RSS Capping Type A - South - S.A.W - 1A
7da5d783-45c0-4930-875a-6b657339e894 |  | work-in-progress | ITP-046-CIV-CPD-Type A Fill - Road Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0761- Calder - RSS Capping Type A - South - S.A.W - 1A | ITP-046-CIV-CPD-Type A Fill - Road
0ab52ac8-cad8-48cd-8215-86a6a6239dcf |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0774-Calder - RSS Fill - South - Layer 37 (CH1230-1250) S.A.W
efb5018a-9c55-4d9a-964e-5fef5c317f1d |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0774-Calder - RSS Fill - South - Layer 37 (CH1230-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
2064ca08-a8c5-4c07-b05e-9de3076e4b59 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0758-Calder - RSS Fill - South - Layer 38 (CH1230-1250) S.A.W
2a28c163-5b24-4808-808b-3ef57341b7b8 |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0758-Calder - RSS Fill - South - Layer 38 (CH1230-1250) S.A.W | CHK-009-CIV-CPD-RSS Walls-Fill Placement
3ee7316d-6d18-4d7d-a92c-d8fd48b59f6a |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-759-Calder - RSS Fill - South - Layer 39 (CH1230-1250) RW01
015f7027-8786-4b49-9df1-d24273bf39ff |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-759-Calder - RSS Fill - South - Layer 39 (CH1230-1250) RW01 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
e2c2737f-bc9f-4a09-9687-d7e01b734991 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0700- Calder - RSS Capping Type A - South - S.A.W - 1B
0086e822-1634-4078-a6ed-8103af19053a |  | work-in-progress | ITP-046-CIV-CPD-Type A Fill - Road Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0700- Calder - RSS Capping Type A - South - S.A.W - 1B | ITP-046-CIV-CPD-Type A Fill - Road
4492cc16-c10d-4418-beef-f5f3d4f1c909 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0701- Calder - RSS Capping Type A - South - S.A.W - 1C
3227650a-d6a3-4ac2-8751-616f855741f2 |  | work-in-progress | ITP-046-CIV-CPD-Type A Fill - Road Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - South | 080-0701- Calder - RSS Capping Type A - South - S.A.W - 1C | ITP-046-CIV-CPD-Type A Fill - Road
9f29220a-c0c3-4393-b921-5346730f4127 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05
2a83fa98-42f1-4e8b-b148-f53f5ced5fd9 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0305 - Calder - North - RSS Fill - 000 - RW05 - Ch 1330-1345 - Foundation
111b768f-c1f3-4d5c-8117-167b048d1be0 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0305 - Calder - North - RSS Fill - 000 - RW05 - Ch 1330-1345 - Foundation | CHK-009-CIV-CPD-RSS Walls-Fill Placement
3bd751f1-07b8-4a23-9797-30ff2974c45d |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0306 - Calder - North - RSS Fill - 001 - RW05 - Ch 1330-1345 - Layer 1
9523fa1b-56fc-4930-8b6d-4d00f86e9f50 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0306 - Calder - North - RSS Fill - 001 - RW05 - Ch 1330-1345 - Layer 1 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
c7c4f743-cb21-4ace-a279-8311a72b7168 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0307 - Calder - North - RSS Fill - 002 - RW05 - CH 1330-1345 - Layer 2
03c26430-cf41-4cde-8222-ea0bcdc39ae9 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0307 - Calder - North - RSS Fill - 002 - RW05 - CH 1330-1345 - Layer 2 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
d816a90d-d67a-45ac-b3cb-db30a4a2df73 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0360- Calder - North - RSS FILL - 003 - RW05 - CH 1330-1345 -Layer 3
208d21c5-f85b-48a3-8c19-f5d5b5730e86 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0360- Calder - North - RSS FILL - 003 - RW05 - CH 1330-1345 -Layer 3 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
a521da72-1006-40cd-b28e-1a8cde6c0c4c |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0361- Calder - North - RSS FILL - 004 - RW05 - CH 1330-1345 - Layer 4
94fcc60e-466e-455c-a5f8-0502b5f33155 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0361- Calder - North - RSS FILL - 004 - RW05 - CH 1330-1345 - Layer 4 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
c2fc74f5-4c87-4f9f-bc05-19eb219f922b |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0362- Calder - North - RSS FILL - 005 - RW05 - CH 1330-1345 - Layer 5
f0f58e61-f795-43d8-820f-9caef07d1090 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0362- Calder - North - RSS FILL - 005 - RW05 - CH 1330-1345 - Layer 5 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
643b597c-05d7-4668-bae5-556e973d351c |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0363-Calder - North - RSS FILL - 006 - RW05 - CH 1330-1345 - Layer 6
8e2b171d-a7d5-4941-a8f4-45fd9103f214 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0363-Calder - North - RSS FILL - 006 - RW05 - CH 1330-1345 - Layer 6 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
ec3c9a76-d054-426b-8d31-e28126ad4513 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0364-Calder - North - RSS FILL - 007 - RW05 - CH 1330-1345 - Layer 7
2478d2b5-4356-46c5-bf41-30bdaa70616a |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0364-Calder - North - RSS FILL - 007 - RW05 - CH 1330-1345 - Layer 7 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
12b033e3-052e-4a51-8a26-127ec656e404 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0365-Calder - North - RSS FILL - 008 - RW05 - CH 1330-1345 - Layer 8
3f942cda-ae82-4d74-84d7-25a056e822af |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0365-Calder - North - RSS FILL - 008 - RW05 - CH 1330-1345 - Layer 8 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
529fc068-f6db-46ba-ae0a-4dca38be1841 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0366-Calder - North - RSS FILL - 011 - RW05 - CH 1330-1345 - Layer 9
259864a5-00bd-4f97-94dc-76328bfe7418 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0366-Calder - North - RSS FILL - 011 - RW05 - CH 1330-1345 - Layer 9 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
84fd4131-93fd-4734-b093-16f4ea4f5b43 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0367-Calder - North - RSS FILL - 010 - RW05 - CH 1330-1345 - Layer 10
3b873185-f802-4f18-8ff6-e27f78642021 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0367-Calder - North - RSS FILL - 010 - RW05 - CH 1330-1345 - Layer 10 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
ebac84bf-650b-4305-b0a9-b01d1b764d7a |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0368-Calder - North - RSS FILL - 012 - RW05 - CH 1330-1345 - Layer 11
588b4ab3-cddf-49ac-b11f-6688facac4fc |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0368-Calder - North - RSS FILL - 012 - RW05 - CH 1330-1345 - Layer 11 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
161c13bc-e5be-47a2-84fd-79c54dfc4125 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0369-Calder - North - RSS FILL - 013 - RW05 - CH 1330-1345 - Layer 12
e4db7a69-4af3-4603-9640-a3c317e7a50d |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0369-Calder - North - RSS FILL - 013 - RW05 - CH 1330-1345 - Layer 12 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
782a639c-9e58-4ab3-bef8-6ac08439d043 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0370-Calder - North - RSS FILL - 016 - RW05 - CH 1330-1345 - Layer 13
83175b2c-b85d-4531-a79a-8862497da445 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0370-Calder - North - RSS FILL - 016 - RW05 - CH 1330-1345 - Layer 13 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
a51a61b0-a83a-4dd6-806d-5707edd4f796 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0608-Calder - North - RSS FILL - 019 - RW05 - CH 1330-1345 - Layer 14
1902a322-4f03-4a9b-84bc-54d9ac8eb98d |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0608-Calder - North - RSS FILL - 019 - RW05 - CH 1330-1345 - Layer 14 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
0c537e2c-e9c5-4dca-892e-1ccdff9a5bb2 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0609-Calder - North - RSS FILL - 020 - RW05 - CH 1330-1345 - Layer 15
99eeeace-973a-4944-b33d-417443f091ed |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0609-Calder - North - RSS FILL - 020 - RW05 - CH 1330-1345 - Layer 15 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
7b264041-f890-45c8-b0e2-d6daac4f65fb |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0610-Calder - North - RSS FILL - 021 - RW05 - CH 1330-1345 - Layer 16
a3c7ac65-bb2a-47a8-9d53-30d6280c5722 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0610-Calder - North - RSS FILL - 021 - RW05 - CH 1330-1345 - Layer 16 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
d0f5194a-a425-4cdc-b5fb-5f31af36e203 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0611 - Calder - North - RSS FILL - 025 - RW05 - CH 1330-1345 - Layer 17
6f495e5a-b8e0-4e5d-8d98-ce3d84f085b6 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0611 - Calder - North - RSS FILL - 025 - RW05 - CH 1330-1345 - Layer 17 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
2f8af384-7250-4407-a584-3422a4a2586f |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0612 - Calder - North - RSS FILL - 027 - RW05 - CH 1330-1345 - Layer 18
e0dc4496-cdde-4cc3-b394-1015b96d7ed9 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0612 - Calder - North - RSS FILL - 027 - RW05 - CH 1330-1345 - Layer 18 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
ad55c2c7-0da6-4518-8790-012af5c12f62 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0613- Calder - North - RSS Fill - 029 - RW05 - CH 1330-1345 - Layer 19
060e8433-49c6-4742-b16f-9854b7c94317 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0613- Calder - North - RSS Fill - 029 - RW05 - CH 1330-1345 - Layer 19 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
a26ccbb7-76d8-41ed-9934-52b5b5072e9b |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0614 Calder - North - RSS Fill - 031 - RW05 - CH 1330-1345 - Layer 20
824b687d-19de-4d62-a46c-db9ec37ff63f |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0614 Calder - North - RSS Fill - 031 - RW05 - CH 1330-1345 - Layer 20 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
67c1e5b9-c243-47b2-bf67-4ea560d224e9 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0615- Calder - North - RSS Fill - 033 - RW05 - CH 1330-1345 - Layer 21
a7ed8b2d-a191-4ae2-b4d6-8e38370e783e |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0615- Calder - North - RSS Fill - 033 - RW05 - CH 1330-1345 - Layer 21 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
b84c22dc-6569-4936-82f3-9fa52d153a0f |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0616- Calder - North - RSS Fill - 034 - RW05 - CH 1345-1360 - Layer 22
ac640c67-e95e-4964-8319-2f25a0321e55 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0616- Calder - North - RSS Fill - 034 - RW05 - CH 1345-1360 - Layer 22 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
94378be3-a4b1-4dda-84ec-51874621c269 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0617 - Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 23
b6b7bb54-84ca-42eb-815a-8705526f403c |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0617 - Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 23 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
bdb2ad09-3c1b-472f-b819-29785e2a5f8a |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0618 - Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 24
c9fc0242-62d1-46be-8965-ac5ab32e089e |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0618 - Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 24 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
cd539b0c-5494-4c75-91ea-f25580b02618 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0619 - Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 25
b5f86cd8-44c4-48bc-8ab2-dd334914c60b |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0619 - Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 25 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
757ad147-d37c-45b9-a971-5a8f00fa85d2 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0620- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 26
913fe667-b9dc-4450-91bd-a987b484f188 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0620- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 26 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
6f9af88e-9f5c-4620-855f-2c3872677061 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0621- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 27
a3a8dde1-75de-4fb5-a105-01d3d12f218c |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0621- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 27 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
93d7b6e1-5ecd-4c50-ac84-b806c0f530d1 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0622- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 28
040d3bf9-b85d-4d43-a1c7-d7d8f5db6d3b |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0622- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 28 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
760e7f39-483a-40d5-8574-45784b106c88 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0623- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 29
6a52279c-0ab1-40ee-9989-740f83f03183 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0623- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 29 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
44dbc066-af21-4daf-a933-cf62fdf1c657 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0624- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 30
f07b134a-0aa3-43e8-a00c-9b976d1e49bd |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0624- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 30 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
4a7cb630-1cf3-4c01-8022-fb59e92000ce |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0625- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 31
81bca456-8b7b-4c60-a2d3-f4ddde838089 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0625- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 31 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
f854c483-7b72-4eeb-9c09-c2f86b22b2db |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0626- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 32
5130183c-1dc0-45e6-b266-5d8aac11e162 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0626- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 32 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
6ba7c3ff-dee2-4cee-b4f9-98ddac9b2194 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0627- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 33
643f4710-2668-489b-a978-9ac22bd81c92 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0627- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 33 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
7fb99269-6c53-4a36-b0a7-0ec6d768d59f |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0628- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 34
96c07823-4965-4024-a592-55371a163b6f |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0628- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 34 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
1482d286-8ac5-4623-aa6c-b9d652a0560a |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0629- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 35
0c863962-257a-4a0a-a2f9-53f392992e9f |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0629- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 35 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
10a6c1ec-bd8f-4a79-8d0f-5a482818f221 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0630- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 36
f6265685-ae9d-4899-917e-521c8212b80d |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0630- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 36 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
17daf81d-51be-4eda-9675-7ed98edbac26 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0704- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 37
9fbfe290-e4e4-47a9-b59b-9506ae49fa10 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0704- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 37 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
f7113265-7b3c-4a1e-b517-a11ee11a7b83 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0431- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 38
a02bac15-5b6f-49b5-a0ac-69968161fbde |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0431- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 38 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
e4f764cc-88f0-44d2-b830-f23605ff703f |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0731- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 39
f9ff2d7e-ef0c-4275-96e1-04d6d070c6cd |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0731- Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 39 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
976f48c4-1c1a-4e70-9b76-63d54a639eee |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0733 - Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 40
76b71a4e-b851-4d2e-bd36-693f2ab2d079 |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0733 - Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 40 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
be5fc1e4-1a3c-4361-9248-5c237b6ca5db |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0784 - Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 41
b22b83c8-a93b-4ccb-b1a0-3e94405f8197 |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0784 - Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 41 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
6d7d7fb3-56fc-4ed8-bc3e-63b5d1f97e30 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0785 - Calder - North- RSS CAP - RW05 - CH 1330-1345 - Layer 1a
1f37d96b-be8d-4d0b-99a9-9a7b84a187dc |  | work-in-progress | ITP-046-CIV-CPD-Type A Fill - Road Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0785 - Calder - North- RSS CAP - RW05 - CH 1330-1345 - Layer 1a | ITP-046-CIV-CPD-Type A Fill - Road
f6e88349-38c9-4f42-ba3b-f8cd55ed91d1 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0792 - Calder - North- RSS CAP - RW05 - CH 1330-1345 - Layer 1b
225162fd-1c98-4006-ac06-f6f89f321fe1 |  | work-in-progress | ITP-046-CIV-CPD-Type A Fill - Road Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0792 - Calder - North- RSS CAP - RW05 - CH 1330-1345 - Layer 1b | ITP-046-CIV-CPD-Type A Fill - Road
928d416f-a702-45e7-8088-45b29ccfcc5e |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0798 - Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 42
f4ab7d2c-6597-466f-a48d-52b1b12802a2 |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW05 | 080-0798 - Calder - North- RSS Fill - RW05 - CH 1330-1345 - Layer 42 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
ff87cecb-07ae-418b-b0aa-4fef769228e3 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06
1c53a11e-0961-43cf-a729-23c3ae08f8ee |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0301- Calder - North - RSS FILL - RW06 - C19-21 ( CH 1403-1410 ) - Foundation
c62a03c0-ea8a-4dfb-815c-76c51cd2987e |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0301- Calder - North - RSS FILL - RW06 - C19-21 ( CH 1403-1410 ) - Foundation | CHK-009-CIV-CPD-RSS Walls-Fill Placement
0fff832c-99e8-4749-97e0-ef0d9bf5ee53 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0302- Calder - North - RSS FILL - 001 - RW06 - C19-21 ( CH 1403-1410 ) - Layer 1
55f9c6f1-4c87-40f5-ba40-255989d88c63 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0302- Calder - North - RSS FILL - 001 - RW06 - C19-21 ( CH 1403-1410 ) - Layer 1 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
70bae760-799d-4e77-9a78-62d5898c45a7 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0303- Calder - North - RSS FILL - 002 - RW06 - C19-21 ( CH 1403-1410 ) - Layer 2
1745fe74-ff68-4384-bded-7ddacbb340e3 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0303- Calder - North - RSS FILL - 002 - RW06 - C19-21 ( CH 1403-1410 ) - Layer 2 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
e14b3e83-a9ef-461d-970e-dffcca5cb9d7 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0304- Calder - North - RSS FILL - 003 - RW06 - C19-21 ( CH 1403-1410 ) - Layer 3
9b860768-96ec-4884-bfb1-404de5baa810 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0304- Calder - North - RSS FILL - 003 - RW06 - C19-21 ( CH 1403-1410 ) - Layer 3 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
a3e02ee0-1b9c-4799-aa83-d4378cc0283d |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0308-Calder - North - RSS FILL - 004 - RW06 - C3-22 - CH 1365 - 1412 - Layer 4
9838a8ae-0c3f-4a56-82ac-ed8cca490537 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0308-Calder - North - RSS FILL - 004 - RW06 - C3-22 - CH 1365 - 1412 - Layer 4 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
b618d0e9-34b7-44b6-af11-fa85d798fb10 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0309-Calder - North - RSS FILL - 005 - RW06 - C3-22 - CH 1365 - 1412 - Layer 5
2f85d5e4-8355-439a-9dab-5bad27623f1e |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0309-Calder - North - RSS FILL - 005 - RW06 - C3-22 - CH 1365 - 1412 - Layer 5 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
88bee5b3-6b1d-437f-8efe-c3da8c4cf44a |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0310-Calder - North - RSS FILL - 006 - RW06 - C3-22 - CH 1365 - 1412 - Layer 6
0f673376-2f03-468a-b7c3-ca0a76d92bab |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0310-Calder - North - RSS FILL - 006 - RW06 - C3-22 - CH 1365 - 1412 - Layer 6 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
07b64515-76ba-4563-a66a-b15897b89d5c |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0314-Calder - North - RSS FILL - 007 - RW06 - C1-22 - CH 1360 - 1412 - Layer 7
859242f1-6cdc-49fb-aec1-7ec38f6d2424 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0314-Calder - North - RSS FILL - 007 - RW06 - C1-22 - CH 1360 - 1412 - Layer 7 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
4da4b416-667c-4a90-b088-c777785716a6 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0315-Calder - North - RSS FILL - 008 - RW06 - C1-22 - CH 1360 - 1412 - Layer 8
89ed3990-b99f-448e-9111-8e26eabec640 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0315-Calder - North - RSS FILL - 008 - RW06 - C1-22 - CH 1360 - 1412 - Layer 8 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
bdc3b462-954b-4bbe-bd08-3767c5d3c32b |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0316-Calder - North - RSS FILL - 009 - RW06 - C1-22 - CH 1360 - 1412 - Layer 9
adc99485-6e17-43aa-a06b-9266a7aa3c8e |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0316-Calder - North - RSS FILL - 009 - RW06 - C1-22 - CH 1360 - 1412 - Layer 9 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
9e519da1-6bce-43d9-b422-b691d99c8b74 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0317-Calder - North - RSS FILL - 014 - RW06 - C1-23 - CH 1360 - 1417 - Layer 10
749bd358-e56d-4b6f-a750-3dc01cf48710 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0317-Calder - North - RSS FILL - 014 - RW06 - C1-23 - CH 1360 - 1417 - Layer 10 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
7f4dcf71-4d41-4fea-82ae-2d4a075e8438 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0318-Calder - North - RSS FILL - 015 - RW06 - C1-23 - CH 1360 - 1417 - Layer 11
254875c7-b989-4b5b-90f8-232762292cb9 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0318-Calder - North - RSS FILL - 015 - RW06 - C1-23 - CH 1360 - 1417 - Layer 11 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
0df22fd9-3970-450d-a78a-bdd9dcfb2c34 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0319-Calder - North - RSS FILL - 017 - RW06 - C1-23 - CH 1360 - 1421 - Layer 12
8c8355f6-a502-415a-b274-342cb15c90c9 |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0319-Calder - North - RSS FILL - 017 - RW06 - C1-23 - CH 1360 - 1421 - Layer 12 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
561657e5-2ba9-484e-adb3-1e2f3aff7768 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0320-Calder - North - RSS FILL - 018 - RW06 - C1-23 - CH 1360 - 1421 - Layer 13
6b2e0a5b-4412-412c-a90b-610af79ea12f |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0320-Calder - North - RSS FILL - 018 - RW06 - C1-23 - CH 1360 - 1421 - Layer 13 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
7af5ca0f-3795-45df-8707-4f40636b4f67 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-03321-Calder - North - RSS FILL - 019 - RW06 - C1-23 - CH 1360 - 1421 - Layer 14
01865bb6-8012-42e9-bdfc-bfca5c95259f |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-03321-Calder - North - RSS FILL - 019 - RW06 - C1-23 - CH 1360 - 1421 - Layer 14 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
8ae0e281-8144-41fb-8231-162859d22ad2 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0322-Calder - North - RSS FILL - 020 - RW06 - C1-23 - CH 1360 - 1421 - Layer 15
c222818d-bdaa-4d84-bd28-cbe6f9d08e2b |  | pass | 132ba702c98a31284b24a605f33ff452ce7fa40714c212c6fc75f05d22f49afd | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0322-Calder - North - RSS FILL - 020 - RW06 - C1-23 - CH 1360 - 1421 - Layer 15 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
9a8e5c7e-a8de-44c2-bd86-8967926608ce |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0323-Calder - North - RSS FILL - 021 - RW06 - C1-23 - CH 1360 - 1421 - Layer 16
37d671b1-4cdb-436f-8e4d-cd452a519f6f |  | pass | b94b885ce2b0fc87b9508d637878b4298496365dea2352c502cbb2064cde5f49 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0323-Calder - North - RSS FILL - 021 - RW06 - C1-23 - CH 1360 - 1421 - Layer 16 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
b857374d-029b-43c6-833b-e1c46ca37157 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0324-Calder - North - RSS FILL - 022 - RW06 - C1-23 - CH 1360 - 1423 - Layer 17
8fd66de9-791e-4aeb-bda8-67148484a479 |  | pass | b94b885ce2b0fc87b9508d637878b4298496365dea2352c502cbb2064cde5f49 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0324-Calder - North - RSS FILL - 022 - RW06 - C1-23 - CH 1360 - 1423 - Layer 17 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
9bf08317-7612-4294-afc4-82b994a05de9 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0325-Calder - North - RSS Fill - 023 - RW06 - C1-23 - CH1360 - 1423 - Layer 18
62991f79-dc4b-4eb1-aa69-7b281325f056 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0325-Calder - North - RSS Fill - 023 - RW06 - C1-23 - CH1360 - 1423 - Layer 18 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
4e77585b-ee34-422f-b53e-985d22871fa7 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0326-Calder- North - RSS Fill - 024 - RW06 - C1-23 - CH1360 - 1423 - Layer 19
f9e11e07-05ee-4a96-b8b1-eb8ef3631810 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0326-Calder- North - RSS Fill - 024 - RW06 - C1-23 - CH1360 - 1423 - Layer 19 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
4b70295e-9776-47e8-a70b-2565668b2b98 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0327-Calder- North - RSS Fill - 032 - RW06 - C1-23 - CH1360 - 1423 - Layer 20
5abf9410-ec1e-4157-be4d-40b43267b668 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0327-Calder- North - RSS Fill - 032 - RW06 - C1-23 - CH1360 - 1423 - Layer 20 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
3c89e3a2-f23a-4036-94ba-183ac37e327b |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0328-Calder- North - RSS Fill - 035 - RW06 - C1-23 - CH1360 - 1423 - Layer 21
3a98d258-6380-46fb-8d7e-af25f5d13ac6 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0328-Calder- North - RSS Fill - 035 - RW06 - C1-23 - CH1360 - 1423 - Layer 21 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
65d39413-2336-4675-ad32-bbd019d97b13 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0329-Calder- North - RSS Fill - 036 - RW06 - C1-23 - CH1360 - 1423 - Layer 22
9ef904a9-7a3b-4532-92c1-468473ad3883 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0329-Calder- North - RSS Fill - 036 - RW06 - C1-23 - CH1360 - 1423 - Layer 22 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
b17c44e2-b38f-44d6-b188-2cd801b66063 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0330- Calder - North - RSS Fill - RW06 - CH1360 - 1423 - Layer 23
ec2adf16-66a9-4bfc-adf0-0b75528f0dfa |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0330- Calder - North - RSS Fill - RW06 - CH1360 - 1423 - Layer 23 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
523833ae-b2c7-439f-8b5c-855a359ecd7f |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0331 - Calder - North - RSS fill - RW06 - CH1360 - 1423 - Layer 24
85227805-bc2c-4685-8d9a-d600883e657b |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0331 - Calder - North - RSS fill - RW06 - CH1360 - 1423 - Layer 24 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
17501f0d-46f6-4e4a-bc2e-53bfe4299ae4 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0332 - Calder - North - RSS Fill - RW06 - CH1360 - 1423 - Layer 25
39135c3a-4d96-4ed6-82d7-3d83c636aca8 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0332 - Calder - North - RSS Fill - RW06 - CH1360 - 1423 - Layer 25 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
2205d804-cb9d-4ac4-a16e-f0dbd450b5e3 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0333- Calder - North - RSS Fill - RW06 - CH1360 - 1440 - Layer 26
e3981624-a350-4c0a-8a41-2337fccf08dd |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0333- Calder - North - RSS Fill - RW06 - CH1360 - 1440 - Layer 26 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
b4484763-0109-416a-a64e-0cf79505a6f6 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0334- Calder - North - RSS Fill- RW06 - CH1360 - 1440 - Layer 27
88f77305-10b4-4bf2-87ca-7c859174bcbe |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0334- Calder - North - RSS Fill- RW06 - CH1360 - 1440 - Layer 27 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
040e617c-fb90-4d20-a444-61dcb872fb88 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0335-Calder - North - RSS Fill - RW06 - CH1360 - 1440 - Layer 28
d290ba68-2833-48d6-bfd8-ec2d3d27e49c |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0335-Calder - North - RSS Fill - RW06 - CH1360 - 1440 - Layer 28 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
871b4285-b2dc-4087-b560-988ed4c31805 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0336 - Calder - North - RSS Fill - RW06 - CH1360 - 1440 - Layer 29
179d165c-e8b9-45b2-b3c3-737b57e07e68 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0336 - Calder - North - RSS Fill - RW06 - CH1360 - 1440 - Layer 29 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
8a03b6ff-e01d-4dd3-95f6-da1bea7dad8d |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0337 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 30
0ca39801-47ac-47a0-b4e7-990bfe4fb68d |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0337 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 30 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
abab6db2-d030-4eaa-b795-1b318a21542e |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0338 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 31
110e0901-30b2-4977-8c33-aa0f3a647f40 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0338 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 31 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
d017788e-4f88-49a3-a305-b723aeb77114 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0339 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 32
99982e61-bf2f-4bf6-aa1d-05d36a010c82 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0339 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 32 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
9930d721-adea-478b-a585-85ad905cd8db |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0340 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 33
d8fc5b3c-68aa-4609-88b2-28776c957461 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0340 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 33 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
ac75419f-4974-4ad6-aa68-9fd8d52db2dc |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0342 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 34
29fa848a-8458-43c7-ab1b-eccd5b0ee0c8 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0342 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 34 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
dc74518f-9f8b-4a99-a110-5970ea07d77b |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0342 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 35
09e0e81c-52b0-49a7-a88b-208a7b1f1f94 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0342 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 35 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
6479fe30-89da-42bd-9f3a-293cc3f9218e |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080- 343 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 36
07bd917e-5485-407c-9f67-4c89970d5087 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080- 343 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 36 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
b6faf611-87f1-429d-9ad8-c6ead0d706eb |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080- 344 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 37
4676042d-b962-4431-a08d-5c6d59b6aeb9 |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080- 344 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 37 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
303c1e03-ce59-474b-8990-f48a14ad2d79 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080- 345 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 38
ace9e3c4-04af-4c3a-a86b-abd5507587a2 |  | pass | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080- 345 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 38 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
a71cca42-6658-4468-90a7-591ed39c76f5 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080- 346 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 39
c69733d1-9615-4315-b2bf-ff7d1c2a2a30 |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080- 346 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 39 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
1ec691e2-8a57-423e-9252-ce0f837bb268 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0347 - Calder - North - RSS Fill - RW06 - CH1360 - 1440 - Layer 40
249c491f-a5e8-4c31-a0cb-a1d409cdbefd |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0347 - Calder - North - RSS Fill - RW06 - CH1360 - 1440 - Layer 40 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
aed2352b-64e5-435a-847b-bfdaccd00aa6 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0348- Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 41
59119e8f-7de3-4261-a751-f53b776315b9 |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0348- Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 41 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
2482f53f-8ea2-4501-815f-9729418df85e |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0349 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 42
a907c481-255d-43df-8c3a-f2d15a20efa8 |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0349 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 42 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
7223b749-ef3f-4185-ae81-2bdbb1e79ca3 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0350 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 43
5bf71a4a-6bde-4b03-9faf-fd0ea2079b3d |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0350 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 43 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
768baf1b-93bc-4993-a585-afa4c76515e4 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0351 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 44
a3ae3762-1387-4990-bbf8-26c2c50ba492 |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0351 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 44 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
43bf87d5-6c86-446d-b491-114ad3399287 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0352 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 45
9089477a-2b1e-4e39-872e-768518a09488 |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0352 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 45 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
64965025-7b30-4e75-9f97-b702ada3c942 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0353 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 46
920a67fb-cde0-4c6d-8d7a-bc8671fd1a39 |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0353 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 46 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
1058b746-f82e-42b6-af49-07d449bfff20 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0354 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 47
dc9f716c-3d38-4cb2-b31c-b1bb24243ecc |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0354 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 47 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
ad4bfca9-5918-4477-9bc4-5b5dbf04a7a7 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0355 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 48
78dea219-1fa7-4916-9b40-d6de575cdfc4 |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0355 - Calder - North - RSS - Fill - RW06 - CH1360 - 1440 - Layer 48 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
c869841d-77bb-4c70-ac01-d8c649e8356b |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0789 - Calder - North - RSS - Fill - RW06 - CH1360 - 1430 - Layer 49
afc8e873-b76e-41eb-9dc4-e012669ef375 |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0789 - Calder - North - RSS - Fill - RW06 - CH1360 - 1430 - Layer 49 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
745c8f01-ed93-4185-93fa-2f4b61bd1002 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0790 - Calder - North - RSS - Fill - RW06 - CH1360 - 1430 - Layer 50
7c85848f-74f5-44cb-9403-44f70e630621 |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0790 - Calder - North - RSS - Fill - RW06 - CH1360 - 1430 - Layer 50 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
6a4e8861-621b-4c31-9cc5-7b72baac224a |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0791 - Calder - North - RSS - Fill - RW06 - CH1360 - 1430 - Layer 51
de771698-f22a-42eb-af5f-fc2eb07c927b |  | work-in-progress | CHK-009-CIV-CPD-RSS Walls-Fill Placement Rev 2 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Fill Placement - North - RW06 | 080-0791 - Calder - North - RSS - Fill - RW06 - CH1360 - 1430 - Layer 51 | CHK-009-CIV-CPD-RSS Walls-Fill Placement
b2967ca5-1cb7-457f-9346-e621678eb003 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | Material Inspections - Track Strips
5680f80e-b847-455b-827d-9babcb036332 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | Material Inspections - Track Strips | 080-0665 - Calder - Material Inspection - Track Strips - 18/10/2023
2afe2970-25a1-4ab7-91c5-2672891d8569 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | Material Inspections - Track Strips | 080-0665 - Calder - Material Inspection - Track Strips - 18/10/2023 | CHK-006-STR&CIV-Material Inspection-RSS Track Strips
081cfd52-328a-436d-8632-a66f295dffb2 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | Material Inspections - Track Strips | 080-0666 - Calder - Material Inspection - Track Strips - 25/10/2023
58a6f384-04a9-4a93-ba43-966f928ad912 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | Material Inspections - Track Strips | 080-0666 - Calder - Material Inspection - Track Strips - 25/10/2023 | CHK-006-STR&CIV-Material Inspection-RSS Track Strips
69ef4ca2-dc62-4839-95f2-d46f351b867a |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | Material Inspections - Track Strips | 080-0668 - Calder - Material Inspection - Track Strips - 1/11/2023
5c8c4cb0-c514-418b-9cc6-da499acad043 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | Material Inspections - Track Strips | 080-0668 - Calder - Material Inspection - Track Strips - 1/11/2023 | CHK-006-STR&CIV-Material Inspection-RSS Track Strips
05cf47a5-703d-4ec5-8f25-d5c56e440e1e |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | Material Inspections - Wire Mats
bef0e4be-9108-42b4-b758-07ee7bae9afb |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | Material Inspections - Wire Mats | 080-0667 - Calder - Material Inspection - Wire Mats - 30/10/2023
5706e2e2-0059-4f5c-9089-e557776eb49b |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | Material Inspections - Wire Mats | 080-0667 - Calder - Material Inspection - Wire Mats - 30/10/2023 | CHK-006-STR&CIV-Material Inspection-RSS Wire Mats
9f9059a7-069a-430a-a130-bc49966a3acf |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | Material Inspections - Wire Mats | 080-0669 - Calder - Material Inspections - Wire Mats - 18/10/2023
6ce73f28-ef95-4580-8b21-1902b3f3bcac |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | Material Inspections - Wire Mats | 080-0669 - Calder - Material Inspections - Wire Mats - 18/10/2023 | CHK-006-STR&CIV-Material Inspection-Wire Facing Element
313385e0-7a23-45e9-9bd1-5600596e4fcb |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | Material Inspections - Wire Mats | 080-0670 - Calder - Material Inspection - Wire Mats - 18/10/2023
58ffcf8a-9699-4bb1-bf08-64410ba6b4c3 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | Material Inspections - Wire Mats | 080-0670 - Calder - Material Inspection - Wire Mats - 18/10/2023 | CHK-006-STR&CIV-Material Inspection - Wire Facing Elements
53af6eb9-517d-49c2-90ec-43929efc5cd8 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | Material Inspections - Wire Mats | 080-0671 - Calder - Material Inspection - Wire Mats - 31/10/2023
fd6a2c37-39b2-4b4b-b2cf-24fdb3cf4e26 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | Material Inspections - Wire Mats | 080-0671 - Calder - Material Inspection - Wire Mats - 31/10/2023 | CHK-006-STR&CIV-Material Inspection-Wire Facing Elements
35b84701-ceef-4df2-9783-a587fbcc1d43 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections
d27881ab-5695-4bba-987c-350d117da69d |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0541 - Calder - RSS Precast Panels Inspection - RW-04 - 16/01/2024
6e22bc26-356e-4af5-b00f-bfe5f466777a |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0541 - Calder - RSS Precast Panels Inspection - RW-04 - 16/01/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
49e4e8d3-09d7-49f1-9a95-fb99eb96c643 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0542 - Calder - Panels Inspection - RW03 and RW04 - 07/02/2024
efbb9335-f640-4a03-a91e-65a1c894cb8a |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0542 - Calder - Panels Inspection - RW03 and RW04 - 07/02/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev0
662fe86b-a599-4e40-b427-d65720c0f62b |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0538 - Calder - RSS Precast Panels Inspections- RW-03 - Lift 1 - 01/02/2024
d475c136-f29f-4493-bf1e-3adeab1310ed |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0538 - Calder - RSS Precast Panels Inspections- RW-03 - Lift 1 - 01/02/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
85f5c076-a5c1-43f9-bfc4-6e5909717992 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0543 - Calder - RSS Precast Panels Inspection - RW02 - Lift 1 - 14/02/2024
6684f131-2d35-459f-8a42-7c7497936f0b |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0543 - Calder - RSS Precast Panels Inspection - RW02 - Lift 1 - 14/02/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
1087027d-1911-4b33-945e-dd52c171b898 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0544 - Calder - RSS Precast Panels Inspection - RW02 - Lift 2 - 21/02/2024
c15457ef-9fe6-4d7f-b562-0b3de27bb4ef |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0544 - Calder - RSS Precast Panels Inspection - RW02 - Lift 2 - 21/02/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
d1066b2b-0879-4ae0-8fbe-c511e6a72f03 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0545 - Calder - RSS Precast Panels Inspection - RW02 - Lift 1 - 22/02/2024
7116adb0-bd89-43d5-8698-8f55d89e63fa |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0545 - Calder - RSS Precast Panels Inspection - RW02 - Lift 1 - 22/02/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
a1c11779-2cdd-4756-8280-27947863f4ac |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0358 - Calder - RSS Precast Panels Inspection- RW02, RW03 & RW04 - Lift 3 - 18/03/2024
fbc4c6fc-4097-4a1d-bf74-525305e62a42 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0358 - Calder - RSS Precast Panels Inspection- RW02, RW03 & RW04 - Lift 3 - 18/03/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
6d7d9600-52dd-4ac5-ae2d-eb78ee4dd14f |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0537 - Calder - RSS Precast Panels Inspection - RW05 - 1st Load - 27/03/2024
bf14cacd-a176-44ad-9d4e-e15f47d92d7d |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0537 - Calder - RSS Precast Panels Inspection - RW05 - 1st Load - 27/03/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
53d09889-162b-42be-b746-5013cd85b535 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0540 - Calder - RSS Precast Panels Inspection - RW05 - 2nd Load - 27/03/2024
96fef05d-dc33-43b9-a0ac-9c1fc2d7cab6 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0540 - Calder - RSS Precast Panels Inspection - RW05 - 2nd Load - 27/03/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
117ef34b-8a78-4372-a552-f8e75ddf3b05 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0546 - Calder - RSS Precast Panels Inspection - RW05 - 3rd Load - 27/03/2024
649d99ce-b100-4ca9-976b-6fc7aa151bc3 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0546 - Calder - RSS Precast Panels Inspection - RW05 - 3rd Load - 27/03/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
b53d49f8-c843-4686-83a7-425b3352ceba |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0550 - Calder - RSS Precast Panel Inspection - RW02 (L4&L5) RW04 (L4) - 04/04/2024
3f1a5933-be3a-44ec-9c05-b02ed2a59c17 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0550 - Calder - RSS Precast Panel Inspection - RW02 (L4&L5) RW04 (L4) - 04/04/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
8bf1ddd8-75cc-4220-865f-242dfd6e766a |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0551 - Calder - RSS Precast Panel Inspection - RW03 - 28/03/2024
5e9a4f4f-7fe8-44fe-8565-6a67595f8334 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0551 - Calder - RSS Precast Panel Inspection - RW03 - 28/03/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
2c1af307-8720-4084-b619-4b14ad3409a1 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0547 - Calder - RSS Precast Panels Inspection - RW05 - 1st Load - 05/04/2024
2dc127a3-029d-4f1b-8e39-e2a59f299f55 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0547 - Calder - RSS Precast Panels Inspection - RW05 - 1st Load - 05/04/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
7e0dc016-a228-4532-baad-b4bf8f9dde24 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0548 - Calder - RSS Precast Panels Inspection - RW05 - 2nd Load - 05/04/2024
52b59491-e171-438e-9cb6-0384a6945f6f |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0548 - Calder - RSS Precast Panels Inspection - RW05 - 2nd Load - 05/04/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
cfdc3126-1157-4e40-b188-5631dcb9a641 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0549 - Calder - RSS Precast Panels Inspection - RW05 - 3rd Load - 05/04/2024
291d14c7-c3a0-440c-875e-558f700d16c2 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0549 - Calder - RSS Precast Panels Inspection - RW05 - 3rd Load - 05/04/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
abe55fb0-6696-4256-abff-ed5f8c4473e8 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-539 - Calder - RSS Precast Panels Inspections- RW03 (L6 & L7) - 29/04/2024
8c7850b0-9b90-446d-9e62-ec2654b663f8 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-539 - Calder - RSS Precast Panels Inspections- RW03 (L6 & L7) - 29/04/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
80e1d4e7-d6ba-450f-a7b2-502fd0cc2e22 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0XXX - Calder - RSS Precast Panels Inspections- RW03 -10/05/2024
b6216157-2870-4a98-a3b7-89ef1ea21e1c |  | work-in-progress | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0XXX - Calder - RSS Precast Panels Inspections- RW03 -10/05/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
729737ab-034d-4601-a1b9-f420f5cf96d2 |  | not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0705 - Calder - RSS Precast Panels Inspection - RWXX - 2nd Load - 23/11/2023
3aa56d8c-b6a2-4a9b-bfeb-602763ef0794 |  | not-started | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0705 - Calder - RSS Precast Panels Inspection - RWXX - 2nd Load - 23/11/2023 | CHK-006-STR&CIV-Material Inspection-Precast Panel
8c6cee11-ee2a-4f25-aef2-68f3f6bb69c4 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0706 - Calder - RSS Precast Panels Inspection - RW04 - 2nd Load - 01/02/2024
9a11b833-2122-420f-b38e-492809290169 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0706 - Calder - RSS Precast Panels Inspection - RW04 - 2nd Load - 01/02/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
85795036-d020-40bd-a553-6105edbbc660 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0707 - Calder - RSS Precast Panels Inspection - RW03 - 2nd Load - 07/02/2024
67ab7c83-9876-40d7-8d93-c64c5d0d1229 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0707 - Calder - RSS Precast Panels Inspection - RW03 - 2nd Load - 07/02/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
539c36ec-4d15-481d-bfb1-4f08ffaa0b4c |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0708 - Calder - RSS Precast Panels Inspection - RW02 - 2nd Load - 14/02/2024
942ea67d-5bb1-4608-b549-ea0a2ab25226 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0708 - Calder - RSS Precast Panels Inspection - RW02 - 2nd Load - 14/02/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
fd74c2a7-f873-46b6-987b-d9e0378e0ba3 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0709 - Calder - RSS Precast Panels Inspection - RW02 - 1st Load - 18/03/2024
6a99eb42-e263-407f-ba05-17541c13e054 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0709 - Calder - RSS Precast Panels Inspection - RW02 - 1st Load - 18/03/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
41ad50d8-5c9c-4bef-8272-f68badf314a1 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0710 - Calder - RSS Precast Panels Inspection - RW03 - 2nd Load - 18/03/2024
bc6df0c5-802b-4a72-9134-626790d3f391 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0710 - Calder - RSS Precast Panels Inspection - RW03 - 2nd Load - 18/03/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
a5f669cb-7abe-49a2-94a2-a12d23a3efb6 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0711 - Calder - RSS Precast Panels Inspection - RW03 - 2nd Load - 04/04/2024
14743861-6824-4e51-aba7-6f43eab3df37 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0711 - Calder - RSS Precast Panels Inspection - RW03 - 2nd Load - 04/04/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
7544546e-ea36-4bd5-90af-361628a3088a |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0712 - Calder - RSS Precast Panels Inspection - RW03 - 1st Load - 15/04/2024
4d3744db-8307-42dc-aced-65f32d49b261 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0712 - Calder - RSS Precast Panels Inspection - RW03 - 1st Load - 15/04/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
436122b1-8e58-409e-b4fb-c0b04a9220f5 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0713- Calder - RSS Precast Panels Inspection - RW04 - 2nd Load - 15/04/2024
82e484c2-b71d-439e-a204-e6c31e3edac0 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | RSS Panels - Material Inspections | 080-0713- Calder - RSS Precast Panels Inspection - RW04 - 2nd Load - 15/04/2024 | CHK-006-STR&CIV-Material Inspection-Precast Panel
1ca92847-98fd-4a7a-b291-7b9895250c92 |  | not-started | ITP-046-CIV-CPD-Type A Fill - Road Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSW-0033-0 - RSS Wall | ITP-046-CIV-CPD-Type A Fill - Road
07e749e4-c895-41e3-8811-13ceb9ac6f0c |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0036-0 - Taylors Creek Culvert and Drainage Structures
73307d8e-7eb4-4b1d-bc97-e2657f7086cb |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0036-0 - Taylors Creek Culvert and Drainage Structures | Taylors Creek Culvert and Drainage Structures
207abad1-8658-4972-8433-7b16fe9ce772 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0036-0 - Taylors Creek Culvert and Drainage Structures | Taylors Creek Culvert and Drainage Structures | Culverts
6bee2c89-fca9-4df0-a0ce-cc7559ddc182 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0036-0 - Taylors Creek Culvert and Drainage Structures | Taylors Creek Culvert and Drainage Structures | Culverts | Stormwater - Pipe and Culvert Installation Rev0.0
7b604c91-d29d-4983-b2ed-1d4c7213d881 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0036-0 - Taylors Creek Culvert and Drainage Structures | Taylors Creek Culvert and Drainage Structures | General Concrete
4a7cbc43-46a9-405e-9360-20564a9bd3e8 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0036-0 - Taylors Creek Culvert and Drainage Structures | Taylors Creek Culvert and Drainage Structures | General Concrete | ITP-CIV-General Concrete Rev 1
7dc703a4-5c06-4079-ab95-d173e11891ab |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0036-0 - Taylors Creek Culvert and Drainage Structures | Taylors Creek Culvert and Drainage Structures | Rock Beaching
3de4e5d9-dfef-4332-9d77-4999fb60dc1c |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CDR-0036-0 - Taylors Creek Culvert and Drainage Structures | Taylors Creek Culvert and Drainage Structures | Contingency lots
40766aca-b0ef-4754-9564-d4341394ac97 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-AUD-0071-0 - Landscaping
1528c4c4-c5bc-4de8-b109-98f5ac4490c3 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-AUD-0071-0 - Landscaping | Calder Park Drive
4a667e32-9504-455b-b18d-eb359eafcf5e |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-AUD-0071-0 - Landscaping | Calder Park Drive | Site Wide (Location TBC)
86a6c1c9-8b3b-4527-874d-c1c92b04f801 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-AUD-0071-0 - Landscaping | Calder Park Drive | Site Wide (Location TBC) | ITP-CIV-Landscaping - Ground Preparation Rev 0
76b64a11-ce01-47c5-a5ea-0e7776bfdd56 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-AUD-0071-0 - Landscaping | Calder Park Drive | Site Wide (Location TBC) | ITP-CIV-Landscaping - Planting Rev 0
a0043497-a95e-42af-ae23-9ee5d7b9d7d0 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-AUD-0071-0 - Landscaping | Holden Rd
5072e1ad-dd92-4eed-9269-1628796c9abb |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-AUD-0071-0 - Landscaping | Holden Rd | Site Wide
48299e50-1e4e-4571-94b6-24ddf9bb3d1c |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-AUD-0071-0 - Landscaping | Holden Rd | Site Wide | ITP-CIV-Landscaping - Ground Preparation Rev 0
3839e9ed-8681-430d-a101-c54714d758c8 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-AUD-0071-0 - Landscaping | Holden Rd | Site Wide | ITP-CIV-Landscaping - Planting Rev 0
731e50b6-495a-4bb2-9bc3-b2fd21c53764 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-AUD-0071-0 - Landscaping | Contingency
e6d0306a-8f20-4b0d-a1ee-ccd85979331d |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment
fb0c7a5d-c4b8-49c1-8418-31e6671ba1a0 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment
334d9512-eb35-4541-9c7a-984066660868 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0600 - Calder - Embankment Fill - SAW - Layer 01 - CH 1100-1142
769969fb-27f4-4a30-bda7-863fce476212 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0600 - Calder - Embankment Fill - SAW - Layer 01 - CH 1100-1142 | ITP-047-CIV-CPD-Type B FIll - Road
10b1ce1f-4fb5-478c-8f70-50513527d23d |  | not-started | ITP-045-CIV-CPD-Subgrade Preparation - Road Rev 0 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0600 - Calder - Embankment Fill - SAW - Layer 01 - CH 1100-1142 | ITP-045-CIV-CPD-Subgrade Preparation - Road
793dca55-8d28-46b9-b4f9-7a2763fffad5 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0601 - Calder - Embankment Fill - SAW - Layer 02 - CH 1100-1142
9cf23c0d-6294-482e-b921-b1eae961e04b |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0601 - Calder - Embankment Fill - SAW - Layer 02 - CH 1100-1142 | ITP-047-CIV-CPD-Type B FIll - Road
203cef13-0f83-4441-be0a-cb1c95e46501 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0602 - Calder - Embankment Fill - SAW - Layer 03 - CH 1100-1142
669d9aa3-7b8c-4286-8119-280223ec53b1 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0602 - Calder - Embankment Fill - SAW - Layer 03 - CH 1100-1142 | ITP-047-CIV-CPD-Type B FIll - Road
de828940-f181-4a94-9d69-b24edfb39208 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0603 - Calder - Embankment Fill - SAW - Layer 04 - CH 1100-1142
7ba255a6-cd49-4f6c-9105-1744ccc239f6 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0603 - Calder - Embankment Fill - SAW - Layer 04 - CH 1100-1142 | ITP-047-CIV-CPD-Type B FIll - Road
b8b84510-7acb-45ec-abd8-dde416451f51 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0604 - Calder - Embankment Fill - SAW - Layer 05 - CH 1100-1142
7380470d-4c66-4bb4-a62b-cc3a0ba38b5d |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0604 - Calder - Embankment Fill - SAW - Layer 05 - CH 1100-1142 | ITP-047-CIV-CPD-Type B FIll - Road
deee9ba4-ec28-4434-8d22-df61228e2851 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0605 - Calder - Embankment Fill - SAW - Layer 06 - CH 1100-1142
55548d49-9fde-4ef7-8ba7-d0350c6235fe |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0605 - Calder - Embankment Fill - SAW - Layer 06 - CH 1100-1142 | ITP-047-CIV-CPD-Type B FIll - Road
5fa0ab6c-f566-4293-be04-d6a5394f73f7 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0606 - Calder - Embankment Fill - SAW - Layer 07 - CH 1100-1142
80690596-ede4-478b-b134-d67a4c8f5062 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0606 - Calder - Embankment Fill - SAW - Layer 07 - CH 1100-1142 | ITP-047-CIV-CPD-Type B FIll - Road
b5e2c662-26ad-423f-bb22-9720d43c62f9 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0607 - Calder - Embankment Fill - SAW - Layer 08 - CH 1100-1142
d60e2c19-9177-4c59-a596-3f68a0d8a4a4 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0607 - Calder - Embankment Fill - SAW - Layer 08 - CH 1100-1142 | ITP-047-CIV-CPD-Type B FIll - Road
8dafc9b4-ebdd-466d-a919-2b22ba3c0988 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0676 - Calder - Embankment Fill - SAW - Layer 09 - CH 1100-1142
fec5c820-555a-4f9d-9c28-f1973ac7b560 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | South Embankment | 080-0676 - Calder - Embankment Fill - SAW - Layer 09 - CH 1100-1142 | ITP-047-CIV-CPD-Type B FIll - Road
fd700f4e-e0e9-4e19-97f6-3aad9aed21c8 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1
daa4f8fe-44e4-4cf7-9c97-fe94ce985615 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0264 - Calder - Embankment Fill - North - Foundation - CH 1435 - 1635
ed14f6ec-0164-4828-b2a9-78bd29bd34a8 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0264 - Calder - Embankment Fill - North - Foundation - CH 1435 - 1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
b2ed4d80-743a-47a3-a440-2d4b27c890a5 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0265 - Calder - Embankment Fill - NAW1 - Layer 1 - CH 1435 - 1635
883f5cff-03f8-4acd-9955-0499256e365a |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0265 - Calder - Embankment Fill - NAW1 - Layer 1 - CH 1435 - 1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
5af46b25-7c87-42eb-aa50-23e54df5a2e8 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0266 - Calder - Embankment Fill - NAW1 - Layer 2 - CH 1435 - 1635
0e6be09a-b984-41f5-8e85-503467166b58 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0266 - Calder - Embankment Fill - NAW1 - Layer 2 - CH 1435 - 1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
c5bd0af8-8b57-4ca1-b4c3-5f239bd59383 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0267 - Calder - Embankment Fill - NAW1 - Layer 3 - CH 1435 - 1635
ae228f8e-6691-4f59-be18-e6a12ffac5e8 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0267 - Calder - Embankment Fill - NAW1 - Layer 3 - CH 1435 - 1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
0c237a17-fd49-46a3-ba45-656a60a41814 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0268 - Calder - Embankment Fill - NAW1 - Layer 4 - CH 1435 - 1635
ef09f53d-a15b-450a-9cc6-defa6f59f98b |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0268 - Calder - Embankment Fill - NAW1 - Layer 4 - CH 1435 - 1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
c0b74006-4ea1-4a0a-a794-47c0ccb88683 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0269 - Calder - Embankment Fill - NAW1 - Layer 5 - CH 1435 - 1635
2474a0c8-92bd-4f79-baa7-8a7746f7747c |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0269 - Calder - Embankment Fill - NAW1 - Layer 5 - CH 1435 - 1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
7018d745-91cb-4197-8386-de4448973bf3 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0278 - Calder - Embankment Fill - NAW1 - Layer 6 - CH 1435 - 1635
e288aade-c494-4997-bbde-442cb042cd3d |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0278 - Calder - Embankment Fill - NAW1 - Layer 6 - CH 1435 - 1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
f6be1a14-73f2-445a-b9f8-47337a13a6c9 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0279 - Calder - Embankment Fill - NAW1 - Layer 7 - CH 1435 - 1635
e0acb84b-5cad-4a79-ad67-8ee38db7919f |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0279 - Calder - Embankment Fill - NAW1 - Layer 7 - CH 1435 - 1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
8b1f70f1-d33b-4014-bbad-43e5d88cf470 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0280 - Calder - Embankment Fill - NAW1 - Layer 8 - CH 1435 - 1635
7fb1e1aa-d38b-4160-969e-f2831cd3095a |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0280 - Calder - Embankment Fill - NAW1 - Layer 8 - CH 1435 - 1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
c17ee2e8-c0fc-4237-ae39-eb606f670e37 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0281 - Calder - Embankment Fill - NAW1 - Layer 9A - CH 1435 - 1635
18e51f7a-cb4d-46c8-a6df-7a757aec3c99 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0281 - Calder - Embankment Fill - NAW1 - Layer 9A - CH 1435 - 1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
aae331f2-b143-476c-bf4e-fee05c3b4aad |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0282 - Calder - Embankment Fill - NAW1 - Layer 9B - CH 1435 - 1635
7ee6bbc9-5861-4c36-8ebc-4180e363a4c2 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0282 - Calder - Embankment Fill - NAW1 - Layer 9B - CH 1435 - 1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
586d2133-3e33-47cd-8574-ec4cc0edfeeb |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0284 - Calder - Embankment Fill - NAW1 - Layer 10A - CH 1435 - 1635
021c6d19-df5b-4297-8b40-f770bc4492c5 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0284 - Calder - Embankment Fill - NAW1 - Layer 10A - CH 1435 - 1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
98010270-35b7-40c6-a714-20905ad35c0d |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0285 - Calder - Embankment Fill - NAW1 - Layer 10B - CH 1435 - 1635
b78b30b2-a87b-4401-8e66-3879766c723d |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0285 - Calder - Embankment Fill - NAW1 - Layer 10B - CH 1435 - 1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
7aa3ce65-5dd5-4e69-9c8e-437d751d5793 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0286 - Calder - Embankment Fill - NAW1 - Layer 11 - CH 1435 - 1635
b7fb8a4f-5ea7-4639-89f4-6f43929c5b41 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0286 - Calder - Embankment Fill - NAW1 - Layer 11 - CH 1435 - 1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
8b742147-eed5-45e7-95be-5cffd72bb772 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0287 - Calder - Embankment Fill - NAW1 - Layer 12 - CH 1435 - 1635
98d80ec2-1784-4b36-b09b-8d2f0af4f5c3 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0287 - Calder - Embankment Fill - NAW1 - Layer 12 - CH 1435 - 1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
77a4ad32-b6c6-4652-85e4-1b47b691e1db |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0291 - Calder - Embankment Fill - NAW1 - Layer 13 - CH 1435-1635
3e5a0980-dd1b-4178-9f27-90a9c967e99b |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0291 - Calder - Embankment Fill - NAW1 - Layer 13 - CH 1435-1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
fc573e09-7547-4bb7-aadd-1120fd7c0ef9 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0292 - Calder - Embankment Fill - NAW1 - Layer 14 - CH 1435-1635
893b9d25-2565-484f-a92f-e0d1c3062e3a |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0292 - Calder - Embankment Fill - NAW1 - Layer 14 - CH 1435-1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
5b9953ba-c3f2-42d9-b02c-69d743c879cb |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0293 - Calder - Embankment Fill - NAW1 - Layer 15 - CH 1435-1635
1cf9cd81-2855-4e8a-b2ba-90cee8010671 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0293 - Calder - Embankment Fill - NAW1 - Layer 15 - CH 1435-1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
e08ca356-b2f3-47a2-a216-62f0234a6263 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0294 - Calder - Embankment Fill - NAW1 - Layer 16A - CH 1435-1635
662e8779-0e0b-4976-9aba-fb903230f8cd |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0294 - Calder - Embankment Fill - NAW1 - Layer 16A - CH 1435-1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
14fee171-a875-440e-88b9-538345ef676e |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0296 - Calder - Embankment Fill - NAW1 - Layer 16B - CH 1435-1635
d607d93f-4e7d-4dd4-9873-5ca6933f652f |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0296 - Calder - Embankment Fill - NAW1 - Layer 16B - CH 1435-1635 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
872f3941-261f-40c8-9d97-97444347ccb9 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0297 - Calder - Embankment Fill - NAW1 - Layer 17 - CH 1440-1625
1744938b-e19f-4361-bfbc-30d374a11ed4 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0297 - Calder - Embankment Fill - NAW1 - Layer 17 - CH 1440-1625 | ITP-047-CIV-CPD-Type B FIll - Road
88f81531-4ffe-46f9-94c1-c5e02acaa175 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0298 - Calder - Embankment Fill - NAW1 - Layer 18 - CH 1440-1625
0dbe0a9f-4bb0-4063-a83a-e2add46788b9 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0298 - Calder - Embankment Fill - NAW1 - Layer 18 - CH 1440-1625 | ITP-047-CIV-CPD-Type B FIll - Road
6cfba565-b5a7-4452-8b1c-cfc025c68ccb |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0300 - Calder - Embankment Fill - NAW1 - Layer 19 - CH 1440-1625
d60a701c-f02c-4dbd-9c4d-dbcf5b56e2b8 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0300 - Calder - Embankment Fill - NAW1 - Layer 19 - CH 1440-1625 | ITP-047-CIV-CPD-Type B FIll - Road
3c67b74a-123b-471a-8db0-cb06f6067141 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0466 - Calder - Embankment Fill - NAW1 - Layer 20 - CH 1440-1625
5feb3c54-26f0-429f-81cb-1bbe2d13b9f8 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0466 - Calder - Embankment Fill - NAW1 - Layer 20 - CH 1440-1625 | ITP-047-CIV-CPD-Type B FIll - Road
50821636-d5d9-4728-9d53-a5b851aa7970 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0467 - Calder - Embankment Fill - NAW1 - Layer 21 - CH 1445-1620
ac96594a-1262-4651-a24c-2f68614d71c0 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW1 | 080-0467 - Calder - Embankment Fill - NAW1 - Layer 21 - CH 1445-1620 | ITP-047-CIV-CPD-Type B FIll - Road
fb78c6b6-9c9a-4881-9670-99d50b3c7147 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW2
e05b8089-8dd1-4ff5-be04-78470fb5f5df |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW2 | 080-0288- Calder - Embankment Fill - NAW2 - Layer 1 - CH 1360-1435
4d66d994-a5c4-475e-822d-dd737f5e34ee |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW2 | 080-0288- Calder - Embankment Fill - NAW2 - Layer 1 - CH 1360-1435 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
051882da-2556-4fc5-ac90-3f39122193d4 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW2 | 080-0289- Calder - Embankment Fill - NAW2 - Layer 2 - CH 1360-1435
63e3b9cf-af4b-45c2-b5f8-97e8a543d12b |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW2 | 080-0289- Calder - Embankment Fill - NAW2 - Layer 2 - CH 1360-1435 | ITP-047-CIV-CPD-Type B FIll - Road
34bc82ce-a6e6-4344-bc6a-8f3dbb3e11de |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW2 | 080-0290- Calder - Embankment Fill - NAW2 - Layer 3 - CH 1360-1435
cd9ae8c0-958c-4795-b823-09971f11e422 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW2 | 080-0290- Calder - Embankment Fill - NAW2 - Layer 3 - CH 1360-1435 | ITP-047-CIV-CPD-Type B FIll - Road
503c3eea-5394-4ccc-b20d-a40807dc2da6 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW2 | 080-0295- Calder - Embankment Fill - NAW2 - Layer 4 - CH 1360-1435
8d02c90c-a186-4f67-a43a-7e66f4be6faf |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW2 | 080-0295- Calder - Embankment Fill - NAW2 - Layer 4 - CH 1360-1435 | ITP-047-CIV-CPD-Type B FIll - Road
b4d17c2b-d67f-4e86-a91b-887c4069d6de |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW2 | 080-0299- Calder - Embankment Fill - NAW2 - Layer 5 - CH 1360-1435
d79fc579-11ae-4a62-87f5-1ced62f227a1 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW2 | 080-0299- Calder - Embankment Fill - NAW2 - Layer 5 - CH 1360-1435 | ITP-047-CIV-CPD-Type B FIll - Road
f9fcf724-a28d-4348-90c9-fe66e86ed1eb |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW2 | 080-0469- Calder - Embankment Fill - NAW2 - Layer 6 - CH 1360-1435
62e35c80-3acf-4bd5-ae52-52331ca30f68 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW2 | 080-0469- Calder - Embankment Fill - NAW2 - Layer 6 - CH 1360-1435 | ITP-047-CIV-CPD-Type B FIll - Road
53f6bd3c-3ed9-4eda-a1a5-adc434eaa5b5 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW3
67e46ec6-e765-4e8a-ab30-acd86cf4f5c4 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW3 | 080-0470 - Calder - Embankment Fill - NAW3 - Layer 01 - CH 1360 - 1435
d875fe95-fa6c-4b70-b882-d464cb2aeb19 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW3 | 080-0470 - Calder - Embankment Fill - NAW3 - Layer 01 - CH 1360 - 1435 | ITP-047-CIV-CPD-Type B FIll - Road
c911a768-db92-4280-ade9-073158d0f0bc |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW3 | 080-0563 - Calder - Embankment Fill - NAW3 - Layer 2 - CH 1360 - 1435
39699f3f-c41f-441e-903a-74f78f10afce |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW3 | 080-0563 - Calder - Embankment Fill - NAW3 - Layer 2 - CH 1360 - 1435 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
01adb555-951c-48b2-bd86-bb9fb1e1ea22 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW3 | 080-0564 - Calder - Embankment Fill - NAW3 - Layer 3 - CH 1360 - 1435
baf4e3b8-8b3f-4cbd-b5bb-be82241fd913 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW3 | 080-0564 - Calder - Embankment Fill - NAW3 - Layer 3 - CH 1360 - 1435 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
0d9a75bb-3e05-4b63-81f7-998d67843246 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW3 | 080-0565 - Calder - Embankment Fill - NAW3 - Layer 4 - CH 1360 - 1435
770184c6-f6ec-4b17-a6ce-771bd33cd7a4 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW3 | 080-0565 - Calder - Embankment Fill - NAW3 - Layer 4 - CH 1360 - 1435 | ITP-047-CIV-CPD-Type B Fill - Road Rev 1
75604118-4f4a-497c-8940-895e204241dd |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW3 | 080-0566 - Calder - Embankment Fill - NAW3 - Layer 5 - CH 1360-1435
f9f222b6-8992-41c2-8ae1-21af9cf76422 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW3 | 080-0566 - Calder - Embankment Fill - NAW3 - Layer 5 - CH 1360-1435 | ITP-047-CIV-CPD-Type B FIll - Road
d7a70c47-bcad-4989-aa24-61a33786c323 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW3 | 080-0567 - Calder - Embankment Fill - NAW3 - Layer 6 - CH 1360-1435
da901cd8-46e6-4891-9fa7-2096387b8faa |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW3 | 080-0567 - Calder - Embankment Fill - NAW3 - Layer 6 - CH 1360-1435 | ITP-047-CIV-CPD-Type B FIll - Road
06af5b9a-e0b8-4082-95e3-25020a775ee6 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4
ce6d5600-6560-422c-ac98-4fa7d2d871cd |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0634 - Calder - Embankment Fill - NAW4 - Layer 7 - CH 1435-1650
174794c7-a7cf-429e-b23e-925a216e414d |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0634 - Calder - Embankment Fill - NAW4 - Layer 7 - CH 1435-1650 | ITP-047-CIV-CPD-Type B FIll - Road
50a8f8e4-9103-4d36-b589-ad2717b1434a |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0635 - Calder - Embankment Fill - NAW4 - Layer 8 - CH 1435-1650
68e264ba-bd70-4921-8ee5-b25a9d95cdd4 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0635 - Calder - Embankment Fill - NAW4 - Layer 8 - CH 1435-1650 | ITP-047-CIV-CPD-Type B FIll - Road
bdd76685-5f96-4399-9c0a-9f84a4cc5ad7 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0637 - Calder - Embankment Fill - NAW4 - Layer 9 - CH 1435-1650
6216a937-4ae8-4473-af56-e8f1455284ec |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0637 - Calder - Embankment Fill - NAW4 - Layer 9 - CH 1435-1650 | ITP-047-CIV-CPD-Type B FIll - Road
3446c15d-0565-4776-b5fa-46378da7c283 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0639 - Calder - Embankment Fill - NAW4 - Layer 10 - CH 1435-1650
0e12877c-d8a6-4f5e-a906-b003c39871ed |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0639 - Calder - Embankment Fill - NAW4 - Layer 10 - CH 1435-1650 | ITP-047-CIV-CPD-Type B FIll - Road
2ce290cf-fde6-4dbf-bc6d-b0ee9ddc098f |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0641 - Calder - Embankment Fill - NAW4 - Layer 11 - CH 1435-1650
4b69598a-88c4-4a54-98b4-901dc9d6c175 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0641 - Calder - Embankment Fill - NAW4 - Layer 11 - CH 1435-1650 | ITP-047-CIV-CPD-Type B FIll - Road
9fc6b211-0153-49cd-9782-1d27430a152b |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0643 - Calder - Embankment Fill - NAW4 - Layer 12 - CH 1435-1650
09cba2f4-3122-4107-8979-18254b5d3f61 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0643 - Calder - Embankment Fill - NAW4 - Layer 12 - CH 1435-1650 | ITP-047-CIV-CPD-Type B FIll - Road
57fc33c2-2938-4c6c-8c26-d242e6317985 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0649- Calder - Embankment Fill - NAW4 - Layer 13 - CH 1435-CH1650
2b600ab8-6236-4804-99b2-5653c602a0f8 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0649- Calder - Embankment Fill - NAW4 - Layer 13 - CH 1435-CH1650 | ITP-047-CIV-CPD-Type B FIll - Road
12ed257b-b1c4-4c8c-833c-d0d0cfed00ec |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0650 - Calder - Embankment Fill - NAW4 - Layer 14 - CH 1435 - 1650
fc99cc38-e47e-4561-a4b9-06f6231fb3b4 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0650 - Calder - Embankment Fill - NAW4 - Layer 14 - CH 1435 - 1650 | ITP-047-CIV-CPD-Type B FIll - Road
205cca04-2adc-4a32-99c5-2ceff2cff15a |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0653 - Calder - Embankment Fill - NAW4 - Layer 15A CH1470 - CH1650
525706ab-f897-49e1-b6bd-88d0386f19d9 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0653 - Calder - Embankment Fill - NAW4 - Layer 15A CH1470 - CH1650 | ITP-047-CIV-CPD-Type B FIll - Road
49ef62bf-f334-40b8-9aca-6dfc3b2a66a5 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0654 - Calder - Embankment Fill - NAW4 - Layer 15B CH1435 - CH1470
b9721841-8bd4-4e19-ba78-6eb693b0f802 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0654 - Calder - Embankment Fill - NAW4 - Layer 15B CH1435 - CH1470 | ITP-047-CIV-CPD-Type B FIll - Road
67a05540-61ef-43ce-8b94-528eaa10e28a |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0656 - Calder - Embankment Fill - NAW4 - Layer 16 CH1435 - CH1650
bed330ab-359e-48e4-9dd3-eeaeebe46e79 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0656 - Calder - Embankment Fill - NAW4 - Layer 16 CH1435 - CH1650 | ITP-047-CIV-CPD-Type B FIll - Road
91ca2d9e-c19e-40b5-a5a4-de7a2c294351 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0657 - Calder - Embankment Fill - NAW4 - Layer 17 CH1435 - CH1650
e5ebb350-6551-4119-b49d-03602975e7a3 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW4 | 080-0657 - Calder - Embankment Fill - NAW4 - Layer 17 CH1435 - CH1650 | ITP-047-CIV-CPD-Type B FIll - Road
c053cc63-fe8a-491a-9f4f-aaa74519d3d9 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski
cbd998e6-1984-4b93-87aa-9c64329112b8 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0636- Calder - Embankment Fill - NAW5 - Layer 07 - CH 1360-1435
30275c1c-3de1-4c0d-85c5-a0faa1c5641d |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0636- Calder - Embankment Fill - NAW5 - Layer 07 - CH 1360-1435 | ITP-047-CIV-CPD-Type B FIll - Road
3f5509ba-2473-4cd6-9d11-e288e1e4c50e |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0638- Calder - Embankment Fill - NAW5 - Layer 08 - CH 1360-1435
7b7de6e1-effa-4098-bb65-59563dba9fab |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0638- Calder - Embankment Fill - NAW5 - Layer 08 - CH 1360-1435 | ITP-047-CIV-CPD-Type B FIll - Road
b81c3e5b-7eb6-4597-a8d6-b5e5a539f84e |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0640- Calder - Embankment Fill - NAW5 - Layer 09 - CH 1360-1435
92d9efc7-ce8b-4e34-9a97-aad985ceb856 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0640- Calder - Embankment Fill - NAW5 - Layer 09 - CH 1360-1435 | ITP-047-CIV-CPD-Type B FIll - Road
780293fa-bf34-46e6-be44-7584639cdc90 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0642- Calder - Embankment Fill - NAW5 - Layer 10 - CH 1360-1435
a62f2893-265b-4b31-b0ee-0f553daa3f2f |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0642- Calder - Embankment Fill - NAW5 - Layer 10 - CH 1360-1435 | ITP-047-CIV-CPD-Type B FIll - Road
88602e85-d76a-490d-b0cf-b2a1c028bf6b |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0644- Calder - Embankment Fill - NAW5 - Layer 11 - CH 1360-1435
d32318e6-1b15-4bff-b3ca-ffd6d650315a |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0644- Calder - Embankment Fill - NAW5 - Layer 11 - CH 1360-1435 | ITP-047-CIV-CPD-Type B FIll - Road
0c704a15-813e-41d8-94c0-d578010bb530 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0645- Calder - Embankment Fill - NAW5 - Layer 12 - CH 1360-1435
d1db4fbf-9e93-441b-a3d5-169dafe99092 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0645- Calder - Embankment Fill - NAW5 - Layer 12 - CH 1360-1435 | ITP-047-CIV-CPD-Type B FIll - Road
cca20992-554d-4001-9ffd-6349b501bd56 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0646- Calder - Embankment Fill - NAW5 - Layer 13 - CH 1360-1435
3e4bfe4e-d4e3-4170-9824-8a84fb83417d |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0646- Calder - Embankment Fill - NAW5 - Layer 13 - CH 1360-1435 | ITP-047-CIV-CPD-Type B FIll - Road
0e323799-512d-4baf-b0dc-ab9b2e01820d |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0647- Calder - Embankment Fill - NAW5 - Layer 14 - CH 1360-1435
824d313f-440e-4ccf-bf03-4853cdb446a4 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0647- Calder - Embankment Fill - NAW5 - Layer 14 - CH 1360-1435 | ITP-047-CIV-CPD-Type B FIll - Road
ef52c696-aa88-4206-89c2-0f858b48a778 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0648- Calder - Embankment Fill - NAW5 - Layer 15 - CH 1360-1375
d4a2d906-7312-4574-831a-6361d98f7e42 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0648- Calder - Embankment Fill - NAW5 - Layer 15 - CH 1360-1375 | ITP-047-CIV-CPD-Type B FIll - Road
20504059-8578-4352-904d-46c5748aa1b2 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0651 - Calder - Embankment Fill - NAW5 - Layer 15B - CH 1375-1435
c3a8173d-19ba-48fc-be5e-7bd65dae8088 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0651 - Calder - Embankment Fill - NAW5 - Layer 15B - CH 1375-1435 | ITP-047-CIV-CPD-Type B FIll - Road
d2c0ebe4-c40a-4e47-bc5f-fd017d284f40 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0652 - Calder - Embankment Fill - NAW5 - Layer 16 - CH1360 - 1650
4b51ec3e-fe99-4bcb-9632-48935bceafc5 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0652 - Calder - Embankment Fill - NAW5 - Layer 16 - CH1360 - 1650 | ITP-047-CIV-CPD-Type B FIll - Road
ab6b1b19-edb7-45ed-9578-9d4b478f7fe0 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0655 - Calder - Embankment Fill - NAW5 - Layer 17 CH1360 - CH1435
f5b3e14c-c053-4cb2-b3e0-1ae008c67a93 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0655 - Calder - Embankment Fill - NAW5 - Layer 17 CH1360 - CH1435 | ITP-047-CIV-CPD-Type B FIll - Road
bf030e12-c740-49b9-ae89-01ed017d6a91 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0659 - Calder - Embankment Fill - NAW5 - Layer 18 CH1360 - CH1435
152771e4-e9be-44ab-bc3c-2a911ce21fa4 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0659 - Calder - Embankment Fill - NAW5 - Layer 18 CH1360 - CH1435 | ITP-047-CIV-CPD-Type B FIll - Road
26ae709d-b7a5-4da7-bebc-9076fc47ad57 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0662- Calder - Embankment Fill - North - Layer 19 - Ch 1360 - 1435
83b25470-000c-415b-b072-48402a7f2a3c |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0662- Calder - Embankment Fill - North - Layer 19 - Ch 1360 - 1435 | ITP-047-CIV-CPD-Type B FIll - Road
53409c7f-5ff9-43dc-a88f-8a4e6944de46 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0728 - Calder - Embankment Fill - NAW - Layer 20 - CH 1360 - 1435
488ce99d-bed6-4d06-a870-5d142f9e3858 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0728 - Calder - Embankment Fill - NAW - Layer 20 - CH 1360 - 1435 | ITP-047-CIV-CPD-Type B FIll - Road
24a82138-40a6-46a5-a2e0-641413003853 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0632- Calder - Embankment Fill - NAW5 - Layer 21
5e0928d3-540f-4f13-888c-2f85c60b7144 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0632- Calder - Embankment Fill - NAW5 - Layer 21 | ITP-047-CIV-CPD-Type B FIll - Road
599d7851-ae5e-48c1-a1d2-6eb0ccd4d7a2 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0356-Calder - Embankment Fill - NAW - Layer 22
ec753a80-f210-4c54-b939-bd82b2f297c5 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0356-Calder - Embankment Fill - NAW - Layer 22 | ITP-047-CIV-CPD-Type B FIll - Road
1c5caa50-9c6a-4224-b928-e698b3df9a6a |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0753 - Calder - Embankment Fill - NAW - Layer 23
44108496-4cfc-4534-909a-702ff74d744c |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0753 - Calder - Embankment Fill - NAW - Layer 23 | ITP-047-CIV-CPD-Type B FIll - Road
3817ba8a-7c1c-4e11-a7fc-8a35a435fc2f |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0756 - Calder - Embankment Fill- NAW - Layer 24
7b78616e-5322-4440-8d81-a67edead5e20 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0756 - Calder - Embankment Fill- NAW - Layer 24 | ITP-047-CIV-CPD-Type B FIll - Road
81c646d3-ab2e-48fb-804a-eefe7da72e7c |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0762 - Calder - Embankment Fill - NAW - Layer 25
ad1517e4-fc94-49f7-8948-1220c235c0c5 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0762 - Calder - Embankment Fill - NAW - Layer 25 | ITP-047-CIV-CPD-Type B FIll - Road
6ff67dd4-3137-431e-bad4-9db0206038e1 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0763- Calder- Embankment Fill - NAW - Layer 26
665ad63f-ccab-44ec-8aec-3d98ff5e2c23 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0763- Calder- Embankment Fill - NAW - Layer 26 | ITP-047-CIV-CPD-Type B FIll - Road
836f2fd1-88d1-4f79-a4e2-99353b219f8d |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0766 - Calder - Embankment Fill - NAW - Layer 27
65068f88-d0d4-4cc6-8981-caee0ecb1e50 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0766 - Calder - Embankment Fill - NAW - Layer 27 | ITP-047-CIV-CPD-Type B FIll - Road
4146ded9-5ff3-4330-a295-55a8eeaad58e |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0767 - Calder - Embankment Fill - NAW - Layer 28
be0a6e3d-9fcb-4753-bb7e-05b916ecc58a |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0767 - Calder - Embankment Fill - NAW - Layer 28 | ITP-047-CIV-CPD-Type B FIll - Road
5edf8ef3-e023-4ac8-8965-166769a99693 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0771- Calder - Embankment Fill - NAW - Layer 29
e5a05c2c-3e41-4500-959f-2934a5bdf3bb |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0771- Calder - Embankment Fill - NAW - Layer 29 | ITP-047-CIV-CPD-Type B FIll - Road
b37cbed1-9036-49e5-99ff-d4f76d0693d1 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0772-Calder - Embankment Fill - NAW - Layer 30
aced43b5-f1c7-448e-b6ce-17f08aaa4e62 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0772-Calder - Embankment Fill - NAW - Layer 30 | ITP-047-CIV-CPD-Type B FIll - Road
68acac1d-12f4-4919-b725-5a81123cf960 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0359 - Calder - Embankment Fill - NAW - Layer 31
2f158356-5683-4c8f-baa8-4393446d99dc |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0359 - Calder - Embankment Fill - NAW - Layer 31 | ITP-047-CIV-CPD-Type B FIll - Road
289cc8b5-d406-4de7-b403-9180634b076f |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0696 - Calder - Embankment Fill - NAW - Layer 32
8611e00a-5b92-43b3-af99-db002f031669 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0696 - Calder - Embankment Fill - NAW - Layer 32 | ITP-047-CIV-CPD-Type B FIll - Road
f793c4d5-e0fc-4c2e-872c-a819c3ac732d |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0723 - Calder - Embankment Fill - NAW - Layer 33
454851ce-7420-4d12-ad21-878fdf906afd |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0723 - Calder - Embankment Fill - NAW - Layer 33 | ITP-047-CIV-CPD-Type B FIll - Road
4f5bcbbc-a9a0-4115-b124-0900960888f2 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0730 - Calder - Embankment Fill - NAW - Layer 34
b7c0c0ee-57b6-48e9-afee-5e9a1af73089 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0730 - Calder - Embankment Fill - NAW - Layer 34 | ITP-047-CIV-CPD-Type B FIll - Road
247954de-6b66-4103-99cf-5fe1f1ca9395 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0754 - Calder - Embankment Fill - NAW - Layer 35
e8000f69-f372-4ed6-b16b-c0038000da08 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0754 - Calder - Embankment Fill - NAW - Layer 35 | ITP-047-CIV-CPD-Type B FIll - Road
b4a0b722-3043-4939-94f7-f2cfc67cf56f |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0716 - Calder - Embankment Fill - NAW - Layer 36
62e0ea74-73e1-4f81-bbb7-99ca9515c5d9 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0716 - Calder - Embankment Fill - NAW - Layer 36 | ITP-047-CIV-CPD-Type B FIll - Road
0b846fe3-ed54-41e5-b59e-5019001b6bd4 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0776 - Calder - Embankment Fill - NAW - Layer 37
c816a046-0eb1-47dd-bb3f-e8202304ec6a |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0776 - Calder - Embankment Fill - NAW - Layer 37 | ITP-047-CIV-CPD-Type B FIll - Road
cc62bbea-f445-468b-a43a-cad3a09db66b |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0777 - Calder - Embankment Fill - NAW - Layer 38
a0c595e4-c595-4d37-ac47-aba7f1625b6f |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0777 - Calder - Embankment Fill - NAW - Layer 38 | ITP-047-CIV-CPD-Type B FIll - Road
e776f5cb-2104-417d-86a0-404d2229e3be |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0778 - Calder - Embankment Fill - NAW - Layer 39
546b414c-0193-48f9-8cc0-3d0099b3293f |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0778 - Calder - Embankment Fill - NAW - Layer 39 | ITP-047-CIV-CPD-Type B FIll - Road
c062f575-c400-4921-8fbd-e2bea375caa3 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0779 - Calder - Embankment Fill - NAW - Layer 40
ea74b46d-94b9-4231-85c7-a983db7607b8 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0779 - Calder - Embankment Fill - NAW - Layer 40 | ITP-047-CIV-CPD-Type B FIll - Road
bc10797e-e7cb-4ddf-b6bd-174e7790cd7b |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0787 - Calder - Embankment Fill - NAW - Layer 41
e9d26f85-92f3-4e4f-b533-915c3bbcfb3a |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0787 - Calder - Embankment Fill - NAW - Layer 41 | ITP-047-CIV-CPD-Type B FIll - Road
d4d2f470-6ee1-475f-bea2-6d12d0c9ec0c |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0788 - Calder - Embankment Fill - NAW - Layer 42
47ec77e1-248d-486c-99f4-107526aef3b7 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0788 - Calder - Embankment Fill - NAW - Layer 42 | ITP-047-CIV-CPD-Type B FIll - Road
952ba7dc-ed99-4968-bf91-f5cff830fc7a |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0220 - Calder - Embankment Fill - NAW - Layer 43
7375d7bf-6e2c-4236-b95b-cc135c561612 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0220 - Calder - Embankment Fill - NAW - Layer 43 | ITP-047-CIV-CPD-Type B FIll - Road
27c0044d-bbc1-4d84-a1ad-ed7cb8506be4 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0434 - Calder - Embankment Fill - NAW - Layer 44
0aea9f25-d67d-455b-966d-955bbfa8b7ef |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW5 - Masalkovski | 080-0434 - Calder - Embankment Fill - NAW - Layer 44 | ITP-047-CIV-CPD-Type B FIll - Road
6b2cff58-6615-4b69-b82a-0a3db935fd95 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW East - Site Won
7dcf10fd-abe8-4183-a299-76454991c37e |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW East - Site Won | 080-0661- Calder - Embankment Fill - North East- Layer 19 - Ch 1435 - 1635
1db9ef92-969d-4d10-a8ca-4368d39bbb8e |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW East - Site Won | 080-0661- Calder - Embankment Fill - North East- Layer 19 - Ch 1435 - 1635 | ITP-047-CIV-CPD-Type B FIll - Road
f51f0b6f-e471-4225-bd06-1938beffb557 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW East - Site Won | 080-0714- Calder - Embankment Fill - North East- Layer 20 - Ch 1435 - 1635
c6ba8b20-af8d-4151-8627-b0c5d51bdc91 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW East - Site Won | 080-0714- Calder - Embankment Fill - North East- Layer 20 - Ch 1435 - 1635 | ITP-047-CIV-CPD-Type B FIll - Road
d4734388-4bc4-4e5c-9b5c-e639142f39d2 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW East - Site Won | 080-0729 - Calder - Embankment Fill - NAW East - Layer 21 - CH 1435 - 1625
db24a989-3038-49a1-ac78-5bc214f7e4b4 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW East - Site Won | 080-0729 - Calder - Embankment Fill - NAW East - Layer 21 - CH 1435 - 1625 | ITP-047-CIV-CPD-Type B FIll - Road
4387d0f5-c764-4518-bc6f-c9c1d807620f |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW East - Site Won | 080-0734 - Calder - Embankment Fill - NAW East - Layer 22 - CH 1435 - 1625
05213023-44d4-41ab-8693-d1c8a8844303 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW East - Site Won | 080-0734 - Calder - Embankment Fill - NAW East - Layer 22 - CH 1435 - 1625 | ITP-047-CIV-CPD-Type B FIll - Road
4d98e0e8-502b-409a-9da6-e7b66d632f55 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW East - Site Won | 080-0357-Calder - Embankment Fill - NAW East - Layer 23 - CH 1435 - 1625
2c7966e1-4b3a-4156-bba7-e4df56b0c633 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW East - Site Won | 080-0357-Calder - Embankment Fill - NAW East - Layer 23 - CH 1435 - 1625 | ITP-047-CIV-CPD-Type B FIll - Road
4969dd36-8dec-4157-9632-05f2b7b09e4d |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW East - Site Won | 080-0755 - Calder - Embankment Fill - NAW East - Layer 24
e0e6f466-0f3d-4e95-a5b4-a8b66a46d115 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW East - Site Won | 080-0755 - Calder - Embankment Fill - NAW East - Layer 24 | ITP-047-CIV-CPD-Type B FIll - Road
9570dccd-47c7-457c-a5b3-6028fd1cd972 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW East - Site Won | 080-0756 - Calder - Embankment Fill - NAW East - Layer 25
4639d88b-c778-4bdb-9e5d-88c4a37cce46 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW East - Site Won | 080-0756 - Calder - Embankment Fill - NAW East - Layer 25 | ITP-047-CIV-CPD-Type B FIll - Road
68eedf0a-df80-4def-b2be-c418c6a04519 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone
d79d2d27-41c1-4473-a264-cc8c4775bca0 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0660- Calder - Embankment Fill - North West- Layer 18 - Ch 1435 - 1635
2821b653-40bc-4474-ae85-e485a66cd278 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0660- Calder - Embankment Fill - North West- Layer 18 - Ch 1435 - 1635 | ITP-047-CIV-CPD-Type B FIll - Road
747f15d6-900d-46a6-abca-34ade49237b8 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0703- Calder - Embankment Fill - North West- Layer 19 - Ch 1435 - 1635
9564da65-3c38-481a-8a06-194f93a2f9bd |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0703- Calder - Embankment Fill - North West- Layer 19 - Ch 1435 - 1635 | ITP-047-CIV-CPD-Type B FIll - Road
a49e73dc-97ab-4a15-bf1f-1bffe88445e8 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0719- Calder - Embankment Fill - North West- Layer 20 - Ch 1435 - 1635
2d4affce-48b4-4efa-8cfc-11781fe9e4fb |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0719- Calder - Embankment Fill - North West- Layer 20 - Ch 1435 - 1635 | ITP-047-CIV-CPD-Type B FIll - Road
f9f5b2b0-384c-4f80-ab02-c02749152487 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0720- Calder - Embankment Fill - North West- Layer 21 - Ch 1435 - 1635
2ed82cd5-52b8-47aa-96ab-a5c7a6fe265a |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0720- Calder - Embankment Fill - North West- Layer 21 - Ch 1435 - 1635 | ITP-047-CIV-CPD-Type B FIll - Road
441c97ea-2fbb-43c3-b651-7c96063c4c9f |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0721- Calder - Embankment Fill - North West- Layer 22 - Ch 1435 - 1635
63e11583-bc2f-4f64-8e3a-3e4ebaca8848 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0721- Calder - Embankment Fill - North West- Layer 22 - Ch 1435 - 1635 | ITP-047-CIV-CPD-Type B FIll - Road
be186c8c-30cd-4603-a8af-6ae3dcfd57a1 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0732 - Calder - Embankment Fill - North West Layer 23 - CH1435 - CH1635
1121f953-6783-434e-8a4c-97b8c2c3b282 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0732 - Calder - Embankment Fill - North West Layer 23 - CH1435 - CH1635 | ITP-047-CIV-CPD-Type B FIll - Road
3da5c407-aa09-4e5e-bc34-35370f71eb05 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0633-Calder- Embankment Fill - North West - Layer 24
479893a0-d8cb-417c-a4ff-2317f329adfb |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0633-Calder- Embankment Fill - North West - Layer 24 | ITP-047-CIV-CPD-Type B FIll - Road
147d4a27-eed2-4462-9ae9-6a4eb917751a |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0631-Calder - Embankment Fill - NAW West - Layer 25
cea040fc-df5e-44ba-a586-c67956871198 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0631-Calder - Embankment Fill - NAW West - Layer 25 | ITP-047-CIV-CPD-Type B FIll - Road
7046abd0-3869-4fa2-b5f6-89334dfd7838 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0751-Calder - Embankment Fill - NAW West - Layer 26
72b4703e-8a87-4cbf-9303-2206d900d8ea |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0751-Calder - Embankment Fill - NAW West - Layer 26 | ITP-047-CIV-CPD-Type B FIll - Road
da8d2e99-abb3-4b43-8f62-56e2ec9e71e1 |  | pass |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0760 - Calder - Embankment Fill - NAW West - Layer 27
ecdf80e2-520c-46e8-b696-c1a75fedd260 |  | pass | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0760 - Calder - Embankment Fill - NAW West - Layer 27 | ITP-047-CIV-CPD-Type B FIll - Road
4c696337-136e-417b-a19d-ed32f4c1bb27 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0764- Calder- Embankment Fill - NAW West- Layer 28
f048aaf8-4ad6-436b-b460-759094ace2d9 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0764- Calder- Embankment Fill - NAW West- Layer 28 | ITP-047-CIV-CPD-Type B FIll - Road
9e015a63-8246-454c-8030-d9da069ad4fb |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0765- Calder - Embankment Fill - North West - Layer 29
94aed4e0-508a-4069-af2c-e9eb80aa1c4f |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0765- Calder - Embankment Fill - North West - Layer 29 | ITP-047-CIV-CPD-Type B FIll - Road
3047b805-3739-4b0f-bb24-d8c31bbeb4ec |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0770- Calder - Embankment Fill - NAW - Layer 30
df0a5d40-dcca-454c-a5db-c7ba9f97b953 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0770- Calder - Embankment Fill - NAW - Layer 30 | ITP-047-CIV-CPD-Type B FIll - Road
15cb2a4c-3a65-4cc1-aa4b-143097c31139 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0313- Calder - Embankment Fill - NAW - Layer 31
736dfc26-567c-4f72-ac8f-75a500cd89dd |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0313- Calder - Embankment Fill - NAW - Layer 31 | ITP-047-CIV-CPD-Type B FIll - Road
15187a16-2ed0-4490-86be-08cc27a7085f |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0773- Calder- Embankment Fill - NAW - Layer 32
7ab9f09c-489d-4193-99fd-a21565954294 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0773- Calder- Embankment Fill - NAW - Layer 32 | ITP-047-CIV-CPD-Type B FIll - Road
4bc43ef1-5412-4d3e-a591-f193c26f385e |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0697- Calder - Embankment Fill - NAW - Layer 33
c8d7b1b5-6060-4d06-8895-3b2b03c926fe |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0697- Calder - Embankment Fill - NAW - Layer 33 | ITP-047-CIV-CPD-Type B FIll - Road
2f225b93-672b-4c47-b6b1-d3ab37464347 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0699 - Calder - Embankment Fill - NAW - Layer 34
6e0f39d3-7669-4dd1-ba3d-c1d396d6d0c4 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0699 - Calder - Embankment Fill - NAW - Layer 34 | ITP-047-CIV-CPD-Type B FIll - Road
85431baa-abae-48c7-ad64-a04df1b679ab |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0468 - Calder - Embankment Fill - NAW - Layer 35
65b2b48e-bc6f-4b21-ade8-42be6f3b2b30 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0468 - Calder - Embankment Fill - NAW - Layer 35 | ITP-047-CIV-CPD-Type B FIll - Road
10bfbfec-9a0f-425a-80c2-e08c6048df88 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0750 - Calder - Embankment Fill - NAW - Layer 36
d81a7cab-b615-4df4-9e64-0ad0d91c3115 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0750 - Calder - Embankment Fill - NAW - Layer 36 | ITP-047-CIV-CPD-Type B FIll - Road
b9e5dc35-a333-443d-81b4-33880e98478c |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0780 - Calder - Embankment Fill - NAW - Layer 37
289314ed-4aa2-447d-b0b1-44d2cbc2ea1d |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0780 - Calder - Embankment Fill - NAW - Layer 37 | ITP-047-CIV-CPD-Type B FIll - Road
15f0ec0e-3d1b-4aa1-8489-adc0374634d4 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0781 - Calder - Embankment Fill - NAW - Layer 38
99e9c9b9-ceb1-40e3-b593-302be09f8481 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0781 - Calder - Embankment Fill - NAW - Layer 38 | ITP-047-CIV-CPD-Type B FIll - Road
f240f647-1db2-44ad-a4d5-396f694c7a61 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0782 - Calder - Embankment Fill - NAW - Layer 39
1583a0a4-87d4-4b86-9bcb-24a1165a87d2 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0782 - Calder - Embankment Fill - NAW - Layer 39 | ITP-047-CIV-CPD-Type B FIll - Road
2b0e35f3-a61e-4bad-91ab-f6a6bc880670 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0783 - Calder - Embankment Fill - NAW - Layer 40
c30c2bce-36e7-4a2d-8955-14d16f389339 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0783 - Calder - Embankment Fill - NAW - Layer 40 | ITP-047-CIV-CPD-Type B FIll - Road
d210c1de-e826-4e32-9775-12c8cdeeac74 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0783 - Calder - Embankment Fill - NAW - Layer 41
6b97dc6f-27b4-40db-b0a5-37450f03bb0c |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0783 - Calder - Embankment Fill - NAW - Layer 41 | ITP-047-CIV-CPD-Type B FIll - Road
4e7a5a9b-5681-41e2-9e35-4bd9af408190 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0793 - Calder - Embankment Fill - NAW - Layer 42
5ac1fc87-4dd9-44de-98f3-55ebb4c8522e |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0793 - Calder - Embankment Fill - NAW - Layer 42 | ITP-047-CIV-CPD-Type B FIll - Road
338cf0c0-1451-4f91-9fb1-a437967f984f |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0794 - Calder - Embankment Fill - NAW - Layer 43
35428fab-3285-4f44-812f-cd3fb9354a88 |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0794 - Calder - Embankment Fill - NAW - Layer 43 | ITP-047-CIV-CPD-Type B FIll - Road
464dbaa4-9cd1-4dcb-93f2-c2cf5d1459d1 |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0559 - Calder - Embankment Fill - NAW - Layer 44
a6adc53e-0b9c-41bc-a3ff-128fe9e8947b |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0559 - Calder - Embankment Fill - NAW - Layer 44 | ITP-047-CIV-CPD-Type B FIll - Road
2326e7d7-c542-4c0b-8045-5f575ba5e88e |  | work-in-progress |  | folder | TRUE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0776 - Calder - Embankment Fill - NAW - Layer 45
5f465bdd-27b5-487c-bf23-41277774d3dd |  | work-in-progress | ITP-047-CIV-CPD-Type B FIll - Road Rev 1 | checklist | FALSE | FALSE | Civil | MRPA-DPK-080-00-CPT-0010-0 - Fill Embankment | North Embankment NAW West - Mudstone | 080-0776 - Calder - Embankment Fill - NAW - Layer 45 | ITP-047-CIV-CPD-Type B FIll - Road
65d0a4e9-afc1-4c1c-b033-77d759b277bd |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSF-0034-0 - Miscellaneous Structures & L-shape Retaining Walls
7289a760-45c9-432f-b4df-0320b84301dc |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSF-0034-0 - Miscellaneous Structures & L-shape Retaining Walls | L-Shape Wall - Material Inspection
32ed3910-d2c8-4cca-9283-322e30955464 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSF-0034-0 - Miscellaneous Structures & L-shape Retaining Walls | L-Shape Wall - Material Inspection | 080-00475 - L-Shape Wall - L-1
2fa82b7e-486e-4227-9b6f-68f7b33402c8 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSF-0034-0 - Miscellaneous Structures & L-shape Retaining Walls | L-Shape Wall - Material Inspection | 080-00475 - L-Shape Wall - L-1 | CHK-006-STR&CIV-Material Inspection-Precast Panel-L-Shape-Wall-1
2990d233-e5b5-414b-b7ad-5e056d1c0468 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSF-0034-0 - Miscellaneous Structures & L-shape Retaining Walls | L-Shape Wall - Material Inspection | 080-00474 - L-Shape Wall - L-2
9fb86762-bebd-4a0c-83aa-d178d8d75ecc |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSF-0034-0 - Miscellaneous Structures & L-shape Retaining Walls | L-Shape Wall - Material Inspection | 080-00474 - L-Shape Wall - L-2 | CHK-006-STR&CIV-Material Inspection-Precast Panel-L-Shape-Wall- 2
c804454a-8299-4fba-a566-45545d60f7cc |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSF-0034-0 - Miscellaneous Structures & L-shape Retaining Walls | L-Shape Wall - Material Inspection | 080-00473 - L-Shape Wall - L-3
72474341-0806-45cb-a77c-abb372f2410b |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSF-0034-0 - Miscellaneous Structures & L-shape Retaining Walls | L-Shape Wall - Material Inspection | 080-00473 - L-Shape Wall - L-3 | CHK-006-STR&CIV-Material Inspection-Precast Panel- L-Shape Wall - 3
dd7deaaa-5c38-400b-934c-d745c5e79190 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSF-0034-0 - Miscellaneous Structures & L-shape Retaining Walls | L-Shape Wall - Material Inspection | 080-00472 - L-Shape Wall - L-4
88ad64bf-4288-482d-aa8e-a0c2d810d91f |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSF-0034-0 - Miscellaneous Structures & L-shape Retaining Walls | L-Shape Wall - Material Inspection | 080-00472 - L-Shape Wall - L-4 | CHK-006-STR&CIV-Material Inspection-Precast Panel-L-Shape-Wall-4
a7a9f93a-6a25-4bf3-84c0-191478d7397b |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSF-0034-0 - Miscellaneous Structures & L-shape Retaining Walls | L-Shape Wall - Material Inspection | 080-00471 - L-Shape Wall - L-5
769b3eac-776d-48ba-9cca-86f5b98a9088 |  | pass | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSF-0034-0 - Miscellaneous Structures & L-shape Retaining Walls | L-Shape Wall - Material Inspection | 080-00471 - L-Shape Wall - L-5 | CHK-006-STR&CIV-Material Inspection-Precast Panel-L-Shape Wall -5
1c05e654-896e-440d-8f54-4f6087e2a223 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSF-0034-0 - Miscellaneous Structures & L-shape Retaining Walls | L-Shape supply and Install
fa24fe66-e3f2-4a53-8c18-a74286300075 |  | pass |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSF-0034-0 - Miscellaneous Structures & L-shape Retaining Walls | L-Shape supply and Install | 080-0476 - L-Shape Wall Supply and Install
f8986ade-3cc9-4b0b-a9a4-213e96a2603a |  | pass | ITP-112-STR Precast L-shape Wall Rev1 | checklist | FALSE | FALSE | Civil | MRP-DPK-080-00-CSF-0034-0 - Miscellaneous Structures & L-shape Retaining Walls | L-Shape supply and Install | 080-0476 - L-Shape Wall Supply and Install | ITP-112-STR Precast L-shape Wall Rev1
999c154b-df7c-45ae-a7c1-54fb014e3557 |  | no-status-not-started |  | folder | TRUE | FALSE | Civil | MRP-DPK-080-00-CSF-0034-0 - Miscellaneous Structures & L-shape Retaining Walls | L-Shape Capping Units Supply and Install
71acb9de-f24a-4541-97a6-474d50cd7e45 |  | work-in-progress |  | folder | TRUE | FALSE | Rail
4c12aaa6-e92f-496b-ba11-39ce1ad93f5f |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-GSG-0050-0 - Rail Signalling (Enabling Works)
f0e648ac-12b9-4894-8a39-e59e8d893738 |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-GSG-0050-0 - Rail Signalling (Enabling Works) | Stage 1
0e116dc2-0fd2-4f33-bdbf-e3b32d8c1e5e |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-GSG-0050-0 - Rail Signalling (Enabling Works) | Stage 1 | Test Copies and CTC for all works (Cerified Copies)
9459089a-d34b-4a63-87db-3100bfd7c2e7 |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-GSG-0053-0 - COC - Transformer Removal
c1c7c8bf-46c9-4ccd-af72-15857be9b5ed |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-GSG-0053-0 - COC - Transformer Removal | Stage 2
611cdfbd-0527-43e0-adcb-2e02a8a0c361 |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-GSG-0053-0 - COC - Transformer Removal | Stage 2 | Test Copies and CTC for all works (Cerified Copies)
57eace83-f5b3-4d2c-b56b-071677b082c3 |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-GSG-0052-0 - Rail Signalling (Final)
9127c4fc-054d-4e69-bdc1-f8017d5b7de9 |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-GSG-0052-0 - Rail Signalling (Final) | Final Works
1d97db85-09fd-4965-9764-ffdbc8f3cee7 |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-GSG-0052-0 - Rail Signalling (Final) | Final Works | Test Copies and CTC for all works (Cerified Copies)
9965fea9-31e6-4c75-b2de-2edc6c7a3ca9 |  | work-in-progress |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures
47561cb7-d035-4fdb-9b09-6172ea9318eb |  | work-in-progress |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive - North West (A894+83)
a03b355f-2ca2-416e-8bbd-dae2788d07d4 |  | pass |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive - North West (A894+83) | 080-0371 - Overhead Wiring Structure Pile- North West (A894+83)
78a92132-6c0b-4c89-a104-2950b1418db5 |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive - North West (A894+83) | 080-0371 - Overhead Wiring Structure Pile- North West (A894+83) | ITP-009-STR-Bored Piling Rev0
6b7e3c64-e5e0-490b-820b-b1c08abeabc6 |  | work-in-progress |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive - North West (A894+83) | 080-536-OHLE Installation - North West (A894+83)
0a8b7d2b-f228-42f8-91ea-81ee68b55e0e |  | work-in-progress | ITP-050-CPD-RAIL-Calder Park-OHLE Installation - Rev 1 | checklist | FALSE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive - North West (A894+83) | 080-536-OHLE Installation - North West (A894+83) | ITP-050-CPD-RAIL-Calder Park-OHLE Installation - A894+83
906c0ee1-8de9-4bf9-bc8e-d6b4b3fe48b5 |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive (A893+99 and A894+02)
04fa8ab0-c6ca-4df0-90a7-6028a2c9df53 |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive (A893+99 and A894+02) | Overhead Wiring Structure Under Bridge (A893+99 and A894+02)
5b3cfeb6-a9c0-428a-9eb0-aa202828a412 |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive (From A880+57 to A900+80)
e7b3db84-912b-4117-ab45-82401bca3ccd |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive (From A880+57 to A900+80) | Regrading of Wires (From A880+57 to A900+80)
48ccea82-54ec-4b87-90bd-0ab3d2cc4c1b |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive - Modification of Existing Structures (10 No. of)
0c867eea-541f-4ae1-9d1c-051d1f3c61f3 |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive - Modification of Existing Structures (10 No. of) | Modification of Existing Structure (10 no. of)
59d70510-861c-40b2-a005-6ddfb9ad6e7b |  | pass |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive - South West (A894+89)
1299e491-91a5-4109-b117-e826cf36aa80 |  | pass |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive - South West (A894+89) | 080-0372 - Overhead Wiring Structure Pile - South West (A894+89)
eea52b73-99db-407f-8845-5e80de3e7c3a |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive - South West (A894+89) | 080-0372 - Overhead Wiring Structure Pile - South West (A894+89) | ITP-009-STR-Bored Piling Rev0
09f2b62d-8848-4b8c-b787-8c14b2bea87b |  | pass |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive - South East (A893+16)
acabf59d-19d9-4a44-8db5-684b5e5d06d7 |  | pass |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive - South East (A893+16) | 080-0558 - Overhead Wiring Structure Pile - South East (A893+16)
afe7ea11-728f-4d18-acc5-5e9e39c0c61f |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Rail | MRP-DPK-080-00-CBR-0060-0 - Rail Overhead Wiring and Structures | Calder Park Drive - South East (A893+16) | 080-0558 - Overhead Wiring Structure Pile - South East (A893+16) | ITP-009-STR-Bored Piling
46bd126a-c24e-43b6-abf9-ef061c314f50 |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil
edc41121-1d90-4d17-9100-db89e2cc9b17 |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil | Calder Park Drive
b8e0ad6e-891c-4274-9c8e-425564b0341a |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil | Calder Park Drive | Calder Park Dr. Pavement Removal
535b5807-b632-42da-8f4e-28076c7418be |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil | Calder Park Drive | Calder Park Dr. Pavement Removal | ITP-Rail-Track Removal & Construction Rev 1 (CPK)
b8447058-c992-4494-b534-d80bd3a7357d |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil | Calder Park Drive | IRJ Removals - 25.936km - 25.959km (Calder Park)
129a0e24-7fe5-4663-a122-48ddeb29735f |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil | Calder Park Drive | IRJ Removals - 25.936km - 25.959km (Calder Park) | ITP-Rail-Track Removal & Construction Rev 1 (CPK)
8d892302-647b-4e19-bb76-205a59a01758 |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil | Calder Park Drive | IRJ Removals - 27.003km - 27.198km (Calder, Holden)
a10f437e-db66-476a-bd45-158c2f6d03c3 |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil | Calder Park Drive | IRJ Removals - 27.003km - 27.198km (Calder, Holden) | ITP-Rail-Track Removal & Construction Rev 1 (CPK)
0f6e8bcb-8ea8-4422-84df-be53b77e30c0 |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil | Holden Road
a804c492-465d-4e58-b4c7-526f873d2f67 |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil | Holden Road | IRJ Removals - 29.448km - 29.617km (Holden Road)
f521e2ff-8aa2-42de-b660-4a154d5e1725 |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil | Holden Road | IRJ Removals - 29.448km - 29.617km (Holden Road) | ITP-Rail-Track Removal & Construction Rev 1 (CPK)
2af95d68-1699-4d16-bc32-76a6de9b7b6b |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil | Calder Park Drive
1542634a-a824-41e8-b422-570fdbe8fbbb |  | no-status-not-started |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CPW-0063-0 - Rail Track & Civil | Calder Park Drive | Contingency
1369a287-9718-420c-9acf-76154a656f9e |  | pass |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CPW-0066-0 - CSR Enabling Works
a1d9216c-83aa-4508-a736-04572bbc356d |  | pass |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CPW-0066-0 - CSR Enabling Works | Calder Park Drive - North of Rail
b297af72-da53-443e-8704-e59709635119 |  | pass |  | folder | TRUE | FALSE | Rail | MRP-DPK-080-00-CPW-0066-0 - CSR Enabling Works | Calder Park Drive - North of Rail | 080-0283 - Calder - Relocation of CSR Service
7bafc650-965a-4ec1-b600-fcb173e2df4e |  | pass | ITP-055-CIV-CPD-Conduit & Pits-Rail (Supply & Install) - Rev 0 | checklist | FALSE | FALSE | Rail | MRP-DPK-080-00-CPW-0066-0 - CSR Enabling Works | Calder Park Drive - North of Rail | 080-0283 - Calder - Relocation of CSR Service | ITP-055-CIV-CPD-Conduit & Pits-Rail (Supply & Install) Rev 0
07402d04-3d27-472d-be13-1581635a1a4c |  | work-in-progress |  | folder | TRUE | FALSE | Structures
d166e3ac-8999-4477-83ec-e138157398fb |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers
9f65c118-447a-4e63-9382-e918875e07c1 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment
a5945e71-900d-47c1-9594-1682430ae53d |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0001 - Calder - Piling - SA-01 - Pile Installation
41221560-d96b-4032-bb69-61df27865b4e |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0001 - Calder - Piling - SA-01 - Pile Installation | ITP-009-STR-Bored Piling Rev0
b92d56ed-0e4c-4574-aec9-2bfe95e2ca63 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0001 - Calder - Piling - SA-02 - Pile Installation
d782185e-b3b8-44b2-99da-e2b8b8a821ef |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0001 - Calder - Piling - SA-02 - Pile Installation | ITP-009-STR-Bored Piling Rev0
876414da-568e-470e-a389-e9df2eeb1112 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0007 - Calder - Piling - SA-03 - Pile Installation
d9ea1b10-479d-4e47-8dd7-c2e887cd0cce |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0007 - Calder - Piling - SA-03 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
cceb813b-bcc7-4893-945f-fee4603b1bac |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0008 - Calder - Piling - SA-04 - Pile Installation
a0fef585-8910-443e-847f-ace44ae571f0 |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0008 - Calder - Piling - SA-04 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
72705c6c-1ddc-4cc6-997f-2358b19eeb1d |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0009 - Calder - Pile Extension - SA-01
1244b936-b46b-4015-b886-9de9e1f1fdbd |  | pass | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0009 - Calder - Pile Extension - SA-01 | ITP-017-STR-Structural concrete Rev 0
532a3d57-ef05-4364-9a3d-5ceb7de36f89 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0010 - Calder - Pile Extension - SA-02
590a3d3b-1b66-41ee-8ba1-a3a7ccb5ec34 |  | pass | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0010 - Calder - Pile Extension - SA-02 | ITP-017-STR-Structural concrete Rev 0
39ba2c61-f08a-4055-a764-16916db79928 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0011 - Calder - Pile Extension - SA-03
02c6a526-e679-44c3-954a-56e9b7f8694e |  | pass | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0011 - Calder - Pile Extension - SA-03 | ITP-017-STR-Structural concrete Rev 0
03ea3275-0ebb-4428-8405-75ea13bac76b |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0012 - Calder - Pile Extension - SA-04
54eabbc8-04e7-4f64-aceb-26d7539949f7 |  | pass | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0012 - Calder - Pile Extension - SA-04 | ITP-017-STR-Structural concrete Rev 0
b265579c-5fd4-4f39-98dc-487bf1b6f6dd |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0013 - Calder - Headstock - SA-HS - FRP
2e9caf52-17b1-4358-b6fd-a801232733a2 |  | pass | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0013 - Calder - Headstock - SA-HS - FRP | ITP-017-STR-Structural concrete Rev 0
ce9f3ef0-c9af-497f-befc-70e5ade7d1f5 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0014 - Fenderwall - SA-FW - FRP
8e86572a-7b9a-45df-a645-ff27cedc563c |  | pass | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0014 - Fenderwall - SA-FW - FRP | ITP-017-STR-Structural concrete Rev 0
22a56634-f685-49b1-8268-236497513ab4 |  | pass | ITP-132-STR-CPD-Structural Concrete Crack Repair Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0014 - Fenderwall - SA-FW - FRP | ITP-132-STR-CPD-Structural Concrete Crack Repair South Fender Wall
8cc79fe9-1e1e-44b1-9a62-5decc1a9cba0 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0015 - Bearing Pedestal - SA-01 to SA-04 - FRP
87a51349-7848-4127-a227-32d513050f52 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0016 - Bearing Pedestal - SA-05 to SA-09 - FRP
8efbf24b-bfb2-42a7-8e0c-be1f0ebca508 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0017 - Lateral Restraint Block - SA-01 - FRP
3f2ce837-abc5-44d3-99f4-3c9892a2e31a |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0017 - Lateral Restraint Block - SA-01 - FRP | ITP-STR Structural Concrete Rev 3
e2c81dac-16bd-41fa-b14e-77dcfe41274e |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0018 - Approach Slab - SA-01 - FRP
afb90756-57fd-42bf-8092-573e2db3e71a |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0018 - Approach Slab - SA-01 - FRP | ITP-STR Structural Concrete Rev 3
fe743122-9090-44c8-9158-ff86385910bf |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0019 - SUP Approach Slab - SA-02 - FRP
788ea73a-30d4-4845-b266-7ed49a663c78 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0019 - SUP Approach Slab - SA-02 - FRP | ITP-STR Structural Concrete Rev 3
7cac68f6-d7f8-434e-86fd-557db192a19c |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0020 - Concrete Coatings - SA-01
57920839-a295-4fd4-a542-2071b0f0a0b0 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0020 - Concrete Coatings - SA-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1
369d77d5-c2a9-4d49-86ad-5206aa5f978a |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0698 - Calder - Wing Wall - SA-01
76087be5-ed43-400f-8bfd-e470ed484385 |  | pass | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Abutment | 080-0698 - Calder - Wing Wall - SA-01 | ITP-017-STR-Structural concrete
85fdc31b-ba4c-416a-876d-513dd52502d5 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Contingency
944d3239-bcb7-41cd-83ab-67499b8df099 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier
f9cd7024-dcb3-483d-9faf-a31c0b958eec |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-01 - Pile Installation
12226487-bdd7-4071-8619-a9c418b69bd6 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-01 - Pile Installation | ITP-STR Bored Piling Rev 5
741d7a76-7072-4ae1-8428-75f80c8428fb |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-02 - Pile Installation
30aaa4f3-5029-4c0c-b4d9-8c15eb86ff7f |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-02 - Pile Installation | ITP-STR Bored Piling Rev 5
18009671-b494-4248-8a0b-d25208697f7a |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-03 - Pile Installation
ce27e28f-b0d0-40a6-bd4c-b281aea61e0e |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-03 - Pile Installation | ITP-STR Bored Piling Rev 5
ea4195f9-4d82-4530-8aab-93b1329455f3 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-04 - Pile Installation
4ef29c41-2125-4241-a08a-8f8927f22868 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-04 - Pile Installation | ITP-STR Bored Piling Rev 5
9088c18d-8ae1-49e9-a911-9379d6061bfc |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-05 - Pile Installation
746bac16-fd33-401b-a943-8cec15fa30a3 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-05 - Pile Installation | ITP-STR Bored Piling Rev 5
81827da0-88db-4740-bc5b-37d25ac2b964 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-06 - Pile Installation
01ba0f75-caef-4fb5-baee-fbc74e88ec72 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Piling - P1-06 - Pile Installation | ITP-STR Bored Piling Rev 5
57be326d-4ae3-4ca2-8873-e5f47fda8547 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Pile Cap - P1-01 - FRP
c184b3f0-6fc6-43d5-9028-3d0846a95a02 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Pile Cap - P1-01 - FRP | ITP-STR Structural Concrete Rev 3
0e3910e0-d2ef-4c1e-8c81-94bceb44e9e6 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Blade Wall/Headstock - P1-01 - FRP
27a9e3dc-7f23-4c8f-88e9-93fd419830c6 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Blade Wall/Headstock - P1-01 - FRP | ITP-STR Structural Concrete Rev 3
286d6ed6-2d11-44a4-9b75-9dca6d0cd24c |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Bearing Pedestal - P1-01 to P1-05- FRP
a2a7da6e-0340-49de-9327-a531eabebd1e |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Bearing Pedestal - P1-01 to P1-05- FRP | ITP-STR Grout Pedestals & Bearings Rev 0
51e4a193-b21f-4ac0-9b7a-42270cc5df2a |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Bearing Pedestal - P1-01 to P1-05- FRP | ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0
aa4c2753-ab6a-42bf-a4b2-ad906d921680 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Bearing Pedestal - P1-06 to P1-11 - FRP
58283908-5f0c-48e3-a562-a92f032f4217 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Bearing Pedestal - P1-06 to P1-11 - FRP | ITP-STR Grout Pedestals & Bearings Rev 0
1ea363b3-4bc9-4a21-a292-6c43a07889cd |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Bearing Pedestal - P1-06 to P1-11 - FRP | ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0
ccc9ed4a-13fd-4fd9-ba9e-79fbbfe58a47 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Bearing Pedestal - P1-12 to P1-18- FRP
aef1ac30-8e39-4654-a4c8-16abc218ec21 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Bearing Pedestal - P1-12 to P1-18- FRP | ITP-STR Grout Pedestals & Bearings Rev 0
8a20f9c6-af49-42e4-be53-2ad610331983 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Bearing Pedestal - P1-12 to P1-18- FRP | ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0
c5fdb829-7061-4474-a0de-17c36d9a1c48 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Lateral Restraint Block - P1-01- FRP
44a2d30a-6295-473e-a085-0c8ce682f605 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Lateral Restraint Block - P1-01- FRP | ITP-STR Structural Concrete Rev 3
45b7dc58-e43e-476e-b72e-ed19f8c032ec |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Concrete Coatings - P1-01
f07cb008-ad01-4617-aa71-5ba30e67a58e |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | South Pier | Concrete Coatings - P1-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1
9286dffb-5b0a-4145-85b6-6cf281478135 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier
9b4a9087-caaf-4375-a66d-c9a28b646689 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0034 - Calder - Piling - P2-01 - Pile Installation
11b34ea7-c3bc-4607-b6fa-7f8defbb1270 |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0034 - Calder - Piling - P2-01 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
6aa083dd-100a-4095-b473-5f9268e163ba |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0035 - Calder - Piling - P2-02 - Pile Installation
806be413-cd96-457d-b22e-f4c2899ff5a6 |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0035 - Calder - Piling - P2-02 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
9802972c-9288-41b8-8e71-efb1f1c09ebe |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0036 - Calder - Piling - P2-03 - Pile Installation
d104f9b8-69eb-4a58-8ebc-02bdfe946d92 |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0036 - Calder - Piling - P2-03 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
0150b574-3058-41ec-ac22-31be15be9d82 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0037 - Calder - Piling - P2-04 - Pile Installation
a6dea61a-9134-4556-84b7-23f9fe0e9d17 |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0037 - Calder - Piling - P2-04 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
f3da84ed-47e3-423e-a8e3-890ff5e2cfbd |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0038 - Calder - Piling - P2-05 - Pile Installation
10b83fc7-0fa6-43bf-a197-a70158e03a88 |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0038 - Calder - Piling - P2-05 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
23f6c11a-d3e3-4bfb-bab3-e73fc4956e30 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0039 - Calder - Piling - P2-06 - Pile Installation
8ee0788f-0f0b-4af5-a010-2005f89ab05d |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0039 - Calder - Piling - P2-06 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
fa5c67a8-4abc-4e99-8526-2c73289babeb |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0040 - Calder - North - Pile Cap - P2-01
2b085a28-43d6-44fc-b937-b3d100045f9b |  | pass | ITP-013-STR-Pile Cap Construction Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0040 - Calder - North - Pile Cap - P2-01 | ITP-013-STR-Pile Cap Construction - P2-01
ea63318f-cc2e-4ec3-a71f-94133062816b |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0041 - Calder - North - Blade Wall - P2-01 - FRP
0809df4a-88a7-4151-b973-b6c050f5135b |  | pass | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0041 - Calder - North - Blade Wall - P2-01 - FRP | ITP-017-STR-Structural concrete Rev 0
02c721ae-ee19-456f-b4de-7ad93eb3b5ca |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Bearing Pedestal - spare
202ea213-16d2-46ff-9bbe-30de6691649d |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Bearing Pedestal - spare | ITP-STR Grout Pedestals & Bearings Rev 0
2631cee8-7dc1-4146-993b-ccd95593467f |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Bearing Pedestal - spare | ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0
23219211-b326-4123-a924-e0d3f91de51b |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0042 - Bearing Pedestal - P2-01 to P2-09- FRP
5615799d-1ec2-4067-9c98-fac1c47dd008 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0042 - Bearing Pedestal - P2-01 to P2-09- FRP | ITP-STR Grout Pedestals & Bearings Rev 0
7ef0c37f-e608-4e7d-a612-1cf3bf51e100 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0042 - Bearing Pedestal - P2-01 to P2-09- FRP | ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0
2e5175aa-564b-46ae-a766-2c1777adb89c |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0044 - Bearing Pedestal - P2-10 to P2-16- FRP
0ebe181f-8dba-44e7-ba43-cfea60e09e1a |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0044 - Bearing Pedestal - P2-10 to P2-16- FRP | ITP-STR Grout Pedestals & Bearings Rev 0
1003bf7e-4ff8-4c45-8e6d-0e1040526fad |  | work-in-progress | ITP-121-STR-CPD-Grout Pedestals & Bearings Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0044 - Bearing Pedestal - P2-10 to P2-16- FRP | ITP-STR Grout Pedestals & Bearings Rev 0 | ITP-121-STR-CPD-Grout Pedestals & Bearings
88624296-d122-4cbd-b669-462912041ba7 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0044 - Bearing Pedestal - P2-10 to P2-16- FRP | ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0
da61d2cc-2bda-409a-9c92-8c698f4c3a53 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Lateral Restraint Block - P2-01 - FRP
6c53bd17-25e8-408f-affe-7fe1d812d667 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Lateral Restraint Block - P2-01 - FRP | ITP-STR Structural Concrete Rev 3
a5c555af-5bdc-4528-b500-9dca065bccc1 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Concrete Coatings - P2-01
2ed9666f-1e87-48fb-b009-5a45d2a4744c |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | Concrete Coatings - P2-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1
b1ed4e81-1e28-48fd-a999-c959377dcc45 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0465 - Calder - North - Crosshead - P2-02 - FRP
241894f9-78c7-479e-a664-45d2d221c376 |  | pass | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Pier | 080-0465 - Calder - North - Crosshead - P2-02 - FRP | ITP-017-STR-Structural concrete
e578210b-4d1e-41bc-b941-ca2c68802579 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment
f8a594f8-c4ab-4013-836e-710b8c0d7fb8 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0047 - Piling - NA-01 - Pile Installation
9b5a28b5-87d3-4530-bead-dbc391b60161 |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0047 - Piling - NA-01 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
770921e6-c7e4-432e-a9b0-58f649b72bb9 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0048 - Piling - NA-02 - Pile Installation
57398016-8b97-49e1-8b56-1cff2220b1b6 |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0048 - Piling - NA-02 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
1406b9db-5e92-4f6f-8433-ca420135857c |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0049 - Piling - NA-03 - Pile Installation
9125fb34-cda4-446d-939f-6b4a4dccd6d5 |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0049 - Piling - NA-03 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
8eea1b57-ff0f-4462-a234-2888987facd1 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0050 - Piling - NA-04 - Pile Installation
59d53176-2b47-4227-97ea-b941c34501ec |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0050 - Piling - NA-04 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
59e4455a-77db-4e43-8b62-14580c27b0c3 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0051 - Piling - NA-05 - Pile Installation
79b3315e-7cff-4f08-acb0-80cb6a9ae860 |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0051 - Piling - NA-05 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
4d049dc0-c903-4ba0-857c-b272f5c7f41b |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0052 - Piling - NA-06 - Pile Installation
749ab0ef-d860-49c8-b072-5de572f71b02 |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0052 - Piling - NA-06 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
1696c48c-5bfd-4dd4-b439-4d7d4a84958f |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0053 - Piling - NA-07 - Pile Installation
5546190f-c3e4-4cb6-96d6-65daba9853cf |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0053 - Piling - NA-07 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
819de41c-0d80-4feb-94da-b857907f7b46 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0054 - Piling - NA-08 - Pile Installation
ec995a14-58da-48a0-bf1c-5b18fb2fd977 |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0054 - Piling - NA-08 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
f03d5db0-429d-42de-8c83-b52b5fb47a91 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0055 - Piling - NA-09 - Pile Installation
7d55bb7d-42c3-4fe1-820a-dbd2bc5cb8bc |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0055 - Piling - NA-09 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
74cfed58-1b2f-4b6d-9ce4-3a488a86b09e |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0056 - Piling - NA-10 - Pile Installation
eeac885e-5891-4f25-aedb-82cd82ab94b1 |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0056 - Piling - NA-10 - Pile Installation | ITP-009-STR-Bored Piling Rev 0
f2ebcecb-65b9-4e4b-b398-21b272f6d3d6 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0057 - Pile Cap - NA-01 - Pile Cap
3f5329ac-69da-4725-a666-97647699502b |  | pass | ITP-013-STR-Pile Cap Construction Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0057 - Pile Cap - NA-01 - Pile Cap | ITP-013-STR-Pile Cap Construction
c052cdc3-aad9-47cc-b3ed-3fd532ec5ee1 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0058 - Abutment Wall - NA-01
fe9d93f4-67f9-42a4-ba77-a80632bf16a2 |  | pass | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0058 - Abutment Wall - NA-01 | ITP-017-STR-Structural concrete Rev 0
ad02ef9a-0d1d-4d26-a24c-b0b4b11b5ea7 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0059 - Abutment Wall - Fender Wall - NA-02
0f56c4c2-6f38-410f-860b-93933ea5bd0e |  | pass | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0059 - Abutment Wall - Fender Wall - NA-02 | ITP-017-STR-Structural concrete Rev 0
840217be-58cf-473f-817e-ff914969fe17 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0060 - Abutment Wall - East Wingwall - NA-03
d91f1719-c988-40a2-bac1-fa52983c49f6 |  | work-in-progress | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0060 - Abutment Wall - East Wingwall - NA-03 | ITP-017-STR-Structural concrete
3a008e52-3738-4b54-aeca-d5e0d63f77dd |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0061 - Bearing Pedestal - NA-01 to NA-03 - FRP
d7f78305-99a3-47c1-b947-1c56f5cf77ca |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0061 - Bearing Pedestal - NA-01 to NA-03 - FRP | ITP-STR Grout Pedestals & Bearings Rev 0
7c98945d-3f67-4617-a539-182f4ac333bb |  | work-in-progress | ITP-121-STR-CPD-Grout Pedestals & Bearings Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0061 - Bearing Pedestal - NA-01 to NA-03 - FRP | ITP-STR Grout Pedestals & Bearings Rev 0 | ITP-121-STR-CPD-Grout Pedestals & Bearings
a257ac2f-8a03-4fc2-a046-f0cfafc0b7f8 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0061 - Bearing Pedestal - NA-01 to NA-03 - FRP | ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0
bfdc2025-f560-41c6-b350-66fa254e6c77 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0062 - Bearing Pedestal - NA-04 to NA-07 - FRP
3e210aff-b6aa-4712-a1e9-e52d0001ca96 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0062 - Bearing Pedestal - NA-04 to NA-07 - FRP | ITP-STR Grout Pedestals & Bearings Rev 0
5882f37a-c599-430e-8d72-0272a416023c |  | work-in-progress | ITP-121-STR-CPD-Grout Pedestals & Bearings Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0062 - Bearing Pedestal - NA-04 to NA-07 - FRP | ITP-STR Grout Pedestals & Bearings Rev 0 | ITP-121-STR-CPD-Grout Pedestals & Bearings
32d56d35-8c02-4ca2-9286-e43bf8fdb900 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0062 - Bearing Pedestal - NA-04 to NA-07 - FRP | ITP-STR Elastomeric Bearings (Supply & Installation) Rev 0
e298e4b5-e87a-4f6b-b559-5a706a0e32e5 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0063 - Approach Slab - Roadway - NA-01
04ebb811-61fd-4848-a600-5aa19555e99c |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0063 - Approach Slab - Roadway - NA-01 | ITP-STR Structural Concrete Rev 3
7ac3f795-bb25-4378-b439-dcfa1f5bfb5a |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0064 - Approach Slab - SUP - NA-01
bd7eb259-a718-47ad-bd9e-19b3db39b9df |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0064 - Approach Slab - SUP - NA-01 | ITP-STR Structural Concrete Rev 3
87a77219-023a-40a9-8137-4072f30fa0c7 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0065 - Concrete Coatings - NA-01
95ac0d05-5f82-42cb-a3b2-157a7985ff52 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0065 - Concrete Coatings - NA-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1
e183ae50-6792-4365-a542-5a82cfb6fd30 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0724 - Calder - Abutment Wall - NA-01 - Crack Repair
67eaab20-b7d6-49c2-84b0-ac7fee31eccc |  | pass | ITP-132-STR-CPD-Structural Concrete Crack Repair Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | North Abutment | 080-0724 - Calder - Abutment Wall - NA-01 - Crack Repair | ITP-132-STR-CPD-Structural Concrete Crack Repair
a7ae3a59-61b2-4009-a5c3-9b32fc853746 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1)
9267cbd6-9b45-4e81-beeb-c1e1cdc4563b |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Bridge Girders - S1-G01 to S1-G07- Precast
4f8c91a6-31c7-48c0-b4a3-8f14b2d23d04 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Bridge Girders - S1-G01 to S1-G07- Precast | ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1
e70335dc-df99-4aa8-8359-49a901336df6 |  | work-in-progress | ITP-124-STR-CPD-Precast Super T Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Bridge Girders - S1-G01 to S1-G07- Precast | ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1 | 080-0477 - ITP-124-STR-CPD-Precast Super T Installation
0f8ffcb3-74de-4620-a720-cd1c90dfbf6b |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Bridge Girders - S1-G08 to S1-G09 - Precast
649f8ed3-e681-4890-8ba2-e782a02e22f4 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Bridge Girders - S1-G08 to S1-G09 - Precast | ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1
705ce0a8-6306-4d5a-a0da-6c30c1b4cec6 |  | work-in-progress | ITP-124-STR-CPD-Precast Super T Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Bridge Girders - S1-G08 to S1-G09 - Precast | ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1 | 080-0479 - ITP-124-STR-CPD-Precast Super T Installation
890f0dcc-2e9a-4442-a43b-7dc79242876b |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | In-Situ Diaphram - S1-G07 - FRP
b3d3a132-08a0-498b-8965-0a425f57ab6f |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | In-Situ Diaphram - S1-G07 - FRP | ITP-STR Structural Concrete Rev 3
d69d644e-cf12-4220-976b-4445979f1091 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Deck Pour - S1-01 - FRP
dc85eb1e-2ad4-4175-a6e7-a342883bd327 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Deck Pour - S1-01 - FRP | ITP-STR Structural Concrete Rev 3
8b0c1cb6-0f08-452e-b512-3f78355b402c |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Expansion Joint - S1-01
4f16f1a1-b5f2-4593-b848-c5dfbdff2771 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Expansion Joint - S1-01 | ITP-STR Expansion Joints (Supply & Installation)
b323149e-9940-41f9-b2fd-6270ed7ed2dd |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Expansion Joint - S1-01 | ITP-STR Structural Concrete Rev 3
35d576a0-6ed3-4752-aebb-96d3232386df |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Medium Performance Barrier - BE-01 to BE-08 - Precast
ccab7a87-b504-4436-99fb-ed7e767c208c |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Medium Performance Barrier - BE-01 to BE-08 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
f8d599b6-fe45-4886-b1b2-69d7b77a09ef |  | work-in-progress | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Medium Performance Barrier - BE-01 to BE-08 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
f49fb5c2-a5b6-46ad-893f-32b4286ea7b1 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Medium Performance Barrier - BW-01 to BW-08 - Precast
ef2bddcc-3cfc-46f2-80a4-0bdde9f6369f |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Medium Performance Barrier - BW-01 to BW-08 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
d1b13c6f-6f78-44a0-973c-ff005e80c56a |  | work-in-progress | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Medium Performance Barrier - BW-01 to BW-08 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
677a3820-02b2-41d3-a13c-34ea4c14b65b |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Kerb - PK-01 to PK-07 - Precast
6c1f106f-d72b-433b-ab13-ae6a73f53d12 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Kerb - PK-01 to PK-07 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
a75787eb-6225-42a8-b0f7-ea511ac5f4b1 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Barrier Stitch Pour - S1-E-01 - FRP
d54fddb3-0f0b-43b6-a6ac-48055825529c |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Barrier Stitch Pour - S1-E-01 - FRP | ITP-STR Structural Concrete Rev 3
794d3818-90f2-44a2-b0b0-496db198bc63 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Barrier Stitch Pour - S2-W-01-FRP
b19c4fd6-0880-4df3-955c-158aaa2824d7 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Barrier Stitch Pour - S2-W-01-FRP | ITP-STR Structural Concrete Rev 3
5ec8c522-dbd4-4bea-8ad4-7a1bcc6ce12f |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Concrete Coatings - East Barriers - BE-01
0117ea1e-dad4-4ef2-b30a-c7e69cf3488b |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Concrete Coatings - East Barriers - BE-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1
d8fbdf18-37b1-40e7-a26c-6f8ed6750516 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Concrete Coatings - West Barriers - BW-01
ef4c36cb-299b-426f-824e-c5852b5736ca |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 1) | Concrete Coatings - West Barriers - BW-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1
c51a96dc-d5d2-4778-a6e8-32b490a2703c |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2)
e07cd74a-e62e-42fc-b6f2-2a29494e337d |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Bridge Girders - S2-G01 to S2-G07 - Precast
b94a131e-449f-4997-a539-472228af34ff |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Bridge Girders - S2-G01 to S2-G07 - Precast | ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1
5df44120-2d4b-4b4b-8f52-fe39fd33934c |  | work-in-progress | ITP-124-STR-CPD-Precast Super T Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Bridge Girders - S2-G01 to S2-G07 - Precast | ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1 | 080-0487 - ITP-124-STR-CPD-Precast Super T Installation
473514d2-859d-4539-b2b0-41894780a8fe |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Bridge Girders - S2-G08 to S2-G09 - Precast
2b5efa66-98a5-48e0-8fbd-486db16517fc |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Bridge Girders - S2-G08 to S2-G09 - Precast | ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1
815a0df7-1131-4252-ac02-829a3003d09f |  | work-in-progress | ITP-124-STR-CPD-Precast Super T Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Bridge Girders - S2-G08 to S2-G09 - Precast | ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1 | 080-0488 - ITP-124-STR-CPD-Precast Super T Installation
84b9c4f7-9f8b-4a62-b13a-0c3cb3960661 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Deck Pour - S2-01 - FRP
40b4b80d-6299-4837-95a4-02344263ee36 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Deck Pour - S2-01 - FRP | ITP-STR Structural Concrete Rev 3
2dab2e71-a786-4e2a-b6b6-568c51754231 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Deck Link Pour - S1-S2-01 - FRP
3d0fd72b-42e7-486e-a55a-bd833f3fc8a4 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Deck Link Pour - S1-S2-01 - FRP | ITP-STR Structural Concrete Rev 3
18f05108-75c5-45f2-b75d-739742e98bcc |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Deck Link Pour - S2-S3-01 - FRP
8ca6349e-c41c-4393-932e-b7e4e56efb9f |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Deck Link Pour - S2-S3-01 - FRP | ITP-STR Structural Concrete Rev 3
d6a8c114-2cce-4308-a932-6f4072d748a7 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Medium Performance Barriers - BE-09 to BE-15- Precast
34408b3b-8daf-4611-bca5-d6a9776cdb82 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Medium Performance Barriers - BE-09 to BE-15- Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
ffb0389b-e01f-45dd-b9b3-c568ca701276 |  | work-in-progress | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Medium Performance Barriers - BE-09 to BE-15- Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
c7a98d67-df4f-4f00-aeab-88f08370470e |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Medium Performance Barriers - BW-09 to BW15 - Precast
b0d431ff-d287-4e08-983d-929dead40fcc |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Medium Performance Barriers - BW-09 to BW15 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
3cb0137b-1c33-4e0f-9073-8748eb4c9c6e |  | work-in-progress | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Medium Performance Barriers - BW-09 to BW15 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
1f40c76a-ac0a-4c02-9ca7-35c331fc0366 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Kerb - PK-08 to PK-13 - Precast
481460dc-1b55-482d-9106-8de20efec186 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Kerb - PK-08 to PK-13 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
9c6122b2-5ae5-46ca-a20d-86b2871def09 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Stitch Pour - S2-E-01- FRP
ac8593f9-b689-47a6-bb5d-66d3eb6fc8a7 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Stitch Pour - S2-E-01- FRP | ITP-STR Structural Concrete Rev 3
0bc33010-dce3-400f-84d3-f49c463ca525 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Stitch Pour - S2-W-01 - FRP
f81f0fc0-287e-4b1e-a09c-e46e594bb2cd |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Stitch Pour - S2-W-01 - FRP | ITP-STR Structural Concrete Rev 3
b1144853-60d4-44ad-a3be-cce5b0869580 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Concrete Coatings - East Barriers - BE-01
14467372-ac38-4f3c-a690-1f1ab8b72773 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Concrete Coatings - East Barriers - BE-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1
49a3132f-c83c-4f87-b425-2d9fbe1fb029 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Concrete Coatings - West Barriers - BW-01
bd986fb9-fa5b-4031-96be-7ce131a57e77 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 2) | Concrete Coatings - West Barriers - BW-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1
59ea903e-5f0a-42e0-98d7-4be64e6af104 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3)
35e4c3c4-1501-4eb1-a54c-df4717610795 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Medium Performance Barriers - BE-16 to BE-20 - Precast
05042ab7-14b8-4317-97b0-f7a7cf553fad |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Medium Performance Barriers - BE-16 to BE-20 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
22981c0a-9faa-4b82-81cc-40f88da3d77d |  | work-in-progress | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Medium Performance Barriers - BE-16 to BE-20 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
83f98b62-c3a3-4d97-88fb-82fe89e23ee1 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Medium Performance Barriers - BW-16 to BW-20 - Precast
d1e3cfc4-3ff3-4b60-afce-040118430070 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Medium Performance Barriers - BW-16 to BW-20 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
198a1a62-f155-462c-bd2d-e4c4607c82de |  | work-in-progress | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Medium Performance Barriers - BW-16 to BW-20 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
c704f0eb-f858-4118-9f6b-78648994699c |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Kerb - PK-15 to PK-19 - Precast
0b1c00df-b2f8-4487-a4cc-c39ce07a39b6 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Kerb - PK-15 to PK-19 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
a4c37aa9-4f39-42f6-a66e-f3f280f114f4 |  | work-in-progress | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Kerb - PK-15 to PK-19 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
1f276b4b-3975-43ed-8208-b2f01f017878 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Stitch Pour - S3-E-01- FRP
ff9b7310-90a2-4da6-9b23-43baeac42513 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Stitch Pour - S3-E-01- FRP | ITP-STR Structural Concrete Rev 3
6ab9e279-e2ac-4997-9cc9-b87598985693 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Stitch Pour - S3-W-01 - FRP
81d8ce29-0d81-4622-b935-4746fa12a279 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Stitch Pour - S3-W-01 - FRP | ITP-STR Structural Concrete Rev 3
ae0638bc-ea85-42e8-938b-4bb76ee17ef7 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Concrete Coatings - East Barriers - BE-01
5a76d7ab-1ddd-404b-94b1-a6231aa267b6 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Concrete Coatings - East Barriers - BE-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1
82aed4e4-41c1-4c22-935e-92e1062de035 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Concrete Coatings - West Barriers - BW-01
8839601c-18b0-4275-98a3-ada489cee886 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Concrete Coatings - West Barriers - BW-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1
8e5c72d6-6cca-45f2-bd2c-8cc46ab9a68c |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Expansion Joint - S3-01
1eb203f0-a826-4e47-946f-67fbd817441f |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Expansion Joint - S3-01 | ITP-STR Expansion Joints (Supply & Installation)
c570ffc3-0dff-4da8-964a-79e0be26fc5f |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Expansion Joint - S3-01 | ITP-STR Structural Concrete Rev 3
45b3860c-5c10-4a08-99bd-26dddf3bce89 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Bridge Girder - S3-G01 to S3-G05 - Precast
0ab8bc7b-8336-48a7-a844-c2cc168d946c |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Bridge Girder - S3-G01 to S3-G05 - Precast | ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1
813e2813-ab73-4ff2-ac51-a77ddee8a099 |  | work-in-progress | ITP-124-STR-CPD-Precast Super T Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Bridge Girder - S3-G01 to S3-G05 - Precast | ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1 | 080-0497 - ITP-124-STR-CPD-Precast Super T Installation
3b609864-6236-4b7b-af13-583a7d6a7e23 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Bridge Girder - S3-G06 to S3-G07 - Precast
0226c8ee-87d8-415e-8008-3f81912bdb1f |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Bridge Girder - S3-G06 to S3-G07 - Precast | 080-0498 - ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1
db902a07-d5d5-4c2a-9f8d-8adb424ab2ca |  | work-in-progress | ITP-124-STR-CPD-Precast Super T Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Bridge Girder - S3-G06 to S3-G07 - Precast | 080-0498 - ITP-STR Precast Bridge Beams (Supply & Installation) Rev 1 | 080-0498 - ITP-124-STR-CPD-Precast Super T Installation
a29f15de-98bb-44ad-ae9c-f6977d77205b |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Deck Pour - S3-01 - FRP
dc6daba7-c074-48cd-984c-b101d534e148 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (Bridge - Span 3) | Deck Pour - S3-01 - FRP | ITP-STR Structural Concrete Rev 3
364ad323-84b9-4bf4-b313-f1d81d6661fe |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South)
f43dbce6-727e-4f17-8e89-0d6f4ccfdfc7 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South West - FS-01 - FRP
1ccea36a-eb84-4903-8fb9-bdc83a51727c |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South West - FS-01 - FRP | ITP-STR Structural Concrete Rev 3
69a12598-5959-4694-bca3-948dc0a5c5ca |  | work-in-progress | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South West - FS-01 - FRP | ITP-STR Structural Concrete Rev 3 | ITP-017-STR-Structural concrete - Base
2a137e6b-13bd-42d9-9d59-8d930e45b26b |  | work-in-progress | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South West - FS-01 - FRP | ITP-STR Structural Concrete Rev 3 | ITP-017-STR-Structural concrete - Upstand
64a693da-e42e-423c-a76e-e6439693b2cc |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02A - FRP
6b4339ee-914a-447a-aaa0-9a98f0ee66ae |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02A - FRP | ITP-STR Structural Concrete Rev 3
677ca3cb-4de8-49bd-b87a-36de660ac6ab |  | work-in-progress | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02A - FRP | ITP-STR Structural Concrete Rev 3 | ITP-017-STR-Structural concrete - First Pour
c79939c6-c3df-41be-a263-53bb7715dd71 |  | not-started | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02A - FRP | ITP-STR Structural Concrete Rev 3 | ITP-017-STR-Structural concrete - Stitch Pour
3372b037-0dd1-4b5d-9059-c8f0f9b93a82 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02B - FRP
52e91f2e-c214-49e8-8d1f-2487b03d5ed3 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02B - FRP | ITP-STR Structural Concrete Rev 3
e6ddb55b-ce7e-4489-b512-d93fccca61e8 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02B - FRP | ITP-STR Structural Concrete Rev 3 | FS02B - sections
e32dbd20-ffa7-4d3f-8c16-9daecd5a0dae |  | work-in-progress | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02B - FRP | ITP-STR Structural Concrete Rev 3 | FS02B - sections | ITP-017-STR-Structural concrete - Base
62a9599b-bbc6-4c62-9217-7ed658e4bf9c |  | work-in-progress | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02B - FRP | ITP-STR Structural Concrete Rev 3 | FS02B - sections | ITP-017-STR-Structural concrete - Upstand
34016e92-bd02-4503-bdb2-1393260a019c |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02C - FRP
97689bf0-7b7a-46ab-8816-34e41c652235 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02C - FRP | ITP-STR Structural Concrete Rev 3
1d1d60e1-00af-4fb5-ae26-4b14ea63a4ee |  | not-started | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02C - FRP | ITP-STR Structural Concrete Rev 3 | ITP-017-STR-Structural concrete - First Pour
e2f12343-9874-4673-bae8-c0873eafa8f2 |  | not-started | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02C - FRP | ITP-STR Structural Concrete Rev 3 | ITP-017-STR-Structural concrete - Second Pour
6e0587d3-a45f-4d51-9118-1edeccdf419f |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02D - FRP
ce5cece5-b6bd-47b0-af3e-bf86af6b08a6 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02D - FRP | ITP-STR Structural Concrete Rev 3
5ca55d97-3941-4b11-96e3-d0ebf5748066 |  | not-started | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02D - FRP | ITP-STR Structural Concrete Rev 3 | ITP-017-STR-Structural concrete - First Pour
7409163b-cbcb-4acb-92b5-5f92489bcc8f |  | not-started | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Friction Slab in South East - FS-02D - FRP | ITP-STR Structural Concrete Rev 3 | ITP-017-STR-Structural concrete - Second Pour
8adba837-4673-45fb-a5e8-31ba4c0aa085 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | End Post - SE-01 - FRP
90e81428-0b98-4b71-b9c4-6c842684a4ff |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | End Post - SE-01 - FRP | ITP-STR Structural Concrete Rev 3
d95bcd7f-092d-4379-b7d1-42489e6aa833 |  | not-started | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | End Post - SE-01 - FRP | ITP-STR Structural Concrete Rev 3 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
6bd675a6-f42b-4809-9ffe-52337d491823 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Regular Performance Barrier - SE-02 to SE-25 - Precast
b289592a-8c71-4e44-96e0-62e796277dc0 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Regular Performance Barrier - SE-02 to SE-25 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
ada250fe-7757-42de-a8f3-702c14b56013 |  | work-in-progress | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Regular Performance Barrier - SE-02 to SE-25 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
12974def-12fe-42df-9853-12c21da6121a |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Transition Barrier - SE-26 - Precast
4312e9e6-6fba-41ec-b9a9-091d40f10b80 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Transition Barrier - SE-26 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
122ec2da-b280-496b-9e03-dd54dc638d95 |  | work-in-progress | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Transition Barrier - SE-26 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
b80df9e5-d3ea-4f9b-8cd4-0aff899a2382 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Medium Performance Barrier - SE-27 to SE-30 - Precast
44ae863f-7852-4dfb-bad5-d296f2bbf552 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Medium Performance Barrier - SE-27 to SE-30 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
f95322b2-349e-482f-8568-1820bd1ddba7 |  | work-in-progress | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Medium Performance Barrier - SE-27 to SE-30 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
9dd29bc4-7e20-4605-96c3-1fad363b26f5 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | End Post - SW-01 - FRP
3adf934c-6fab-4e0f-b8b5-fa6734670beb |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | End Post - SW-01 - FRP | ITP-STR Structural Concrete Rev 3
6d13e02a-2361-4490-bbf0-b49b4885b7f2 |  | not-started | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | End Post - SW-01 - FRP | ITP-STR Structural Concrete Rev 3 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
5a7a7c12-dfc8-4037-9aaf-cca540507d17 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Test Level-4v Barrier - SW-02 to SW-15 - Precast
a26412aa-a9dd-48e8-85e8-cd344142c3b2 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Test Level-4v Barrier - SW-02 to SW-15 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
110802f8-1850-404d-b90b-55bb033895d8 |  | not-started | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Test Level-4v Barrier - SW-02 to SW-15 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
4eceeec3-602f-4cbf-a5da-18998a967bcd |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Regular Performance Barrier - SW-16 - Precast
ffc2e051-3e20-470a-bbe6-dd7bb063f39f |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Regular Performance Barrier - SW-16 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
99b5af1e-6224-4e3c-ad99-df46c9dd4177 |  | not-started | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Regular Performance Barrier - SW-16 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
127a9b0f-7513-4db3-8af5-d9ebd7acb9cd |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Transition Barrier - SW-17 - Precast
23c62540-2469-4d4c-a726-8ddf926ce02d |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Transition Barrier - SW-17 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
d85294f2-a139-4e98-9b4f-a41fbf283949 |  | not-started | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Transition Barrier - SW-17 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
4681dedd-1b3a-4ea3-83e9-2c218613b0ea |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Medium Performance Barrier - SW-18 to SW-21 - Precast
cf49c99b-1232-47b0-b853-7e3c1c056268 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Medium Performance Barrier - SW-18 to SW-21 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
61182c2f-8a1e-492c-bae0-f037572b2bcc |  | work-in-progress | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Medium Performance Barrier - SW-18 to SW-21 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
398a4176-3447-4e6a-baf7-48e64f574b56 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Stitch Pour - SE-01 - FRP
63c9893e-f5df-4012-886f-c6e0a7d0fed7 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Stitch Pour - SE-01 - FRP | ITP-STR Structural Concrete Rev 3
91b0e9e2-c629-4a3f-9976-b7e1eea6057c |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Stitch Pour - SW-01 - FRP
10b4284d-c4ab-42d1-b22c-2caf1271d5ab |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Stitch Pour - SW-01 - FRP | ITP-STR Structural Concrete Rev 3
6545568a-f27f-44f7-bc3a-3f233132a4f5 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Concrete Coatings - East Barriers - SE-01
b83762e9-54de-4ec3-9138-a76f6fb798b4 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Concrete Coatings - East Barriers - SE-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1
2edec6d9-d5b8-4b84-a563-de699e39fd5a |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Concrete Coatings - West Barriers - SW-01
d7329346-cf0f-495f-9665-12bbad584ddf |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Concrete Coatings - West Barriers - SW-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1
a4ec6e8f-aabd-45f0-97fa-c22505f14f44 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Kerb - PK51 to PK-60 - Precast
55d478f3-3173-411e-9941-ea6c25cd82d0 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Kerb - PK51 to PK-60 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
8f4affbe-8bff-453d-9138-c272ebd36a9f |  | work-in-progress | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | Kerb - PK51 to PK-60 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
64182144-cf72-4be5-b558-6efe436e1eea |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | SUP Footing South
4a8efbc8-594b-4250-a896-2dd286e15bb5 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | SUP Footing South | ITP-017-STR-Structural Concrete
6c02d37f-3929-418f-92a9-155ea7b15f23 |  | work-in-progress | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (South) | SUP Footing South | ITP-017-STR-Structural Concrete | ITP-017-STR-Structural concrete
7d242ada-9021-43d2-87ae-d4f0dc612015 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North)
22a73745-437e-43e1-af88-deba96387e83 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Friction Slab in North West - FS-03 - FRP
e1d71498-a867-4344-a084-005126017301 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Friction Slab in North West - FS-03 - FRP | ITP-STR Structural Concrete Rev 3
65bf6ce5-2874-42ef-bd75-0006e66fbbf9 |  | not-started | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Friction Slab in North West - FS-03 - FRP | ITP-STR Structural Concrete Rev 3 | ITP-017-STR-Structural concrete - Base
f36a6762-030d-462b-b331-999209f7595a |  | not-started | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Friction Slab in North West - FS-03 - FRP | ITP-STR Structural Concrete Rev 3 | ITP-017-STR-Structural concrete - Upstand
b4bad484-2623-4e32-8545-ea683c505aee |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Friction Slab in North East - FS-04 - FRP
8b3741c2-854a-4498-b974-9accfdcdb5a1 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Friction Slab in North East - FS-04 - FRP | ITP-STR Structural Concrete Rev 3
22666015-8804-42ae-bf82-e04622edc90d |  | not-started | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Friction Slab in North East - FS-04 - FRP | ITP-STR Structural Concrete Rev 3 | ITP-017-STR-Structural concrete - Base
b892f496-d126-4ab4-8d68-f0afe081e441 |  | not-started | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Friction Slab in North East - FS-04 - FRP | ITP-STR Structural Concrete Rev 3 | ITP-017-STR-Structural concrete - Upstand
94a7e9c1-9866-470e-8bde-5b4ff72a3a9f |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Medium Performance Barrier - NE-01 to NE-05- Precast
3cdcb45a-6dbb-44e1-8ff7-c46345ed7e5c |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Medium Performance Barrier - NE-01 to NE-05- Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
50f151ac-671e-416a-96a4-24de6457eb85 |  | work-in-progress | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Medium Performance Barrier - NE-01 to NE-05- Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
4c36bbba-9b29-46fd-935a-1b1ddd3dc0d4 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Transition Barrier - NE-06 - Precast
638f0175-1b32-4b4c-8286-403e87552268 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Transition Barrier - NE-06 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
58c9b818-2887-4adc-a510-e6d122e0019d |  | not-started | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Transition Barrier - NE-06 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
85552718-4e64-4703-b679-59062d78fbcf |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Endpost - NE-07 - FRP
aeb59723-fc2b-4199-8740-6894df8d9a38 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Endpost - NE-07 - FRP | ITP-STR Structural Concrete Rev 3
9e3780c8-3934-4e79-bc49-a952970276cd |  | not-started | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Endpost - NE-07 - FRP | ITP-STR Structural Concrete Rev 3 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
9e101357-f29d-4be4-a29d-0d845ae83abb |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Medium Performance Barrier - NW-01 to NE-05 - Precast
5feb2bb7-9925-43a0-a70e-5dbded167293 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Medium Performance Barrier - NW-01 to NE-05 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
7aa9ea6d-b0ef-4586-9ab3-c35b26a49ed5 |  | work-in-progress | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Medium Performance Barrier - NW-01 to NE-05 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
0d8a6dd0-6d87-41c1-825d-8d9eac9ea40a |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Transition Barrier - NW-06 - Precast
a35909d1-9281-4f94-9326-72500920c1ae |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Transition Barrier - NW-06 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
3a1f172c-444d-428c-a6d5-f2d7fa86793a |  | not-started | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Transition Barrier - NW-06 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
337cef85-e74f-4767-a3a3-f1d8db92d71b |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Test Level-4 Barrier - NW-07 to NW-16 - Precast
836e30b2-9a73-40a6-bf65-66f21f433160 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Test Level-4 Barrier - NW-07 to NW-16 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
33c582a8-2ed8-44a0-9ca1-d3da71be9fcc |  | not-started | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Test Level-4 Barrier - NW-07 to NW-16 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
eb37dc97-80cd-483f-b780-931d8050f3a2 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Endpost - NW-17 - FRP
a9bd91a7-7dfa-4df1-8614-219af72ffc17 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Endpost - NW-17 - FRP | ITP-STR Structural Concrete Rev 3
9b3116ff-5339-472d-a17e-f7476908accf |  | not-started | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Endpost - NW-17 - FRP | ITP-STR Structural Concrete Rev 3 | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation
ea9f8716-2b33-433e-b5bb-d98abc4c5635 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Stitch Pour - NE-01 - FRP
f10692b7-a42a-4f9b-b700-dfe6d85a802c |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Stitch Pour - NE-01 - FRP | ITP-STR Structural Concrete Rev 3
396aed2b-6060-4031-bdc2-762a72a34ac7 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Stitch Pour - NW-01 - FRP
df62edab-0346-4cb0-8779-b734f4f57308 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Stitch Pour - NW-01 - FRP | ITP-STR Structural Concrete Rev 3
e8a9e8a7-fabd-4419-aea2-2cd19fa83a39 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Concrete Coatings - East Barriers - NE-01
837c0ed4-7074-4d9b-977e-a92e1266036c |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Concrete Coatings - East Barriers - NE-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1
65c8e2a2-7532-47dc-af72-bda3f3a454e3 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Concrete Coatings - West Barriers - NW-01
dd21b8e9-3659-4a1c-8a2e-fc2d0335bd8d |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | Concrete Coatings - West Barriers - NW-01 | ITP-STR Concrete Coatings (Protection &/or Decorative) Rev 1
b6f2614c-2030-4238-8a03-8270787a7558 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | SUP Footing North
9bd6bbd5-3073-4ae4-a386-19e4f352f758 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | SUP Footing North | ITP-017-STR-Structural Concrete
0fdd9a42-a335-4e71-9fee-c0d6b5a25ca5 |  | work-in-progress | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CBR-0030-0 - Bridge Structure and Off-Structure Barriers | Calder Park Drive (North) | SUP Footing North | ITP-017-STR-Structural Concrete | ITP-017-STR-Structural concrete
faac13f0-d694-48f8-be95-553421e58f62 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures
51e74c3d-6f08-4869-a0f3-942523207b06 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South)
ebdcd074-221d-43e6-a974-175355aed97d |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Wall - L-1 - Precast
2f6828ce-0c0c-4634-acf1-ac7660bc9d29 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Wall - L-1 - Precast | ITP-STR Precast Retaining Walls &/or Architectural Panels (Supply & Installation) Rev 0
22102dea-5189-4227-8f05-a84dc62f0960 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Wall - L-2 - Precast
9bf4042f-4635-49bd-a8e9-9fec0da45fe6 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Wall - L-2 - Precast | ITP-STR Precast Retaining Walls &/or Architectural Panels (Supply & Installation) Rev 0
dbaabae5-77f2-4cc4-b6fa-35ca656a1d56 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Wall - L-3 - Precast
224922d2-8989-49c4-bac9-fa60142af799 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Wall - L-3 - Precast | ITP-STR Precast Retaining Walls &/or Architectural Panels (Supply & Installation) Rev 0
66241930-9ba2-46e3-9284-116e321eeea1 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Wall - L-4 - Precast
a4ae7db3-3e14-4421-acd0-b273e7f2c1c7 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Wall - L-4 - Precast | ITP-STR Precast Retaining Walls &/or Architectural Panels (Supply & Installation) Rev 0
5146ec0b-8216-42cc-89b9-4f7e880822b7 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Wall - L-5 - Precast
c3074007-f47f-4898-aa59-47a5e0714565 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Wall - L-5 - Precast | ITP-STR Precast Retaining Walls &/or Architectural Panels (Supply & Installation) Rev 0
ec9e449a-ff52-4c14-99cc-fdad42b05c7e |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Kerb - SK-01 to SK03 - Precast
a38918f1-71a5-4485-b311-079dd1c241d5 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Kerb - SK-01 to SK03 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
2ef49d69-49c5-429b-aa11-a1cf2d31dfe6 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Capping - LC-01 - Precast
7a4e9838-7124-48db-b561-a044152e42da |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Capping - LC-01 - Precast | ITP-STR Precast Retaining Walls &/or Architectural Panels (Supply & Installation) Rev 0
76748a43-4b09-4fce-824a-46a287f723fc |  | work-in-progress | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Capping - LC-01 - Precast | CHK-006-STR&CIV-Material Inspection-Precast
595faeda-ff88-40d3-a84b-fa2c5339bb98 |  | work-in-progress | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shaped Capping - LC-01 - Precast | CHK-006-STR&CIV-Material Inspection-Precast Panel
27ab9de7-61ef-4665-852a-21e1a4091d5c |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | SUP Stairs Case - SE-01 - FRP
d9cc33cb-5895-4ea4-85c4-2a25226f510a |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | SUP Stairs Case - SE-01 - FRP | ITP-STR Structural Concrete Rev 3
b9dec608-9d87-42eb-ba32-d01184180013 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | SUP Type B - SE-02 - FRP
606cc192-c8f8-42ec-9651-e0233e9a0473 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | SUP Type B - SE-02 - FRP | ITP-STR Structural Concrete Rev 3
40afa541-06b7-49ea-b351-7cb5fb097de7 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | SUP Type A - SE-03 - FRP
117ffbaa-256a-49f9-a7f0-1fb166a8c490 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | SUP Type A - SE-03 - FRP | ITP-STR Structural Concrete Rev 3
f6b1a4cc-6ea4-4377-b692-43c83f1afcde |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Posts & Screens - F1-1
ce92e20a-85c9-4def-afb4-cad9d2504764 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Posts & Screens - F1-1 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
5f811493-b160-4c11-a3c9-f0068f2f46ab |  | not-started | ITP-123-STR-CPD-Steel Structures Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Posts & Screens - F1-1 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2 | ITP-123-STR-CPD-Steel Structures Installation
54f804cc-2c07-4f54-94c8-02800df1ee4b |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Posts & Screens - F1-2
f689633f-aad5-4d42-9683-37f48a39f217 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Posts & Screens - F1-2 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
f58a458d-3d94-491a-91c7-2d2bc5be67a1 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Posts & Screens - F1-3
0f1d9103-de21-4b81-8e43-3ecab279e720 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Posts & Screens - F1-3 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
dc9c7c06-468a-49f5-89ec-524f246ac37f |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Posts & Screens - F1-4
3513dfa8-b432-4eb9-a9da-39cc99726763 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Posts & Screens - F1-4 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
2d183fd3-d4a5-4cbd-9386-f233b462be7f |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Posts & Screens - F3-1
be4d1551-0456-40cb-9caf-40344b3e567a |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Posts & Screens - F3-1 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
a3f3188a-b588-431c-ae37-2c21926ca103 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Barrier Rail - South West
5a6a6046-cc50-41bc-bef0-1f86e9ae7026 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Steel Barrier Rail - South West | ITP-STR Structural Steel Barrier Rail (Supply & Installation) Rev 3
4aa8da3a-bd49-4c67-82ee-848538d569d9 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Spoon Drain - South West - FRP
5305910a-6ba7-4a78-a86b-7987fdfd10c3 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Spoon Drain - South West - FRP | ITP-STR Structural Concrete Rev 3
0bfac6d8-1942-4306-b2e2-1d5d7dfcec04 |  | not-started | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | Spoon Drain - South West - FRP | ITP-STR Structural Concrete Rev 3 | ITP-017-STR-Structural concrete
663e3664-d2d3-41fb-a1ff-f104028010da |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shape Capping Units - North - 04/09/2024
826f10dc-5c7c-42b6-8a21-a3cef49b6e94 |  | not-started | ITP-112-STR Precast L-shape Wall Rev1 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (South) | L-Shape Capping Units - North - 04/09/2024 | ITP-112-STR Precast L-shape Wall Rev1
f10bf13b-cfdf-4255-adf3-b2d50b2edc86 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Contingency
673fec9a-c30a-45c3-bae2-f1e3f71d42ed |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 1)
3fbe195d-e553-4331-9849-92a1f00eb265 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 1) | Steel Posts & Screens - F1-5
c24732f8-2b30-4e2f-8c0b-c43f3e003b88 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 1) | Steel Posts & Screens - F1-5 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
4cfe86a7-07d7-47de-8a2f-ce7e7c1f480c |  | not-started | ITP-123-STR-CPD-Steel Structures Installation Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 1) | Steel Posts & Screens - F1-5 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2 | ITP-123-STR-CPD-Steel Structures Installation
9efd6911-03ba-47ee-9869-2294314bcf1f |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 1) | Steel Posts & Screens - F1-6
6f68202e-bfef-4710-87ff-e3bda4d0b638 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 1) | Steel Posts & Screens - F1-6 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
25af393a-49c8-414e-988d-2c5a8b37368f |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 1) | Steel Posts & Screens - F2-1
c2a9bfb7-6028-4e28-a65b-be4028c38e34 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 1) | Steel Posts & Screens - F2-1 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
6a578903-76e7-4bad-ac9e-196b20861f75 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 2)
eea1949d-0686-4c50-9943-10894d130a1b |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 2) | Steel Posts & Screens - F1-5
29466e44-55cc-4732-9c7b-727621b300c3 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 2) | Steel Posts & Screens - F1-5 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
ed2f6c4d-625c-49cc-b740-06783686a16f |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 2) | Steel Posts & Screens - F2-2
db5f99aa-9c9d-4248-8196-4d9ffe79b318 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 2) | Steel Posts & Screens - F2-2 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
c0ae3e01-2f78-488d-9323-e3ad5e374a73 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 2) | Steel Posts & Screens - F5
64400dad-3df9-4640-b9af-0ec158024a0b |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 2) | Steel Posts & Screens - F5 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
32e93ad3-4bf9-4c22-b85c-cd03bc502570 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 3)
8f97d262-6166-4e1a-9afe-159add4ab082 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 3) | Steel Posts & Screens - F1-2
d79a7e65-86ee-4f27-a814-0f0e0747ef51 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 3) | Steel Posts & Screens - F1-2 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
a7075773-2654-471f-bbe5-03b1dc783709 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 3) | Steel Posts & Screens - F1-3
5745b5e5-da2a-43b3-9803-04a72379fc91 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 3) | Steel Posts & Screens - F1-3 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
36f7a330-9047-493d-99d8-7af5682a5f31 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 3) | Steel Posts & Screens - F3-2
7996a7f6-e35b-4392-b6c2-19be9d77e4b0 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (Bridge - Span 3) | Steel Posts & Screens - F3-2 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
0f835ac2-e212-46f4-8024-f400a5b10ad1 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North)
3c718138-7388-4242-82e0-b73c90eeafaf |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Kerb - PK-10 - Precast
73e3eb67-ce19-4b45-9d5c-9b6e6c10973b |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Kerb - PK-10 - Precast | ITP-STR Precast Barriers & Kerbs (Supply & Installation) Rev 1
650dba94-a805-4170-9b21-6ddb3db245b3 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | L-Shaped Capping - LC-01 - Precast
2a671841-49ac-4aa0-ac66-b78375ac920d |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | L-Shaped Capping - LC-01 - Precast | ITP-STR Precast Retaining Walls &/or Architectural Panels (Supply & Installation) Rev 0
1ffbcfea-b81f-4cd5-9a45-52329989e19e |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | SUP Type A - NE-01 - FRP
9a3b6dc8-4633-4ad0-a667-6d23556b7ec6 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | SUP Type A - NE-01 - FRP | ITP-STR Structural Concrete Rev 3
ab46cb9e-bd7a-4021-94c2-e4f37412b275 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | SUP Type C - NE-02 - FRP
5964dfa0-5584-455c-ad20-6efc175a3c12 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | SUP Type C - NE-02 - FRP | ITP-STR Structural Concrete Rev 3
1ba86052-46cd-47e4-bfd8-d61b12814c55 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Steel Posts & Screens - F1-7
367b82e3-8bf6-41f3-9ec6-29600c90436c |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Steel Posts & Screens - F1-7 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
b95593eb-be99-489b-8268-9f704a4ce315 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Steel Posts & Screens - F4
52372395-0ed1-4f51-a664-63f81e01d001 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Steel Posts & Screens - F4 | ITP-STR Structural Steel Posts & Screens (Supply & Installation) Rev 2
3943675a-688a-4871-ac37-85a386d5bd93 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Steel Barrier Rail - North West
72b95d05-0616-49a4-a1d0-4edef6c6a3c3 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Steel Barrier Rail - North West | ITP-STR Structural Steel Barrier Rail (Supply & Installation) Rev 3
7b10218a-d5a7-4cdb-91fa-aca415bba070 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Spoon Drain - North West - FRP
576930e1-952b-48c4-81fe-d28eb65a6fb6 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Spoon Drain - North West - FRP | ITP-STR Structural Concrete Rev 3
9e7d748e-13b9-4f60-bdbd-98ae384be9de |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Spoon Drain - North East - FRP
e401ff82-a891-4a0e-9671-2df1f82a94df |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSW-0034-0 - Retaining Walls and Miscellaneous Structures | Calder Park Drive (North) | Spoon Drain - North East - FRP | ITP-STR Structural Concrete Rev 3
c1517b7d-20ed-4869-bc9a-2727d2c18765 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure
8d6d0733-9c1b-4c27-b4a7-f4b608a104e9 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure
a26d6d66-49c8-446b-ab37-6351294f4242 |  | work-in-progress |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0418 - Piling - SUP-01 - Pile Installation
f73ef994-b695-4a55-978b-1a168392a73d |  | work-in-progress | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0418 - Piling - SUP-01 - Pile Installation | ITP-009-STR-Bored Piling
028329c9-9dda-4832-bd4e-692594197a41 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0419 - Piling - SUP-02 - Pile Installation
e3dc4871-efbf-4ac0-83e7-f99bb74f5eaa |  | not-started | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0419 - Piling - SUP-02 - Pile Installation | ITP-009-STR-Bored Piling
dc8bc243-61bd-4b08-8dda-12bde13892b2 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0420 - Piling - SUP-03 - Pile Installation
56cbe27a-f9eb-441c-a76c-0bb9ac08e432 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0421 - Piling - SUP-04 - Pile Installation
6c1f777a-237f-476e-92a0-4dbb4e5b8a4b |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0422 - Piling - SUP-05 - Pile Installation
2880f39b-0f4c-4354-aff2-ab7459f46929 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0423 - Piling - SUP-06 - Pile Installation
013cb397-bd42-496c-8067-2d44650e1430 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0424 - Piling - SUP-07 - Pile Installation
320b5ab1-1c33-4a20-a3cc-4bc565c8b1ca |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0424 - Piling - SUP-07 - Pile Installation | ITP-009-STR-Bored Piling
882dc0e7-1da0-4ed7-ba44-7e6940593e9f |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0425 - Piling - SUP-08 - Pile Installation
80ab894c-5536-42c2-a99f-6930d11f1b95 |  | pass | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0425 - Piling - SUP-08 - Pile Installation | ITP-009-STR-Bored Piling
d310cb45-897a-43de-84a3-d06edc82f863 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0568 - Pile Cap - Abutment 1 - FRP
bcd44427-b645-43e8-ad82-7269646829d3 |  | not-started | CHK-006-STR&CIV-Material Inspection-Precast Panel Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0568 - Pile Cap - Abutment 1 - FRP | CHK-006-STR&CIV-Material Inspection-Precast Panel
b9bc62a5-bcf6-4303-8526-663cc92491df |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0569 - Pile Cap - P1 - FRP
32596916-16fd-4837-abe8-c1e6216a9dc0 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0570 - Pile Cap - P2 - FRP
7a4aa0f7-4150-420d-bd1b-3457169b7e91 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0571 - Pile Cap - P3 - FRP
40be101f-1829-4721-8864-db15df269708 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0573 - Pile Cap - P4 - FRP
a5f50147-79f6-48c5-b5c6-f653c3e20b86 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Pile Cap - P5 - FRP
a5fe181a-6d40-4f4b-b264-57aaf733b3fb |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Pile Cap - Abutment 2 - FRP
9659a795-f15e-474b-8282-7f08cf0234a4 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | Pile Cap - Abutment 2 - FRP | ITP-STR Structural Concrete Rev 3
af1d550e-1797-4c31-85ae-b6b54e493ccb |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0574 - Pier - P1 - FRP
79e8df02-67f8-4cb9-8ef1-511c9fc3a742 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0575 - Pier - P2 - FRP
8a417d9a-59e6-45df-a39d-7377e391d39e |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0576 - Pier - P3 - FRP
404ea903-9493-426d-9ce8-be71c34f5d45 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0577 - Pier - P4 - FRP
61b7fc7c-b0d8-4253-b445-7fb3b9bc61c8 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0578 - Pier - P5 - FRP
3c7709b2-d688-48d6-956d-b0fd5dd2a3bb |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0534 - Pile Extension - SUP-07
5de89fdc-9082-4df6-9d93-1d084ea613b8 |  | pass | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0534 - Pile Extension - SUP-07 | ITP-017-STR-Structural concrete Rev 0
8521f803-a889-4cca-a80b-006bd7c471c7 |  | pass |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0535 - Pile Extension - SUP-08
94eba89a-99c6-4212-bef0-b7043253670c |  | pass | ITP-017-STR-Structural concrete Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0535 - Pile Extension - SUP-08 | ITP-017-STR-Structural concrete Rev 0
25ace20d-4b00-41b7-9509-bb6940e3c869 |  | not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0030 - Below Approach Trough - Type A Layer 1
6025164c-6659-4814-9542-4a10ca3d580a |  | not-started | ITP-009-STR-Bored Piling - Rev 0 | checklist | FALSE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Substructure | 080-0030 - Below Approach Trough - Type A Layer 1 | ITP-009-STR-Bored Piling
cb8eca89-0cfc-4424-a5c0-129589a579ed |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure
e6959b31-c26c-4b17-8831-69b90d5b909e |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Plank - S1-G01/G02 - Precast
9d0490d0-2e48-405f-bf0d-253d6b941764 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Plank - S2-G01/G02 - Precast
fb6ac1ef-481c-4c60-b394-c59fd0d83d6b |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Plank - S3-G01/G02 - Precast
6faf0b83-4eba-4b35-9139-46a90de700da |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Plank - S4-G01/G02 - Precast
8dfa0514-4b2f-42d2-8a77-3f7834848b0c |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Platform Pour - 1 - FRP
9dfb6722-e241-4328-a784-a622d8a586e8 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Platform Pour - 2 - FRP
8ae9145f-a2fa-4705-aa64-c1ab0222997f |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Stitch Pour - Abutment 1 - FRP
c07bbd9b-9371-41b8-a010-bc68f216867f |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Stitch Pour - Abutment 2 - FRP
fbeb6157-5da8-4748-ba9b-c36d071facd1 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Stitch Pour - Pier 5 - FRP
7bef20e7-948b-4136-b0f0-9c716f803359 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Deck Pour - FRP
3f709f3c-3812-4368-8c24-69ac413455c6 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | 080-0593 - Approach Trough Slab - FRP
8961deae-16ce-4da0-b43c-54052df50c45 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | 080-0595 - Approach Slab - 1 - FRP
fc3343b5-b5f3-4f66-9f09-9d0e421e5ac3 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | Pavement Slab - FRP
f84c7294-2ee9-4dd0-bc52-14e7c84f3264 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | 080-0596 - Steel Posts & Screens - SUP
c171e088-7597-4e2a-87f4-49164f86e44c |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Superstructure | 080-0594 - Approach Trough Walls - FRP
8e2305a5-7ef5-4aa4-8548-6ecc3006dce0 |  | no-status-not-started |  | folder | TRUE | FALSE | Structures | MRP-DPK-080-00-CSF-0035-0 - SUP Switchback Elevated Structure | Contingency
b92a8d4d-0c11-47c0-b87f-442eff815c1e |  | work-in-progress |  | folder | TRUE | FALSE | Temp
3a071b4a-8a86-4f3c-9f2c-f9f7b702bdd2 |  | work-in-progress |  | folder | TRUE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion
f03bcb3c-c7be-4dd5-9d33-a59cc3bd24db |  | work-in-progress |  | folder | TRUE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | South of LX
1ecaf441-17aa-4f9d-9eeb-562d32e187a2 |  | work-in-progress |  | folder | TRUE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | South of LX | Temp Road Pavements
965df072-ff83-4552-8621-242f2a998621 |  | pass | ITP-045-CIV-CPD-Subgrade Preparation - Road Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | South of LX | Temp Road Pavements | STH-TEM-SUB-001-Subgrade Preparation - Road
ed092b4f-2a86-407c-9298-9402929ca59c |  | pass | ITP-046-CIV-CPD-Type A Fill - Road Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | South of LX | Temp Road Pavements | STH-TEM-CAP-001-Capping Preparation - Road
03ea3b5a-2e69-480e-bade-c43f2223c394 |  | pass | ITP-046-CIV-CPD-Type A Fill - Road Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | South of LX | Temp Road Pavements | STH-TEM-CAP-002-Capping Preparation
1cdd4b60-feef-4be3-a75f-c054d8486478 |  | pass | ITP-046-CIV-CPD-Type A Fill - Road Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | South of LX | Temp Road Pavements | STH-TEM-CAP-003-Capping Preparation
0530037d-e6e0-41c3-b7bd-5c35a9f7e596 |  | pass | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction - Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | South of LX | Temp Road Pavements | STH-TEM-Subbase-001-Subbase preparation
01f0b419-84a0-4a74-ba99-548c21fd1527 |  | pass | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction - Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | South of LX | Temp Road Pavements | STH-TEM-Subbase-002-Subbase preparation
be1192f7-3b14-4877-8db1-778cc99addd8 |  | work-in-progress | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction - Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | South of LX | Temp Road Pavements | STH-TEM-Subbase-003-Subbase preparation
b48efb49-b6c4-4b50-958a-ae6aff4b9360 |  | pass | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | South of LX | Temp Road Pavements | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) - BC - CH0-300
fd44e626-1360-4b1d-8321-6215307237d9 |  | pass | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | South of LX | Temp Road Pavements | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) - IC1 - CH135-300
b32e7237-b3ab-4d1f-9770-18af5a83689c |  | pass | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | South of LX | Temp Road Pavements | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) - IC1 - CH0-135
a2c49252-d703-4eb3-bf9e-5359ada7480a |  | pass | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | South of LX | Temp Road Pavements | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) - IC2 - CH0-300
acd15512-cd33-48a4-bd1a-b2148e3f6962 |  | pass | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | South of LX | Temp Road Pavements | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) - WC - CH0-300
91870563-0bd3-46c7-bd54-b3badd6b4cc9 |  | no-status-not-started |  | folder | TRUE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | South of LX | Subsurface Drainage
c33c2a49-4b43-4186-809d-9b4a297f19c4 |  | no-status-not-started |  | folder | TRUE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | South of LX | Storm water Drainage
ebde38b3-dba6-420f-87df-a113fefa0973 |  | work-in-progress |  | folder | TRUE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX
8a09a44f-ac95-463e-908d-16dd92d6742f |  | work-in-progress |  | folder | TRUE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX | Temp Road Pavement
3cdeea65-5a92-4c38-a1cb-96b163a69df5 |  | pass | ITP-045-CIV-CPD-Subgrade Preparation - Road Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX | Temp Road Pavement | NTH-TEM-SUB-001- Subgrade Preparation - Road
ddf21f04-026f-4dbe-8a1b-19ccfcfb8aea |  | pass | ITP-046-CIV-CPD-Type A Fill - Road Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX | Temp Road Pavement | NTH-TEM-CAP-001-Capping Preparation - Road
b42c36c2-3752-4c78-811b-514a318f65c1 |  | pass | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX | Temp Road Pavement | ITP-063-CIV-CPD- CH400-570 BC Hot Mix Asphalt (Supply and Install) CPDLXRP-230809D-BC
6caf733f-306b-4eed-92b2-8088e72debac |  | pass | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX | Temp Road Pavement | ITP-063-CIV-CPD- CH400-570 IC1 Hot Mix Asphalt (Supply and Install)
3aa0bc62-5304-41c0-be1c-aabc8468ad9c |  | pass | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX | Temp Road Pavement | ITP-063-CIV-CPD- IC1 - CH400-570 - Hot Mix Asphalt (Supply and Install)
35d3c79f-c2f0-4c7c-b275-440cd205c76e |  | pass | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX | Temp Road Pavement | ITP-063-CIV-CPD- IC2 - CH400-570 - Hot Mix Asphalt (Supply and Install)
b5e727d1-4d89-4191-b74d-1c74bbde7a47 |  | pass | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX | Temp Road Pavement | ITP-063-CIV-CPD- BC - CH350-400 and CH570-650 - Hot Mix Asphalt (Supply and Install)
899c0f55-cb51-45d3-ad1e-ebfc85ae5469 |  | pass | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX | Temp Road Pavement | ITP-063-CIV-CPD- IC - CH350-400 - Hot Mix Asphalt (Supply and Install)
7e707f61-494c-4bea-b69d-a45d3c5824a8 |  | pass | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX | Temp Road Pavement | ITP-063-CIV-CPD- BC - CH570-650 - Hot Mix Asphalt (Supply and Install)
21ebab26-d058-482d-8a2f-9e6210f313f3 |  | pass | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX | Temp Road Pavement | ITP-063-CIV-CPD- IC - CH600-725 - Hot Mix Asphalt (Supply and Install)
8a46a018-80ee-4a57-af46-9736575e4693 |  | pass | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX | Temp Road Pavement | ITP-063-CIV-CPD- WC - CH325-400 - Hot Mix Asphalt (Supply and Install)
6f64195e-68a5-4172-b588-85cc3623eb4a |  | pass | ITP-063-CIV-CPD- Hot Mix Asphalt (Supply and Install) Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX | Temp Road Pavement | ITP-063-CIV-CPD- WC - CH400-700 - Hot Mix Asphalt (Supply and Install)
8fb794c1-4aad-4c5c-b812-323f99f69bcb |  | pass | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction - Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX | Temp Road Pavement | NTH-TEM-Subbase-001
c35e79a6-199d-44d7-8e01-06d47fdf0740 |  | pass | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction - Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX | Temp Road Pavement | NTH-TEM-Subbase-002
88abee56-1646-41ca-8552-2c2acd6bc369 |  | not-started | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction - Rev 0 | checklist | FALSE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX | Temp Road Pavement | ITP-060-CIV-CPD-Unbound Flexible Pavement Construction
ea25bbd7-34cd-4c19-9b81-87f6b966b2f8 |  | no-status-not-started |  | folder | TRUE | FALSE | Temp | MRP-DPK-080-00-CDR-0091-0 - Temporary Road Diversion | North of LX | Storm water Drainage
a6b0945f-6a45-4874-a480-72e9bc0855c3 |  | no-status-not-started |  | folder | TRUE | FALSE | Temp | MRP-052-C-PIT-DRG-92-MPK-CTW-092-0 -Temporary Rail Delineation Fencing
a1cd450c-3185-4ea0-ab39-cb4acfd8cb50 |  | not-started |  | folder | TRUE | FALSE | Temp | Extra Temporary Lots
6b1729f2-99f1-4da9-9a60-6f4dbca1a64b |  | no-status-not-started |  | folder | TRUE | FALSE | Temp | Extra Temporary Lots | Landscaping
381386b1-fc56-4866-956f-cf8264f88980 |  | no-status-not-started |  | folder | TRUE | FALSE | Temp | Extra Temporary Lots | Landscaping | Clearing and Grubbing
c89689a0-170b-43d6-8501-208acaf8b9e2 |  | no-status-not-started |  | folder | TRUE | FALSE | Temp | Extra Temporary Lots | Landscaping | Clearing and Grubbing | ITP-CIV-Site Clearing and Grubbing
a749aa3b-2062-4e47-a331-e3207cbf2688 |  | not-started | ITP-102-STR-RSS Wall Main Rev 0 | checklist | FALSE | FALSE | Temp | Extra Temporary Lots | ITP-102-STR-RSS Wall Main
d5913b0c-8cca-47e7-bd94-e04a791ff747 |  | no-status-not-started |  | folder | TRUE | FALSE | Temp | Materials Inspection
63f1601e-f0d0-432c-9365-50638f2f4360 |  | not-started | ITP-054-CPD-Subsurface Drainage (Supply and Install) - Rev 0 | checklist | FALSE | FALSE | Temp | ITP-054-CPD-Subsurface Drainage (Supply and Install)