## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation Rev 1 | itp | ITP-122-STR-CPD-Precast Barriers and Kerbs Installation |  | dcbcfbeb-c210-4449-9a89-a119dcf5f8e1
| section | 1. Referenced Documentation
| checkpoint-no-value | 1. Referenced Documentation
f6383529-49d8-56eb-ba06-5a01383d031b | note | Document Title: ITP-122-STR-CPD -Precast Barriers and Kerbs Installation
5c9abf57-444c-504f-aeae-cdd52928671e | note | ITP Description: CPD -Precast Barriers and Kerbs Installation
a7c6cc13-9e0f-50cc-9188-0fa997489897 | note | ITP Number: 122
e5135bd5-42ec-52a5-ae31-6770f70488f6 | note | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
54136beb-d494-5e74-8917-1440cb91e7ee | note | Discipline (e.g. CIV/STR/RAIL): STR
7bb2518c-f0f3-5695-bb7e-4be3bd26541d | note | Revision Number: 1
d546f5a8-0ea2-507b-9f1b-4b18b69fe2ae | note | Revision Date: 19/01/2024
7694ff07-8845-5046-8ca1-a22ff65407f0 | note | ITP created by: Andrew Carlini
97b9c826-d04a-5955-9101-113af18911cc | note | ITP approved for use by: Pradeep Talasila
| checkpoint | 1.1 - Non Dependent
039fe781-83dd-5276-ba09-09a136e06c59 | note | Reference - VicRoads Section 610 Feb 2020
| checkpoint | 1.2 - Non Dependent
044524f2-02b0-5c30-843e-64d2a39ad16b | note | Reference - VicRoads Section 620 May 2009
| checkpoint | 1.3 - Non Dependent
c83d3581-d20f-5258-8021-9a95aa8a8f2c | note | Reference - VicRoads Section 630 October 2013
| checkpoint | 1.4 - Non Dependent
ba43cb52-c44e-51f1-9704-8f590cb759f4 | note | Reference - VicRoads Section 670 October 2013
| checkpoint | 1.5 - Non Dependent
6399ae26-b717-542f-8a6d-ef9843b35fa0 | note | Reference - VicRoads Section 671 October 2013
| section | 2. Preliminaries Materials
| checkpoint | 2.1 - Grout
c8d381c3-5677-5694-83c1-b21c57b0eabd | note | Reference - MRPA Quality Management Plan
619dd369-9d62-53f5-88d0-e1420f0960da | note | Acceptance Criteria - Details of the grout to be placed between the precast elements to be submitted for review to the Nominated Authority.
90526186-0ee6-588d-ba6c-0007754829d3 | textbox | Enter: Teambinder Material Approval number
dfa0979a-2190-52aa-9ce3-5f87f5abeb6a | note | Method - Document Review
d06cdcb6-ccae-52a0-89d6-699a8dc39aee | note | Frequency - Once, for each product
1323e4f6-1c4c-5ef4-a735-2be1cd1f104b | note | Category - HP
df4bc97b-9954-5a15-988f-f2e4cec31d16 | note | Responsibility - Nominated Authority
05ebd81f-6c46-5c69-a561-2a06515b588f | note | Verifying Documents - This ITP
0907ca29-effc-5d86-8b6d-c64d880a3740 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Shims
f178c70b-fed4-5cc4-a0a2-3e2137bee850 | note | Reference - MRPA Quality Management Plan
c4ea7f71-a1ee-53bb-afb0-e50e1dce4cf5 | note | Acceptance Criteria - Details of the Shims to be placed beneath the precast elements to be submitted for review to the Nominated Authority.
c242a327-be07-5dad-ba67-4e13331b8095 | textbox | Enter: Teambinder Material Approval number
aedc183a-2216-5eda-b168-84839943b329 | note | Method - Document Review
05fa81f7-214c-5b7b-aff4-d772bffd09fe | note | Frequency - Once, for each product
979fc28f-e88d-58e4-b1c7-bbc502e8ba74 | note | Category - HP
7d1f7e66-aba7-50c1-a2a2-55ed5b8a413c | note | Responsibility - Nominated Authority
18a6c869-def1-5870-8fda-a37578262ae9 | note | Verifying Documents - This ITP
09e06f68-e9c5-5a34-9f9d-3b68240d0bf6 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Bitumen Board
21e3e88d-5dd8-5761-8a8a-22660cd9c9db | note | Reference - MRPA Quality Management Plan
b9b58b7e-8769-57c3-a7a7-30afba18ac24 | note | Acceptance Criteria - Details of the Bitumen Board to be placed between the precast elements to be submitted for review to the Nominated Authority.
55fbce2c-7990-5b24-b747-767a57ac6283 | textbox | Enter: Teambinder Material Approval number
8cf47468-cb1a-5172-b455-30f29c81c098 | note | Method - Document Review
292a0c1a-452c-5f3f-b60c-e827f56a2aee | note | Frequency - Once, for each product
5a8cbdd1-a047-5898-a3cd-f218f0fa3ce2 | note | Category - HP
e8c4ff70-db77-5732-8db3-bdbf1b52d0f3 | note | Responsibility - Nominated Authority
b5932c3b-4311-5414-b81e-271818fd0486 | note | Verifying Documents - This ITP
c80d5ac7-3530-59ea-9a33-9c5117101c58 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Abelflex
38b4ff9f-7160-56dd-9aea-a46a597c1cfb | note | Reference - MRPA Quality Management Plan
b8a5d2d1-0b46-5da2-ba5d-d457e8279a76 | note | Acceptance Criteria - Details of the Abelflex to be placed between the precast elements to be submitted for review to the Nominated Authority.
14214c45-b509-5c3a-a7ea-5824990a09bc | textbox | Enter: Teambinder Material Approval number
cf4e16b1-dd4d-5d29-8db1-37d1300d3815 | note | Method - Document Review
3d07a681-fafa-5c2e-b3e3-080a59141c43 | note | Frequency - Once, for each product
77e79fe5-1c75-5b46-9c30-df5c0bf432ff | note | Category - HP
717c139c-efa1-5abc-9897-155bc48b3985 | note | Responsibility - Nominated Authority
9b4644ca-415f-588b-818a-9b1e2a7bc3b4 | note | Verifying Documents - This ITP
c37000ad-1ba4-5812-96e7-6224f438228d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Documents
| checkpoint | 3.1 - Precast Elements
d07805be-8880-518c-9200-5f32dfec4bfa | note | Reference - IFC Drawings VR 610
c508fe9c-299e-554d-a15b-e2ede3136b2a | note | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
c0e409a3-f1de-5ec3-9f5a-57372e0a384b | note | i. Certificate of Compliance / Birth Certificate
ddf3f85c-7cc6-5e1b-a617-08d402d1c9ae | note | ii. Compressive strength test results
9aee2bfb-46c9-5b15-89fc-029b8b06a4b4 | note | iii. Precast Lifting Design
251debd4-fa4f-5938-9269-c1911bd8ee53 | note | iv. Pre-pour check sheet / ITP
f2ae5362-ce4b-51b6-a125-2c1b3238125f | note | v. Post-pour check sheet / ITP
f05d37b4-e45f-59dc-93f6-e71f8623530b | note | vi. Covermeter check record
d79f9f1b-7e19-5077-b4b3-1b62579830e0 | note | vii. Record of dimensional measurements
2f3d0aef-f3fe-564e-b971-81dc98730b05 | note | All above documents are uploaded into corresponding Worklot.
ebc6ac92-729c-52e2-8393-0040347ad3ee | note | Method - Document Review
d16b979d-0c9b-5b91-9bac-219203687690 | note | Frequency - Each element
22895b96-2e7c-5c97-a4db-bd8e18203be7 | note | Category - IP
74dbed88-f264-5368-88ef-5acc5bd36b2c | note | Responsibility - PE/SE/SPE
4a96ab7d-5971-5761-98a3-9add1573f8ea | note | Verifying Documents - This ITP
a46a7a70-0fe9-5d2b-9793-a0e03a89f5dd | date | Date Completed:
| checkpoint | 3.2 - Bridge Deck / Foundation Compressive Strength
25ebcb7d-591d-5c9e-8268-e606c81bbcfa | note | Reference - 671.03
2c597354-f156-5dd2-aa68-fcccfa118b8e | note | Acceptance Criteria - For Preccast elements installed on bridge deck, check that the 7 day compressive strength as shown on the IFC Drawings has been achieved.
f2143ff4-039f-5686-87b2-58a7faf36b76 | note | Method - Document Review
c6ca7946-d0ac-5728-88e2-814f45415aec | note | Frequency - Each installation location
c5e08dd0-9eb1-5007-8f1e-c5e369841dbd | note | Category - HP*
52f8c2f7-6118-5fd8-b2c8-91cab75aa73f | note | Responsibility - SE/PE/SPE
0ec87aa1-f127-53ce-a24b-3d49a0b11344 | note | Verifying Documents - This ITP
aba0e334-dd71-55b9-a52c-1ce9b134b14f | date | Date Completed:
| section | 4. Pre-installation Activities
| checkpoint | 4.1 - IFC Drawings
e37db948-2665-50bd-9128-6abb70702539 | note | Reference - MRPA Quality Management Plan
6a0ec849-08af-56a7-b0e2-113d4adf6e37 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
b745af10-29a3-544c-aea8-152efbc1959e | note | Method - Document Review
ac430811-9391-54c0-b4a8-0f8594e6b6a1 | note | Frequency - Prior to starting Works and at regular intervals
ba528a03-ab05-5f2c-93eb-f6ea0d3deec5 | note | Category - HP*
ac5b1d0a-b9d5-5709-adb6-e33abe6180a5 | note | Responsibility - All
b78e7b1c-b70b-53b9-bc80-9ba6fc1a74b5 | note | Verifying Documents - This ITP Signed Off
0f8c14ca-4075-51d5-b2b1-33eef2018f3e | date | Date Completed:
| checkpoint | 4.2 - Survey Set-out of Precast Elements
a48747ab-b45c-59f4-92a4-ccca276aaba4 | note | Reference - IFC Drawings
ff5772f8-9349-5c04-9c87-ace9263472b8 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances.
9b63a396-4ac0-5a47-a2c1-b2e8fc445d1d | note | ○ Where anchor bolts are cast in to the concrete, ensure that these are within tolerance.
4d0dad05-753a-57d6-aee4-f6725dc943ed | note | ○ If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
e890f311-3439-54a7-93bc-35105d3b396c | note | Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
90c3e77b-0bf4-5a69-a2d0-a76dd04a881d | note | Method - Measure, Visual
b7618d06-41b0-5cea-87fc-b9b9e99b93db | note | Frequency - Each element
4fa6ddb7-a2a9-52ea-86ba-856efd6326af | note | Category - IP
3210137a-6d46-5ea0-93ab-0b5261ff2495 | note | Responsibility - Surveyor, SE/PE/SPE
13ce24e6-13c9-5e2d-b0fc-87a9ad5b742f | note | Verifying Documents - This ITP
037eea51-3acd-5c0e-a38a-ed61e3f1adb9 | date | Date Completed:
| checkpoint | 4.3 - Bearing Shims or Bearing Strip Placement or Mortar Pads
2bb11bef-286e-55a8-924a-04f6175d69a8 | note | Reference - IFC Drawings
560f2b28-fac3-589f-80a5-b9a8cdc4b642 | note | Acceptance Criteria - Place the bearing shims, strip or variety of shims to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
d502ee49-70ce-54a1-ac18-1e0046d98074 | note | Note: If the precast elements are to be grouted, the minimum and maximum thicknesses of the bearing will determine the product for the grouting activities (usually 10mm min.)
5535a376-c680-5067-b1bc-38f367cc546b | note | Method - Measure, Visual
eca329f5-e9f3-5357-a4ee-51a21572255f | note | Frequency - Where applicable, each installation location
a9fe7921-956d-58fd-888e-e12e1f672b4b | note | Category - IP
57b3b62c-d9fd-5c1f-ba5b-f3b7d6a90538 | note | Responsibility - Surveyor, SE/PE/SPE
e5b3fdef-65d7-5eea-a8b0-5eef3a1d34ec | note | Verifying Documents - This ITP
45d8d7ea-6a23-5b8e-880e-a84c05f22bcd | date | Date Completed:
| checkpoint | 4.4 - Bitumen Board and Ableflex placement
cede9589-61c7-5871-abfb-cc552eab3b5a | note | Reference - IFC Drawings
32e2dda7-3552-58b5-96ea-d20111c42931 | note | Acceptance Criteria - Adhere any bitumen impregnated fibre-board and ableflex into the positions shown on the IFC Drawings and where grout or concrete ingress will affect the end use (such as around conduits).
39b9c2d0-b2e6-56ab-9036-a39154ade0ea | note | Method - Measure, Visual
6312929f-2d1a-5756-a116-5e2f74fbb9cb | note | Frequency - Where applicable, each installation location
1920d53a-c5ff-58e2-bc49-4b811abbb173 | note | Category - IP
8d6f5d5c-dfff-5dcb-86b2-a71269f9e0d5 | note | Responsibility - Surveyor, SE/PE/SPE
009af049-21b5-572f-b2bb-540954eb21cb | note | Verifying Documents - This ITP
db836cb4-8e42-5ac2-ab8a-8ccd529377aa | date | Date Completed:
| checkpoint | 4.5 - Precast kerbs roughened surface
604639ae-b4dd-5ffe-8a79-eb385a0f1ecc | note | Reference - IFC Drawings Section 610.20
7fca641c-2afe-5e4f-bd85-61f63a318825 | note | Acceptance Criteria - Roughened surface means concrete surface shall be roughned as construction joint in accordance with IFC drawings and VR Section 610.20
2c93be35-48a3-5bf4-994a-c965d472bec3 | note | Method - Visual
d350928f-2a9f-5ff6-aae8-93cfb9dbc541 | note | Frequency - Each element
7271d59c-ff5e-579e-8472-d8e5e809be25 | note | Category - IP
cb29ff7e-ce3b-5f78-a22a-9c294cfea18d | note | Responsibility - Surveyor, SE/PE/SPE
4a3b3760-2a2c-54fc-bb78-8de2fcb3202f | note | Verifying Documents - This ITP Signed Off
ac8928c1-429e-55ec-9782-f1cc6c0a6d42 | date | Date Completed:
| section | 5. Installation Activities
| checkpoint | 5.1 - Precast Handling
1b05d33c-5e30-5d5b-b9d3-cb7aea2f68c8 | note | Reference - 620.07 Crane Lift Study
8b5235d5-ff31-55b2-a3a4-6a04f0a2e4ad | note | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
2ffdb81b-fee6-5a86-aa0d-db6a098000d6 | note | Method - Visual
c57a54d9-1b01-586b-a6fc-ef33eb0c52df | note | Frequency - Each element
535d1f66-43a5-58ad-8005-a2dbb480f07a | note | Category - IP
9b33ff38-2182-5bb1-ae84-20f04a738d9a | note | Responsibility - SE/PE/SPE
5795b6d1-bb15-567e-96c0-d7e69da033d5 | note | Verifying Documents - This ITP
815d4b7d-c0e1-5fcc-b72e-ffce79be8880 | date | Date Completed:
| checkpoint | 5.2 - Precast Placement
09287f00-8b53-5976-9337-41143fbc46f1 | note | Reference - IFC Drawings VR 670.05
5e0df7b1-5013-5998-8919-c8cdb417513f | note | Acceptance Criteria - Precast elements shall be placed onto the bearing shims and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
6a735383-c07e-5004-b306-cfe0f3c8ddf4 | note | Adjustments to be made to achieve following tolerances:
4fbfaec4-dc2e-5cf6-a245-f522a807d909 | note | (a) Departure from plan position .... 25mm
a53e3333-00a6-57cb-bec2-a73dc738a7e8 | note | (b) Departure from alignment ........ 5mm
abb86bb6-383b-5a47-a940-2c7b1f1a12fa | note | (c) Irregularities in alignment ......... 3mm in 3m
56d59de2-f16d-59dc-9e35-5a386a877379 | note | (d) Variation in joint gap width ....... 3mm
019b0ed9-1e36-57f3-8dd6-f4e336f0d342 | note | (e) Vertically of posts, panels, balusters and openings ... 2mm
cbd38737-91a2-5213-baa1-e6ee812fbcd1 | note | ○ The nominal gap between elements is as per the IFC Drawings.
08d2951a-0fa7-5881-81b7-10df7c63b578 | note | Method - Measure, Visual
f0778c63-c904-5455-a04b-f7e153be66d5 | note | Frequency - Each element
ea1ebd64-c37d-50f1-9f3b-0c6bef2e6424 | note | Category - IP
3ce0406c-f01b-5969-8d85-f6dda85847cd | note | Responsibility - Surveyor, SE/PE/SPE
62cca861-2810-5909-883d-007f3fdfa3a4 | note | Verifying Documents - This ITP
d991d9c3-cf97-5b7a-98b2-ac1a407feadc | date | Date Completed:
| checkpoint | 5.3 - Hold-down Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
1819b323-7a0b-5794-8379-a43e5ca2c7ab | note | Reference - IFC Drawings 630.20 (a) & (c) AS5131 Clause 8.3
067993dc-7c87-5cae-b4f2-efdbfcbe8e3c | note | Acceptance Criteria - Place washers and nuts onto the embedded thread as detailed on the IFC Drawings.
cac3936e-049c-5b18-b35e-2c75bb294153 | note | ○ Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
db5a2d51-c086-5d3d-b1fd-e98402ed3ace | note | ○ Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
d0e8018c-887b-546b-9a8f-b2c8cb11b3d4 | note | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
77539608-2b04-53d6-a288-62ef5f645722 | note | Method - Visual
f619ad8e-9b34-560f-8d86-56d868970f3d | note | Frequency - Where applicable, each bolted connection
38eaa1e8-5485-54d7-ba1a-77d92ecdab4a | note | Category - IP
aaa4dc79-66da-55ed-9820-3c6a5303c6e9 | note | Responsibility - SE/PE/SPE
75d0b9ac-9ac5-58e4-afa3-1c284bf97715 | note | Verifying Documents - This ITP
f86bc712-e3b0-51d4-a0ce-6331e9e21161 | date | Date Completed:
| checkpoint | 5.4 - Precast Traceability
f57ab36e-fa41-533c-af8e-2aca81cb706d | note | Reference - 620.09
855415d0-324e-56da-bb43-24f196d348dd | note | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
018c7c76-1693-560b-8dc7-0d8308351e61 | note | Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
cf6b1ecb-fc6c-5c78-9125-acf056b1e7fc | note | Method - Visual
63584100-4f9b-5094-92f5-aa34de8df9b5 | note | Frequency - Each element
c5bd0559-8955-5c80-8942-610181b4210f | note | Category - IP
d2dc337c-25e5-53c1-8e36-d09558e21c21 | note | Responsibility - SE/PE/SPE
c63867e8-b7d9-54c1-a8c1-1bd784eb995b | note | Verifying Documents - This ITP
bfde12e4-6966-5408-90e6-eab6ef5b525b | date | Date Completed:
| section | 6. Post-installation Activities
| checkpoint | 6.1 - As-built Survey
6391522d-8675-5de3-9ef9-455f4752ee2b | note | Reference - IFC Drawings VR 670.05
40f36976-ae58-56ce-9b23-cc3cacdc3966 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per VR 670.05
9ead845a-4420-514c-b706-6ee5feef7412 | note | (a) Departure from plan position: 25 mm
53bd0c4d-c12e-5111-86d1-74937de01e1a | note | (b) Departure from alignment: 5 mm
98a83268-a7a2-5183-9f6f-e227811eab67 | note | (c) Irregularities in alignment 3 mm in 3 m
ac36c247-edca-53e8-86a4-aa58dd3a15f9 | note | (d) Variation in joint gap width 3 mm
a99f9905-8064-5e3c-a030-54f929687048 | note | (e) Verticality of posts, panels, balusters and openings ±2 mm
7d6a32ba-4059-574f-8b3e-7f872aa7cd20 | note | Attach: Survey As-builts / Survey Report
ea8ed7cb-4dea-58d2-8e7b-fe5ea5a32e2f | note | Method - Document Review
783a39e2-b346-5f38-8490-9a9569294984 | note | Frequency - Each element
0d5354f8-1c12-5c32-9733-7dfa866010a3 | note | Category - IP
1bace8ee-fd6b-5618-8faa-c06420d6b3f6 | note | Responsibility - Surveyor, SE/PE/SPE
8a55d85b-b889-58ca-bbc4-800a7e38f7d5 | note | Verifying Documents - This ITP
de0445fe-e505-5dcf-bd39-d74acae4851c | date | Date Completed:
| checkpoint | 6.2 - Non-conformance Report (NCR) Closure
d94c852a-a02e-54f5-bf3c-dc1d6191c2e8 | note | Reference - MRPA Quality Management Plan
a75337cb-98b0-5ff1-92e5-39db13135af2 | note | Method - Document Review
62c989ec-cdb1-515b-ab5f-58567acf4e85 | note | Frequency - Once, prior to closure of this lot / element / Work area
6a9c1117-dc1c-5dae-9e4a-83973aed63bd | note | Category - HP*
a14fc6db-799e-5881-aa03-68ae06d92059 | note | Responsibility - SE/PE/SPE
25acb7a9-c4a7-580b-9590-e3fe85648549 | note | Verifying Documents - This ITP
c7808271-5247-568c-a6d2-4250fd9cf123 | date | Date Completed:
| checkpoint | Final Inspection
f12f50b2-c77d-5a98-b848-4989b4be79f3 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
40a2eb17-650f-5c71-bf39-8e87ef3d6538 | textbox | Name:
fd402052-0efe-5e9f-a365-10cc009651ee | textbox | Position:
9597eef7-0f27-542a-a396-490dd82acaf2 | date | Date Completed:
| signoff | Sign ITP