## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
cefcbe1f-3776-4bf7-bcd1-cfc1f9fcea98 | checklist | Add Daily Work Task Report |  | Daily Work Task Report -
2a079a0f-3aa9-4e01-8fd1-82c59006897a | checkpoint-no-value | All Work tasks instructed by icon/airport Supervisor
4d7dc096-6e00-5496-adfc-64b8b2007de5 | textbox | Work Task:
ce3afd7b-1ab6-5bfa-bc47-6b1a6781e3ac | textbox | Working area:
e78b928a-fb45-574b-8997-77b7dfcf770c | textbox | Worker:
2233e4e1-8e64-4ee3-abf4-25a94d611b44 | checkpoint | 1. Safety requirement
8498e5f5-8f7d-5e92-a282-59bc02e92384 | note | Create a safe working area
2b8adb10-353d-5322-b394-ea96e0b1f227 | note | – Use roadblock to create working area
14b8dd2f-41f9-5438-bea7-f55cd04987e4 | note | – One worker on each side of working area for Passenger traffic control
02c47dc6-932e-4a34-b5e5-dad006237093 | checkpoint | 2. Task
d496538c-14a5-5e4a-8f4e-1cf34edb60f7 | textbox | 2.1
3fa85dfe-a0be-5bb6-bd76-83c138c0aa50 | textbox | 2.2
1066eedd-7821-5705-8777-dfa421af6ca6 | textbox | 2.3
77c5f55e-505b-5e60-88d7-16678b7d7211 | textbox | 2.4
b7ade1d3-1e4e-541d-9215-230768c459f4 | textbox | 2.5
d980d9a1-072c-5496-be83-789302064e31 | textbox | 2.6
838529fb-6c58-5874-866c-aaeeb8e8efea | textbox | 2.7
794fd4d0-9009-5d21-a055-eee00d82d53b | textbox | 2.8
b01b33e1-7729-5c29-b01a-af553df6b513 | textbox | 2.9
e55c9cd2-2191-504e-9c80-f51c80b48651 | textbox | 2.10
8a14dfac-e9a9-4c2a-9e5d-c58a7d9f06b0 | checkpoint | 3. Housekeeping
800d6dfb-c545-5af8-954e-db71d76dce32 | note | Requirements before finishing a working area
a7840a1a-1f3d-50e1-a2d5-ec9ce26ce58e | note | – Housekeeping (vacuum, Secure all the tools)
c47d02de-532c-52d6-82c2-8012e14984e0 | note | – Permission from Supervisor to move out and into new area
31ee3d39-8a62-4ca7-a770-1c4afd15811b | checkpoint | 4. Airport supervisor to inspect
09aaf97d-72a6-42fe-8798-827d7e7c7cfa | checkpoint | 5. Complete on site requirement as Instructed IF NEEDED
42eedbf1-814f-4af7-b12e-484847090f3d | checkpoint | 6. Picture attached below includes
b626507e-9171-536b-93e3-c849a7ee0f50 | note | Picture record: Before work, Operating work, Work completed AND confirmed by airport supervisor
d0a8b08d-073c-4e7d-ae87-add94f3cc9ef | checklist | Add Pre-start Checklist |  | Pre-start Checklist
c9735dd3-fc3e-456b-a332-4b93662fd835 | checkpoint | Hand over from previous trade received
0d137910-cd1f-43fc-ba11-c3358c1e7a88 | checkpoint | Work area is clean and free of debris
a339afad-90e1-41dd-8770-53f8bf5c8299 | checkpoint | Work area has grid lines and RL supplied
452885bd-9b07-40a9-bbc6-59cf7558a65b | checkpoint | Access to work area is available
a976f604-2089-48a2-9683-65b523b323be | checklist | Add Variation |  | Variation Details -
8481a8f7-b962-4973-a954-025de696d655 | checkpoint | Variation Details Approved
28d26279-c304-4689-8317-1deb797dc8fe | textbox | Reference/Drawing/Instruction Number
2247155b-6de8-434c-a1e1-058d724a6a62 | textbox | Variation Area
ae7fc046-dca9-4fab-98f8-374caeb044ec | textbox | Materials & labour breakdown
b64f9997-0323-43d1-9efc-67d1c77303a1 | signoff | Request Variation Acknowledgement
0c83b247-771f-45e5-86aa-f94e000b0883 | checkpoint | Variation Completed
92578560-2aaf-4f48-b2c6-4d7b3bdf4bf4 | signoff | Request Variation Signoff
225baf7b-630b-4198-b43f-42515d213bfe | checklist | Carpentry - Architrave |  | Carpentry - Architrave
b537f72c-326e-4313-a571-76619e2afca9 | checkpoint | Level and Flush with walls
a46743eb-01a4-47d0-8cc3-6cc4a1c84def | checkpoint | Gaps and joints angle are acceptable
4c2082bd-fe0c-436a-a0ed-9b8fc14ec9c6 | checkpoint | Silicon and finishing nails have been used correctly
fc183d3c-7ee4-46ea-9e8d-09f34ddfb37b | checklist | Carpentry - Cavity Installation |  | Carpentry - Cavity Installation
e634d078-515f-4f4b-b940-ddcfb2e68cef | checkpoint | Spec followed for timber type
2bbf1ef3-96f5-4b9b-a687-bc91c11833d0 | checkpoint | Flashings Installed ( Tape with aluband)
65ffaf2f-15cc-5018-8739-d7ea9e652ed8 | textbox | ( Please note flashings )
0d79e28e-eab9-4f6a-bbaf-f5422d3d1a48 | checkpoint | Ventstrip Install
3c92e802-1639-43df-a36b-2e4ebca5d288 | checkpoint | Cavity batterns fixed plumb
88d77b7f-c4dc-44d8-8c33-e64e8858e975 | checkpoint | Cavity batterns at correct Centres
ae6e6e84-f25c-4680-b3e5-e7e9f583d4fa | checkpoint | Signed off ready for Board/Cladding
7c056739-dcb4-49ab-a583-52a8539cf95f | checklist | Carpentry - Cedar Cladding |  | Carpentry - Cedar Cladding
b96a1cc4-4d09-4a45-960e-59d1989b436f | checkpoint | Cavity Inspected and passed
d2ca4e22-727d-43bd-a2cf-1d92f1d64d55 | checkpoint | Datums set correctly
76b2bbbb-e24c-462d-b33b-39afb818c970 | checkpoint | All flashings and penetrations set and sealed
ad7057f7-20f8-4916-a159-18bc124ed9d6 | checkpoint | Corners formed correctly
f4398403-6b76-4892-8b75-37fb19ae3cbf | checkpoint | Joints formed correctly
327196ff-adf5-4c96-b19d-c68e47745651 | checkpoint | Nailed in alignment
e51fc926-3127-4bdb-937b-c8e63aa5867c | checkpoint | Drip Edges Straight
4f48403e-d3da-48f3-af09-f24b18c724d4 | checkpoint | Painting to exposed edges
2e66ffa8-a6f0-4bbb-be65-6b853240ce32 | checkpoint | Cedar complete
6aca0379-6798-41ab-80b3-89cbdd7394c5 | checklist | Carpentry - Doors |  | Carpentry - Doors
6e45bc3e-040c-4ec1-bd9b-6044f1eb9859 | checkpoint | Direction of door correct
ad51b677-9038-49f5-abe4-418d505433ff | checkpoint | Plumb of door jamb
380609b6-6bf1-41f6-8019-166e0b6ce267 | checkpoint | Door gap on both sides
eaadd273-4fc0-4ade-9991-db963da08c6d | checkpoint | Door hinges in place with screw
82d7a6cc-3529-401a-891a-2ef919429553 | checkpoint | Floor clearance correct
b34ee8a4-0f96-4217-a6d1-4b4d6a354d0f | checklist | Carpentry - External Framing |  | Carpentry - External Framing
41c22232-95d3-440e-93e8-353216ba83b7 | checkpoint | Plans / Specs followed and correct type of timber used
b34a78b1-1882-499f-a90e-d8da67e55d7b | checkpoint | Check for location
500ecf83-562e-43c9-8a51-49072156b82e | checkpoint | Bolted at correct centres (please indicate)
afd76b28-49c7-4d9d-809e-2b3319a83897 | checkpoint | Studs installed (Plumb)
70c0cd2f-9cf4-45a9-bdad-1a98f42f6afc | checkpoint | Nogs installed (Level)
7ddccf53-0201-407b-9253-5f16cbb21b64 | checkpoint | Correct head detail
1c505db4-f36f-4b8f-8e63-0153a7a0c743 | checkpoint | Correct centres (please indicate)
2472b9a1-2fea-417a-90b8-d004479009be | checkpoint | Check for Straight
ffce6cee-5e42-4549-a53d-d93a25751e8a | checkpoint | Check for Level
c3aae3aa-0371-45bd-8434-16bdcdd5589c | checkpoint | Seismic/Engineer details apply
2e96964e-450b-4e92-bff7-d3edf9d6eed1 | checklist | Carpentry - Insulation |  | Carpentry - Insulation
a002f8cb-574b-492a-9273-8aa506103355 | checkpoint | Area tidy and accessible
72f5e4fe-35ef-4d19-bac6-47c9e81a77c3 | checkpoint | Plans / Specs followed
3dbbdf49-7866-4415-9e6c-380d50def587 | checkpoint | Friction fitted
e0c5f98c-89ac-49fe-bc22-bc1656d47db4 | checkpoint | No gaps in product
1c6eb80c-6fd4-4134-9451-c70b0905657b | checkpoint | No bulging
a1dd5de2-93ff-4078-a709-7dfb79faa88c | checkpoint | No Compression
994885d1-277a-445c-97c9-6969d8fb7198 | checkpoint | Area left tidy and accessible
dffdf62f-ca70-4996-a946-dd20fd390876 | checklist | Carpentry - Internal Framing |  | Carpentry - Internal Framing
4595cefd-48a3-4194-b640-fa31013b5b96 | checkpoint | Plans / Specs followed and correct type of timber used
5f9d47ee-be9e-4f5b-b091-2442fc0f0b50 | checkpoint | Check for location
611e4db3-ad52-4624-a2cd-c9ef715d9f49 | checkpoint | Bolted at correct centres (please indicate)
97bc7676-4a5a-412a-af45-faf2cbc63d40 | checkpoint | Studs installed (Plumb)
584b51b3-384c-482a-8b01-b0d87dd97d2a | checkpoint | Nogs installed (Level)
a2349d49-d014-445e-925f-6157a0c4f9e8 | checkpoint | Correct centres (please indicate)
4883c6c6-4b88-4eba-8d02-e17359ca8cb7 | checkpoint | Check for Straight
ffccee40-5ff6-42fc-a324-a4e332cc2935 | checkpoint | Check for Level
0fdeb5b4-c588-4ed9-9e31-4cc1fd5d7d2b | checkpoint | Seismic/Engineer details apply
97e9084f-9c5b-4e55-a7ec-87daca1633b8 | checklist | Carpentry - RAB |  | Carpentry - RAB
30e339fc-82b9-41a0-ae22-ea584adf71e4 | checkpoint | Plans / specs followed
d75ba0ca-9c50-4cee-828a-17c12766e7ac | checkpoint | Flashings in place
da71ec9d-3f90-4061-86a2-999a58bdf4bb | checkpoint | Sheet neatly cut and 1-2mm gaps at join
40d163ce-d40d-49f1-9b94-e4d06a484a16 | checkpoint | Correct nails / nailing pattern
b6b66caf-73ae-4c70-b82c-3ff4dd10df2a | checkpoint | All nails flat and not puncturing board
82fba127-713e-443f-b105-57cb7744f3f3 | checkpoint | Taped / Sealed
a4726eb8-2d91-415e-8445-a0e9c60e70c3 | checkpoint | Area RAB complete
d17fea36-c373-49c1-8adc-2d6cc22d13ef | checklist | Carpentry - Roof |  | Carpentry - Roof
8ef38a68-c809-46cc-8360-47e5d29f4f00 | checkpoint | All relevant drawings and revision numbers checked and attached/referenced
5b49d21e-0567-44c3-a9db-61e85431eaf9 | checkpoint | Timber treatment correct as per spec
7274599d-1c36-44e9-920f-914d0db0f328 | checkpoint | Timber spacings are correct
77732506-07dc-4746-8e77-280bdacd43d0 | checkpoint | Fixings installed with correct fixing pattern
ec829757-cc06-43dc-8717-e555b3f2d945 | checkpoint | Insulation installed
bd297ad9-f3ef-4cbf-bf3e-204c6ed83830 | checkpoint | Plywood is correct thickness
890b6bb1-df1b-461f-ab48-de1e605d9dd1 | checkpoint | Fixings installed with correct fixing pattern
64ab8a82-7e34-45a6-8a43-87df39ac042c | checkpoint | Correct screws used
cc1cd439-a988-4bbc-b195-ada12d4f531c | checkpoint | Correct adhesive used
e16bc7ae-6ec3-4b07-908a-ac2a5c6e8dd5 | checkpoint | Sheets installed in staggered pattern
ac0a0d14-0005-460d-a4ca-bdbcc31d0269 | checkpoint | No gaps between sheets
8098d7f8-7d3e-4840-aef7-6f01235d4d36 | checkpoint | Installation completed correctly within tolerance in respective area
a6bcbbd3-afa0-4885-918b-8df6bd329c45 | checklist | Carpentry - Roof & Gutter Framing |  | Carpentry - Roof & Gutter Framing
f11f9d7d-3451-4db9-8d56-055174025c28 | checkpoint | Plans / Specs followed and correct type of timber used
f37d2286-4b6b-4954-b63a-23cdc3ff7850 | checkpoint | Rafters at correct locations
81accf3f-0509-4ab5-af39-ca679fb2327c | checkpoint | Engineer details followed including brackets
10c58f14-6ed3-4c23-baaf-a395f08bd645 | checkpoint | Gutter Falls to correct location
8386dd71-e120-45b0-abbe-e6117d8a6418 | checkpoint | 3mm gaps in Ply
0ae74a77-e972-4600-87d9-f5929bc9fe51 | checkpoint | Sumps formed correctly
a7ccdbe8-3f24-4aef-a9a5-a487c52c1fa1 | checklist | Carpentry - Roof Subframe |  | Carpentry - Roof Subframe
2541c4c8-a343-43ad-ba7f-b50c3731e5c5 | checkpoint | Area tidy and accessible
e0a2fb85-b6f1-45e7-b201-0c5f9a3a8f45 | checkpoint | Rafters at 400c / Nogs 400c
06da0b51-39e2-44a8-b5f4-bd8f22ba832c | checkpoint | Hexagon Mesh fixed
dfa2d8f2-408e-4e83-9221-7ad1b383715b | checkpoint | All brackets / hold downs fixed
aa83ba40-36c1-465d-9812-5b0f044525f3 | checkpoint | Insulation and friction fitted ready for ply. Photos must be taken
21672bdd-2a61-4ba2-a71e-ca04540a670b | checkpoint | Ply fixed for membrane following manufacturers recommendations
560f4f03-2a04-45e6-b2b9-d026072af36c | checkpoint | Area complete ready for taping
7ea99a5b-7b76-421a-a5c5-bd8c841951b9 | checkpoint | Area left tidy and accessible
b004cd49-8823-4fbb-affe-eb9790b1a37a | checklist | Carpentry - Soffits |  | Carpentry - Soffits
d3fc11c6-99c8-4042-941b-4f6983f1c9c4 | checkpoint | All Specs for timber followed
f908c433-bc1f-432d-9901-19e9a8af7a97 | checkpoint | Soffits to correct RL/Fascias installed neatly and pre primed
082a6738-ba27-413e-a991-369c77163d5f | checkpoint | Bulkheads at correct location
c988f9e3-8a90-4af7-88f2-f82853f4ab56 | checkpoint | Soffits lined with correct board
f6c082c4-ce25-49a6-94e6-7022bc6a7c1b | checkpoint | All plastering complete
b43ccd66-409c-47bb-abe1-d051da15afa8 | checkpoint | Ready for paint
9636a3b9-ba8f-4237-982d-6490f208ca74 | checklist | Carpentry - Steel Stud |  | Carpentry - Steel Stud
106f818d-1701-4936-8ded-14114669e6cd | checkpoint | Area ready for Steel Stud install
72904ef6-1e10-4422-894b-90ed10495f4b | checkpoint | Dimensions / locations checked and accurate
0b457778-3ac3-4d1f-8caf-d9b6c4f021c2 | checkpoint | All frames are square, straight and level
2ebdd4cc-384c-45fc-815a-239c50ba9bdc | checkpoint | Fixings are correct
b6ff6671-d778-46ce-95c6-b97b6cc30785 | checkpoint | Any bracing requirements installed
b0896a1b-8311-4a35-906b-96583a31832c | checkpoint | Fire rating elements installed as per spec
98945645-62f9-4dd9-930e-2dbcd1bc4600 | checkpoint | Nogs / service nogs installed correctly as per plan
44129e7c-f315-4e67-9bd1-f3a55a10893f | checkpoint | All Steel Stud completed correctly within tolerance in area
4fbd058c-43db-4004-8706-9f8227b7cce2 | checklist | Carpentry - Subfloor |  | Carpentry - Subfloor
59414ed2-92cd-4ddf-a5eb-ab265c596315 | checkpoint | Beams in correct location
956bde2d-8236-49d1-8c36-02f03ee41447 | checkpoint | Timber treatment correct
8a53ae40-5b32-403b-a08c-7a4946c65769 | checkpoint | Timber joists installed - sizes / spans
e5da9925-964b-493e-b237-a4aaf2a5db65 | checkpoint | Joist / notches / holes
732bc17b-c8c5-4494-ab68-7d9379db4a0e | checkpoint | All mechanical connections complete
27e2b542-d7d5-5724-b656-8d4dc91ff340 | textbox | Type
c8150466-ff77-47b6-bb14-35b5d15795df | checkpoint | All nogs and blocking complete
0ff7d957-5e99-4391-9e20-5db94b79c6f4 | checkpoint | Plywood fixed (braces / flooring)
56dbac7e-2412-426e-bef0-f9b1365075ce | checkpoint | Correct fixings are being used
9a02f891-dd5a-403c-976f-1f7539150d45 | checkpoint | Is the flooring glued and nailed/screwed to the joists?
67b45fe5-435f-40ea-b58c-daa010d83720 | checkpoint | Correct screw pattern
a4316176-0f15-4f95-a3fd-2ca996f99a0c | checkpoint | Floor framing and flooring complete
3cb5f286-00f8-4525-8d6e-fc6891ee5764 | checkpoint | Control joints installed as per design
6606d8ed-46c7-4691-8b10-7a5851fb2070 | checklist | Carpentry - Timber Floors |  | Carpentry - Timber Floors
202e7fa8-5a1e-458e-8d8b-41d0bbf75805 | checkpoint | Bearers installed
25379e15-1ac4-4b39-9845-87a7e1a96455 | checkpoint | Floor Joists Installed
9f676d26-1e6b-4a95-93a6-8c778cf3dc46 | checkpoint | Engineer Details followed
862ee543-1c8a-42a4-b078-e0de05391ff2 | checkpoint | Flooring Installed
9dd312c4-7b27-4c66-9bf2-565fc8768dcd | checkpoint | Flooring Complete
2d42b22f-b1d7-4d2f-b6a9-05cfb2af4aeb | checklist | Carpentry - Timber Joist |  | Carpentry - Timber Joist
c23a534a-69ce-442a-86ed-f38f128f9e01 | checkpoint | All relevant drawings and revision numbers checked and attached
42fa926d-edb9-4382-8bf0-3b6519d6345b | checkpoint | Barriers in correct height
55a711fd-dfee-45db-9d9a-fb3491ad1ad2 | checkpoint | Timber size / treatment correct
ee055f23-141e-4f54-8b38-a8a52253db23 | checkpoint | Joists are installed at correct centres
55d555b8-f72b-4752-8472-367381458326 | checkpoint | Solid timber blockings are installed at correct centres
468d5271-d0cc-483b-bca3-3f4149fc6d13 | checkpoint | Correct fixings being used – joist hangers / nailon plates / nails / bolts / washers
eb93482d-d666-47a1-a4b5-bbbd83266ed5 | checklist | Carpentry - Trims |  | Carpentry - Trims
71d95bdc-2195-47a6-bd74-8ae16071dd33 | checkpoint | Correct trim used
1bfcbe52-4e3d-4b9b-9060-80c19637be65 | checkpoint | All internal comers scribed
c42dfbdc-2788-4f3e-a210-f89a9c3f29f6 | checkpoint | Adhesive applied to skirting
ee3a8747-e97c-4de6-a072-ef5346a2543f | checkpoint | All external comers neat
69c3704e-fdef-4ad7-a2e2-edeeb167e5f4 | checkpoint | Skirting fixed correctly and all edges sanded
9888f5e2-6d2d-438b-9e75-6a5caf1cd5ab | checkpoint | Areas complete ready for paint
d6abb7ab-568f-4ca6-b2d5-635fc1d02fb9 | checklist | Carpentry - Trusses Checklist |  | Carpentry - Trusses Checklist
447bdfe0-841d-4638-8733-25ec0875d3f2 | checkpoint | Truss locations checked, correct and approved as per latest revised drawing
a4376260-1825-4d2a-89d5-97ed1566319f | checkpoint | Hardware fixings checked and correct
f74580f1-f070-4d4e-bdd4-6a66f39eaa81 | checkpoint | All openings (doors / windows etc) checked, correct and approved
dd1ae7d3-1132-4bcd-877b-8c049f00cb70 | checkpoint | Truss checked (straight and plumb) and within tolerance
9943dd14-3add-438d-bdc3-486eeadac586 | checkpoint | All relevant nogs (service and special/fixtures) installed, checked and correct
d221734c-f264-5ec6-8773-2c64c1c74144 | tickbox | Service nogs checked and approved
3e5fca2c-d9ba-5ef8-afa0-6c9a9f4e5ffe | tickbox | All other nogs checked and approved
14c2c295-1471-4d69-8d14-20b1879775ce | checkpoint | All truss installation checks completed & inspections carried out
978509cf-1688-466c-ac5d-8b901acfeb74 | checklist | Carpentry - Weatherboards |  | Carpentry - Weatherboards
6c62cd73-92b0-4c6b-ba09-0899d3166766 | checkpoint | Plans/Specs followed
74b0f31c-46b9-4a85-bc0f-2ddca18524e7 | checkpoint | Datums for weatherboards set correctly
be85d071-a99d-4571-b6c5-324eea4f4b94 | checkpoint | Weatherboards cut with primed ends
9a2ba9f9-03fa-4d9a-b891-ccc033c0a9a5 | checkpoint | Installed and Nailed to every Stud location with Stainless Stud R Jolt
0a159f97-3a63-4270-9ea4-63fb78ee7292 | checkpoint | Scribers/soakers installed
236a0826-dd74-441c-81de-c5d2dede73a1 | checkpoint | Sealant applied
1b856b6d-2295-4b86-965b-73d0bf98b2b2 | checkpoint | Area complete
e947a359-44ac-434e-8d43-d6a73acb4504 | checklist | Carpentry - Wraps/Tape Install |  | Carpentry - Wraps/Tape Install
fe03863c-d9bb-4808-9ef6-7652ffe3c61d | checkpoint | Plans / Specs followed and correct type of paper/wraps used
28a0fe3a-8d44-4010-8f1c-48005ef4b670 | checkpoint | Paper install level
5c708eb6-f0ab-444f-a413-9e2a8f412f96 | checkpoint | Packing tape applied
1a28b293-98e9-4df7-b3d8-798b6c3a6f9e | checkpoint | All Flashing Tape installed prior taped onto paper
192ba230-5e87-4b8d-ab59-615b3cb674a3 | checkpoint | All tapes applied around window
78325fec-ed79-4ca7-a927-c2349c9671e4 | checklist | Carpentry - Wrapshield |  | Carpentry - Wrapshield
a8f89f14-9eef-4de6-8c60-0a89599d9922 | checkpoint | Area tidy and accessible
3d9dadcb-ca86-4974-bb7b-081a4f829671 | checkpoint | All surfaces clean of debris and dry at install
cbfe7da1-15d4-4964-b6b6-1e7fa8a588ef | checkpoint | Method of direction ok
19d90afe-0d63-414d-8778-1905782548e7 | checkpoint | All laps 6 inches horizontally 3 inches vertically
96f46489-3f26-448e-a343-b5956289841b | checkpoint | Vertical Seams Staggered
b7e1488c-34cf-451c-beda-da6fb393c35b | checkpoint | Roller used for Adhesion at seams
84af65a3-a987-4b20-af63-d835fcf5ab3c | checkpoint | Penetrations sealed
a45adce7-2d6b-472b-8669-92fbbada4e03 | checklist | Carpentry Wall Strapping |  | Carpentry Wall Strapping
631dd811-8f95-41d2-adc9-7a6c1773fef1 | checkpoint | Has PC panel issued QA and handed over
5309ca87-dbb4-4a43-b1fa-774833d7445b | checkpoint | Has PC panel surface been spot checked and achieved stander
8aac8f0a-599c-4b3e-a11a-a40511f7bbe0 | checkpoint | Have the strapping been installed correctly & straight?
9150dd36-dfd4-4c9b-ad1c-e6e2f50d522a | checkpoint | Has the stapping been installed plumb & in line?
fc48132a-ccea-4bea-bbce-f8220bdbabe7 | checkpoint | Has the stapping been installed in right spacing?
2f579189-b517-45cf-a746-7d1d6b878bcd | checkpoint | Has strapping used right fixing?
51f9dc85-85da-4306-a7cb-56817516299f | checkpoint | Has the timber nogs been install on bottom, celeing height and top
d731eb5b-f63a-4e42-aee6-80102c11ec34 | checkpoint | Has the strapping timber followed window or door structure opening?
e5620ff1-110d-47b6-9818-211224a54fee | checkpoint | Has DPC been installed in between timber and pc panel ?
f03ea428-cc05-4979-832d-cce32fe2b82d | checkpoint | Has all the service nogs been installed in right place?
9fa6d83e-cac3-42dd-a1bc-e2463fb77893 | checkpoint | Has a pre-line inspection been completed by ACC?
49ca6fd1-591f-4c2b-a3d1-60f41d8953cd | checklist | Ceiling - Ceiling Grid |  | Ceiling - Ceiling Grid
16c6d4a5-a423-49c7-98c7-f6d2977666d1 | checkpoint | Substrate correct (nogging installed if required)
3897df78-9eab-4e6e-81e8-49ab0c3fc469 | checkpoint | Ceiling Grid installed level and to correct heights
40facdf7-5f11-44bf-9aa9-9c391508c570 | checkpoint | Correct fixings and number of fixings
4f55c4b0-50ca-49a8-a4b2-40ec044ec45a | checkpoint | Member centres correct
808bd480-6972-408c-9b43-9fe7f9a2fed0 | checkpoint | Correct Clips installed
4a4ceb12-318b-4724-a3e4-3395a703ebd7 | checkpoint | Earth strap installed
84bd27f3-1738-4491-bc35-1426d0c48bc0 | checkpoint | Hatches openings trimmed out and installed
60a26f60-27cc-45c0-b65b-3f900f8de12d | checkpoint | Bulkheads installed plumb/level/square
2b54affd-bea5-42b6-8130-752bab8cfcaa | checkpoint | Ceiling Grid completed correctly, checked & reviewed - as per specification
69121335-6dbb-4266-8aa7-76f14bd20d4b | checklist | Ceiling - Ceiling Tile |  | Ceiling - Ceiling Tile
6c2fa7ad-4c61-4949-91a0-51a33d146dbc | checkpoint | Correct tiles installed as per design
b6dbb082-a09e-459f-91c3-88e98ee77b5f | checkpoint | All tiles installed and sitting flat
1d56f9f6-f338-499d-abcf-05e4f58410e1 | checkpoint | Cuts complete and accurate
f1908ac4-1002-499b-aa69-13fc1d3c147c | checkpoint | Correct clearance/cutouts around penetrations
a0c0fa7a-6859-41a3-801b-7071fda956ea | checkpoint | All tiles installed, mark/damage free and area completed to required specification (attach relevant photos)
eb0bc950-576d-4afe-8004-5e2139cc7290 | checklist | Ceiling - GIB Lining |  | Ceiling - GIB Lining
6fb48865-aa53-4ba6-8621-002f6c9bcf84 | checkpoint | Area ready for GIB install
5a6adfea-44f9-4dc4-b160-06f79160797c | checkpoint | Correct lining checked and approved and area specifics checked
7fd9d699-ebc7-4658-b3d4-1ca65cc54542 | checkpoint | Correct fixings used and installed at correct centres
6eb14df2-0d5f-4cdc-b07d-ff9c6825f096 | checkpoint | Sealant applied as per spec
896f88ce-e514-4034-b5c4-e29233caeaf6 | checkpoint | Any bracing elements completed to design specification
84e3189e-d2cb-4281-8f4c-c60a4d276cb5 | checkpoint | GIB Lining Ceiling completed correctly within specified tolerance, checked and approved
68fadb72-c9aa-4dcf-93b3-8bec4336cbfb | checklist | Ceiling - GIB Stopping |  | Ceiling - GIB Stopping
4a88c2a6-116e-4b56-bb0c-af142666c54a | checkpoint | Area ready for GIB stopping
965df982-caa3-4a82-a64d-6b0d3f37de4a | checkpoint | Correct stopping product and applied correctly
cdeebe85-829c-4985-84a9-cee4cbec6088 | checkpoint | Square stopping, slimlines and joints checked and acceptable
f3aa6e96-1f82-42b8-970b-2710de4ab1a0 | checkpoint | Adequate drying time between applications & no visible bubbling
81e5522b-5c7c-42df-8d6c-2b5d6d6ea52e | checkpoint | GIB Stopping Ceiling completed correctly within specified tolerance, checked and approved
70db494c-9207-4922-9918-3bfd6b717c24 | checklist | CLD Batten Checklist |  | CLD Batten Checklist
c0e4136c-5f08-41a0-9386-3e8077ae0654 | section | Details
1ac28e4a-75e2-4be3-ae00-fe78898b11e5 | checkpoint | Cut CLD batten to suit and primer the cutting edge
4efbd6bf-c7f7-484c-82b9-2c1373548f4f | checkpoint | Cut CLD batten 20 to 45 degree for joint if batten needs joint
811b8392-dedc-4e9e-bacc-9e3e0410f14e | checkpoint | Use s/s 6.5mm *70mm concrete screw
c8bb3523-6eac-44cb-b51f-1ade1565da27 | checkpoint | Concrete screw fixing @ 200mm
9aa5c942-fa15-4f81-b846-415d53751eed | checkpoint | Batten fix to blockwork @ 600mm batten spacing maximal
cce444a5-cf90-4701-826d-aa0c16bf73dd | checkpoint | Fixing needs to be 75mm away from top and bottom edge
67f862b2-c9b8-4de0-8398-34ba827f6433 | checkpoint | Apply sealant for batten joint (include vertical and corner joint)
b2b147fa-1d6b-4e9a-8a6c-b7fde3e52d5d | checkpoint | Area CLD batten complete
9c30c574-4cce-45a3-aec7-ad7dd866c80b | checklist | Column Handover |  | Column Handover
447afcf7-994c-4176-b3b4-ab5736e638f6 | checkpoint | Correct location from drawing
05fbf79f-9d44-45b0-8d71-ce7906097492 | checkpoint | Square
3ae09743-92de-434f-bd99-ec3299091770 | checkpoint | Plumb
b9c677f1-bc8d-4daa-aec1-b260324d61ab | checkpoint | Angle at edges
52e96f59-1162-456b-9a54-dca72b26ed36 | checkpoint | Smooth surface
8b4de58c-7ff9-4daa-a2f6-1a93c0382b1a | checkpoint | Colour
aad3bc5e-d83d-4068-9320-fb3274e6b4d7 | checkpoint | Smooth finish at angled corners
2627f125-53e0-46c9-a94e-31c13788a48b | checkpoint | Products used
e96b3817-f42b-438e-9388-365e82bc57a3 | checkpoint | Within tolerances
42c885a4-194f-438e-9b21-f9d2d2b96c66 | checkpoint | Any honeycomb patch for structural purposes
18e19059-f53b-4466-9f7a-ee5e7498e5b5 | checkpoint | Tidy finish from column to beam stitch conjunction
cd613aa3-faf4-4498-93c4-8788399c927b | checkpoint | Dwvidag holes filled
b96287a6-caa8-4dcf-82bd-af4674b142c7 | checkpoint | F4 concrete finish
3fe5975e-cb78-4f39-9469-49c4556d35a8 | checkpoint | Signed off by main contractor
d289f373-5052-4c70-812f-5ac0d8c8a729 | checklist | Concrete - Retaining Walls |  | Concrete - Retaining Walls
257394b9-4395-4572-9d6f-32ad3ca56864 | checkpoint | Retaining wall(s) setout/heights confirmed
9b161962-e5d1-4923-884f-acc6125b7eb3 | checkpoint | Area prepared - Excavation depths and location of wall checked and correct
cbe2ccc6-6011-4c91-9a45-93fcc9cac8f7 | checkpoint | Correct materials used and installed using appropriate methodology
680fd85f-b0b4-4172-aab6-e8513911cc73 | checkpoint | Additional observations/ inspections
74c79a6c-898d-424a-b91a-0a94953efe38 | checkpoint | Retaining wall completed to required specifications
9027a935-7ba3-4094-a52b-fa50e877f10a | checklist | Concrete - Speedwall |  | Concrete - Speedwall
f22770c8-7970-4065-a37f-87d31d0cac34 | checkpoint | All relevant drawings and revision numbers checked and attached/commented
b3bc65c4-db15-448d-b7ba-b789df89df9f | checkpoint | Area ready for Speedwall install
8b70701e-8f47-43d3-9ced-4761edb763ba | checkpoint | Bottom track correctly installed (size, location and fixings)
d406bf86-cc01-48b4-b17f-57fd7d725298 | checkpoint | Top track correctly installed (size, location and fixings)
636c7d7d-9910-4c02-8f95-5de960815b0f | checkpoint | Install C track as per spec
ccb1d265-3e8d-4e58-973b-e36045f885a5 | checkpoint | Fixings as per spec
4435325e-865c-4bc1-ab4a-7f130b20f604 | checkpoint | Fire sealant installed correctly and photographed
5673c088-6f1e-4ede-8a34-480cde8e47b8 | checkpoint | All joints sealed correctly as per specification
798cd16c-5e4a-43d0-9434-b0e90350d624 | checkpoint | Speedwall installed straight and level
671c58ac-8440-4927-bada-2294bcb645dd | checkpoint | Openings installed for services as per drawings
11516e02-6c94-4c41-94ce-5e1cf67184b6 | checkpoint | Speedwall completed within specified tolerance, checked and approved
f7d863eb-024d-49a0-9316-68dc18188281 | checklist | Concrete Pour - Slab/Foundations |  | Concrete Pour - Slab/Foundations
0a039ae9-561a-4297-80ae-bb32691c58e5 | section | Pour Details
284ec807-761a-4b2d-8221-bf6e37febb55 | checkpoint | Pour Details
c1a15f5c-b181-5706-a039-6d06df9066ee | textbox | Area to be poured
4e065bfb-abfb-51c7-8152-1e59dcf1775a | textbox | Date of pour
8a5e5e09-bebd-4064-9bec-9260cca5299d | checkpoint | Latest drawings available, checked and referenced
79266398-b9fa-415a-b219-b9736750cc5e | section | Formwork and embedded items
8e758079-2d5c-487d-8d17-477080f4433e | checkpoint | Grids and RLs clearly marked fore reference
8d6a4f1f-b3e8-4a5c-b159-ff3b188520a8 | checkpoint | Formwork - location, heights, falls and dimensions checked and accurate
d066fcde-6867-44ea-9471-c61f2c31a4a0 | checkpoint | Formwork sufficiently fixed and braced
c11da632-5ad2-411e-a34c-13e43b4dd2e3 | checkpoint | Any rebates / nibs / cast in items are correctly positioned, sized and appropriately fixed in place.
09b92d2f-105f-4b56-aee4-9ae814e99829 | checkpoint | Hold down bolts checked and correct
57225f5c-b958-4e2e-8c65-2b10906b632f | checkpoint | Precast panel starters checked and correct
fdfce17d-7183-49f8-aacd-037cecb959a9 | checkpoint | Service penetrations formed correctly and locations checked/correct
79c214bf-b1f9-45ff-bd89-233119010d74 | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork, etc.)
6bb8a3cd-d0f8-411a-bcd8-7c5fdb21dce0 | checkpoint | Any control joints / stop ends installed accurately and correctly braced
6e484d40-69e8-4916-8691-f4cf82cc4aa5 | checkpoint | Any additional formwork photos and observations
6dae16ea-683a-4051-b10e-67d8dc69cbfb | checkpoint | All formwork elements completed and ready for concrete pour (excess debris removed)
16a4676a-80ef-42e2-bda9-afc68e25b3fd | checkpoint | Formwork and embedded items report sent through to client
5acdf4df-1158-415b-b9de-52c89cab5983 | section | Ordering and Placement
24c65e2d-9740-4322-96f8-c46f223ca606 | checkpoint | Correct mix and strength
86a454df-d66a-5e60-a8fc-427817cae95a | textbox | Mix
90b41033-a198-51cc-829c-e1faaadab160 | textbox | Strength
ac17b577-a4e5-4512-9935-b480d730664f | checkpoint | Concrete docket attached
89668503-cab5-469d-9849-07a29c33d57d | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
ef057b7c-bc2e-5c7a-8637-69c1ba11664d | textbox | Who is placing the concrete
9416e561-dbcf-4db9-b00c-5a8faf80ac4f | checkpoint | Height and falls checked / confirmed before placement
5349ba03-97f6-4908-b6d7-a880587f4ec5 | checkpoint | Cover correct to specification
b9cb4bbf-34ee-4eb9-a766-b24d162a94bb | checkpoint | General photos and observations of concrete placement attached
3aaedcad-b358-4b0c-98ee-72fe77efc567 | checkpoint | Heights and falls checked / confirmed after placement
f4649994-b2b9-4d7f-8c70-75d09c08b20f | checkpoint | Any curing compound applied correctly
46bf8309-37b4-4c32-aa6b-ab9e1a116a4f | checkpoint | Concrete placement completed - specified level of finish achieved
fc46a89c-d79e-4dbc-9750-1fc3ab3a0173 | checkpoint | Area left clean and tidy
faafa74f-100f-4598-a152-bb2c23a16c1c | section | Post Pour Checks / Signoff
acbfecd4-0910-4c10-bcba-b0f7a974e830 | checkpoint | Any remedial work completed
11b7569b-51fd-44d7-97ef-12456daa9b2c | checklist | Easylap Checklist |  | Easylap Checklist
6cdb12a6-8be4-4c30-a849-b627459410db | section | Details
09404d07-f9f9-4364-98d9-e52f245b611a | checkpoint | Cut Panel to suit and primer the cutting edge
facda79d-1e65-48df-a809-c4953868c26c | checkpoint | Nails flush with the panel surface
9a3bca1e-86c4-4906-8afa-4be1e1bb9de0 | checkpoint | Use C-25 straight ‘T’ - Head stainless steel brad nail
66457848-e95b-447d-afa5-743a719e4c4e | checkpoint | Nail fixing @ 150mm
82057982-b1be-4492-a265-fc0adfcbaf62 | checkpoint | Nail fix to Panel @ 600mm spacing maximal
f7bf20f3-d8b5-4b63-9599-6f71d7bef73e | checkpoint | Fixing needs to be 75mm away from top and bottom edge
43f9f32d-460c-4635-883e-ff9e0a8bb8eb | checkpoint | Apply Bostik® Seal N Flex™ - 1 for Panel joint
a2432889-2b94-465f-bce4-bf722c326c7b | checkpoint | Fixing T nails is 18mm from the underlap edge and 16mm from the overlap edge
53c21353-5e66-4847-ab5e-3eae8fbb75b9 | checkpoint | Area Panel complete
bac20149-cfb6-4810-9913-1f9d75e440e2 | checklist | Exterior Cladding Checklist |  | Exterior Cladding Checklist
6b561fcd-4b79-454b-aed8-857ed7792811 | checkpoint | Product checked and correct as per specification
077a3f5d-0cca-47e4-94f8-ab468ee6e9c8 | checkpoint | All prestart checks completed and approval given to install
bd86825c-87db-42f4-80f0-b613d3859c6a | checkpoint | General photos, comments and observations during install
cfc67eda-cfc2-4a77-8d16-c997c113b763 | checkpoint | Relevant Services considered, checked and approved where applicable
8f59665d-87e2-47cd-bb9d-ce04cfeabdc3 | checkpoint | All cladding elements completed, checked and approved as per specifications
9308bbce-2c73-42bd-8c49-0c2461253c19 | checklist | Formwork |  | Formwork
1fdf6f0f-de09-4d73-8da9-60557311f6b0 | checkpoint | Formwork
27b15f0d-b4d7-5d70-8aac-17f969b2d48e | textbox | Relevant drawings & revisions for reference:
6b585e9e-cd19-4f38-9488-b6c03a4d72e0 | checkpoint | Work area acceptable & approval to start work
214701a4-a23f-43d7-a25b-fd21cc592f3b | checkpoint | Grids and RLs clearly marked for reference
86ac8c61-60a8-4a98-bdd5-37221ee0e4f8 | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
05349774-baaf-472f-9534-e9a908c0e5df | checkpoint | Formwork sufficiently fixed and braced
b6a43c08-079e-4100-81de-2f1d4063369d | checkpoint | Any rebates/ nibs / cast in items are correctly positioned, sized and appropriately fixed in place
82534ae5-5c21-4ff7-b1a6-fb62de8fad2d | checkpoint | Service penetrations formed correctly and locations checked/correct
38c51055-142a-42d1-8fd6-2f903f423c09 | checkpoint | All surfaces correctly prepared (e.g joints to existing concrete, release agent to formwork etc)
00d7c16a-b6ea-480a-98ab-94981b207b5b | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
29fe7155-3b7e-4054-ada9-33ff2efed383 | checkpoint | All formwork elements completed and ready for concrete pour ( excess debris removed )
e5422f56-695f-4f28-8f42-59a22e2f02b2 | checklist | Formwork - Reinforcing |  | Formwork - Reinforcing
aabdf3a9-e979-491c-bb7c-ea3108461f7c | checkpoint | Work area ready
6060cc32-acfa-423d-bd3e-43a2bb927463 | checkpoint | Latest drawings available, checked and referenced
cf7e711c-d1ff-40ba-9bf6-95220a18436b | checkpoint | Correct product delivered, reviewed & approved
6c427c72-0823-43f6-a4e2-bee1fa11ac41 | checkpoint | Correct size & type installed as per design
621e1aad-6492-4766-bfe1-df47ed05fb24 | checkpoint | Reinforcing spacing and location correct
66c8f30f-2a00-49f8-a189-8c8796a1095d | checkpoint | Specified covers checked/correct
2366acf3-91bd-4d14-87ca-543d89dd4a60 | checkpoint | Laps correct per size of bar
fac4923c-7ac8-44e7-b266-d9d92c6a9c34 | checkpoint | Any starter bars are installed correctly (location, size and spacing)
d19c1741-c553-448c-9e4e-bb5eae1fdd00 | checkpoint | All bars fixed appropriately
2d4e785c-a110-4d71-b904-24e5467d7bd6 | checkpoint | Couplers installed at correct height
2e045697-cc9f-4217-959f-6cf733eb03df | checkpoint | Cast in plates installed correctly
67e72626-6b95-42df-8459-8ceee2f28dec | checkpoint | Any additional items considered, installed & completed e.g. trimmer bars, reid bar couplers, foot plates, drag bars
17ce4d44-f204-43ad-82b0-81d38b1576fb | checklist | Internal Carpentry – Prestart Checklist |  | Pre-Start QA Checklist
9e2812e5-93b6-4330-8b80-6c802a3d16f5 | checkpoint-no-value | Details
e2911ea3-e979-510e-ba20-ae35bb13cd96 | textbox | Date
c232e7cb-c25d-577f-a3af-dad225b8ed87 | textbox | Area
d814a6d5-65a4-5998-8990-e77a80dd4cd4 | note | Attach mark-up plan
da1e18a3-a5fb-4527-8eba-817b8522ccef | checkpoint | Is the site ready for window reveal?
39c03050-7674-56ac-a7a7-bd8307aa3d07 | note | 1.1 Yes - Window installed and QA received
905c89d3-2d9f-545b-9f01-acf56fbfb838 | note | 1.2 No - Provide photos
859b6fdd-9f5c-5b6e-8232-7e42a43cc31c | note | Attach photos
61631964-a2fe-48c3-a8ad-0dc43603ef70 | checkpoint | Is the site ready for Fire Door installation?
06ab8597-2f5e-5199-b961-4f8ca2cad5d8 | note | 2.1 Yes - Previous trade / Company wall and door opening size QA received
bdd1f6fd-480e-5740-a8bd-098d372c75cc | note | 2.2 No - Provide photos
aaf2e3f2-9e8c-59db-a093-7d117281f1cd | note | 2.3 No - Fire Door not available
270fe90c-b54e-5e85-a4d7-9becb8cd20fb | note | Attach photos
186427cf-f009-416a-b698-560a8197e8b8 | checkpoint | Is the site ready for Architrave and skirting?
28e96c76-0a81-5073-89ca-bf78ff8e3ae7 | note | 3.1 Yes - Previous trade / Company plasterboard and stopping QA received
dd942b9f-09be-5f01-a34d-9eaa9c6b9843 | note | 3.2 No - Provide photos
aea4f04a-3ddb-54b8-9d08-5944fbdb0a80 | note | 3.3 No - Wall not square, provide photos
91c09c82-ef72-52b9-8a34-9a77ef7bef80 | note | 3.4 No - Room still full of other trades materials
40278255-3131-55c2-9ab4-5bd75f7a026a | note | Attach photos
9fae13b4-2b69-4d64-9567-e58272937dcd | checklist | POST - S - Fire door installation |  | POST - S - Fire door installation
7387cbc0-4292-4d6a-9aff-7725ffe725e9 | checkpoint | Door Number(s) / Location checked and accurate
19f21183-1133-4890-a940-a52c6eedb48e | checkpoint | Floor clearance - Adequate for proposed floor coverings
423f2706-8921-4550-8258-869218f822d3 | checkpoint | Services/Mechanisms & FRR/Acoustic requirements considered & applied (where applicable)
eca809f2-4293-45e2-ae3a-289587a6a558 | checkpoint | Fixings - Consider Jamb/Hinges, all installed & secure (Size & type)
cf0a7b3c-0161-479b-acf1-8b4559f96be9 | checkpoint | Door leaf to jamb gaps parallel & correct (Consider paint thickness(s))
4b3fa9c4-11b3-4839-b2f6-24f82b5f781e | checkpoint | Door opening as required & is plumb
a4a0cdbc-9cbb-463b-b67c-afff3ff1b517 | checkpoint | Door tags installed
ac94c593-1b01-474f-903b-a85c5e83b637 | checkpoint | All doors installed, damage free & completed correctly to specification in respective area(s)
b7e06e55-66dc-46e8-9e7a-f705aa8b6fc5 | checkpoint | Inspections completed and issued to Foreman
917ef2ae-a7a6-4e94-8404-3036ddbf3a07 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
a854f143-86db-4580-be50-6a3ae65cea66 | checklist | POST - S - Internal door installation |  | POST - S - Internal door installation
6e8056d4-acdc-4caf-81a7-aa5d6376886e | checkpoint | Door Number(s) / Location checked and accurate
dfd16a2b-899c-49db-bedb-01df2da8cc59 | checkpoint | Floor clearance - Adequate for proposed floor coverings
f8609183-5a8d-46e0-be8d-3531e1ac76b1 | checkpoint | Fixings - Consider Jamb/Hinges/Door Packer, all installed & secure (Size & type)
1ad82c79-72f2-48da-baad-3b0ce0a5120c | checkpoint | Door leaf to jamb gaps parallel & correct (Consider paint thickness(s))
1de6572d-30bc-425c-add4-fcecd6cea424 | checkpoint | Door opening as required & is plumb
0bb547d0-79f2-492e-94ab-c031a1c51612 | checkpoint | All doors installed, damage free & completed correctly to specification in respective area(s)
063e1a2f-a44d-4db9-af2a-211f983224a6 | checkpoint | Inspections completed and issued to Foreman
5abaaad6-a963-4bc7-b993-a8c065282df5 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
d36e1244-9801-4586-ba1e-35cdb3a38554 | checklist | POST - S - Joinery and Cabinets Installation - Kitchen, Ensuite, Bathroom and Wardrobes |  | POST - S - Joinery and Cabinets Installation - Kitchen, Ensuite, Bathroom and Wardrobes
63735512-7f48-4957-b0c2-15bde1a91d04 | checkpoint | All units & scribers in apartment
f43fec60-cb62-4557-a7e6-69168ab163b0 | checkpoint | Joinery free from damage pre install
3c3e18ab-0126-4096-8310-ba778d02f1a6 | checkpoint | Joinery installed free from defect and damage
69e636f6-3d0e-4238-bd57-e9c98e417beb | checkpoint | Silicone installed, correct colour & clean and tidy
a050569c-62fd-4243-a5d9-5d71cce4813b | checkpoint | Joinery and Cabinets installation completed - specified level of finish achieved
e1d2e42a-a3a4-455b-8b6a-b042e234fe99 | checkpoint | Inspections completed and issued to Foreman
74eec6a8-2dc4-4b1d-a79f-bddbdf97d78c | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
b36fb860-dd36-4f4b-b5e2-ddfddefb9299 | checklist | POST - S - Skirting/ Architraves & Trims |  | POST - S - Skirting/ Architraves & Trims
7c46a6bc-6fb1-40b1-a6d8-b120135726b6 | checkpoint | Architraves/ skirtings & trims are the correct size and profile
d7e9af80-aa73-4048-9895-48d764a02c97 | checkpoint | Skirting boards have been properly scribed, sanded, glued and mitred
f1897b5e-6061-4a79-906b-62d9fd8683d8 | checkpoint | Architraves/skirtings & trims have been installed with consistent even margins
0b750db4-670e-43fc-a3fb-274fd61e48af | checkpoint | Skirting/Architraves & trim work completed - specified level of finish achieved
52e1f658-73c2-46e4-b944-f4c98fb2698b | checkpoint | Inspections completed and issued to Foreman
8e1a4988-eba1-43fd-b5cb-0b2c7a268244 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
03597460-4962-40b9-a487-14e2bade6dd6 | checklist | PRE - S - Nogs |  | PRE - S - Nogs
87dc8f5e-a7fa-4731-ab97-b9cf543f34e6 | section | Service Nogs Toilet
d981a33e-0768-4155-a33e-d61566798eb7 | checkpoint | Wall Vanity nogs installed
326cd74a-2197-45a3-a766-7dba7bef9bfd | checkpoint | Handrail and Toilet roll holder Nogs installed
2b3c20e2-2213-4478-9a32-34dc08905cbb | section | Bathroom
09aea554-24d0-40c8-8860-ce47d57b5de7 | checkpoint | Mirror cabinet nogs installed
82a21293-4183-4212-9146-56f548f3ad08 | checkpoint | Wall Vanity nogs installed
87f43a3d-cfb8-4f35-8981-ceebd7d1a379 | checkpoint | Toilet: Handrail nogs Installed
b2fa9719-1252-4b71-ba67-2f39915eebfa | checkpoint | Shower: Handrails nogs (3 areas) installed
6c02b4e1-6661-4cb4-8187-259516b2d810 | checkpoint | Wall Mounted Heater nog installed
d7e8da1e-dee8-40e5-8187-011a483cf830 | checkpoint | Towel rail nogs installed
5f30ac07-5863-4968-8c5b-4203ea1b35cc | checkpoint | Shower head nog installed
4eb9231b-7750-4edf-83a3-dd6f1456643e | checkpoint | Shower mixer nog installed
90fa4e59-670d-4af1-a3b7-57b9a6dd5958 | section | Laundry
ecc6e46f-1318-407c-9481-e8aa73e7fb06 | checkpoint | Dryer nogs installed
1487687a-655b-47a1-aedc-33c84d4a31d1 | checkpoint | Cupboard nogs installed
cb8cdcaf-5920-4d7d-a94c-da948f1651bd | section | Service Nogs General
0109fa10-3ea9-4d36-b3b6-46670be30e6f | checkpoint | Nogs / Service Nogs installed correctly as per plan
1ecd342a-7943-47f3-8534-bb2509d990f8 | checkpoint | Inspections completed and issued to Foreman
136c9de2-9e1c-4772-9e7a-1921bd6347a7 | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
502cb0bf-a560-4503-b2e1-b8441906e6d1 | checklist | Precast - Flooring Placement |  | Precast - Flooring Placement
b715512f-d8de-4207-ab96-da5e8d29320a | checkpoint | Precast Flooring received and damage free
ee4b96cb-53d2-416d-a3c6-4ff74d888a7e | checkpoint | Setout completed and clearly marked (heights and locations) ready for installation
ab5790c7-d481-46f3-855c-94b2a8d5bb3d | checkpoint | Installed in correct location with adequate seating
f3a57646-b900-4708-995f-aa1935194f76 | checkpoint | Bearing strip installed correctly as required
c17bc5a9-1e7e-4957-960f-b90e34f9764a | checkpoint | Precast flooring install complete (checked location, height and level)
818cd29d-c8c1-41b6-ba57-94e1e3f0b594 | checklist | Precast - Panel / Column Placement |  | Precast - Panel / Column Placement
4f5eac1a-c4ae-4d55-a4cc-b8b7258cac7f | checkpoint | Precast panel / column received and damage free
2678f09b-3afc-49c1-ba99-f42132c37173 | checkpoint | Setout completed and clearly marked (heights and locations) ready for installation
af7a3aab-7bd2-412b-8e19-dd40381b0647 | checkpoint | Installed in correct location with adequate seating
76b85853-4032-471f-b18e-a4209911f5c4 | checkpoint | Adequately braced
2f2f0dfb-f534-44f8-852e-2d99dd3e27a3 | checkpoint | Panel / column install complete (checked location, height and level)
3d181d7e-b474-456c-86d2-cd57f9ef015e | checkpoint | All props removed for respective panels and stacked neatly
9ca2394c-6272-4c8f-8369-0da491122eee | checklist | QA - External Framing |  | QA - External Framing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f2e9d09d-73cd-4f20-963f-6d5ce44d9e59 | checkpoint | Plans / Specs followed and correct type of timber used
43491832-735b-43f2-abac-76b9feb87651 | checkpoint | DPC
483c9cc0-cb18-4c58-ae2c-e4ab6747b4ad | checkpoint | frame follow grid as plan
79737ef0-3098-4eba-a76b-af3951757653 | checkpoint | correct jamb, sill and lintel detail
23db3882-a6d5-4391-9b41-689acdb62e69 | checkpoint | Bolted at correct centres
cfeff08b-c1aa-4fe1-a2c4-9c558ee80082 | checkpoint | correct fixing
72227704-0bb7-487b-8a8e-d6fa655a520b | checkpoint | frame straight, plumb and level
649d836d-550b-442e-b3c7-d7249224d559 | checkpoint | correct opening
0b35246a-9656-45c7-b189-f410aa4ba64e | checkpoint | Correct head detail (fire & seismic)
0056be80-bcbb-4705-9a3c-c5b5c0e55672 | checkpoint | stud at correct center
2dd1e45b-bfde-424f-8552-57e5c51128a6 | checkpoint | nog at correct center
0c6c3580-8b77-4c70-9159-f02f7bd1c7f4 | checklist | QA - Pro Clima install |  | QA - Pro Clima install
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a42d8478-fdb8-4d00-9c85-1dcc172d7741 | checkpoint | correct materials
fe028c82-7c56-4e56-90ac-2afff3d6064c | checkpoint | substrade check and dust free
eb603148-b04e-4c5f-8bee-d175ab383031 | checkpoint | correct fixing distance
a1f8f3d0-97fa-41bd-a5b5-9a95a4ea7b68 | checkpoint | correct edge fixing distance
8b793fb7-a288-4078-9bdb-363d8e8e6fc5 | checkpoint | correct corner detail
75166cae-3969-4299-ab6d-521ed06edb4b | checkpoint | correct opening detail
e1f03a2b-e4dc-478c-a7fb-9da16b477213 | checkpoint | 150mm min overlap, top cover bottom
4d1a80d4-b852-4b36-9db0-8e038d86a958 | checkpoint | no bubble or folds when finish
515f545a-78ca-4f78-b4cc-7bc2c6f2c6c1 | checkpoint | correct glue to concrete at bottom
9ca11ad5-67bc-4d67-a577-e5d6c30b86bb | checkpoint | all penetrations are sealed / taped
cbfa15f6-b852-48f2-af4a-0efb812a18bb | checklist | QA - RAB |  | QA - RAB
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
e67c3a76-7e9e-446f-a0a9-332318c6b031 | checkpoint | correct materials
6f83cd41-a852-4994-9b8e-1c42b7221acc | checkpoint | correct fixing distance
29c99f29-90d6-4245-94f3-327dda0c92ce | checkpoint | correct edge fixing distance
118701da-b6f9-46b9-ad63-ee07decc16a7 | checkpoint | flashings in place
5611f233-9ec1-4410-b73c-2b5725ea2e1b | checkpoint | sheet neatly cut and 2mm gaps at join
ee5ca397-c7df-4131-9557-294bf9b57aaf | checkpoint | correct nails / nailing pattern
b77f1e99-e23e-47cf-97b5-471993ef3230 | checkpoint | all nails flat and not puncturing board
52aa33b3-dbe5-472f-a5c6-e756d3b20e7c | checkpoint | tape cover damaged holes
49422163-84a5-47c3-bfea-f5c1ee0bbc4e | checkpoint | Correct joint detail
a1625556-85ac-46c2-8ecb-c47eb05ec52e | checkpoint | correct taped & sealed
6d035876-4699-4421-8124-5e936bb2afc9 | checkpoint | 15mm minimum over concrete foundation
513bfa14-abe4-46f5-8af5-eada0584525f | checklist | QA - Stria Cladding install |  | QA - Stria Cladding install
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a6bec0db-b608-4b95-bdd3-e4b9ea9cc1f7 | checkpoint | correct materials
568e2302-819d-4fa9-9cdf-60e2f69b33be | checkpoint | correct fixing distance
8f7cfb09-67ba-4760-a918-1d61dbb28e42 | checkpoint | correct edge fixing distance
7bb0cdb6-5f37-4170-a63c-c20e64ab1011 | checkpoint | 3-5mm gap with flashing
15a34fb4-bbda-4850-b88a-048352d22c24 | checkpoint | 10mm over soffit board bottom
15464733-7458-48ea-8c82-a6de86ae3f29 | checkpoint | correct glue to concrete at top
40b2e55b-04bd-4514-9691-c894f670ea9b | checklist | RAB board checklist |  | RAB board checklist
a0c80ce2-0380-4938-8f77-bb5f661f328f | checkpoint | Plans/specs followed
5d9ce3ae-1a46-4869-9909-bdead8b8314b | checkpoint | 50mm R-head nall galv 150mm C/C nail fix
a6b7001c-c651-43b6-a467-117237c64ad3 | checkpoint | Nail flat with board surface.
810c8b45-1f5d-45a9-8f94-9ce5b18dd895 | checkpoint | Vertical joint/internal conner/internal conner with 2mm-4mm gap
09c87b5e-c3c7-4d40-9360-98ea6b288385 | checkpoint | Rab board overhang below bottom plate 15mm
ac572ed0-2b8e-48f4-b6ae-592de7fe6c97 | checkpoint | The nail have minimum clearance of 12mm from the sheet edges and a minimum of 50 mm horizontally and 75mm vertically
6b6d29f2-4879-42c4-8da0-cf03d000bf1e | checkpoint | Taped/sealed
736d0840-f91d-4ad4-8256-995d726c1743 | checkpoint | Special detail requirements
3f7f4c0e-eea2-4f85-92fe-155ba098f581 | checkpoint | Area Rab complete
a125c7f2-e02d-4496-942f-3cd10618e2f0 | checklist | Reveal Shied and Vaproliqui-flash Checklist |  | Reveal Shied and Vaproliqui-flash
19c60e92-a54e-4484-92be-eefb038a7ae8 | checkpoint | Plans/specs followed
e7aa7626-73ee-4201-a481-bc9c881b8d83 | checkpoint | VAPROFLASHING SA SILL FLASHING LAPPED MIN. 70mm INTO EACH OPENING
e3d0bbbe-25b0-4e6f-954f-d57cc7fac787 | checkpoint | Vaproshield Wrapshield SA wrapped minimum 80mm around corner
ecaf13c1-6bf5-48ed-adb6-aae018aa5bf8 | checkpoint | Vaproshield Wrapshield SA lapped minimum 80mm past RAB joint
137af28f-cc9c-4bd5-bd83-dce6a09da4dd | checkpoint | Next floor vertically installed minimum 80mm overlap
616071aa-1ab0-4ad3-b93f-da9737fb2e29 | checkpoint | Vertically installed first floor with minimum 80 overlap
eec72d28-50a1-4629-9e15-91f05d558b86 | checkpoint | Apply additional Vaproliqui-flash onall inner surfaces of the rough opening
ea392f57-2a76-4638-b7b7-fb05789ab30a | checkpoint | Vaproliqui-flash a 25mm border around the rough opening
01cd78d2-e5f0-4d0f-8494-1cc69e7a03db | checkpoint | Install VaproSilicone Vaprobond for deflection head area
bbeb2f4e-d3ff-4469-808f-8db9d992e464 | checkpoint | Wall Penetrations Apply VaproLiqui-Flash min. 51 mm onto face and min. 25 mm out along all side of the penetration.
ad446645-fb38-4cd2-b41b-f63587d59b35 | checkpoint | Area Reveal Shied complete
f675de65-27c3-4bb8-bfbd-2854010ac6f7 | checklist | Soffit Frame |  | Soffit Frame
c720fbfc-38a0-4c72-83dd-fd8cf2d26e27 | checkpoint | Correct timber used
5ec1d06d-fd58-4a4e-a870-92407319c0c7 | checkpoint | Frame follow plan at correct RL or angle
65042663-8d23-449a-ba95-75cd6e4ce7f9 | checkpoint | Correct fixings
e7f44f1c-0205-40ac-b922-f1dc4187e780 | checkpoint | Joist at correct center
70d1592c-64d5-4ddb-a208-d28a8cb38f16 | checkpoint | Line with correct material
6bea7364-aee1-4790-bf79-f220dbf8789d | checklist | Steel Stud Frame |  | Steel Stud Frame
c96ab0c1-70a2-45b2-b472-0f3eaae05237 | checkpoint | Area of frame finished
4a30dcf9-40bf-4fee-9bc8-56bbf35940ad | checkpoint | Correct material used, size and BMT
41ae3609-e3b5-4db3-a89c-cce5602c335e | checkpoint | Follow plan at right position and height
9af599cb-573a-4c3d-b5ba-4d4909df0bb1 | checkpoint | Frame is straight and plumb
1382c332-723d-4b43-9ce7-47c5a680d1cc | checkpoint | Correct fixing
97d3ad4f-d9d9-4ccd-8562-4ea6b900c3fd | checkpoint | Stud at correct center
85bb4112-d0b5-4bd0-b8fb-5d7388837c96 | checkpoint | Nog at correct center
f6015639-e28f-4a0a-b81a-33753b5df3f9 | checkpoint | Correct top deflection head deatail follow
aa609f6d-0036-48ec-b410-4a75bb456a77 | checkpoint | DPC between steel frame and treated timber/concrete/steel beam
80f14647-d55e-4c20-8419-e131227e9c83 | checkpoint | Opening is at right position and RL
5d3a1946-0790-49ee-92cc-d870c230cd4f | checkpoint | Correct jamb, sill and lintel detail follow
8da21716-c3b6-4bc0-b558-37b32c66f3e8 | checkpoint | Control joint if applicable
be6760f4-9d97-4b07-894b-9b18bd90a6e6 | checklist | Timber Strupsing |  | Timber Strupsing
e6c82e8e-d1ab-4048-9a63-10959477d2f3 | checkpoint | Plans/specs followed and correct type of timber used
7006fda4-1ae6-4a2d-8d8d-496a8b4d6817 | checkpoint | Check for location
06160d16-af04-4ca6-ab59-f45a45562c8a | checkpoint | Correct head detail
ae920419-0824-47e5-9687-c1bb5ad958fb | checkpoint | Check for level
c9918ad4-778e-41b7-bd8d-e33d011fd649 | checkpoint | Check for plumbles
0264fec3-07db-4507-a743-aae644a74652 | checkpoint | Opening size match with drawing
9e6b9cb4-8d84-42b7-9c8c-9e920c28662f | checkpoint | 3M tape installed to manifacture spec
570360d5-29cc-442c-8c35-882893087e34 | checkpoint | Silicon adhered fully to concrente and timber
9252ebff-697d-4d84-813e-397d15bfa06a | checklist | Vapro Liqui-flash Checklist |  | Vapro Liqui-flash
2f6e1c9a-146d-47a2-8bed-6c9aa335069f | checkpoint | Wrapshield completed and clean
2146ea65-faf6-4311-9238-b58e5df2fc5b | checkpoint | Liqui-flash applied as per manufacturers specification
be3c8859-674a-4e45-a53a-67f0cd8bf986 | checkpoint | Vapro Liqui-flash (waterproofing) as per details
029be7f3-d11c-4fb2-8acc-14a46e54bc94 | checkpoint | Opening complete and ready for windows
8f3a858d-a324-4ada-8766-1aa294c386d1 | checklist | Wall - GIB Lining |  | Wall - GIB Lining
4670b391-a98e-4a75-bee3-3fdc9829f914 | checkpoint | Area ready for GIB install
4ce4cce2-ea75-4287-bb13-a1fe12fc09d8 | checkpoint | Correct lining checked and approved and area specifics checked
871ce707-ac84-4a23-8b9d-39ec05c4dec0 | checkpoint | Correct fixings used and installed at correct centres
79c3e677-0359-4f5e-baa7-27d7814fd8ce | checkpoint | Sealant applied as per spec
fb544338-76ba-49cf-ac9e-a9c4f505497c | checkpoint | Any bracing elements completed to design specification
df22470d-c93c-492e-b62f-f9dd385390ae | checkpoint | GIB Lining completed correctly within specified tolerance, checked and approved
913a612e-f298-49dd-bc1d-b4ff465460f4 | checklist | Wall - GIB Stopping |  | Wall - GIB Stopping
d848bb80-3e54-4721-9768-833507e844ad | checkpoint | Area ready for GIB stopping
88c25689-1453-4ab7-a4de-63c5a31864ea | checkpoint | Correct stopping product and applied correctly
37b64698-fc60-49b5-9ee6-4d0f244193dc | checkpoint | Square stopping, slimlines and joints checked and acceptable
d2c8118a-df9b-4e1e-b397-db2fc3b1727e | checkpoint | Adequate drying time between applications & no visible bubbling
4c7aa0c9-2444-41fa-9e57-e6c940ca4eac | checkpoint | GIB Stopping Ceiling completed correctly within specified tolerance, checked and approved
40f0309b-5658-4d7d-93b0-b0ff6fad1e37 | checklist | Window - Jamb Liners |  | Window Jamb Liners
42191512-dbc1-4559-86f7-cb321e8635e1 | checkpoint | QA Handover from previous trades
dbc12c6d-d201-403f-955c-646b79b101a8 | checkpoint | MC approval to start work
31125c64-3c81-4575-b211-378578a378d3 | checkpoint | Correct materials and drawings checked
2092899c-bdb9-4911-a91b-223298eb235f | checkpoint | Fixed at 600 ctrs
a1084ec5-f512-49e6-a01f-3108b00fbde1 | checkpoint | Window line has been sealed correctly