## Sheet1
Treatment Selection | Physical / Site video/photographic record | Asset Team - Base Preservation | Annually Pre-reseal | Documented approval from at time of Tender -Team/Client | Mandatory HOLD POINT - Client Approval | Approved Seal Designs | Sealing Contract Manager / Engineer | Treatment Selection | Verification Activity - Physical / Site video/photographic record | Methods or Reference - Asset Team - Base Preservation | Frequency - Annually Pre-reseal | Acceptance Criteria - Documented approval from at time of Tender -Team/Client | Hold / Witness Point - Mandatory HOLD POINT - Client Approval | Records - Approved Seal Designs | Responsible Person - Sealing Contract Manager / Engineer | Treatment Selection
Chipseal Design | Peer review by Authorised Seal Design Approver | Chipsealing in NZ | One per design prior to commencing onsite | Design meets requirements of P17 | Mandatory HOLD POINT - Seal Design peer Reviwer - Client Approval | Peer Reviewed Seal Designs | Sealing Contract Manager / Engineer | Chipseal Design | Verification Activity - Peer review by Authorised Seal Design Approver | Methods or Reference - Chipsealing in NZ | Frequency - One per design prior to commencing onsite | Acceptance Criteria - Design meets requirements of P17 | Hold / Witness Point - Mandatory HOLD POINT - Seal Design peer Reviwer - Client Approval | Records - Peer Reviewed Seal Designs | Responsible Person - Sealing Contract Manager / Engineer | Verification Activity - Physical / Site video/photographic record
[1] Size (Grades 2-5) CHAR(AMP) Shape (Grades 2-4) | Lab Test | NZTA M/6 | 1/500m3 | Size (ald mm) G2 9.5-12.0 G3 7.5-10.0 G4 5.5-8.0 G5 Report | Witness Point | IANZ Lab Reports | Sealing Contract Manager / Engineer | [1] Size (Grades 2-5) CHAR(AMP) Shape (Grades 2-4) | Verification Activity - Lab Test | Methods or Reference - NZTA M/6 | Frequency - 1/500m3 | Acceptance Criteria - Size (ald mm) G2 9.5-12.0 G3 7.5-10.0 G4 5.5-8.0 G5 Report | Hold / Witness Point - Witness Point | Records - IANZ Lab Reports | Responsible Person - Sealing Contract Manager / Engineer | Methods or Reference - Asset Team - Base Preservation
[2] Size (Grades 2-5) CHAR(AMP) Shape (Grades 2-4) | Lab Test | NZTA M/6 | 1/500m3 | Shape AGD/ALD Ratio G2,3,4 = 2.25 max G2,3,4 = min 98% with 2+ broken faces | Witness Point | IANZ Lab Reports | Sealing Contract Manager / Engineer | [2] Size (Grades 2-5) CHAR(AMP) Shape (Grades 2-4) | Verification Activity - Lab Test | Methods or Reference - NZTA M/6 | Frequency - 1/500m3 | Acceptance Criteria - Shape AGD/ALD Ratio G2,3,4 = 2.25 max G2,3,4 = min 98% with 2+ broken faces | Hold / Witness Point - Witness Point | Records - IANZ Lab Reports | Responsible Person - Sealing Contract Manager / Engineer | Frequency - Annually Pre-reseal
Cleanliness (Grades 2-6) | Lab Test | NZTA M/6 | 1/500m3 | Cleanness value G2 = 89 G3 = 87 G4 = 85 G5 CHAR(AMP) G6 Report only | Witness Point | IANZ Lab Reports | Sealing Contract Manager / Engineer | Cleanliness (Grades 2-6) | Verification Activity - Lab Test | Methods or Reference - NZTA M/6 | Frequency - 1/500m3 | Acceptance Criteria - Cleanness value G2 = 89 G3 = 87 G4 = 85 G5 CHAR(AMP) G6 Report only | Hold / Witness Point - Witness Point | Records - IANZ Lab Reports | Responsible Person - Sealing Contract Manager / Engineer | Acceptance Criteria - Documented approval from at time of Tender -Team/Client
[1] Compatibility (Multi Layered seals) | Comparison Of Chip ALD | Chipsealing in New Zealand NZTA (NZTA 2005) | 11.5 |  | Witness Point | IANZ Lab Reports | Sealing Contract Manager / Engineer | [1] Compatibility (Multi Layered seals) | Verification Activity - Comparison Of Chip ALD | Methods or Reference - Chipsealing in New Zealand NZTA (NZTA 2005) | Frequency - 11.5 | Acceptance Criteria - | Hold / Witness Point - Witness Point | Records - IANZ Lab Reports | Responsible Person - Sealing Contract Manager / Engineer | Hold / Witness Point - Mandatory HOLD POINT - Client Approval
[2] Compatibility (Multi Layered seals) | Comparison Of Chip ALD | Chipsealing in New Zealand NZTA (NZTA 2005) | 7.2 |  | Witness Point | IANZ Lab Reports | Sealing Contract Manager / Engineer | [2] Compatibility (Multi Layered seals) | Verification Activity - Comparison Of Chip ALD | Methods or Reference - Chipsealing in New Zealand NZTA (NZTA 2005) | Frequency - 7.2 | Acceptance Criteria - | Hold / Witness Point - Witness Point | Records - IANZ Lab Reports | Responsible Person - Sealing Contract Manager / Engineer | Records - Approved Seal Designs
Bitumen Distributor | IANZ Lab E/2 Results | Code of Compliance | Annual | Speed Test(+-3% over 100m), Dipstick Test (+-50L over 2000L), Matt Test (app rate within 0.10L/m2, longitudinal within 10%, thirds within 5%, transverse within 20%) | Mandatory HOLD POINT - Client - Engineer Witness | RNZ E2 Certificate | Sealing Contract Manager / Engineer | Bitumen Distributor | Verification Activity - IANZ Lab E/2 Results | Methods or Reference - Code of Compliance | Frequency - Annual | Acceptance Criteria - Speed Test(+-3% over 100m), Dipstick Test (+-50L over 2000L), Matt Test (app rate within 0.10L/m2, longitudinal within 10%, thirds within 5%, transverse within 20%) | Hold / Witness Point - Mandatory HOLD POINT - Client - Engineer Witness | Records - RNZ E2 Certificate | Responsible Person - Sealing Contract Manager / Engineer | Responsible Person - Sealing Contract Manager / Engineer
Emulsion/PME Testing | Lab Testing | Manufacture Specification | Per Emulsion/Bitumen Production Batch | Bitumen Content, ITM 11-01, Viscosity, ITM 10-02, PH ITM-08-02 | Witness Point | IANZ Lab Reports | Road Science | Emulsion/PME Testing | Verification Activity - Lab Testing | Methods or Reference - Manufacture Specification | Frequency - Per Emulsion/Bitumen Production Batch | Acceptance Criteria - Bitumen Content, ITM 11-01, Viscosity, ITM 10-02, PH ITM-08-02 | Hold / Witness Point - Witness Point | Records - IANZ Lab Reports | Responsible Person - Road Science | Chipseal Design
[1] Surface Texture - Measurement | Sandcircle Measurement | NZTA T/3 | At time of Seal Inspection | Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture | Witness Point | Sandcircle Data | Sealing Contract Manager / Engineer | [1] Surface Texture - Measurement | Verification Activity - Sandcircle Measurement | Methods or Reference - NZTA T/3 | Frequency - At time of Seal Inspection | Acceptance Criteria - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture | Hold / Witness Point - Witness Point | Records - Sandcircle Data | Responsible Person - Sealing Contract Manager / Engineer | Verification Activity - Peer review by Authorised Seal Design Approver
[2] Surface Texture - Measurement | ARRB Hawkeye or | NZTA T/3 | At time of Seal Inspection | Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture | Witness Point | Hawkeye Data | Sealing Contract Manager / Engineer | [2] Surface Texture - Measurement | Verification Activity - ARRB Hawkeye or | Methods or Reference - NZTA T/3 | Frequency - At time of Seal Inspection | Acceptance Criteria - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture | Hold / Witness Point - Witness Point | Records - Hawkeye Data | Responsible Person - Sealing Contract Manager / Engineer | Methods or Reference - Chipsealing in NZ
[3] Surface Texture - Measurement | NZTA HSD | NZTA T/3 | At time of Seal Inspection | Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture | Witness Point | High Speed Data | Sealing Contract Manager / Engineer | [3] Surface Texture - Measurement | Verification Activity - NZTA HSD | Methods or Reference - NZTA T/3 | Frequency - At time of Seal Inspection | Acceptance Criteria - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture | Hold / Witness Point - Witness Point | Records - High Speed Data | Responsible Person - Sealing Contract Manager / Engineer | Frequency - One per design prior to commencing onsite
Pre Seal Survey | Downer Survey or MS Forms Pre Reseal Inspection | Downer Survey or MS Forms Pre Reseal Inspection | At time of Seal Inspection | Record CHAR(AMP) any noted issues / Client | Witness Point | Lucidity | Sealing Contract Manager / Engineer | Pre Seal Survey | Verification Activity - Downer Survey or MS Forms Pre Reseal Inspection | Methods or Reference - Downer Survey or MS Forms Pre Reseal Inspection | Frequency - At time of Seal Inspection | Acceptance Criteria - Record CHAR(AMP) any noted issues / Client | Hold / Witness Point - Witness Point | Records - Lucidity | Responsible Person - Sealing Contract Manager / Engineer | Acceptance Criteria - Design meets requirements of P17
Construction Compliance testing |  |  | 24 hours in advance of seal construction commencement | Confirmation from renewals manager all testing has met requirements | Hold Point | Email Confirmation | Sealing Contract Manager / Engineer | Construction Compliance testing | Verification Activity - | Methods or Reference - | Frequency - 24 hours in advance of seal construction commencement | Acceptance Criteria - Confirmation from renewals manager all testing has met requirements | Hold / Witness Point - Hold Point | Records - Email Confirmation | Responsible Person - Sealing Contract Manager / Engineer | Hold / Witness Point - Mandatory HOLD POINT - Seal Design peer Reviwer - Client Approval
Go/No Go Survey | Visual, Zeus, Iris | Downer Survey Sealing Go / No Go, Road Science Zeus app CHAR(AMP) Downer Iris app | Prior to sealing on each site | Pass on Go / No Go, Marginal CHAR(AMP) discussion with Contract Manager or written approval from Rehab Manager | Witness Point | Lucidity | Supervisor / Foreperson / QA | Go/No Go Survey | Verification Activity - Visual, Zeus, Iris | Methods or Reference - Downer Survey Sealing Go / No Go, Road Science Zeus app CHAR(AMP) Downer Iris app | Frequency - Prior to sealing on each site | Acceptance Criteria - Pass on Go / No Go, Marginal CHAR(AMP) discussion with Contract Manager or written approval from Rehab Manager | Hold / Witness Point - Witness Point | Records - Lucidity | Responsible Person - Supervisor / Foreperson / QA | Records - Peer Reviewed Seal Designs
Pavement Markings/RRPMs | Tagging of existing Pavement Markings, Removal of RRPMs | Pavement Marking Set Out Sheet, CBP | Prior to sealing on each site | All raised pavement markers to be removed (1st CHAR(AMP) 2nd Coat Seal surfaces excluded) and existing line marking "tagged". Check for any new markings required | Witness Point | None | Foreperson / QA | Pavement Markings/RRPMs | Verification Activity - Tagging of existing Pavement Markings, Removal of RRPMs | Methods or Reference - Pavement Marking Set Out Sheet, CBP | Frequency - Prior to sealing on each site | Acceptance Criteria - All raised pavement markers to be removed (1st CHAR(AMP) 2nd Coat Seal surfaces excluded) and existing line marking "tagged". Check for any new markings required | Hold / Witness Point - Witness Point | Records - None | Responsible Person - Foreperson / QA | Responsible Person - Sealing Contract Manager / Engineer
Road Furniture CHAR(AMP) Sumps protected | Visual Inspection | Crew Breifing Plan / Visual | Prior to sealing on each site | Protect all road furniture in accordance with Crew Breifing Plan. Fabric CHAR(AMP) protect all sumps. | Witness Point | None | Foreperson | Road Furniture CHAR(AMP) Sumps protected | Verification Activity - Visual Inspection | Methods or Reference - Crew Breifing Plan / Visual | Frequency - Prior to sealing on each site | Acceptance Criteria - Protect all road furniture in accordance with Crew Breifing Plan. Fabric CHAR(AMP) protect all sumps. | Hold / Witness Point - Witness Point | Records - None | Responsible Person - Foreperson | [1] Size (Grades 2-5) CHAR(AMP) Shape (Grades 2-4)
Surface Condition/Temp | Physical / Visual Inspection | Visual / NZTA T/3 | Prior to sealing on each site | Surface area shall be dry and free from any loose chip, dust, dirt, vegetation. Temperature recorded on site prior to sealing commencing | Witness Point | None | Foreperson / QA | Surface Condition/Temp | Verification Activity - Physical / Visual Inspection | Methods or Reference - Visual / NZTA T/3 | Frequency - Prior to sealing on each site | Acceptance Criteria - Surface area shall be dry and free from any loose chip, dust, dirt, vegetation. Temperature recorded on site prior to sealing commencing | Hold / Witness Point - Witness Point | Records - None | Responsible Person - Foreperson / QA | Verification Activity - Lab Test
Stockpiles | Visual Inspection | CBP | Each Stockpile | Correct Source, Grade and quantity. Uniquely Identified. | Witness Point | Sealing Data Docket | Foreperson | Stockpiles | Verification Activity - Visual Inspection | Methods or Reference - CBP | Frequency - Each Stockpile | Acceptance Criteria - Correct Source, Grade and quantity. Uniquely Identified. | Hold / Witness Point - Witness Point | Records - Sealing Data Docket | Responsible Person - Foreperson | Methods or Reference - NZTA M/6
Spraying | Paper Start and Finish all runs | Spray Runs | All Runs | Mark out start / Finish | Witness Point |  | Sealing Contract Engineer / QA | Spraying | Verification Activity - Paper Start and Finish all runs | Methods or Reference - Spray Runs | Frequency - All Runs | Acceptance Criteria - Mark out start / Finish | Hold / Witness Point - Witness Point | Records - | Responsible Person - Sealing Contract Engineer / QA | Frequency - 1/500m3
Sealing | Longitudinal Joints out side of wheel tracks | Spray Runs | All Runs | Mark out lane lines by construction team | Witness Point |  | Sealing Contract Engineer / QA | Sealing | Verification Activity - Longitudinal Joints out side of wheel tracks | Methods or Reference - Spray Runs | Frequency - All Runs | Acceptance Criteria - Mark out lane lines by construction team | Hold / Witness Point - Witness Point | Records - | Responsible Person - Sealing Contract Engineer / QA | Acceptance Criteria - Size (ald mm) G2 9.5-12.0 G3 7.5-10.0 G4 5.5-8.0 G5 Report
Binder Application Rate | Tank Level dips prior to and after spray run | Dipstick | At Beginning of the day After 1st spray run of site After last spray run of site At end of tank prior to loading | Quantities used to be within the desired tolerance of design Spray Rate | Mandatory HOLD POINT | Spray Sheets | QA | Binder Application Rate | Verification Activity - Tank Level dips prior to and after spray run | Methods or Reference - Dipstick | Frequency - At Beginning of the day After 1st spray run of site After last spray run of site At end of tank prior to loading | Acceptance Criteria - Quantities used to be within the desired tolerance of design Spray Rate | Hold / Witness Point - Mandatory HOLD POINT | Records - Spray Sheets | Responsible Person - QA | Hold / Witness Point - Witness Point
Chip Spread Rate | Visual | Crew Briefing Plan/Visual | On going whilst seal being constructed | Chip is applied in accordance with the appropriate coverage as specified in the Crew Briefing Plan | Witness Point | Data Docket | QA/Foreperson | Chip Spread Rate | Verification Activity - Visual | Methods or Reference - Crew Briefing Plan/Visual | Frequency - On going whilst seal being constructed | Acceptance Criteria - Chip is applied in accordance with the appropriate coverage as specified in the Crew Briefing Plan | Hold / Witness Point - Witness Point | Records - Data Docket | Responsible Person - QA/Foreperson | Records - IANZ Lab Reports
Removal of Surplus Chip | Physical / Visual | Front Mounted Broom / Suction Truck, Downer Survey or MS Forms Post Seal Inspection | At conclusion of positive traffication within 48 hours | All sump and road furniture protection removed. Meets requirements of P/17 Table 2. | Witness Point | Post Seal Inspection | Sealing Contract Engineer / QA | Removal of Surplus Chip | Verification Activity - Physical / Visual | Methods or Reference - Front Mounted Broom / Suction Truck, Downer Survey or MS Forms Post Seal Inspection | Frequency - At conclusion of positive traffication within 48 hours | Acceptance Criteria - All sump and road furniture protection removed. Meets requirements of P/17 Table 2. | Hold / Witness Point - Witness Point | Records - Post Seal Inspection | Responsible Person - Sealing Contract Engineer / QA | Responsible Person - Sealing Contract Manager / Engineer
Post Seal Traffic Management | Physical / Visual | As per TMP | Full length and width of carriageway | Minimum of 48 hours under normal traffic flow. If rain forecast within 48 hours, traffication recommences until clear weather window of at least 48 hours | Hold Point | Zeus or suitable recorded weather data | Sealing Contract Manager / Engineer | Post Seal Traffic Management | Verification Activity - Physical / Visual | Methods or Reference - As per TMP | Frequency - Full length and width of carriageway | Acceptance Criteria - Minimum of 48 hours under normal traffic flow. If rain forecast within 48 hours, traffication recommences until clear weather window of at least 48 hours | Hold / Witness Point - Hold Point | Records - Zeus or suitable recorded weather data | Responsible Person - Sealing Contract Manager / Engineer | [2] Size (Grades 2-5) CHAR(AMP) Shape (Grades 2-4)
Post Seal Inspection | On Site Visual | Lucidity Post Seal Inpsection | After sealing is complete | Engineers requirements. Any defects identified, repairs programmed and costs estimated | Witness Point | Post Seal Inpsection | Sealing Contract Engineer / Manager / QA | Post Seal Inspection | Verification Activity - On Site Visual | Methods or Reference - Lucidity Post Seal Inpsection | Frequency - After sealing is complete | Acceptance Criteria - Engineers requirements. Any defects identified, repairs programmed and costs estimated | Hold / Witness Point - Witness Point | Records - Post Seal Inpsection | Responsible Person - Sealing Contract Engineer / Manager / QA | Verification Activity - Lab Test
Asbuilts and RAMM data | RAMM Update Sheet | RAMM Database | After sealing is complete | RAMM update sheet 100% complete and accurate, note data provided for RAMM update to be uploaded by others. As Built Drawing Complete. | Witness Point | As built information / RAMM Update Sheet | Sealing Contract Manager/ QA/QE | Asbuilts and RAMM data | Verification Activity - RAMM Update Sheet | Methods or Reference - RAMM Database | Frequency - After sealing is complete | Acceptance Criteria - RAMM update sheet 100% complete and accurate, note data provided for RAMM update to be uploaded by others. As Built Drawing Complete. | Hold / Witness Point - Witness Point | Records - As built information / RAMM Update Sheet | Responsible Person - Sealing Contract Manager/ QA/QE | Methods or Reference - NZTA M/6
Frequency - 1/500m3
Acceptance Criteria - Shape AGD/ALD Ratio G2,3,4 = 2.25 max G2,3,4 = min 98% with 2+ broken faces
Hold / Witness Point - Witness Point
Records - IANZ Lab Reports
Responsible Person - Sealing Contract Manager / Engineer
Cleanliness (Grades 2-6)
Verification Activity - Lab Test
Methods or Reference - NZTA M/6
Frequency - 1/500m3
Acceptance Criteria - Cleanness value G2 = 89 G3 = 87 G4 = 85 G5 CHAR(AMP) G6 Report only
Hold / Witness Point - Witness Point
Records - IANZ Lab Reports
Responsible Person - Sealing Contract Manager / Engineer
[1] Compatibility (Multi Layered seals)
Verification Activity - Comparison Of Chip ALD
Methods or Reference - Chipsealing in New Zealand NZTA (NZTA 2005)
Frequency - 11.5
Acceptance Criteria -
Hold / Witness Point - Witness Point
Records - IANZ Lab Reports
Responsible Person - Sealing Contract Manager / Engineer
[2] Compatibility (Multi Layered seals)
Verification Activity - Comparison Of Chip ALD
Methods or Reference - Chipsealing in New Zealand NZTA (NZTA 2005)
Frequency - 7.2
Acceptance Criteria -
Hold / Witness Point - Witness Point
Records - IANZ Lab Reports
Responsible Person - Sealing Contract Manager / Engineer
Bitumen Distributor
Verification Activity - IANZ Lab E/2 Results
Methods or Reference - Code of Compliance
Frequency - Annual
Acceptance Criteria - Speed Test(+-3% over 100m), Dipstick Test (+-50L over 2000L), Matt Test (app rate within 0.10L/m2, longitudinal within 10%, thirds within 5%, transverse within 20%)
Hold / Witness Point - Mandatory HOLD POINT - Client - Engineer Witness
Records - RNZ E2 Certificate
Responsible Person - Sealing Contract Manager / Engineer
Emulsion/PME Testing
Verification Activity - Lab Testing
Methods or Reference - Manufacture Specification
Frequency - Per Emulsion/Bitumen Production Batch
Acceptance Criteria - Bitumen Content, ITM 11-01, Viscosity, ITM 10-02, PH ITM-08-02
Hold / Witness Point - Witness Point
Records - IANZ Lab Reports
Responsible Person - Road Science
[1] Surface Texture - Measurement
Verification Activity - Sandcircle Measurement
Methods or Reference - NZTA T/3
Frequency - At time of Seal Inspection
Acceptance Criteria - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture
Hold / Witness Point - Witness Point
Records - Sandcircle Data
Responsible Person - Sealing Contract Manager / Engineer
[2] Surface Texture - Measurement
Verification Activity - ARRB Hawkeye or
Methods or Reference - NZTA T/3
Frequency - At time of Seal Inspection
Acceptance Criteria - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture
Hold / Witness Point - Witness Point
Records - Hawkeye Data
Responsible Person - Sealing Contract Manager / Engineer
[3] Surface Texture - Measurement
Verification Activity - NZTA HSD
Methods or Reference - NZTA T/3
Frequency - At time of Seal Inspection
Acceptance Criteria - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture
Hold / Witness Point - Witness Point
Records - High Speed Data
Responsible Person - Sealing Contract Manager / Engineer
Pre Seal Survey
Verification Activity - Downer Survey or MS Forms Pre Reseal Inspection
Methods or Reference - Downer Survey or MS Forms Pre Reseal Inspection
Frequency - At time of Seal Inspection
Acceptance Criteria - Record CHAR(AMP) any noted issues / Client
Hold / Witness Point - Witness Point
Records - Lucidity
Responsible Person - Sealing Contract Manager / Engineer
Construction Compliance testing
Verification Activity -
Methods or Reference -
Frequency - 24 hours in advance of seal construction commencement
Acceptance Criteria - Confirmation from renewals manager all testing has met requirements
Hold / Witness Point - Hold Point
Records - Email Confirmation
Responsible Person - Sealing Contract Manager / Engineer
Go/No Go Survey
Verification Activity - Visual, Zeus, Iris
Methods or Reference - Downer Survey Sealing Go / No Go, Road Science Zeus app CHAR(AMP) Downer Iris app
Frequency - Prior to sealing on each site
Acceptance Criteria - Pass on Go / No Go, Marginal CHAR(AMP) discussion with Contract Manager or written approval from Rehab Manager
Hold / Witness Point - Witness Point
Records - Lucidity
Responsible Person - Supervisor / Foreperson / QA
Pavement Markings/RRPMs
Verification Activity - Tagging of existing Pavement Markings, Removal of RRPMs
Methods or Reference - Pavement Marking Set Out Sheet, CBP
Frequency - Prior to sealing on each site
Acceptance Criteria - All raised pavement markers to be removed (1st CHAR(AMP) 2nd Coat Seal surfaces excluded) and existing line marking "tagged". Check for any new markings required
Hold / Witness Point - Witness Point
Records - None
Responsible Person - Foreperson / QA
Road Furniture CHAR(AMP) Sumps protected
Verification Activity - Visual Inspection
Methods or Reference - Crew Breifing Plan / Visual
Frequency - Prior to sealing on each site
Acceptance Criteria - Protect all road furniture in accordance with Crew Breifing Plan. Fabric CHAR(AMP) protect all sumps.
Hold / Witness Point - Witness Point
Records - None
Responsible Person - Foreperson
Surface Condition/Temp
Verification Activity - Physical / Visual Inspection
Methods or Reference - Visual / NZTA T/3
Frequency - Prior to sealing on each site
Acceptance Criteria - Surface area shall be dry and free from any loose chip, dust, dirt, vegetation. Temperature recorded on site prior to sealing commencing
Hold / Witness Point - Witness Point
Records - None
Responsible Person - Foreperson / QA
Stockpiles
Verification Activity - Visual Inspection
Methods or Reference - CBP
Frequency - Each Stockpile
Acceptance Criteria - Correct Source, Grade and quantity. Uniquely Identified.
Hold / Witness Point - Witness Point
Records - Sealing Data Docket
Responsible Person - Foreperson
Spraying
Verification Activity - Paper Start and Finish all runs
Methods or Reference - Spray Runs
Frequency - All Runs
Acceptance Criteria - Mark out start / Finish
Hold / Witness Point - Witness Point
Records -
Responsible Person - Sealing Contract Engineer / QA
Sealing
Verification Activity - Longitudinal Joints out side of wheel tracks
Methods or Reference - Spray Runs
Frequency - All Runs
Acceptance Criteria - Mark out lane lines by construction team
Hold / Witness Point - Witness Point
Records -
Responsible Person - Sealing Contract Engineer / QA
Binder Application Rate
Verification Activity - Tank Level dips prior to and after spray run
Methods or Reference - Dipstick
Frequency - At Beginning of the day After 1st spray run of site After last spray run of site At end of tank prior to loading
Acceptance Criteria - Quantities used to be within the desired tolerance of design Spray Rate
Hold / Witness Point - Mandatory HOLD POINT
Records - Spray Sheets
Responsible Person - QA
Chip Spread Rate
Verification Activity - Visual
Methods or Reference - Crew Briefing Plan/Visual
Frequency - On going whilst seal being constructed
Acceptance Criteria - Chip is applied in accordance with the appropriate coverage as specified in the Crew Briefing Plan
Hold / Witness Point - Witness Point
Records - Data Docket
Responsible Person - QA/Foreperson
Removal of Surplus Chip
Verification Activity - Physical / Visual
Methods or Reference - Front Mounted Broom / Suction Truck, Downer Survey or MS Forms Post Seal Inspection
Frequency - At conclusion of positive traffication within 48 hours
Acceptance Criteria - All sump and road furniture protection removed. Meets requirements of P/17 Table 2.
Hold / Witness Point - Witness Point
Records - Post Seal Inspection
Responsible Person - Sealing Contract Engineer / QA
Post Seal Traffic Management
Verification Activity - Physical / Visual
Methods or Reference - As per TMP
Frequency - Full length and width of carriageway
Acceptance Criteria - Minimum of 48 hours under normal traffic flow. If rain forecast within 48 hours, traffication recommences until clear weather window of at least 48 hours
Hold / Witness Point - Hold Point
Records - Zeus or suitable recorded weather data
Responsible Person - Sealing Contract Manager / Engineer
Post Seal Inspection
Verification Activity - On Site Visual
Methods or Reference - Lucidity Post Seal Inpsection
Frequency - After sealing is complete
Acceptance Criteria - Engineers requirements. Any defects identified, repairs programmed and costs estimated
Hold / Witness Point - Witness Point
Records - Post Seal Inpsection
Responsible Person - Sealing Contract Engineer / Manager / QA
Asbuilts and RAMM data
Verification Activity - RAMM Update Sheet
Methods or Reference - RAMM Database
Frequency - After sealing is complete
Acceptance Criteria - RAMM update sheet 100% complete and accurate, note data provided for RAMM update to be uploaded by others. As Built Drawing Complete.
Hold / Witness Point - Witness Point
Records - As built information / RAMM Update Sheet
Responsible Person - Sealing Contract Manager/ QA/QE