## ITC
type | name | values | prefix | postfix | usage count
checklist-flat | Colphene Uni NG Riser Pit (ITC)
checkpoint | Substrate
button | All surfaces dry, clean, smooth and free from sharp objects, laitance, oils, grease or any foreign materials which may inhibit or reduce adhesion. | Yes,No
button | Commencement of installation shall be taken as acceptance of the substrate by the Applicator | Yes,No
checkpoint | Colphene BSW UNI NG - To Raft Slab
button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
button | Apply COLPHENE BSW UNI NG loose laid on blinding concrete | Yes,No
button | Confirm minimum 100 mm side overlap | Yes,No
button | Confirm minimum 150 mm end lap between each strip | Yes,No
button | Confirm end laps are staggered by at least 300 mm | Yes,No
button | Confirm laps avoid excessive layering | Yes,No
button | Visual inspection of joint welds at cross laps | Yes,No
button | Confirm no laps at capping beam construction joint | Yes,No
button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 2-10mm bleed | Yes,No
button | Confirm all angle changes (inside and outside corners) are reinforced by heat-welding on additional 300 mm piece of COLPHENE BSW UNI NG centered on the angle | Yes,No
checkpoint | Colphene BSW UNI NG Reiforcement Strip - Floor/Wall Junction and Existing Wall Upturn
button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
button | Confirm minimum 100 mm side overlap | Yes,No
button | Confirm minimum 150 mm end lap between each strip | Yes,No
button | Confirm end laps are staggered by at least 300 mm | Yes,No
button | Confirm laps avoid excessive layering | Yes,No
button | Visual inspection of joint welds at cross laps | Yes,No
button | Confirm no laps at capping beam construction joint | Yes,No
button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 2-10mm bleed | Yes,No
Pressure Seal
button | Pressure seal conecting new membrane with existing - By Delta | Yes,No
button | Confirm Pressure seal steel plate width : 75mm | Yes,No
button | Confirm Pressure seal steel plate thickness: 3mm | Yes,No
button | Bolts sealed galvanised paint - By Delta | Yes,No
button | Bolts: 12mm wide Excalibur bolts with washers installed at 100mm spacing c/c | Yes,No
checkpoint | SOPRAHOSE 13
checkpoint | Substrate Requirements:
button | Flat, dry, clean, and smooth surface. | Yes,No
button | Free from sharp objects, laitance, oils, grease, or any materials that might hinder adhesion. | Yes,No
button | Commencement of installation shall be taken as acceptance of the substrate by the Applicator | Yes,No
checkpoint | Positioning SOPRAHOSE 13:
button | SOPRAHOSE 13 should be centered on the substrate or positioned with a minimum of 100 mm concrete cover from any external edge. | Yes,No
checkpoint | Installation of SOPRAHOSE 13:
button | Must lay flat on the concrete with appropriate hose clamps mechanically fixed. | Yes,No
button | Hose clips should be spaced at 200 mm intervals. | Yes,No
checkpoint | SOPRAHOSE 13 End Box:
button | To be installed on the formwork flask with the internal side of the wall or slab. | Yes,No
checkpoint | Hose End Overlap:
button | A minimum 150 mm parallel overlap required, with 30-50 mm gap between the hoses. | Yes,No
checkpoint | Injection Boxes
button | Installed at a maximum spacing of 10 meters. | Yes,No
checkpoint | Hold Points
button | Bravada Installer: Final review to ensure compliance with the shop drawing/specification. | Yes,No
button | Bravada Supervisor: Final review for compliance.
button | Delta Group Project Team: Review and acknowledgment of the Injection Hose Prototype, ITC completion, and handover of the works package.
checkpoint | Colphene BSW UNI NG - To Insitu Walls
button | ANTIROCK PRIMER can be applied with a brush or roller on clean, dry substrates free of any residue that may hinder adherence. Shake well before using. | Yes,No
button | It must be thoroughly dry before applying the waterproofing membrane. Drying time will vary depending on air and surface temperature and humidity. | Yes,No
button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
button | Confirm minimum 100 mm side overlap | Yes,No
button | Confirm minimum 150 mm end lap between each strip | Yes,No
button | Confirm end laps are staggered by at least 300 mm | Yes,No
button | Confirm laps avoid excessive layering | Yes,No
button | Visual inspection of joint welds at cross laps | Yes,No
button | Confirm no laps at capping beam construction joint | Yes,No
button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 2-10mm bleed | Yes,No
button | Confirm all angle changes (inside and outside corners) are reinforced by heat-welding on additional 300 mm piece of COLPHENE BSW UNI NG centered on the angle | Yes,No
checkpoint | Sopradrain 20 - To Insitu Walls
button | The substrate must be firm, even, clean and free from loose materials or any construction debris on the surface. | Yes,No
button | Install SOPRADRAIN 20 with the geotextile facing the backfill. | Yes,No
button | Join by simply butting edge to edge and overlapping the geotextile overhang and securing with reinforced canvastape | Yes,No
button | Terminate SOPRADRAIN 20 by nailing pressure bar at required height | Yes,No
checkpoint | WPA 100 - To Top of Raft Slab
button | Mix well the product before use | Yes,No
button | WPA100 is applied with a with a brush or a roller in two (2) layers. Application must be a minimum of 2 coats @ >= 1.2kg/m2 per coat to achieve a dry film thickness not less than 2mm as per the technical data sheet. | Yes,No
button | Ready to recoat after 2 hours Dry: 24 hours (remains tacky to touch) | Yes,No
button | Store WPA 100 in chemical bunds provided by Delta | Yes,No
checkpoint | CHECKLIST COMPLETE AND SIGNED
button | ITC completed | Yes,No

## ITP
type | name | values | prefix | postfix | usage count
checklist-flat | Colphene Uni NG Riser Pit ITP
Checkpoint | RISER PIT WATERPROOFING ITP | Yes,No
button | Sample Submissions Approved | Yes,No
button | Shop Drawings Approved | Yes,No
button | Colphene BSW UNI NG Installed - To Raft Slab Blinding | Yes,No
button | Colphene BSW UNI NG Upturn to Installed - Existing Wall | Yes,No
button | Colphene BSW UNI NG Reiforcement Strip Installed - Floor/Wall Junction | Yes,No
button | Pressure Seal installed - By Delta | Yes,No
button | Injection System Installed | Yes,No
button | Primer Installed - To Insitu Walls | Yes,No
button | Colphene BSW UNI NG Installed - To Insitu Walls | Yes,No
button | Sopradrain Installed - To Insitu Walls | Yes,No
button | WPA 100 Installed - To Top of Raft Slab | Yes,No