## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
2a137d84-cdf9-40ab-be63-48fb0850fd2c | checklist | Colphene Uni NG Riser Pit (ITC) |  | Colphene Uni NG Riser Pit (ITC) |  | 66483389-e8f8-4a8c-b149-130d03e504e6
226addae-abb4-43a4-a65a-4fa3f1875217 | section | Details
c3d55f82-0daa-4630-99b3-52e79f5ef482 | checkpoint | Substrate
c2cc497a-8444-5fff-9631-ab9a10d5a42f | button | All surfaces dry, clean, smooth and free from sharp objects, laitance, oils, grease or any foreign materials which may inhibit or reduce adhesion. | Yes,No
3aa758d9-2654-5563-96c0-f2c4bb5deec0 | button | Commencement of installation shall be taken as acceptance of the substrate by the Applicator | Yes,No
c1bb9b38-063c-4d4b-b7ce-b887b115f832 | checkpoint | Colphene BSW UNI NG - To Raft Slab
5f17449b-4f0d-5725-ac86-ce0414158842 | button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
59906662-7e5a-5ced-b989-3536b6bcec18 | button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
8617d554-d0b8-5f59-a820-4cfcdce80649 | button | Apply COLPHENE BSW UNI NG loose laid on blinding concrete | Yes,No
3385c9b4-c4e5-5f50-8b21-fc58fa5ddf52 | button | Confirm minimum 100 mm side overlap | Yes,No
d62fe843-27d0-5765-936d-61149f5cc37f | button | Confirm minimum 150 mm end lap between each strip | Yes,No
729c4898-a9de-5bde-8b13-68a12b9a3c8a | button | Confirm end laps are staggered by at least 300 mm | Yes,No
b11259a7-01d3-5c18-a221-87a2a3a590d3 | button | Confirm laps avoid excessive layering | Yes,No
95b4427a-4f9f-5fdc-8000-1e5b3ac6a19b | button | Visual inspection of joint welds at cross laps | Yes,No
e1d7c715-43e3-5a75-a23f-7de6e427b6c7 | button | Confirm no laps at capping beam construction joint | Yes,No
0a2ba39d-abf7-533d-ac12-8d101b988ba3 | button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 2-10mm bleed | Yes,No
e06df59e-1687-5112-bde9-94e98c23ebf9 | button | Confirm all angle changes (inside and outside corners) are reinforced by heat-welding on additional 300 mm piece of COLPHENE BSW UNI NG centered on the angle | Yes,No
b27d5723-a7cc-48d9-9507-3e78376e9534 | checkpoint | Colphene BSW UNI NG Reiforcement Strip - Floor/Wall Junction and Existing Wall Upturn
fa3e56a1-e41f-5082-a0d0-894b1ce8faf6 | button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
9d63b735-8565-551a-af3b-58af3ffbb405 | button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
149f94ce-ea63-56c8-ab62-163cfaff654f | button | Confirm minimum 100 mm side overlap | Yes,No
2b897576-6890-5038-ae39-45e8ec4fc86c | button | Confirm minimum 150 mm end lap between each strip | Yes,No
8755b459-5512-504d-8fc6-7e648357a72e | button | Confirm end laps are staggered by at least 300 mm | Yes,No
1b104f4d-2edf-53ac-91df-c769acbc84af | button | Confirm laps avoid excessive layering | Yes,No
b4661318-27ad-5524-8ea1-b8ec1625271d | button | Visual inspection of joint welds at cross laps | Yes,No
5adc1450-ff9f-513b-86d4-69760a587566 | button | Confirm no laps at capping beam construction joint | Yes,No
d3e5f15c-9194-5b8b-bb91-5fec6a2213f6 | button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 2-10mm bleed | Yes,No
6ed0694d-0de7-4069-8cc8-470227c394ea | checkpoint | Pressure Seal
86f84565-68ab-5905-8dee-c7fb9e620f2c | button | Pressure seal conecting new membrane with existing - By Delta | Yes,No
| button | Confirm Pressure seal steel plate width : 75mm | Yes,No
| button | Confirm Pressure seal steel plate thickness: 3mm | Yes,No
de7c57e6-54aa-5f18-9f1b-f7c54fe2c72f | button | Bolts sealed galvanised paint - By Delta | Yes,No
| button | Bolts: 12mm wide Excalibur bolts with washers installed at 100mm spacing c/c | Yes,No
fb4ea8c7-981a-4ca3-a0c2-42a64b293a9f | checkpoint | SOPRAHOSE 13
c34909a2-e415-46f8-8942-26f3c731b225 | checkpoint | Substrate Requirements:
cb8f3c7d-8968-5a1a-9772-5f8bcf0c4857 | button | Flat, dry, clean, and smooth surface. | Yes,No
da99fd49-a1a6-5994-a157-d568bdadc285 | button | Free from sharp objects, laitance, oils, grease, or any materials that might hinder adhesion. | Yes,No
11da3e25-e295-581c-95ef-f72e37efbef8 | button | Commencement of installation shall be taken as acceptance of the substrate by the Applicator | Yes,No
a7c09526-948b-4bf2-815b-52318a196314 | checkpoint | Positioning SOPRAHOSE 13:
221a042f-6321-5ad6-b122-49980ff58248 | button | SOPRAHOSE 13 should be centered on the substrate or positioned with a minimum of 100 mm concrete cover from any external edge. | Yes,No
4aae1d52-9409-4541-9ad6-cdfda2bfbb9b | checkpoint | Installation of SOPRAHOSE 13:
11ae3588-27af-505f-8e30-66ccd8ea55aa | button | Must lay flat on the concrete with appropriate hose clamps mechanically fixed. | Yes,No
f613b382-6cc8-5e70-8d5f-50eba1959070 | button | Hose clips should be spaced at 200 mm intervals. | Yes,No
f595cbe6-1710-4181-b452-294e6501b20d | checkpoint | SOPRAHOSE 13 End Box:
53a362a2-8dff-5324-8cb6-abe0b09650eb | button | To be installed on the formwork flask with the internal side of the wall or slab. | Yes,No
eb5eb402-f98f-4f35-986a-b61303a31da0 | checkpoint | Hose End Overlap:
2f331c71-eea7-5d77-843f-f46a8bfa0dee | button | A minimum 150 mm parallel overlap required, with 30-50 mm gap between the hoses. | Yes,No
121da513-e53f-43c9-922b-08f1ef1a6d55 | checkpoint | Injection Boxes
e235398f-e896-5a8f-b9a4-0f24d8e5f2c0 | button | Installed at a maximum spacing of 10 meters. | Yes,No
47f923e5-816e-4e03-a12f-4dd3e46daac7 | checkpoint | Hold Points
6178a85e-9fd6-55db-94ba-1500ce995007 | button | Bravada Installer: Final review to ensure compliance with the shop drawing/specification. | Yes,No
8d302826-85f5-5a65-bccc-4ed5d7050cb9 | button | Bravada Supervisor: Final review for compliance. | Yes,No
3eabff30-a46d-5185-9c6c-a7e2cbecf37e | button | Delta Group Project Team: Review and acknowledgment of the Injection Hose Prototype, ITC completion, and handover of the works package. | Yes,No
cd02caab-d3a6-40ab-bb02-b42cf6d3a35c | checkpoint | Colphene BSW UNI NG - To Insitu Walls
c3afa6a2-f73b-5b0e-8b15-86314bab41ea | button | ANTIROCK PRIMER can be applied with a brush or roller on clean, dry substrates free of any residue that may hinder adherence. Shake well before using. | Yes,No
43a6a1b7-4d89-50af-b714-aa9262319f07 | button | It must be thoroughly dry before applying the waterproofing membrane. Drying time will vary depending on air and surface temperature and humidity. | Yes,No
15ab4212-e7d0-5ba1-a0a1-d3b275e0bbe8 | button | Confirm rolls stored upright, with the selvedge side on top. If the product is stored outdoors confirm covered with an protective cover | Yes,No
af56142b-cbe9-5376-bde5-0343fa00f06e | button | Check COLPHENE BSW UNI NG thickness is 4mm | Yes,No
6ab635e5-9bff-5872-959b-3fbde66a62c7 | button | Confirm minimum 100 mm side overlap | Yes,No
6edbd7f6-5dcf-57e1-af82-15af29d41dce | button | Confirm minimum 150 mm end lap between each strip | Yes,No
87048868-236b-5adc-971b-43cd0fabebfc | button | Confirm end laps are staggered by at least 300 mm | Yes,No
b6e49909-a022-5704-bf25-3659fb08879f | button | Confirm laps avoid excessive layering | Yes,No
f5c1d0f1-1810-56d3-8557-19c92603e710 | button | Visual inspection of joint welds at cross laps | Yes,No
d190e832-393c-56ac-8424-1ea7f978a9c5 | button | Confirm no laps at capping beam construction joint | Yes,No
63693035-c93d-52b4-972c-fd048f89bb19 | button | Confirm all side laps are sealed and end laps by heat-welding the selvedge with a propane torch and minimum 2-10mm bleed | Yes,No
0a5ad080-21cf-52c4-9459-b238aeae3fa7 | button | Confirm all angle changes (inside and outside corners) are reinforced by heat-welding on additional 300 mm piece of COLPHENE BSW UNI NG centered on the angle | Yes,No
428a4757-1f1c-417a-b406-9cd3917e404b | checkpoint | Sopradrain 20 - To Insitu Walls
d87c1f47-34b0-5673-bd1b-35ef23ab6e7f | button | The substrate must be firm, even, clean and free from loose materials or any construction debris on the surface. | Yes,No
00ef31f6-9002-53c7-90d5-f2a1dfb4da1d | button | Install SOPRADRAIN 20 with the geotextile facing the backfill. | Yes,No
e6545ea8-f8c8-5325-afd1-4120e14edcc2 | button | Join by simply butting edge to edge and overlapping the geotextile overhang and securing with reinforced canvastape | Yes,No
71cfece1-bdcf-5f2d-8134-2740d85d93fd | button | Terminate SOPRADRAIN 20 by nailing pressure bar at required height | Yes,No
301c7b4b-cfb8-4f24-b689-e5515667dea3 | checkpoint | WPA 100 - To Top of Raft Slab
c6fb7c09-7280-59b5-972b-e7fd69036bc0 | button | Mix well the product before use | Yes,No
8b519b43-a3ce-5613-9ae3-18d0e11c0c4f | button | WPA100 is applied with a with a brush or a roller in two (2) layers. Application must be a minimum of 2 coats @ >= 1.2kg/m2 per coat to achieve a dry film thickness not less than 2mm as per the technical data sheet. | Yes,No
49dc7a43-299c-51ca-a265-4642388b0ef3 | button | Ready to recoat after 2 hours Dry: 24 hours (remains tacky to touch) | Yes,No
81b1da43-2626-5b45-9d7e-1c5e74f176cd | button | Store WPA 100 in chemical bunds provided by Delta | Yes,No
10291de5-55ec-4684-afbf-63ccfcb2c8ea | checkpoint | CHECKLIST COMPLETE AND SIGNED
770cd23a-7f59-5ae4-a037-2e53c55318f9 | button | ITC completed | Yes,No