## Table 1
Inspection and Test Plan - Switchboard Delivery Electrical Installation ITP Reference 561482-ITP-001
SECTION 1 – GENERAL DETAILS
Project Name: | DCC11014 Water Pump Station Renewals - SILVERSTREAM | [14 empty] | Inspection Key Use in sections 3, 4 and |  |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 561482 | [14 empty] | A Action |  |  | Role Key |  |  | Name |  |  |  |  | Signature/ Initial
Customer: | Dunedin City Council | [14 empty] | B Report by Breach |  |  | CM Construction Manager |  |  | Stephen Vorgers
Contract Number: | DCC11014-WPS002 | [14 empty] | C Check |  |  | CR Cust. Representative |  |  | Joff Riley / Mark Todd
Area/ Sub-System: | Switchboard Installation - SILVERSTREAM | [8 empty] | Lot ID Number: | N/A |  |  |  |  | D Dimension Inspection |  |  | IP Inspection Personnel |  |  | Hamish Watson
[16 empty] | E Examine |  |  | MC Material Controller
ITP Number: | 561482-ITP-001 | [8 empty] | Version: | DRAFT |  |  |  |  | H Hold Point |  |  | OP Operations Manager
ITP Description: | Switchboard Delivery and Electrical Installation | [14 empty] | I Inspection |  |  | PM Project Manager |  |  | Matt Paterson
Discipline: | Switchboard | [14 empty] | M Monitor on Random Basis |  |  | PS Project Supervisor
Specification: | C11014 Water Pump Station Renewals Specification 12581908 | [14 empty] | O Operation |  |  | QE Quality Engineer
[16 empty] | R Review |  |  | QM QA Manager
Drawings: | "Construction Issue Drawings as issued by GHD - Silverstream Pump Station Project Ref: 12581908-GHD-PS-SS-DRG-GN Drawings: G0001, M0001 through M0004 & P0001" | [14 empty] | S Subcontractor |  |  | SP Supervisor |  |  | Hamish Watson
[16 empty] | V Visual Verification |  |  | ST Superintendent
Prepared By: (Name) | Hamish Watson / Matt Paterson | [8 empty] | Date: | 2010-12-24 |  |  |  |  | W Witness Point |  |  | SV Surveyor
Quality Specified: | None - As per Specification requirements | [17 empty] | WS Welding Supervisor
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  |  | Name: |  |  |  | Hamish Watson | [7 empty] | Signature: | [6 empty] | Date:
Downer Approval |  |  | Name: |  |  |  | Matt Paterson/Stephen Vorgers | [7 empty] | Signature: | [6 empty] | Date:
Customer Approval |  |  | Name: |  |  |  | Joff Riley / Bruce Buxton | [7 empty] | Signature: | [6 empty] | Date:
DG-QA-TP018 Internal Use Only © Downer. All Rights Reserved | [22 empty] | Page 1 of 4 Version: 1.2 Warning: Printed documents are UNCONTROLLED
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. |  | Activity/ Task Description |  | Inspection Point: Quality Control Activity |  |  |  |  | Acceptance Criteria |  |  |  | Verifying Document |  |  |  | Frequency |  |  | Inspection Type (Visual, other) |  |  |  |  | Inspection
[25 empty] | Key |  |  |  | By (Role Key)
3.1 |  | Inspection of Switchboard Cabinet Pieces prior to delivery to site |  | Check overall condition. check connections for internal electrical components |  |  |  |  | Visual check and report any defects or areas of concern |  |  |  | Email or NTE to report |  |  |  | Once |  |  | Visual + Photograph |  |  |  |  | C |  |  |  | IP/B
3.2 |  | Delivery of Switchboard materials to site |  | Check and verify that the switchboard materials have been delivered damage free |  |  |  |  | materials are damage free |  |  |  | Material Delivery Docket |  |  |  | Once |  |  | Visual + inspection |  |  |  |  | C |  |  |  | IP
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
4.1 |  | On-site assembly |  |  | Pre-Removal of required covers from Switchboard |  |  | isolation of switchboard is proven |  |  |  | on site testing, isolation tags in place |  |  |  |  | once |  |  | Visual |  |  |  | I |  |  |  | IP
4.2 |  | On-site assembly |  |  | Switchboard exterior panels removed as required |  |  | work area secured, all voltage sources isolated. no signs of degradation on switchboard. |  |  |  | Testing, photos as required |  |  |  |  | once |  |  | Visual + Photograph |  |  |  | I |  |  |  | IP
4.3 |  | Connection of new Generator Change-over cabinet. |  |  | connections of electrical cabling/bus bars. |  |  | Cabling/busbars connected correctly, insulation resistance between conductors acceptable. |  |  |  | Switchboard Acceptance Test. C.O.C from Switchboard Manufacturers. |  |  |  |  | Once |  |  | Visual + Photograph |  |  |  | I |  |  |  | IP
4.4 |  | Re-Energizing of switchboard |  |  | Switchboard work completed. |  |  | Switchboard upgrades completed. testing completed, interlocks between main switch and generator switch tested and verified, phase rotation confirmed |  |  |  | Switchboard C.O.C, instrument test of supply mains. |  |  |  |  | once |  |  | Visual + Inspection |  |  |  | I |  |  |  | IP
4.5 |  | Submission/review/appr oval of the Level 2 FD |  |  | Software functionality meets expectations |  |  | Approval from consultant |  |  |  | NTC |  |  |  |  | Once |  |  | Visual |  |  |  | I |  |  |  | IP
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
5.1 | Switchboard |  |  |  |  | Assembled, inspection carried out and approved |  |  | Electrical Testing completed, all covers in place and secured. all bolts present. R.O.I issued by electrical inspector. |  |  |  |  | Switchboard acceptance test sheet. |  |  |  | once |  |  | Visual + Document |  |  |  |  | I |  |  | IP
SECTION 6 – COMMENTS
[9 empty] | Customer Release Granted: |  |  |  |  | ☐ Yes |  |  |  | ☐ No |  |  | Date:
Certificate Number: