## Table 1
Inspection and Test Plan - Pump/Motor 3 Installation ITP Reference Number 561482-ITP-004.3
SECTION 1 – GENERAL DETAILS
Project Name: | DCC11014 Water Pump Station Renewals - SILVERSTREAM | [14 empty] | Inspection Key Use in sections 3, 4 and |  |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | 561482 | [14 empty] | A Action |  |  | Role Key |  |  | Name |  |  |  |  | Signature/ Initial
Customer: | Dunedin City Council | [14 empty] | B Report by Breach |  |  | CM Construction Manager |  |  | Stephen Vorgers
Contract Number: | DCC11014-WPS002 | [14 empty] | C Check |  |  | CR Cust. Representative |  |  | Joff Riley / Mark Todd
Area/ Sub-System: | Pump Installation - SILVERSTREAM | [8 empty] | Lot ID Number: | N/A |  |  |  |  | D Dimension Inspection |  |  | IP Inspection Personnel |  |  | Aaron Sutherland
[16 empty] | E Examine |  |  | MC Material Controller
ITP Number: | 561482-ITP-004.3 | [8 empty] | Version: | DRAFT |  |  |  |  | H Hold Point |  |  | OP Operations Manager
ITP Description: | Installation of Pumps & Motors (Pump 3) - Inspection Test Plan | [14 empty] | I Inspection |  |  | PM Project Manager |  |  | Matt Paterson
Discipline: | Pumps | [14 empty] | M Monitor on Random Basis |  |  | PS Project Supervisor
Specification: | C11014 Water Pump Station Renewals Specification 12581908 | [14 empty] | O Operation |  |  | QE Quality Engineer
[16 empty] | R Review |  |  | QM QA Manager
Drawings: | Construction Issue Drawings as issued by GHD - Silverstream Pump Station Project Ref: 12581908-GHD-PS-SS-DRG-GN Drawings: G0001, M0001 through M0004 & P0001 | [14 empty] | S Subcontractor |  |  | SP Supervisor |  |  | Bruce Allan
[16 empty] | V Visual Verification |  |  | ST Superintendent
Prepared By: (Name) | Matt Paterson | [8 empty] | Date: | 2024-10-12 |  |  |  |  | W Witness Point |  |  | SV Surveyor
Quality Specified: | None - As per Specification requirements | [17 empty] | WS Welding Supervisor |  |  | Matt York
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
ITP Close-Out by Downer |  |  | Name: |  |  |  | Bruce Allan | [7 empty] | Signature: | [6 empty] | Date:
Downer Approval |  |  | Name: |  |  |  | Matt Paterson/Stephen Vorgers | [7 empty] | Signature: | [6 empty] | Date:
Customer Approval |  |  | Name: |  |  |  | Joff Riley / Bruce Buxton | [7 empty] | Signature: | [6 empty] | Date:
DG-QA-TP018 Internal Use Only © Downer. All Rights Reserved | [22 empty] | Page 1 of 6 Version: 1.2 Warning: Printed documents are UNCONTROLLED
SECTION 3 – RECEIVING INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. |  | Activity/ Task Description |  | Inspection Point: Quality Control Activity |  |  |  |  | Acceptance Criteria |  |  |  | Verifying Document |  |  |  | Frequency |  |  | Inspection Type (Visual, other) |  |  |  |  | Inspection
[25 empty] | Key |  |  |  | By (Role Key)
3.1 |  | Inspection of Plinths for pump 3 |  | Check overall condition. Cracks/fissures or breaks or areas of weakness |  |  |  |  | Visual check and report any defects or areas of concern |  |  |  | Email or NTE to report |  |  |  | once |  |  | Visual + Photograph |  |  |  |  | C |  |  |  | IP/B
3.2 |  | Delivery of Pump 3 to site from Downer storage facility |  | Check and verify that correct pump is delivered |  |  |  |  | Pump is damage free |  |  |  | 1. KSB delivery docket. 2. Pump storage ITP |  |  |  | Once |  |  | Visual |  |  |  |  | C |  |  |  | IP
3.3 |  | Delivery of Pump 3 Motor to site from Downer storage facility. |  | Check and verify that correct motor is delivered |  |  |  |  | Motor is damage free |  |  |  | 1. KSB delivery docket. 2. Pump storage ITP |  |  |  | Once |  |  | Visual |  |  |  |  | C |  |  |  | IP
3.4 |  | Delivery of Pump & Motor mounting plate Downer storage facility |  | Check & Verify that correct Mounting plate is delivered |  |  |  |  | Mounting plate is dumensionally correct and is damage free |  |  |  | 1. KSB delivery docket. 2. Pump storage ITP |  |  |  | Once |  |  | other |  |  |  |  | R |  |  |  | CR
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
4.2 |  | On-site assembly |  |  | Correct Pump to Mounting Plate Assembly. |  |  | Ensure all fasteners are tight and toqued to manufacturers specifications |  |  |  | KSB documentation & Installation Instructiions |  |  |  |  | Once/per pumpset |  |  | Visual + Written |  |  |  | Inspection |  |  |  | IP
4.3 |  | Pump 3 Installation |  |  | Correct Mounting plate position on plinth, correct use of fasteners and torque requirements, in accordance with KSB installation instruction |  |  | Position is determined by the fixed pipework. Ensure alignment of flange face is parallel to wet well wall |  |  |  | Drawing M0001 |  |  |  |  | Once |  |  | Visual + Photograph |  |  |  | A/D |  |  |  | IP
4.4 |  | Pump 3 Motor Installation |  |  | Motor/Pump shaft alignment |  |  | Motor and shaft aligment as best as possible |  |  |  | KSB documentation & Installation Instructiions. Nothing filal alignment to be undertaken by a Technician - Ref: 561482-ITP-005.3 |  |  |  |  | Once |  |  | Visual + Photograph |  |  |  | A/D |  |  |  | IP
Note: Electrical connection of pumps and commissioning are covered in separate ITP's
SECTION 5 – FINAL INSPECTION AND HANDOVER Insert additional or delete unused rows as required. Include reference to specification.
5.1 | Pump 3 & Motor assembly complete |  |  |  |  | Proceed with 561482-ITP005.3 |  |  | Pump & Motor bolted to mounting plate and mounted to plinth. |  |  |  |  | This ITP |  |  |  | once |  |  | Visual + Document |  |  |  |  | I |  |  | IP
SECTION 6 – COMMENTS
[9 empty] | Customer Release Granted: |  |  |  |  | ☐ Yes |  |  |  | ☐ No |  |  | Date:
Certificate Number: