## ITP
Inspection and Test Plan Te Ara o Te Ata MMA-QA-ITP-Z06-BR1-SU003 Title: Insitu Concrete
| This ITP has been prepared by |  |  |  | Reviewed by Quality Manager |  |  | Reviewed by CPS |  |  |  |  | Approved by Construction Manager
Rev # | Name | Signature |  | Date | Name | Signature | Date | Name |  | Signature |  | Date | Name |  | Signature |  | Date
Rev 01 | Nick Myers-Kay | See Approvals Tab |  | 30.01.25 | Whineray Arries | See Approvals Tab | 13.03.25 | Tim Brook |  | See Approvals Tab |  | 13.03.25 | Hardus Pieters |  | See Approval Tab |  | 17.03.25
Rev 02
Rev 03
Rev 04
Method Statement Ref:
Verification Method: Hold [H] – work will not proceed past Hold Point until released by organisation imposing hold; Inspection [I] – formal inspection activity to be undertaken and recorded; ensure correct verifying records are in place; Witness [W] – an inspection that may be witnessed by organisation imposing hold; allow reasonable notification period; Review [R] – review of reports, records or other evidence of compliance. | [7 empty] | Responsibilities PE = MTM Alliance Construction TWD = Temporary Design Team
Activity / Specification: | [7 empty] | Area Location / Work Breakdown:
Item | Construction Step or Material |  |  | Specifications and Standards |  | Acceptance criteria and testing | [5 empty] | Responsible |  |  |  | Verifying Records Checklists, Test and Supplier Certificates
[6 empty] | Method / Description | Test frequency |  | Conformance Criteria |  |  | Contractor | Designer | Client | Lab
1.0 Pre-Construction
1.01 | Approved CWP |  |  |  |  | Document Review | Prior to personnel starting |  | Ensure all crew members are briefed on the CWP |  |  | H | H |  |  | Signed off CWP
1.02 | IFC issued |  |  | Consent conditions |  | Document Review | Prior to starting |  | Ensure all drawings are approved and of the latest revision, or written approval from PAB |  |  | H | H |  |  | IFC drawings or written approval from PAB
1.03 | Approved SCWMP |  |  | Consent conditions |  | Document Review | Once prior to works commencing |  | TRC review and approval |  |  | H |  |  |  | Approved SCWMP
1.04 | Method Statements - At least 5 days before commencing any supply of concrete to site a method statement(s) shall be submitted to the the Design Engineer for review. |  |  | Concrete specification Clause 8.2 |  | Document Review | Prior to starting |  | Review and Approval |  |  | H | H |  |  | CPSA
1.05 | Concrete thermal modelling - large colume pours to consider thermal effects |  |  | Concrete specification Clause 9.2 and Special Concrete NZS 3104 |  | Document Review | Prior to commencement |  | Maximum concrete shall not exceed 70 degree C and maximum differential 20 degree C |  |  | H | H |  |  | Heat of Hydration Report
2.0 Material Compliance
2.01 | Material Compliance - Concrete Concrete mix designs include 30MPa, 40MPa & 50MPa with aggregate sizes ranging from 13mm for SCC to 19mm are to be submitted to the CPS team for review and approval for use with the work covered in this ITP incliding additives required specific to the special contrcrete for heat of hydration. |  |  | CPS Approval Concrete Specifications Clause 7.2 and 9.2 |  | Document Review | Prior to commencement |  | CPS Approval Concrete Specifications Clause 7.2 and 9.1 |  |  | H | H |  |  | Request for approval of concrete mix
2.02 | Material Compliance - Reinforcing Steel Reinforcement shall be Grade 500E and comply with AS/NZS 4671 & NZS 3109 and shall be the grade called up on the design drawing and approved shop drawings. |  |  | AS/NZS4671 & NZS3109 Reinforcing Specifications Clause 6.1 |  | Document review Mill certificates provided | Prior to commencement |  | CPS Approval AS/NZS4671 & NZS3109 Reinforcing Specifications Clause 6.1 |  |  | H | H |  |  | Traceability of steel via Cast Batch/Heat Summary and Detail Sheets and Mill Certificates
2.03 | Material Compliance - Mechanical Anchorage System Mechanical Anchorage system used with grade 300E and 500E complying with AS/NZ 4671. Systems to be considered: Ancon RT, IMBMS, Reidbar Steel |  |  | Systems tested to demonstrate compliance with section 4.2.1.f of the Bridge Manual. Mechanical Coupling system to be tested to demonstrate compliance with AS/NZS4671 |  | Document Review | Prior to commencement |  | CPS Approval Reinforcing Specifications Clause 6.1.5 |  |  | H | H |  |  | Request for approval from CPS and manufactureres certificates
3.0 During Construction
3.1.1 | Pre-Pour Concrete Inspection - Reinforcing, formwork & cast in itmes to be regularly inspected by nominated Quality Representative and or Design Representative. Full pre-pour inspection to be carried out prior to pour date. |  |  | Concrete Specification Clause 5, 7 & 8.5 - 8.7 |  | Site Inspection | Prior to concrete pour |  | Concrete Speciffication Clause 5 & 7 |  |  | H | H |  |  | Signed pre-pour inspection sheet
3.1.2 | Concrete Testing and Monitoring - Onsite testing of each truck for workability. A set of 4 test cylinders per 50m3 or part thereof for 1 cylinder tested at 7 days and the remaining 3 cylinders tested at 28 days for compressive strength. |  |  | Concrete Specification Clause 7.2.1 & 7.2.2 |  | Test results and pour record sheet | During concrete pour |  | Concrete Specification Clause 7.2.1 & 7.2.2 |  |  | H | H |  |  | Concrete Delivery dockets with onsite test records Concrete Compressive Strength test results
3.1.3 | Concrete Placing - Concrete shall be handled, placed, finished and cured in accordance with concrete specification. |  |  | NZS 3109 section 7 and Concrete Specification Clause 8.3 |  | Site Inspection | During concrete pour |  | NZS 3109 section 7 |  |  | W | W |  |  | Site photos
3.1.4 | Special Concrete - Slabs on Grade. Plant engineer to design concrete to eliminate the incidence of plastic shrinkage cracking, plastic settlement and or early age thermal cracking |  |  | Concrete specification Clause 9.1 and Special Concrete NZS 3104 |  | Mix designs and methodologies | During concrete pour |  | NZS 3104 |  |  | H | H |  |  | Data results
3.1.5 | Special Concrete - Mass Concrete Pours. Temperature monitoring using data loggers as per manuacturers reconmendations. Following first mass pour, data results to confirm if further monitoring required at second mass pour. |  |  | Concrete specification Clause 9.2 and Special Concrete NZS 3104 |  | Data loggers | During concrete pour |  | Maximum concrete shall not exceed 70 degree C and maximum differential 20 degree C |  |  | H | H |  |  | Data results
4.0 Post Construction
4.01 | Post pour inspection - Inspection of any Type B Construction Joints if applicable with respective concrete pour. Quality Representative and or Design Representative to inspect concrete surfaces after the formwork have been stripped. 7 days curing required on top and sides of the column. If formwork are not removed before 7 days, they act as curing method. Formworks removed within the 7-day period after the pour requires spaying of curing membrane as per Work Instruction. |  |  | NZS 3109 section 7 and Concrete Specification Clause 8.4 and 8.10 |  | Site Inspection | After each concrete pour |  | NZS 3109 section 7 |  |  | H | H |  |  | Signed post pour inspection sheet
4.02 | As-built - Final survey as-built and red lines to be completed at the column construction completion. |  |  | Concrete Specification Clause 7.8 |  | Drawings | At the completion of the Sub-Lot of work |  | NZS 3109 Table 5.1 |  |  | H | H
4.03 | Final Handover Package - Collation of all QA, as-built drawings, testing and monitoring documentation |  |  | Concrete Specification Clause 5.3 |  | Submit | At Completion |  |  |  |  | H | H | R |  | As-built drawings, testing results, monitoring documentation, operation and maintenance report, Producer Statements
5.0 Close-Out & Approval/Acceptance
ITP Close-Out by
Site Engineer/ Project Engineer |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Zone Manager Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Construction Manager Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Quality Manager Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date: