## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Structures Insitu Concrete | itp |  |  |  |  | ITP - Structures Insitu Concrete Rev 1
section | 1.0 Pre-Construction
checkpoint | 1.01 - Approved CWP
label | Method/Description - Document Review
label | Test frequency - Prior to personnel starting
label | Conformance Criteria - Ensure all crew members are briefed on the CWP
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed off CWP
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - IFC issued
label | Specifications and Standards - Consent conditions
label | Method/Description - Document Review
label | Test frequency - Prior to starting
label | Conformance Criteria - Ensure all drawings are approved and of the latest revision, or written approval from PAB
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - IFC drawings or written approval from PAB
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.03 - Approved SCWMP
label | Specifications and Standards - Consent conditions
label | Method/Description - Document Review
label | Test frequency - Once prior to works commencing
label | Conformance Criteria - TRC review and approval
label | Constructor - H
label | Verifying Records Checklists, Test and Supplier Certificates - Approved SCWMP
checkpoint | 1.04 - Method Statements - At least 5 days before commencing any supply of concrete to site a method statement(s) shall be submitted to the the Design Engineer for review.
label | Specifications and Standards - Concrete specification Clause 8.2
label | Method/Description - Document Review
label | Test frequency - Prior to starting
label | Conformance Criteria - Review and Approval
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - CPSA
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.05 - Concrete thermal modelling - large colume pours to consider thermal effects
label | Specifications and Standards - Concrete specification Clause 9.2 and Special Concrete NZS 3104
label | Method/Description - Document Review
label | Test frequency - Prior to commencement
label | Conformance Criteria - Maximum concrete shall not exceed 70 degree C and maximum differential 20 degree C
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Heat of Hydration Report
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 Material Compliance
checkpoint | 2.01 - Material Compliance - Concrete - Concrete mix designs include 30MPa, 40MPa & 50MPa with aggregate sizes ranging from 13mm for SCC to 19mm are to be submitted to the CPS team for review and approval for use with the work covered in this ITP incliding additives required specific to the special contrcrete for heat of hydration.
label | Specifications and Standards - CPS Approval, Concrete Specifications Clause 7.2 and 9.2
label | Method/Description - Document Review
label | Test frequency - Prior to commencement
label | Conformance Criteria - CPS Approval, Concrete Specifications Clause 7.2 and 9.1
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Request for approval of concrete mix
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.02 - Material Compliance - Reinforcing - Steel Reinforcement shall be Grade 500E and comply with AS/NZS 4671 & NZS 3109 and shall be the grade called up on the design drawing and approved shop drawings.
label | Specifications and Standards - AS/NZS4671 & NZS3109, Reinforcing Specifications Clause 6.1
label | Method/Description - Document review, Mill certificates provided
label | Test frequency - Prior to commencement
label | Conformance Criteria - CPS Approval, AS/NZS4671 & NZS3109, Reinforcing Specifications Clause 6.1
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Traceability of steel via Cast Batch/Heat Summary and Detail Sheets and Mill Certificates
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Material Compliance - Mechanical Anchorage System - Mechanical Anchorage system used with grade 300E and 500E complying with AS/NZ 4671. Systems to be considered: Ancon RT, IMBMS, Reidbar Steel
label | Specifications and Standards - Systems tested to demonstrate compliance with section 4.2.1.f of the Bridge Manual.
label | ○ Mechanical Coupling system to be tested to demonstrate compliance with AS/NZS4671
label | Method/Description - Document Review
label | Test frequency - Prior to commencement
label | Conformance Criteria - CPS Approval, Reinforcing Specifications Clause 6.1.5
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Request for approval from CPS and manufactureres certificates
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 During Construction
checkpoint | 3.1.1 - Pre-Pour Concrete Inspection - Reinforcing, formwork & cast in itmes to be regularly inspected by nominated Quality Representative and or Design Representative. Full pre-pour inspection to be carried out prior to pour date.
label | Specifications and Standards - Concrete Specification Clause 5, 7 & 8.5 - 8.7
label | Method/Description - Site Inspection
label | Test frequency - Prior to concrete pour
label | Conformance Criteria - Concrete Speciffication Clause 5 & 7
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed pre-pour inspection sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Concrete Testing and Monitoring - Onsite testing of each truck for workability. A set of 4 test cylinders per 50m3 or part thereof for 1 cylinder tested at 7 days and the remaining 3 cylinders tested at 28 days for compressive strength.
label | Specifications and Standards - Concrete Specification Clause 7.2.1 & 7.2.2
label | Method/Description - Test results and pour record sheet
label | Test frequency - During concrete pour
label | Conformance Criteria - Concrete Specification Clause 7.2.1 & 7.2.2
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Concrete Delivery dockets with onsite test records, Concrete Compressive Strength test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Concrete Placing - Concrete shall be handled, placed, finished and cured in accordance with concrete specification.
label | Specifications and Standards - NZS 3109 section 7 and Concrete Specification Clause 8.3
label | Method/Description - Site Inspection
label | Test frequency - During concrete pour
label | Conformance Criteria - NZS 3109 section 7
label | Constructor - W
label | Designer - W
label | Verifying Records Checklists, Test and Supplier Certificates - Site photos
checkpoint | 3.1.4 - Special Concrete - Slabs on Grade. Plant engineer to design concrete to eliminate the incidence of plastic shrinkage cracking, plastic settlement and or early age thermal cracking
label | Specifications and Standards - Concrete specification Clause 9.1 and Special Concrete NZS 3104
label | Method/Description - Mix designs and methodologies
label | Test frequency - During concrete pour
label | Conformance Criteria - NZS 3104
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Data results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.5 - Special Concrete - Mass Concrete Pours. Temperature monitoring using data loggers as per manuacturers reconmendations. Following first mass pour, data results to confirm if further monitoring required at second mass pour.
label | Specifications and Standards - Concrete specification Clause 9.2 and Special Concrete NZS 3104
label | Method/Description - Data loggers
label | Test frequency - During concrete pour
label | Conformance Criteria - Maximum concrete shall not exceed 70 degree C and maximum differential 20 degree C
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Data results
holdpoint | AUTHORITY HOLDPOINT
section | 4.0 Post Construction
checkpoint | 4.01 - Post pour inspection - Inspection of any Type B Construction Joints if applicable with respective concrete pour. Quality Representative and or Design Representative to inspect concrete surfaces after the formwork have been stripped. 7 days curing required on top and sides of the column. If formwork are not removed before 7 days, they act as curing method. Formworks removed within the 7-day period after the pour requires spaying of curing membrane as per Work Instruction.
label | Specifications and Standards - NZS 3109 section 7 and Concrete Specification Clause 8.4 and 8.10
label | Method/Description - Site Inspection
label | Test frequency - After each concrete pour
label | Conformance Criteria - NZS 3109 section 7
label | Constructor - H
label | Designer - H
label | Verifying Records Checklists, Test and Supplier Certificates - Signed post pour inspection sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02 - As-built - Final survey as-built and red lines to be completed at the column construction completion.
label | Specifications and Standards - Concrete Specification Clause 7.8
label | Method/Description - Drawings
label | Test frequency - At the completion of the Sub-Lot of work
label | Conformance Criteria - NZS 3109 Table 5.1
label | Constructor - H
label | Designer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.03 - Final Handover Package - Collation of all QA, as-built drawings, testing and monitoring documentation
label | Specifications and Standards - Concrete Specification Clause 5.3
label | Method/Description - Submit
label | Test frequency - At Completion
label | Constructor - H
label | Designer - H
label | Client - R
label | Verifying Records Checklists, Test and Supplier Certificates - As-built drawings, testing results, monitoring documentation, operation and maintenance report, Producer Statements
holdpoint | AUTHORITY HOLDPOINT
section | CLOSE-OUT & APPROVAL/ ACCEPTANCE
checkpoint | ITP Close-Out by
note | Site Engineer/Project Engineer
note | Zone Manager Approval
note | Construction Manager Approval
note | Quality Manager Approval
date | Date:
signoff | SIGNATURE