## ITP Cover Page
[16 empty] | Pavement & Surfacing Inspection and Test Plan | [7 empty] | Subordinate Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 1 | [5 empty] | Subordinate ITP Cover page UPDATE
Project Number: |  |  | DS1205 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Pavement & Surfacing ITP |  |  |  |  | Revision: | 1000 |  | A
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | 146000-002A
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification and Appendices.
Quality Specified: |  |  | NZTA Z/1
Review / Update History | [9 empty] | Verification Activity | [6 empty] | Subordinate Inspection and Test Plan Details
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key |  |  |  | Construction Pack Number: |  |  | CP##
A | Draft for Approval | 2022-12-22 |  | Gabriel Cirne |  | First Revieion for Review and Approval |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep |  |  | Work Area / Chainage / Lot: | [5 empty] | SUB ITP NO. S-
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager |  |  | Master ITP Details:
[10 empty] | E | Examine |  | OP | Operations Manager |  |  | Review / Update History
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep |  |  | Rev: | Status: | Date: |  | Reviewed By: | Revision Details:
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep |  |  | A |  |  |  |  | Subordinate ITP Creation for
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor |  |  | SUB ITP Instructions: 0. Master ITP to be Approved and Accepted 1. Extract Cover page (this page) and Body page to new Workbook 2. Drag and drop the two white cell blocs above into the cover page 3. Assign an ITP Number in Mater ITP Register tab 4. Populate Title Page Details 5. Remove all Inspection points in the Body which do not relate to works 6. Review for approval, submitting to Client / Engineer once internally approved
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Pavement & Surfacing Inspection and Test Plan
|  | SMA10 |  |  |  |  | Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 01 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
1.01 | NZTA M27 2020 - MATERIALS
01.01.01 | Coarse Aggregate - Property Tests and Sampling | The Coarse Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Weathering Quality Index, Crushing Resistance, Broken Faces, and Particle Size Distribution | NZTA M10:2020 - 2 | IANZ Lab Reports | 1 Test per source of the coarse aggregate. Additional samples if source is changed | H | PE
01.01.02 | Fine Aggregate - Property Tests and Sampling | The Fine Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Sand Equivalent, and Particle Size Distribution | NZTA M10:2020 - 2 | IANZ Lab Reports | 1 test on the parent source | H | PE
01.01.03 | Coarse Aggregate | Coarse aggregate is comprised of particles that are retained on the 4.75 mm sieve. Coarse aggregate shall comply with Table 2.1 except that the Engineer can approve the use of non-complying materials from sources of proven performance. | NZTA M10:2020 - 2 | IANZ Lab Reports | Prior to use as per BPG05 - 15 | H | PE
01.01.04 | Fine Aggregate | Fine aggregate shall consist of crushed rock particles finer than the 4.75 mm sieve and manufactured from a source complying with the requirements of Table 2.2. | NZTA M10:2020 - 2 | IANZ Lab Reports | Prior to use as per BPG05 - 15 | H | PE
01.01.05 | Mineral Filler | Filler shall be consistent in mineral composition. It shall be dry, and free from lumps, clay, organic matter or other material deleterious to asphalt. | NZTA M10:2020 - 2 | IANZ Lab Reports | Prior to use | H | PE
01.01.06 | Bitumen | The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification. | NZTA M01-A PS - 7.2.7 | IANZ Lab Reports | 1 test per 25,000 litres or part of | H | PE
01.01.07 | Aggregate Wet Strength | When tested in accordance with AS 2758 Part 5 the aggregate wet strength shall be not less than 100kN. The wet/dry strength variation shall not exceed 30%. | NZTA M10:2020 - 2 | IANZ Lab Reports | Prior to use | H | PE
01.01.08 | Wheel tracking Testing | The acceptance criteria for wheel tracking shall be a tracking depth of no more than 3.0mm after 10,000 passes, in respect to AC20 (Type # 2 pavements). All other asphalt layers, including SMA10 and AC10, shall apply the 6mm maximum tracking depth as per NZTA M/10. | NZTA M10:2020 - 3 | IANZ Lab Reports | Prior to use | H | PE
01.01.09 | SMA PSV Requirements - Pavement Type 2 | A minimum of 85% by mass of the coarse aggregate fraction (fraction retained on the 4.75 mm sieve) of the SMA surfacing shall meet the minimum PSV requirements of 63 for Pavement Type 2 | NZTA M10:2020 - 3 | IANZ Lab Reports | Prior to use | H | PE
01.01.10 | SMA PSV Requirements - Pavement Type 1 | A minimum of 85% by mass of the coarse aggregate fraction (fraction retained on the 4.75 mm sieve) of the SMA surfacing shall meet the minimum PSV requirements of 46 for Pavement Type 1 | NZTA M10:2020 - 3 | IANZ Lab Reports | Prior to use | H | PE
01.01.11 | SMA PSV Requirements - Pavement Type 2 | The minimum PSV for SMA surfacing on Pavement Type 2 (intersections and approaches) shall be 63. | NZTA M10:2020 - 3 | IANZ Lab Reports | Prior to use | H | PE
1.02 | NZTA M10 2020 - MIX DESIGN
01.02.01 | Mix Design / Job Mix Formula | The Contractor shall supply details of the mix designs together with the Job Mix Formula (JMF) and the Marshall or gyratory compaction properties as required to the Engineer for approval. No works shall commence until the JMF of each mixture to be used has been accepted by the Engineer. | NZTA M10:2020 - 3 | Approved Mix Design | 3 tests per mix | HP | ENG
SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
2.01 | Asphaltic Concrete
02.01.01 | Paving Plan | The Contractor shall prepare and submit a paving plan to the Engineer for approval not less than 7 days prior to construction of the asphalt pavement. | NZTA M10:2020 - 8, 9 | Construction Work Pack | 7 days prior to construction of the asphalt pavement. | HP | ENG
02.01.02 | Sealing Inspection | Before sealing and resealing. | NZTA M10:2020 - 8, 9 | Hold Point Release | Min 48h Notice | HP | ENG
02.01.03 | Weather during Paving | Asphaltic concrete shall not be placed when it is raining or on a wet surface. Dense-graded asphalt shall not be placed on a surface with a temperature of less than 10°C. | NZTA M10:2020 - 8, 9 | Weather / Site Notes | Each day prior to placement | H | PE
02.01.04 | Asphaltic Prep | Prior to paving asphaltic concrete, the area to be paved shall be dry and free from loose material or dirt. If swept, all sweepings shall be collected and removed from site. Barriers, kerbs and other adjacent surfaces shall be adequately protected against over-sprayed bitumen or vehicle damage | NZTA M10:2020 - 8, 9 | Site Notes | Prior to paving asphaltic concrete | H | PE
02.01.05 | Asphalt Production Conformance | Conforming Grading and Binder content by mass | NZTA M10:2020 - 8, 9 | Test Results | 1 per 200T Min 3 tests per mix | I | PE
02.01.06 | Asphalt Production Conformance -Volumetrics | Conforming Volumetric testing. Refer clause 5.2 and table 5.2 for frequency and tolerances | NZTA M10:2020 - Table 3.1, 5.1 & 5.2 | Test Results | 1 per 600T | I | PE
02.01.07 | Mat Density | For mixes with a nominal maximum aggregate size 14mm or less cores shall be 100 mm nominal diameter or greater. For mixes coarser than 14mm cores shall be nominally 150mm diameter. For layer thicknesses 40mm or less the core diameter shall be nominally 100mm. | ASTM D5361 NZTA M10:2020 - 9 | Cores | min 8 per lot (day) (1 for every 300 m²) | R | PE
02.01.08 | Joint Density | For mixes with a nominal maximum aggregate size 14mm or less cores shall be 100 mm nominal diameter or greater. For mixes coarser than 14mm cores shall be nominally 150mm diameter. For layer thicknesses 40mm or less the core diameter shall be nominally 100mm. | NZTA M10:2020 - 9 | Cores | min 3 per lot (day) (1 per 100 m of joint) | R | PE
02.01.09 | Core Thickness | The nominal thicnkess for the set or lot of cores shall be equal to or greater than the specified nominal thickness. | NZTA M10:2020 - 9 | Lab Report | Mat - min 8 per lot (day) (1 for every 300 m²) Joints - min 3 per lot (1 for every 100m) | R | SE
02.01.10 | Mat Density | 150 mm nominal diameter Cores shall be cut from the pavement at a rate of one core for every 300 m² with a minimum of eight cores representing each lot | NZTA M10:2020 - 9 | Cores | min 8 per lot (day) (1 for every 300 m²) | R | PE
02.01.11 | Joint Density | 150 mm nominal diameter Cores shall be taken from randomly located distances along joints at the rate of one per 100 m of joint with a minimum of three representing each lot | NZTA M10:2020 - 9 | Cores | min 3 per lot (day) (1 per 100 m of joint) | R | PE
02.01.12 | Density Testing | The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2 | NZTA M10:2020 - 9 | Lab Report | within 24 hours of them being cut from the pavement | I | PE
02.01.13 | NDM Density | NDMs are to be completed at the time of pacing to ensure compile when cores are taken | NZTA M10:2020 - 9 | IANZ Lab Report | min 8 per lot (day) | I | PE
02.01.14 | Transverse truth of the surface | The transverse truth of the surface shall be checked with a 3 m straight edge over the straight cross-fall portion of the cross-section for irregularities, which vary more than 5 mm under this straight edge. | NZTA M10:2020 - 9 | Site Notes | Post Seal | I | SE
02.01.15 | Finished Pavement Level | The level at the top of each layer of asphalt shall not differ from the specified level by more than 10 mm, except that where asphalt is placed against kerb and channel where it shall be flush with, or not more than 5 mm above, the lip of the channel. 2mm at Construction Joints (Bridge). | NZTA M10:2020 - 9 | Survey | Continuous throughout construction | I | SE
02.01.16 | Finished Pavement Alignment | The horizontal location of any point on the pavement shall not vary by more than ±50 mm from the design except where alignment with an existing pavement structure is necessary, when the new work shall be joined to the existing work or structure in a smooth manner. | NZTA M10:2020 - 9 | Survey | Continuous throughout construction | I | SE
02.01.17 | Transverse joints | Transverse joints shall be milled back to provide a square edge and bitumen shall be hand sprayed on the vertical face. Successive transverse joints shall be staggered by a minimum of 2.0m. | NZTA M10:2020 - 9 | Site Records | Continuous throughout construction | I | PE
02.01.18 | Longitudinal joints | Longitudinal joints between successive layers of asphalt shall be offset by at least 150mm. | NZTA M10:2020 - 9 | Site Records | Continuous throughout construction | I | PE
02.01.19 | Asphalt delivery temperature | Asphalt paving should be carried out at temperatures between 121–149°C to ensure optimal workability and compaction. If the temperature falls below 120°C, the asphalt mixture becomes too stiff, leading to inadequate compaction and a compromised pavement structure. Proper temperature control during transportation and placement is essential to achieve a durable and long-lasting surface. | TNZ M10 - 8 | Site Records | Continuous throughout construction | I | QA
02.01.20 | Depth Checks - Loose during paving asphalt material | Best Practice technique. Allowance for depth is dependent on asphalt type and compacted effort required to meet Specification. Normal practice is to add 20% of the nominal depth and use a dip stick to visually check behind the paver. | Industry Best Practice | Site Records | Continuous throughout construction | I | SE
02.01.21 | Plateau Testing | One test at the start of the project. Typically a target density of 93-97% of the maximum theoretical density. | Industry Best Practice | Lab Report | 1 test at the commencement of the project. | M | Spec
02.01.22 | Backfilling Core Holes | Core holes filled with material similar in composition to the surrounding asphalt layer. Well compacted and finished flush with the surrounding pavement. | NZTA M10:2020 | Site Records | As soon as possible after core extraction | O | SE
2.02 | Surface Conformance
28.09.01 | NAASRA | On completion of surfacing and placement of pavement markings and raised pavement markers Contractor shall carry out surface roughness measurements in accordance with the Transport Agency’s Technical Memorandum TM7003 (TM7003). The criteria for acceptance shall be in accordance with Section 2 of the Transport Agency’s TM7003 and in addition no 20m reading in any lane shall exceed 100 NAASRA counts/km. | PS 21.4.1 | Test Results | Each lane. 1 test on surfacing post construction and again at end of defects notification period | I | PE
28.09.03 | Texture | Texture shall be measured in accordance with the TNZ T/3 Specification or with the Mini Texture Meter. The measured texture shall be converted to MPD using the following equations. | PS 21.5.1 | Test Results | Upon completion of the asphalt surfacing and at the end of the Defects Notification Period. | I | PE
SECTION 39 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
39.02 | Site Post Construction Activities
39.02.02 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting | Downer | Records | Post construction | H | SV
39.02.03 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. | Downer | Redlines | Post construction | H | PE