## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Pavement & Surfacing - AC20 - Asphalt | itp |  |  |  |  | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A
section | SECTION 01 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
checkpoint | 01.01.01 - Coarse Aggregate - Property Tests and Sampling
label | Acceptance / Conformance Criteria - The Coarse Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Weathering Quality Index, Crushing Resistance, Broken Faces, and Particle Size Distribution
label | Standard / Specification - NZTA M10:2020 - 2
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 Test per source of the coarse aggregate. Additional samples if source is changed
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.02 - Fine Aggregate - Property Tests and Sampling
label | Acceptance / Conformance Criteria - The Fine Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Sand Equivalent, and Particle Size Distribution
label | Standard / Specification - NZTA M10:2020 - 2
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 test on the parent source
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.03 - Coarse Aggregate
label | Acceptance / Conformance Criteria - Coarse aggregate is comprised of particles that are retained on the 4.75 mm sieve. Coarse aggregate shall comply with Table 2.1 except that the Engineer can approve the use of non-complying materials from sources of proven performance.
label | Standard / Specification - NZTA M10:2020 - 2
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use as per BPG05 - 15
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.04 - Fine Aggregate
label | Acceptance / Conformance Criteria - Fine aggregate shall consist of crushed rock particles finer than the 4.75 mm sieve and manufactured from a source complying with the requirements of Table 2.2.
label | Standard / Specification - NZTA M10:2020 - 2
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use as per BPG05 - 15
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.05 - Mineral Filler
label | Acceptance / Conformance Criteria - Filler shall be consistent in mineral composition. It shall be dry, and free from lumps, clay, organic matter or other material deleterious to asphalt.
label | Standard / Specification - NZTA M10:2020 - 2
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.06 - Bitumen
label | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
label | Standard / Specification - NZTA M10:2020 - 2, NZTA M01-A
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 test per 25,000 litres or part of
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.07 - Aggregate Wet Strength
label | Acceptance / Conformance Criteria - When tested in accordance with AS 2758 Part 5 the aggregate wet strength shall be not less than 100kN. The wet/dry strength variation shall not exceed 30%.
label | Standard / Specification - NZTA M10:2020 - 2
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.08 - Wheel tracking Testing
label | Acceptance / Conformance Criteria - The acceptance criteria for wheel tracking shall be a tracking depth of no more than 3.0mm after 10,000 passes, in respect to AC20 (Type # 2 pavements). All other asphalt layers, including SMA10 and AC10, shall apply the 6mm maximum tracking depth as per NZTA M/10.
label | Standard / Specification - NZTA M10:2020 - 3
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.02.01 - Mix Design / Job Mix Formula
label | Acceptance / Conformance Criteria - The Contractor shall supply details of the mix designs together with the Job Mix Formula (JMF) and the Marshall or gyratory compaction properties as required to the Engineer for approval. No works shall commence until the JMF of each mixture to be used has been accepted by the Engineer.
label | Standard / Specification - NZTA M10:2020 - 3
label | Verifying Document - Approved Mix Design
label | Frequency - 3 tests per mix
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
checkpoint | 02.01.01 - Paving Plan
label | Acceptance / Conformance Criteria - The Contractor shall prepare and submit a paving plan to the Engineer for approval not less than 7 days prior to construction of the asphalt pavement.
label | Standard / Specification - NZTA M10:2020 - 8, 9
label | Verifying Document - Construction Work Pack
label | Frequency - 7 days prior to construction of the asphalt pavement.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 02.01.02 - Sealing Inspection
label | Acceptance / Conformance Criteria - Before sealing and resealing.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Hold Point Release
label | Frequency - Min 48h Notice
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 02.01.03 - Weather during Paving
label | Acceptance / Conformance Criteria - Asphaltic concrete shall not be placed when it is raining or on a wet surface. Dense-graded asphalt shall not be placed on a surface with a temperature of less than 5°C.
label | Standard / Specification - NZTA M10:2020 - 6
label | Verifying Document - Weather / Site Notes
label | Frequency - Each day prior to placement
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 02.01.04 - Asphaltic Prep
label | Acceptance / Conformance Criteria - Prior to paving asphaltic concrete, the area to be paved shall be dry and free from loose material or dirt. If swept, all sweepings shall be collected and removed from site. Barriers, kerbs and other adjacent surfaces shall be adequately protected against over-sprayed bitumen or vehicle damage
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Prior to paving asphaltic concrete
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 02.01.05 - Tack Coating
label | Acceptance / Conformance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Prior to Paving
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 02.01.06 - Asphalt Production Conformance
label | Acceptance / Conformance Criteria - Conforming Grading and Binder content by mass
label | Standard / Specification - TNZ M10 Table 3.1, TNZ M10 Table 5.1, PS - Table No. 7.2 - 3.5
label | Verifying Document - Test Results
label | Frequency - 1 per 200T, Min 3 tests per mix
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 02.01.07 - Asphalt Production Conformance -Volumetrics
label | Acceptance / Conformance Criteria - Conforming Volumetric testing. Refer clause 5.2 and table 5.2 for frequency and tolerances
label | Standard / Specification - NZTA M10:2020 -Table 3.1, 5.1 and 5.2
label | Verifying Document - Test Results
label | Frequency - 1 per 600T
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 02.01.08 - Mat Density
label | Acceptance / Conformance Criteria - For mixes with a nominal maximum aggregate size 14mm or less cores shall be 100 mm nominal diameter or greater. For mixes coarser than 14mm cores shall be nominally 150mm diameter. For layer thicknesses 40mm or less the core diameter shall be nominally 100mm.
label | Standard / Specification - NZTA M10 9
label | Verifying Document - Cores
label | Frequency - min 8 per lot (day) (1 for every 300 m²)
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 02.01.09 - Joint Density
label | Acceptance / Conformance Criteria - For mixes with a nominal maximum aggregate size 14mm or less cores shall be 100 mm nominal diameter or greater. For mixes coarser than 14mm cores shall be nominally 150mm diameter. For layer thicknesses 40mm or less the core diameter shall be nominally 100mm.
label | Standard / Specification - NZTA M10 9
label | Verifying Document - Cores
label | Frequency - min 3 per lot (day) (1 per 100 m of joint)
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 02.01.10 - Density Testing
label | Acceptance / Conformance Criteria - The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2
label | Standard / Specification - TNZ M10 - 9
label | Verifying Document - Lab Report
label | Frequency - 24 hours of them being cut from the pavement
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 02.01.11 - Core Thickness
label | Acceptance / Conformance Criteria - The nominal thicnkess for the set or lot of cores shall be equal to or greater than the specified nominal thickness.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Lab Report
label | Frequency - Mat - min 8 per lot (day) (1 for every 300 m²) Joints - min 3 per lot (1 for every 100m)
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 02.01.12 - Mat Density
label | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be cut from the pavement at a rate of one core for every 300m² with a minimum of eight cores representing each lot
label | Standard / Specification - ASTM D5361, NZTA M10:2020 - 9
label | Verifying Document - Cores
label | Frequency - min 8 per lot (day) (1 for every 300 m²)
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 02.01.13 - Joint Density
label | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be taken from randomly located distances along joints at the rate of one per 100m of joint with a minimum of three representing each lot
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Cores
label | Frequency - min 3 per lot (day) (1 per 100 m of joint)
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 02.01.14 - Density Testing
label | Acceptance / Conformance Criteria - The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Lab Report
label | Frequency - within 24 hours of them being cut from the pavement
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 02.01.15 - NDM Density
label | Acceptance / Conformance Criteria - NDMs are to be completed at the time of placing to ensure compliance when cores are taken
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - IANZ Lab Report
label | Frequency - min 8 per lot (day)
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 02.01.13 - Transverse truth of the surface
label | Acceptance / Conformance Criteria - The transverse truth of the surface shall be checked with a 3 m straight edge over the straight cross-fall portion of the cross-section for irregularities, which vary more than 5 mm under this straight edge (excludes the start and end of the job where the new seal matches the existing road).
label | Standard / Specification - NZTA M27:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Post Seal
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 02.01.14 - Finished Pavement Level
label | Acceptance / Conformance Criteria - The level at the top of each layer of asphalt shall not differ from the specified level by more than 10 mm, except that where asphalt is placed against kerb and channel where it shall be flush with, or not more than 5 mm above, the lip of the channel. 2mm at Construction Joints (Bridge).
label | Standard / Specification - TNZ M10 - 10
label | Verifying Document - Survey
label | Frequency - Continuous throughout construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 02.01.15 - Finished Pavement Alignment
label | Acceptance / Conformance Criteria - The horizontal location of any point on the pavement shall not vary by more than ±50 mm from the design except where alignment with an existing pavement structure is necessary, when the new work shall be joined to the existing work or structure in a smooth manner.
label | Standard / Specification - TNZ M10 - 10
label | Verifying Document - Survey
label | Frequency - Continuous throughout construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 02.01.16 - Finished Pavement Thickness
label | Acceptance / Conformance Criteria - The pavement specified layer thickness shall not be less than the average measured thickness of each lot.
label | Standard / Specification - TNZ M10 - 10
label | Verifying Document - Survey
label | Frequency - Continuous throughout construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 02.01.17 - Transverse joints
label | Acceptance / Conformance Criteria - Transverse joints shall be milled back to provide a square edge and bitumen shall be hand sprayed on the vertical face. Successive transverse joints shall be staggered by a minimum of 2.0m.
label | Standard / Specification - TNZ M10 - 9
label | Verifying Document - Site Records
label | Frequency - Continuous throughout construction
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 02.01.18 - Longitudinal joints
label | Acceptance / Conformance Criteria - Longitudinal joints between successive layers of asphalt shall be offset by at least 150mm.
label | Standard / Specification - TNZ M10 - 9
label | Verifying Document - Site Records
label | Frequency - Continuous throughout construction
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 02.01.19 - Asphalt delivery temperature
label | Acceptance / Conformance Criteria - Asphalt paving should be carried out at temperatures between 121–149°C to ensure optimal workability and compaction. If the temperature falls below 120°C, the asphalt mixture becomes too stiff, leading to inadequate compaction and a compromised pavement structure. Proper temperature control during transportation and placement is essential to achieve a durable and long-lasting surface.
label | Standard / Specification - TNZ M10 - 8
label | Verifying Document - Site Records
label | Frequency - Continuous throughout construction
label | Verification Activity: Activity - I
label | Verification Activity: By - QA
checkpoint | 02.01.20 - Depth Checks - Loose during paving asphalt material
label | Acceptance / Conformance Criteria - Best Practice technique. Allowance for depth is dependent on asphalt type and compacted effort required to mmet Specification. Normal practice is to add 20% of the nominal depth and use a dip stick to visually check behind the paver.
label | Standard / Specification - Industry Best Practice
label | Verifying Document - Site Records
label | Frequency - Continuous throughout construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 02.01.21 - Plateau Testing
label | Acceptance / Conformance Criteria - One test at the start of the project. Typically a target density of 93-97% of the maximum theoretical density.
label | Standard / Specification - Industry Best Practice
label | Verifying Document - Lab Report
label | Frequency - 1 Test at the commencement of the project.
label | Verification Activity: Activity - M
label | Verification Activity: By - Spec
checkpoint | 02.01.22 - Backfilling Core Holes
label | Acceptance / Conformance Criteria - Core holes filled with material similar in composition to the surrounding asphalt layer. Well compacted and finished flush with the surrounding pavement.
label | Standard / Specification - NZTA M10:2020
label | Verifying Document - Site Records
label | Frequency - As soon as possible after core extraction
label | Verification Activity: Activity - O
label | Verification Activity: By - SE
checkpoint | 28.09.01 - NAASRA
label | Acceptance / Conformance Criteria - On completion of surfacing and placement of pavement markings and raised pavement markers Contractor shall carry out surface roughness measurements in accordance with the Transport Agency’s Technical Memorandum TM7003 (TM7003).
label | Standard / Specification - PS 21.4.1
label | Verifying Document - Test Results
label | Frequency - Each lane. 1 test on surfacing post construction and again at end of defects notification period
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
section | SECTION 39 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 39.02.02 - Survey Records
label | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 39.02.03 - Redline Drawings
label | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | ITP - Pavement & Surfacing - SMA10 - Asphalt | itp |  |  |  |  | ITP - Pavement & Surfacing - SMA10 - Asphalt - Rev A
section | SECTION 01 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
checkpoint | 01.01.01 - Coarse Aggregate - Property Tests and Sampling
label | Acceptance / Conformance Criteria - The Coarse Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Weathering Quality Index, Crushing Resistance, Broken Faces, and Particle Size Distribution
label | Standard / Specification - NZTA M10:2020 - 2
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 Test per source of the coarse aggregate. Additional samples if source is changed
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.02 - Fine Aggregate - Property Tests and Sampling
label | Acceptance / Conformance Criteria - The Fine Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Sand Equivalent, and Particle Size Distribution
label | Standard / Specification - NZTA M10:2020 - 2
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 test on the parent source
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.03 - Coarse Aggregate
label | Acceptance / Conformance Criteria - Coarse aggregate is comprised of particles that are retained on the 4.75 mm sieve. Coarse aggregate shall comply with Table 2.1 except that the Engineer can approve the use of non-complying materials from sources of proven performance.
label | Standard / Specification - NZTA M10:2020 - 2
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use as per BPG05 - 15
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.04 - Fine Aggregate
label | Acceptance / Conformance Criteria - Fine aggregate shall consist of crushed rock particles finer than the 4.75 mm sieve and manufactured from a source complying with the requirements of Table 2.2.
label | Standard / Specification - NZTA M10:2020 - 2
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use as per BPG05 - 15
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.05 - Mineral Filler
label | Acceptance / Conformance Criteria - Filler shall be consistent in mineral composition. It shall be dry, and free from lumps, clay, organic matter or other material deleterious to asphalt.
label | Standard / Specification - NZTA M10:2020 - 2
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.06 - Bitumen
label | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
label | Standard / Specification - NZTA M01-A, PS - 7.2.7
label | Verifying Document - IANZ Lab Reports
label | Frequency - 1 test per 25,000 litres or part of
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.07 - Aggregate Wet Strength
label | Acceptance / Conformance Criteria - When tested in accordance with AS 2758 Part 5 the aggregate wet strength shall be not less than 100kN. The wet/dry strength variation shall not exceed 30%.
label | Standard / Specification - NZTA M10:2020 - 2
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.08 - Wheel tracking Testing
label | Acceptance / Conformance Criteria - The acceptance criteria for wheel tracking shall be a tracking depth of no more than 3.0mm after 10,000 passes, in respect to AC20 (Type # 2 pavements). All other asphalt layers, including SMA10 and AC10, shall apply the 6mm maximum tracking depth as per NZTA M/10.
label | Standard / Specification - NZTA M10:2020 - 3
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.09 - SMA PSV Requirements - Pavement Type 2
label | Acceptance / Conformance Criteria - A minimum of 85% by mass of the coarse aggregate fraction (fraction retained on the 4.75 mm sieve) of the SMA surfacing shall meet the minimum PSV requirements of 63 for Pavement Type 2
label | Standard / Specification - NZTA M10:2020 - 3
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.10 - SMA PSV Requirements - Pavement Type 1
label | Acceptance / Conformance Criteria - A minimum of 85% by mass of the coarse aggregate fraction (fraction retained on the 4.75 mm sieve) of the SMA surfacing shall meet the minimum PSV requirements of 46 for Pavement Type 1
label | Standard / Specification - NZTA M10:2020 - 3
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.01.11 - SMA PSV Requirements - Pavement Type 2
label | Acceptance / Conformance Criteria - The minimum PSV for SMA surfacing on Pavement Type 2 (intersections and approaches) shall be 63.
label | Standard / Specification - NZTA M10:2020 - 3
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 01.02.01 - Mix Design / Job Mix Formula
label | Acceptance / Conformance Criteria - The Contractor shall supply details of the mix designs together with the Job Mix Formula (JMF) and the Marshall or gyratory compaction properties as required to the Engineer for approval. No works shall commence until the JMF of each mixture to be used has been accepted by the Engineer.
label | Standard / Specification - NZTA M10:2020 - 3
label | Verifying Document - Approved Mix Design
label | Frequency - 3 tests per mix
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
checkpoint | 02.01.01 - Paving Plan
label | Acceptance / Conformance Criteria - The Contractor shall prepare and submit a paving plan to the Engineer for approval not less than 7 days prior to construction of the asphalt pavement.
label | Standard / Specification - NZTA M10:2020 - 8, 9
label | Verifying Document - Construction Work Pack
label | Frequency - 7 days prior to construction of the asphalt pavement.
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 02.01.02 - Sealing Inspection
label | Acceptance / Conformance Criteria - Before sealing and resealing.
label | Standard / Specification - NZTA M10:2020 - 8, 9
label | Verifying Document - Hold Point Release
label | Frequency - Min 48h Notice
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 02.01.03 - Weather during Paving
label | Acceptance / Conformance Criteria - Asphaltic concrete shall not be placed when it is raining or on a wet surface. Dense-graded asphalt shall not be placed on a surface with a temperature of less than 10°C.
label | Standard / Specification - NZTA M10:2020 - 8, 9
label | Verifying Document - Weather / Site Notes
label | Frequency - Each day prior to placement
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 02.01.04 - Asphaltic Prep
label | Acceptance / Conformance Criteria - Prior to paving asphaltic concrete, the area to be paved shall be dry and free from loose material or dirt. If swept, all sweepings shall be collected and removed from site. Barriers, kerbs and other adjacent surfaces shall be adequately protected against over-sprayed bitumen or vehicle damage
label | Standard / Specification - NZTA M10:2020 - 8, 9
label | Verifying Document - Site Notes
label | Frequency - Prior to paving asphaltic concrete
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 02.01.05 - Asphalt Production Conformance
label | Acceptance / Conformance Criteria - Conforming Grading and Binder content by mass
label | Standard / Specification - NZTA M10:2020 - 8, 9
label | Verifying Document - Test Results
label | Frequency - 1 per 200T, Min 3 tests per mix
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 02.01.06 - Asphalt Production Conformance -Volumetrics
label | Acceptance / Conformance Criteria - Conforming Volumetric testing. Refer clause 5.2 and table 5.2 for frequency and tolerances
label | Standard / Specification - NZTA M10:2020 - Table 3.1, 5.1 & 5.2
label | Verifying Document - Test Results
label | Frequency - 1 per 600T
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 02.01.07 - Mat Density
label | Acceptance / Conformance Criteria - For mixes with a nominal maximum aggregate size 14mm or less cores shall be 100 mm nominal diameter or greater. For mixes coarser than 14mm cores shall be nominally 150mm diameter. For layer thicknesses 40mm or less the core diameter shall be nominally 100mm.
label | Standard / Specification - ASTM D5361, NZTA M10:2020 - 9
label | Verifying Document - Cores
label | Frequency - min 8 per lot (day) (1 for every 300 m²)
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 02.01.08 - Joint Density
label | Acceptance / Conformance Criteria - For mixes with a nominal maximum aggregate size 14mm or less cores shall be 100 mm nominal diameter or greater. For mixes coarser than 14mm cores shall be nominally 150mm diameter. For layer thicknesses 40mm or less the core diameter shall be nominally 100mm.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Cores
label | Frequency - min 3 per lot (day) (1 per 100 m of joint)
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 02.01.09 - Core Thickness
label | Acceptance / Conformance Criteria - The nominal thicnkess for the set or lot of cores shall be equal to or greater than the specified nominal thickness.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Lab Report
label | Frequency - Mat - min 8 per lot (day) (1 for every 300 m²) Joints - min 3 per lot (1 for every 100m)
label | Verification Activity: Activity - R
label | Verification Activity: By - SE
checkpoint | 02.01.10 - Mat Density
label | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be cut from the pavement at a rate of one core for every 300 m² with a minimum of eight cores representing each lot
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Cores
label | Frequency - min 8 per lot (day) (1 for every 300 m²)
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 02.01.11 - Joint Density
label | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be taken from randomly located distances along joints at the rate of one per 100 m of joint with a minimum of three representing each lot
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Cores
label | Frequency - min 3 per lot (day) (1 per 100 m of joint)
label | Verification Activity: Activity - R
label | Verification Activity: By - PE
checkpoint | 02.01.12 - Density Testing
label | Acceptance / Conformance Criteria - The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Lab Report
label | Frequency - within 24 hours of them being cut from the pavement
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 02.01.13 - NDM Density
label | Acceptance / Conformance Criteria - NDMs are to be completed at the time of pacing to ensure compile when cores are taken
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - IANZ Lab Report
label | Frequency - min 8 per lot (day)
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 02.01.14 - Transverse truth of the surface
label | Acceptance / Conformance Criteria - The transverse truth of the surface shall be checked with a 3 m straight edge over the straight cross-fall portion of the cross-section for irregularities, which vary more than 5 mm under this straight edge.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Site Notes
label | Frequency - Post Seal
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 02.01.15 - Finished Pavement Level
label | Acceptance / Conformance Criteria - The level at the top of each layer of asphalt shall not differ from the specified level by more than 10 mm, except that where asphalt is placed against kerb and channel where it shall be flush with, or not more than 5 mm above, the lip of the channel. 2mm at Construction Joints (Bridge).
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Survey
label | Frequency - Continuous throughout construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 02.01.16 - Finished Pavement Alignment
label | Acceptance / Conformance Criteria - The horizontal location of any point on the pavement shall not vary by more than ±50 mm from the design except where alignment with an existing pavement structure is necessary, when the new work shall be joined to the existing work or structure in a smooth manner.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Survey
label | Frequency - Continuous throughout construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 02.01.17 - Transverse joints
label | Acceptance / Conformance Criteria - Transverse joints shall be milled back to provide a square edge and bitumen shall be hand sprayed on the vertical face. Successive transverse joints shall be staggered by a minimum of 2.0m.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Site Records
label | Frequency - Continuous throughout construction
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 02.01.18 - Longitudinal joints
label | Acceptance / Conformance Criteria - Longitudinal joints between successive layers of asphalt shall be offset by at least 150mm.
label | Standard / Specification - NZTA M10:2020 - 9
label | Verifying Document - Site Records
label | Frequency - Continuous throughout construction
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 02.01.19 - Asphalt delivery temperature
label | Acceptance / Conformance Criteria - Asphalt paving should be carried out at temperatures between 121–149°C to ensure optimal workability and compaction. If the temperature falls below 120°C, the asphalt mixture becomes too stiff, leading to inadequate compaction and a compromised pavement structure. Proper temperature control during transportation and placement is essential to achieve a durable and long-lasting surface.
label | Standard / Specification - TNZ M10 - 8
label | Verifying Document - Site Records
label | Frequency - Continuous throughout construction
label | Verification Activity: Activity - I
label | Verification Activity: By - QA
checkpoint | 02.01.20 - Depth Checks - Loose during paving asphalt material
label | Acceptance / Conformance Criteria - Best Practice technique. Allowance for depth is dependent on asphalt type and compacted effort required to meet Specification. Normal practice is to add 20% of the nominal depth and use a dip stick to visually check behind the paver.
label | Standard / Specification - Industry Best Practice
label | Verifying Document - Site Records
label | Frequency - Continuous throughout construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 02.01.21 - Plateau Testing
label | Acceptance / Conformance Criteria - One test at the start of the project. Typically a target density of 93-97% of the maximum theoretical density.
label | Standard / Specification - Industry Best Practice
label | Verifying Document - Lab Report
label | Frequency - 1 test at the commencement of the project.
label | Verification Activity: Activity - M
label | Verification Activity: By - Spec
checkpoint | 02.01.22 - Backfilling Core Holes
label | Acceptance / Conformance Criteria - Core holes filled with material similar in composition to the surrounding asphalt layer. Well compacted and finished flush with the surrounding pavement.
label | Standard / Specification - NZTA M10:2020
label | Verifying Document - Site Records
label | Frequency - As soon as possible after core extraction
label | Verification Activity: Activity - O
label | Verification Activity: By - SE
checkpoint | 28.09.01 - NAASRA
label | Acceptance / Conformance Criteria - On completion of surfacing and placement of pavement markings and raised pavement markers Contractor shall carry out surface roughness measurements in accordance with the Transport Agency’s Technical Memorandum TM7003 (TM7003). The criteria for acceptance shall be in accordance with Section 2 of the Transport Agency’s TM7003 and in addition no 20m reading in any lane shall exceed 100 NAASRA counts/km.
label | Standard / Specification - PS 21.4.1
label | Verifying Document - Test Results
label | Frequency - Each lane. 1 test on surfacing post construction and again at end of defects notification period
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
checkpoint | 28.09.03 - Texture
label | Acceptance / Conformance Criteria - Texture shall be measured in accordance with the TNZ T/3 Specification or with the Mini Texture Meter. The measured texture shall be converted to MPD using the following equations.
label | Standard / Specification - PS 21.5.1
label | Verifying Document - Test Results
label | Frequency - Upon completion of the asphalt surfacing and at the end of the Defects Notification Period.
label | Verification Activity: Activity - I
label | Verification Activity: By - PE
section | SECTION 39 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 39.02.02 - Survey Records
label | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 39.02.03 - Redline Drawings
label | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature