## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Hard Landscape - 900 - Rev B | itp |  |  |  |  | ITP - Hard Landscape - 900 - Rev B
section | 1.01 - Materials
checkpoint | 1.01.1 - 20 MPa Concrete
label | Acceptance / Conformance Criteria - Concrete shall be certified 20Mpa plant mix and comply with NZS3109
label | Standard / Specification - Drawing L105
label | Verifying Document - Mix Design
label | Frequency - Prior to use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.01.2 - 20 MPa Exposed Aggregate Concrete: Grey, Black & Brown
label | Acceptance / Conformance Criteria - 20MPa Uruti exposed aggregate. Allow 4KG/m3 black oxide
label | Standard / Specification - Drawing L105
label | Verifying Document - Mix Design
label | Frequency - Prior to use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.01.3 - 20 MPa Exposed Aggregate Concrete: Black & Dark Grey
label | Acceptance / Conformance Criteria - 20MPa Bulls exposed aggregate. Allow 8KG/m3 black oxide.
label | Standard / Specification - Drawing L105
label | Verifying Document - Mix Design
label | Frequency - Prior to use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.01.4 - 20 MPa Exposed Aggregate Concrete: Brown
label | Acceptance / Conformance Criteria - 20MPa Mangatangi exposed aggregate. Allow 8KG/m3 black oxide.
label | Standard / Specification - Drawing L105
label | Verifying Document - Mix Design
label | Frequency - Prior to use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.01.5 - 1 MPa Mortar around Thriebeam barrier
label | Acceptance / Conformance Criteria - Submit details of the product type and specification
label | Standard / Specification - Drawing L105
label | Verifying Document - Mix Design
label | Frequency - Prior to use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.01.6 - Greywacke Stone
label | Acceptance / Conformance Criteria - Submit details of the product type and specification
label | Standard / Specification - Drawing L105
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.01.7 - Hinuera Stone
label | Acceptance / Conformance Criteria - Submit details of the product type and specification
label | Standard / Specification - Supplier
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.01.9 - Thriebeam Barrier
label | Acceptance / Conformance Criteria - Submit details of the product type and specification
label | Standard / Specification - Drawing L105
label | Verifying Document - Datasheet
label | Frequency - Prior to use
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | 2.00 - Setting out
checkpoint | 2.00.1 - Setting out
label | Acceptance / Conformance Criteria - The Contractor shall be responsible for the correct setting out of all works, including set out of the various patterns and barrier
label | Standard / Specification - IFC drawing
label | Verifying Document - Site photos
label | Frequency - Each Pour
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 2.00.2 - Setout Approval
label | Acceptance / Conformance Criteria - On completion of the set out of the hardlandscaping, the Contractor shall immediately advise the Engineer for the purposes of checking the set out.
label | Standard / Specification - Survey records
label | Verifying Document - Onsite inspection
label | Frequency - Each Pour
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | 2.01 - Construction
checkpoint | 2.01.1 - Exposed Aggregate Concrete
label | Acceptance / Conformance Criteria - All exposed aggregate concrete to be at a depth of 125mm. Saw cuts to be 1/3 the depth of the concrete and space no greater than 3M apart
label | Standard / Specification - Drawing L303
label | Verifying Document - Site photos
label | Frequency - During construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.01.2 - Greywacke Stone: Ø100-200mm
label | Acceptance / Conformance Criteria - Placement & Embedment:
label | ○ Embed each stone at least ½ of its height into the concrete.
label | ○ Secure stones with their wider side set firmly in concrete.
label | Spacing & Arrangement:
label | ○ Place stones closely together, ensuring gaps do not exceed 50mm.
label | Surface Finish:
label | ○ Allow smoother or rounded sides to be exposed where possible.
label | Protrusion Above Concrete Surface:
label | ○ Ensure stones protrude 25-50mm above the finished concrete level.
label | Standard / Specification - Drawing L303
label | Verifying Document - Site photos
label | Frequency - During construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.01.3 - Greywacke Stone: Ø50-100mm
label | Acceptance / Conformance Criteria - Placement & Embedment:
label | ○ Embed each stone at least ½ of its height into the concrete.
label | ○ Secure stones with their wider side set firmly in concrete.
label | Spacing & Arrangement:
label | ○ Place stones closely together, ensuring gaps do not exceed 50mm.
label | Surface Finish:
label | ○ Allow rugged sides at the surface where possible.
label | Protrusion Above Concrete Surface:
label | ○ Ensure stones protrude 25-50mm above the finished concrete level.
label | Standard / Specification - Drawing L303
label | Verifying Document - Site photos
label | Frequency - During construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.01.4 - Hinuera Stone
label | Acceptance / Conformance Criteria - The Hinuera stone shall have a split face look (not a sawn look), laid in a mosaic interlocked pattern. The stones must be mortared in place and securely attached to the concrete plinth. Additionally, a penetrating sealer recommended by the Hinuera stone supplier shall be applied, with the product type and specification to be provided by the supplier.
label | Standard / Specification - Instruction from ER
label | Verifying Document - Site photos
label | Frequency - During construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.01.5 - Thriebeam Barrier
label | Acceptance / Conformance Criteria - The contractor shall submit a completed and signed installation check list
label | Standard / Specification - Ingal Civil Products
label | Verifying Document - Check list
label | Frequency - During construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.01.06 - Asbuilt
label | Acceptance / Conformance Criteria - All construction as per Drawing L105
label | Standard / Specification -
label | Verifying Document - Survey report
label | Frequency -
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature