## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | RR-SEPD-BESS-ITP-006-00 - Sheet piling - Layer | itp |  |  |  |  | RR-SEPD-BESS-ITP-006-00 - Sheet piling
section | Section 1: Preliminaries
checkpoint | 1.1 - Review of approved construction drawings and specifications
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI- SPC-0007
label | Conformance Criteria Summary - Approved IFC drawings and project specifications available on-site
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - IFC Drawings
checkpoint | 1.2 - Site condition check and access preparation
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI- SPC-0007
label | Conformance Criteria Summary - Site cleared, accessible, and suitable for sheet piling works
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
checkpoint | 1.3 - Site safety induction and toolbox talks
label | Responsibility - SE
label | Specification Reference - WBS-SS-CI- SPC-0007
label | Conformance Criteria Summary - All personnel inducted and briefed on safety, site-specific risks
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Site inductions records
checkpoint | 1.4 - Inspection of plant and equipment (e.g., excavator, vibro head)
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI- SPC-0007
label | Conformance Criteria Summary - All equipment calibrated and operational
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Calibration/P re-start
section | Section 2: Piling Works
checkpoint | 2.1 - Verification of work permits
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI- SPC-0007
label | Conformance Criteria Summary - All necessary permits for works are in place (GDA/GDP)
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - GDA/GDP
checkpoint | 2.2 - Review of material, certificates & technical specifications
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI- SPC-0007
label | Conformance Criteria Summary - Verify mill certificates & compliance with AS 2159
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Product certificate of compliance
holdpoint | HOLD POINT
checkpoint | 2.3 - Surveying of centre line of points for sheet pile(s).
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI- DRG-0251
label | Conformance Criteria Summary - Confirm correct position as per drawings
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - TWD FIC
holdpoint | HOLD POINT
checkpoint | 2.4 - Installation Monitoring
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI- SPC-0007 AS 2159 Manufacturer’ s Technical Data
label | Conformance Criteria Summary - Monitor driving sequence, depth and alignment
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - IFC Drawings FIC
holdpoint | HOLD POINT
checkpoint | 2.5 - Check vertical alignment during driving of sheet pile, and adjust if required
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI- SPC-0007
label | Conformance Criteria Summary - Correct positioning of all embedded items as per drawings
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - WP
label | Hold/Witness Point Requirements: SEPD - WP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - IFC Drawings FIC
checkpoint | 2.6 - Ensure sheet piles are interlocked effectively as per technical specifications
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI- DRG-0251 AS 2159 Manufacturer’ s Technical Data
label | Conformance Criteria Summary - Batch plant adheres to mix design, and delivery meets timing requirements
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
section | Section 3: Final Inspection
checkpoint | 3.1 - Pile Verticality Check
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI- DRG-0251
label | Conformance Criteria Summary - Ensure piles are plumb and no gaps or misalignment
label | Method - S
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
checkpoint | 3.2 - As-Built Survey
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI- DRG-0251
label | Conformance Criteria Summary - Confirm final location, depth & alignment
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
checkpoint | 3.3 - Engineer’s Final Sign-Off
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI- SPC-0007 AS 2159
label | Conformance Criteria Summary - Ensure compliance with design
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - WP
label | Hold/Witness Point Requirements: SEPD - WP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
checkpoint | 3.5 - Final inspection and acceptance
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI- SPC-0007
label | Conformance Criteria Summary - Finished levels, dimensions within tolerances
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - FIC
section | Document Sign-off
checkpoint | Close-out
textbox | SEPD - Name:
textbox | SEPD - Position:
date | SEPD - Date:
signoff | Add Signature