## Table 1
BESS Alinta Wagerup Peaking Power Station Field Inspection Checklist – Sheet Piling Document Number: RR-SEPD-BESS-FIC-004
Document Information
Checklist title |  |  | Concrete Retaining Walls
Checklist No |  |  | RR-SEPD-BESS-FIC-004
Lot Description
Revision no. |  |  | 0
Revision Date (DD/MM/YYYY)
Description of Changes |  |  | First Issue
Document Review
Prepared by:
Responsibility |  | Name |  |  | Signature |  | Date (DD/MM/YYYY)
Drafted by (Engineer) |  | Shaun Pham |  |  |  |  | 2025-01-30
Reviewed by (Supervisor) |  | Jake Scott |  |  |  |  | 2025-01-30
Approved by (Manager) |  | Artur Krupinski |  |  |  |  | 2025-01-31
Part 1 – Preliminaries (photos where applicable)
Inspection/Test item |  |  |  | Acceptance Criteria | Specifications/Drawings Reference | (Yes/No/NA) | Initial & Date
[7 empty] | ROBAR | SEPD
1.1 | Review of approved construction drawings and specifications |  |  | All drawings and specifications approved and up to date | WBS-SS-CI-SPC-007
1.2 | Verification of permits |  |  | All relevant permits (GDA/GDP) in place | GDA/GDP
1.3 | Site access and safety preparation |  |  | Site access cleared and made safe | WBS-SS-CI-SPC-007
1.4 | Safety inductions and toolbox talks |  |  | All personnel inducted; safety briefings completed | Induction record
1.5 | Environmental controls in place |  |  | Vibration monitors installed and functioning | SEPD environmental requirements
Part 2 – Survey (photos where applicable)
Inspection Acceptance |  |  |  | Acceptance Criteria | Specifications/Drawings Reference | (Yes/No/NA) | Initial & Date
2.1 | Set-out of sheet wall location |  |  | Sheet wall set-out conforms to approved design coordinates | Site Layout Drawings, Survey Plan
2.2 | Level and alignment check |  |  | Levels and alignment of survey points and position verified | WBS-SS-CI-SPC-0007, Survey Report
2.3 | As-built survey after sheet pile install |  |  | Survey to confirm sheet wall position | As-Built Drawings, Survey Report
Part 3 – Installation process (photos where applicable)
Inspection Acceptance |  |  |  | Acceptance Criteria | Specifications/Drawings Reference | (Yes/No/NA) | Initial & Date
3.1 | Pile alignment |  |  | Ensure proper interlocking and vertically during driving | AS 2159 Project specifications
3.2 | Driving Logs |  |  | Record depth, energy, and any obstructions encountered | AS 2159 WBS-SS-CI-SPC-0007
3.3 | Vibration Monitoring |  |  | Ensure limits comply with environmental requirements | AS 4671 WBS-SS-CI-SPC-0007
Part 4 – Quality control (photos where applicable)
Inspection Acceptance |  |  |  | Acceptance Criteria | Specifications/Drawings Reference | (Yes/No/NA) | Initial & Date
4.1 | Verticality Check |  |  | Confirm deviation tolerance | Safety Plan WBS-SS-CI-SPC-0007
4.2 | Interlock Inspection |  |  | Verify no gaps or misalignment | AS 2159 Delivery dockets
Part 5 – Post-Installation & Handover (photos where applicable)
Inspection Acceptance |  |  |  | Acceptance Criteria | Specifications/Drawings Reference | (Yes/No/NA) | Initial & Date
5.1 | As-Built Survey |  |  | Confirm final location, depth, and alignment | AS 2159 WBS-SS-CI-SPC-0007
5.2 | Cleanup & Debris Removal |  |  | Ensure worksite is left in clean and safe condition | AS 2159 WBS-SS-CI-SPC-0007
5.3 | Engineer’s Sign-Off |  |  | Obtain approval for compliance with design | WBS-SS-CI-SPC-0007
Document sign-off
Final sign-off
Company |  | Name |  |  | Signature |  | Date (DD/MM/YYYY)
ROBAR
SEPD