## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | RR-SEPD-BESS-FIC-006-00 - Sheet Piling - | itp |  |  |  |  | RR-SEPD-BESS-FIC-006-00 - Sheet Piling
section | Part 1 – Preliminaries (photos where applicable)
checkpoint | Review of approved construction drawings and specifications
label | All drawings and specifications approved and up to date
label | WBS-SS-CI-SPC-007
checkpoint | Verification of permits
label | All relevant permits (GDA/GDP) in place
label | GDA/GDP
checkpoint | Site access and safety preparation
label | Site access cleared and made safe
label | WBS-SS-CI-SPC-007
checkpoint | Safety inductions and toolbox talks
label | All personnel inducted; safety briefings completed
label | Induction record
checkpoint | Environmental controls in place
label | Vibration monitors installed and functioning
label | SEPD environmental requirements
section | Part 2 – Survey (photos where applicable)
checkpoint | Set-out of sheet wall location
label | Sheet wall set-out conforms to approved design coordinates
label | Site Layout Drawings, Survey Plan
checkpoint | Level and alignment check
label | Levels and alignment of survey points and position verified
label | WBS-SS-CI-SPC-0007, Survey Report
checkpoint | As-built survey after sheet pile install
label | Survey to confirm sheet wall position
label | As-Built Drawings, Survey Report
section | Part 3 – Installation process (photos where applicable)
checkpoint | Pile alignment
label | Ensure proper interlocking and vertically during driving
label | AS 2159 Project specifications
checkpoint | Driving Logs
label | Record depth, energy, and any obstructions encountered
label | AS 2159, WBS-SS-CI-SPC-0007
checkpoint | Vibration Monitoring
label | Ensure limits comply with environmental requirements
label | AS 4671, WBS-SS-CI-SPC-0007
section | Part 4 – Quality control (photos where applicable)
checkpoint | Verticality Check
label | Confirm deviation tolerance
label | Safety Plan WBS-SS-CI-SPC-0007
checkpoint | Interlock Inspection
label | Verify no gaps or misalignment
label | AS 2159 Delivery dockets
section | Part 5 – Post-Installation & Handover (photos where applicable)
checkpoint | As-Built Survey
label | Confirm final location, depth, and alignment
label | AS 2159, WBS-SS-CI-SPC-0007
checkpoint | Cleanup & Debris Removal
label | Ensure worksite is left in clean and safe condition
label | AS 2159, WBS-SS-CI-SPC-0007
checkpoint | Engineer’s Sign-Off
label | Obtain approval for compliance with design
label | WBS-SS-CI-SPC-0007
section | Document Sign-off
checkpoint | Prepared by:
textbox | SEPD (Engineer) - Name:
date | SEPD (Engineer) - Date:
signoff | Add Signature