## Sheet1
1.1 | Review of approved construction drawings and specifications | SE/PE | WBS-SS-CI- SPC-0007 | Approved IFC drawings and project specifications available on-site | R | PW | V | NA | NA | IFC Drawings | 1.1 - Review of approved construction drawings and specifications | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0007 | Conformance Criteria Summary - Approved IFC drawings and project specifications available on-site | Method - R | Frequency - PW | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - NA | Hold/Witness Point Requirements: Client - NA | Records or Checklist Document Number - IFC Drawings | 1.1 - Review of approved construction drawings and specifications
1.3 | Site safety induction and toolbox talks | S E | WBS-SS-CI- SPC-0007 | All personnel inducted and briefed on safety, site-specific risks | R | P W | V | NA | NA | Site inductions records | 1.3 - Site safety induction and toolbox talks | Responsibility - S E | Specification Reference - WBS-SS-CI- SPC-0007 | Conformance Criteria Summary - All personnel inducted and briefed on safety, site-specific risks | Method - R | Frequency - P W | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - NA | Hold/Witness Point Requirements: Client - NA | Records or Checklist Document Number - Site inductions records | Responsibility - SE/PE
1.4 | Inspection of plant and equipment (e.g., excavator, vibro head) | SE/PE | WBS-SS-CI- SPC-0007 | All equipment calibrated and operational | R | PW | V | NA | NA | Calibration/P re-start | 1.4 - Inspection of plant and equipment (e.g., excavator, vibro head) | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0007 | Conformance Criteria Summary - All equipment calibrated and operational | Method - R | Frequency - PW | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - NA | Hold/Witness Point Requirements: Client - NA | Records or Checklist Document Number - Calibration/P re-start | Specification Reference - WBS-SS-CI- SPC-0007
2.1 | Verification of work permits | SE/PE | WBS-SS-CI- SPC-0007 | All necessary permits for works are in place (GDA/GDP) | R | PL | V | V | NA | GDA/GDP | 2.1 - Verification of work permits | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0007 | Conformance Criteria Summary - All necessary permits for works are in place (GDA/GDP) | Method - R | Frequency - PL | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - V | Hold/Witness Point Requirements: Client - NA | Records or Checklist Document Number - GDA/GDP | Conformance Criteria Summary - Approved IFC drawings and project specifications available on-site
2.2 | Review of material, certificates CHAR(AMP) technical specifications | SE/PE | WBS-SS-CI- SPC-0007 | Verify mill certificates CHAR(AMP) compliance with AS 2159 | R | PW | HP | HP | NA | Product certificate of compliance | 2.2 - Review of material, certificates CHAR(AMP) technical specifications | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0007 | Conformance Criteria Summary - Verify mill certificates CHAR(AMP) compliance with AS 2159 | Method - R | Frequency - PW | Hold/Witness Point Requirements: ROBAR - HP | Hold/Witness Point Requirements: SEPD - HP | Hold/Witness Point Requirements: Client - NA | Records or Checklist Document Number - Product certificate of compliance | Method - R
2.3 | Surveying of centre line of points for sheet pile(s). | SE/PE | WBS-SS-CI- DRG-0251 | Confirm correct position as per drawings | R | PW | HP | HP | NA | TWD FIC | 2.3 - Surveying of centre line of points for sheet pile(s). | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- DRG-0251 | Conformance Criteria Summary - Confirm correct position as per drawings | Method - R | Frequency - PW | Hold/Witness Point Requirements: ROBAR - HP | Hold/Witness Point Requirements: SEPD - HP | Hold/Witness Point Requirements: Client - NA | Records or Checklist Document Number - TWD FIC | Frequency - PW
2.4 | Installation Monitoring | SE/PE | WBS-SS-CI- SPC-0007 AS 2159 Manufacturer’ s Technical Data | Monitor driving sequence, depth and alignment | R | PW | HP | HP | NA | IFC Drawings FIC | 2.4 - Installation Monitoring | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0007 AS 2159 Manufacturer’ s Technical Data | Conformance Criteria Summary - Monitor driving sequence, depth and alignment | Method - R | Frequency - PW | Hold/Witness Point Requirements: ROBAR - HP | Hold/Witness Point Requirements: SEPD - HP | Hold/Witness Point Requirements: Client - NA | Records or Checklist Document Number - IFC Drawings FIC | Hold/Witness Point Requirements: ROBAR - V
2.5 | Check vertical alignment during driving of sheet pile, and adjust if required | SE/PE | WBS-SS-CI- SPC-0007 | Correct positioning of all embedded items as per drawings | R | PW | WP | WP | NA | IFC Drawings FIC | 2.5 - Check vertical alignment during driving of sheet pile, and adjust if required | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0007 | Conformance Criteria Summary - Correct positioning of all embedded items as per drawings | Method - R | Frequency - PW | Hold/Witness Point Requirements: ROBAR - WP | Hold/Witness Point Requirements: SEPD - WP | Hold/Witness Point Requirements: Client - NA | Records or Checklist Document Number - IFC Drawings FIC | Hold/Witness Point Requirements: SEPD - NA
2.6 | Ensure sheet piles are interlocked effectively as per technical specifications | SE/PE | WBS-SS-CI- DRG-0251 AS 2159 Manufacturer’ s Technical Data | Batch plant adheres to mix design, and delivery meets timing requirements | R | PW | V | NA | NA | FIC | 2.6 - Ensure sheet piles are interlocked effectively as per technical specifications | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- DRG-0251 AS 2159 Manufacturer’ s Technical Data | Conformance Criteria Summary - Batch plant adheres to mix design, and delivery meets timing requirements | Method - R | Frequency - PW | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - NA | Hold/Witness Point Requirements: Client - NA | Records or Checklist Document Number - FIC | Hold/Witness Point Requirements: Client - NA
3.1 | Pile Verticality Check | SE/PE | WBS-SS-CI- DRG-0251 | Ensure piles are plumb and no gaps or misalignment | S | PL | V | V | NA | FIC | 3.1 - Pile Verticality Check | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- DRG-0251 | Conformance Criteria Summary - Ensure piles are plumb and no gaps or misalignment | Method - S | Frequency - PL | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - V | Hold/Witness Point Requirements: Client - NA | Records or Checklist Document Number - FIC | Records or Checklist Document Number - IFC Drawings
3.2 | As-Built Survey | SE/PE | WBS-SS-CI- DRG-0251 | Confirm final location, depth CHAR(AMP) alignment | R | PL | V | V | NA | FIC | 3.2 - As-Built Survey | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- DRG-0251 | Conformance Criteria Summary - Confirm final location, depth CHAR(AMP) alignment | Method - R | Frequency - PL | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - V | Hold/Witness Point Requirements: Client - NA | Records or Checklist Document Number - FIC | 1.3 - Site safety induction and toolbox talks
3.3 | Engineer’s Final Sign-Off | SE/PE | WBS-SS-CI- SPC-0007 AS 2159 | Ensure compliance with design | R | PL | WP | WP | NA | FIC | 3.3 - Engineer’s Final Sign-Off | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0007 AS 2159 | Conformance Criteria Summary - Ensure compliance with design | Method - R | Frequency - PL | Hold/Witness Point Requirements: ROBAR - WP | Hold/Witness Point Requirements: SEPD - WP | Hold/Witness Point Requirements: Client - NA | Records or Checklist Document Number - FIC | Responsibility - S E
3.5 | Final inspection and acceptance | SE/PE | WBS-SS-CI- SPC-0007 | Finished levels, dimensions within tolerances | R | PL | V | V | NA | FIC | 3.5 - Final inspection and acceptance | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0007 | Conformance Criteria Summary - Finished levels, dimensions within tolerances | Method - R | Frequency - PL | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - V | Hold/Witness Point Requirements: Client - NA | Records or Checklist Document Number - FIC | Specification Reference - WBS-SS-CI- SPC-0007
Conformance Criteria Summary - All personnel inducted and briefed on safety, site-specific risks
Method - R
Frequency - P W
Hold/Witness Point Requirements: ROBAR - V
Hold/Witness Point Requirements: SEPD - NA
Hold/Witness Point Requirements: Client - NA
Records or Checklist Document Number - Site inductions records
1.4 - Inspection of plant and equipment (e.g., excavator, vibro head)
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- SPC-0007
Conformance Criteria Summary - All equipment calibrated and operational
Method - R
Frequency - PW
Hold/Witness Point Requirements: ROBAR - V
Hold/Witness Point Requirements: SEPD - NA
Hold/Witness Point Requirements: Client - NA
Records or Checklist Document Number - Calibration/P re-start
2.1 - Verification of work permits
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- SPC-0007
Conformance Criteria Summary - All necessary permits for works are in place (GDA/GDP)
Method - R
Frequency - PL
Hold/Witness Point Requirements: ROBAR - V
Hold/Witness Point Requirements: SEPD - V
Hold/Witness Point Requirements: Client - NA
Records or Checklist Document Number - GDA/GDP
2.2 - Review of material, certificates CHAR(AMP) technical specifications
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- SPC-0007
Conformance Criteria Summary - Verify mill certificates CHAR(AMP) compliance with AS 2159
Method - R
Frequency - PW
Hold/Witness Point Requirements: ROBAR - HP
Hold/Witness Point Requirements: SEPD - HP
Hold/Witness Point Requirements: Client - NA
Records or Checklist Document Number - Product certificate of compliance
2.3 - Surveying of centre line of points for sheet pile(s).
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- DRG-0251
Conformance Criteria Summary - Confirm correct position as per drawings
Method - R
Frequency - PW
Hold/Witness Point Requirements: ROBAR - HP
Hold/Witness Point Requirements: SEPD - HP
Hold/Witness Point Requirements: Client - NA
Records or Checklist Document Number - TWD FIC
2.4 - Installation Monitoring
Responsibility - SE/PE
[21 empty] | Specification Reference - WBS-SS-CI- SPC-0007 AS 2159 Manufacturer’ s Technical Data | NA | IFC Drawings
[21 empty] | Conformance Criteria Summary - Monitor driving sequence, depth and alignment | NA | RR-SEPD-CI- SOW-002-01
[21 empty] | Method - R | NA | IFC Drawings
[21 empty] | Frequency - PW | NA | SEPD environment- al plan
[21 empty] | Hold/Witness Point Requirements: ROBAR - HP | NA | SEPD environment- al plan
[21 empty] | Hold/Witness Point Requirements: SEPD - HP | NA | Material certificates
[21 empty] | Hold/Witness Point Requirements: Client - NA | NA | Test results
[21 empty] | Records or Checklist Document Number - IFC Drawings FIC | NA | IFC Drawings
[21 empty] | 2.5 - Check vertical alignment during driving of sheet pile, and adjust if required | NA | SEPD environment- al plan
[21 empty] | Responsibility - SE/PE | NA
[21 empty] | Specification Reference - WBS-SS-CI- SPC-0007 | NA | WBS-SS-CI- ITP-920049
[21 empty] | Conformance Criteria Summary - Correct positioning of all embedded items as per drawings | NA | Test results
[21 empty] | Method - R | NA | As-built drawings
[21 empty] | Frequency - PW | NA | WBS-SS-CI- ITP-920049
[21 empty] | Hold/Witness Point Requirements: ROBAR - WP | NA | WBS-SS-CI- ITP-920049
Hold/Witness Point Requirements: SEPD - WP
Hold/Witness Point Requirements: Client - NA
Records or Checklist Document Number - IFC Drawings FIC
2.6 - Ensure sheet piles are interlocked effectively as per technical specifications
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- DRG-0251 AS 2159 Manufacturer’ s Technical Data
Conformance Criteria Summary - Batch plant adheres to mix design, and delivery meets timing requirements
Method - R
Frequency - PW
Hold/Witness Point Requirements: ROBAR - V
Hold/Witness Point Requirements: SEPD - NA
Hold/Witness Point Requirements: Client - NA
Records or Checklist Document Number - FIC
3.1 - Pile Verticality Check
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- DRG-0251
Conformance Criteria Summary - Ensure piles are plumb and no gaps or misalignment
Method - S
Frequency - PL
Hold/Witness Point Requirements: ROBAR - V
Hold/Witness Point Requirements: SEPD - V
Hold/Witness Point Requirements: Client - NA
Records or Checklist Document Number - FIC
3.2 - As-Built Survey
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- DRG-0251
Conformance Criteria Summary - Confirm final location, depth CHAR(AMP) alignment
Method - R
Frequency - PL
Hold/Witness Point Requirements: ROBAR - V
Hold/Witness Point Requirements: SEPD - V
Hold/Witness Point Requirements: Client - NA
Records or Checklist Document Number - FIC
3.3 - Engineer’s Final Sign-Off
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- SPC-0007 AS 2159
Conformance Criteria Summary - Ensure compliance with design
Method - R
Frequency - PL
Hold/Witness Point Requirements: ROBAR - WP
Hold/Witness Point Requirements: SEPD - WP
Hold/Witness Point Requirements: Client - NA
Records or Checklist Document Number - FIC
3.5 - Final inspection and acceptance
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- SPC-0007
Conformance Criteria Summary - Finished levels, dimensions within tolerances
Method - R
Frequency - PL
Hold/Witness Point Requirements: ROBAR - V
Hold/Witness Point Requirements: SEPD - V
Hold/Witness Point Requirements: Client - NA
Records or Checklist Document Number - FIC