## Project Structure
Folder Structure | Folder Structure | Folder Structure | Folder Structure | Checklists
MATERIAL DELIVERIES
PLANT HIRE
DELAYS
SITE QA
CIVILS / INGROUNDS
|  | PROJECT WIDE INGROUND WORKS |  | ITP-220 - INGROUND WORKS
ZONE #1
|  |  | EW1-1A | ITC-220.1 - INGROUND WORKS
|  |  | EW1-1B | ITC-220.1 - INGROUND WORKS
|  |  | EW1-1C | ITC-220.1 - INGROUND WORKS
|  |  | EW1-1D | ITC-220.1 - INGROUND WORKS
|  |  | EW1-1E | ITC-220.1 - INGROUND WORKS
|  |  | EW1-1F | ITC-220.1 - INGROUND WORKS
ZONE #2
|  |  | EW1-2A | ITC-220.1 - INGROUND WORKS
|  |  | EW1-2B | ITC-220.1 - INGROUND WORKS
|  |  | EW1-2C | ITC-220.1 - INGROUND WORKS
|  |  | EW1-2D | ITC-220.1 - INGROUND WORKS
ZONE #3
|  |  | EW1-3A | ITC-220.1 - INGROUND WORKS
|  |  | EW1-3B | ITC-220.1 - INGROUND WORKS
|  |  | EW1-3C | ITC-220.1 - INGROUND WORKS
|  |  | EW1-3D | ITC-220.1 - INGROUND WORKS
|  | ZONE #4 |  | ITC-220.1 - INGROUND WORKS
|  |  | EW1-4A | ITC-220.1 - INGROUND WORKS
|  |  | EW1-4B | ITC-220.1 - INGROUND WORKS
|  |  | EW1-4C | ITC-220.1 - INGROUND WORKS
|  |  | EW1-4D | ITC-220.1 - INGROUND WORKS
ITC-220.1 - INGROUND WORKS
ITC-220.1 - INGROUND WORKS
ITC-220.1 - INGROUND WORKS
ITC-220.1 - INGROUND WORKS
ITC-220.1 - INGROUND WORKS
ITC-220.1 - INGROUND WORKS
ITC-220.1 - INGROUND WORKS
ITC-220.1 - INGROUND WORKS
ITC-220.1 - INGROUND WORKS
ITC-220.1 - INGROUND WORKS
ITC-220.1 - INGROUND WORKS
ITC-220.1 - INGROUND WORKS
ITC-220.1 - INGROUND WORKS
ITC-220.1 - INGROUND WORKS
ITC-220.1 - INGROUND WORKS

## Checklists
type | name | values
checklist | ITP-220 - INGROUND WORKS
section | MARK OUT ROUTE
checkpoint | Criteria as per Electrical Services Specification issued by consultant
section | POTHOLING / SSERVICE LOCATION
checkpoint | Check against current GFIS drawing + Site Service Drawings
checkpoint | Mark up all documentation identifying any service clashes
checkpoint | Coordinate with others where necessary
checkpoint | Survey level documents
section | DIG PERMIT
checkpoint | Ensure Builder issues permit to dig.
checkpoint | Ensure proposed trench route is clearly identified and all existing and proposed new buried services have been exposed / considered.
section | TRENCHING CORRECT SIZE / ALIGNMENT / DEPTH (USE DATUM POINTS)
checkpoint | As per Electrical Services Specifications + Drawings
section | CONDUIT CORRECT SIZE / ALIGNMENT / SPACING
checkpoint | As per Electrical Services Specifications + Drawings
section | TRENCHING DETAIL & IDENTIFICATION FOR AS-BUILT DOCUMENTATION
checkpoint | Photograph trench detail showing correct installation method.
checkpoint | Photograph trench detail showing correct depth.
section | RAGBOLTS & POLE FOOTINGS
checkpoint | Ensure Augered hole meets minimum engineered requirements
checkpoint | Ensure the rag bolt and footing is completely filled with concrete and finished with FFL
section | PIT INSTALLATION
checkpoint | Ensure pit is installed adjacent to path/building and to FFL using surveyors markers
checkpoint | Smoothen edges of conduit penetrations or installed manufactured bell mouths to allow cables to be neatly pulled through pits safely
section | GFIS TRENCHING DETAIL FOR AS-BUILT DOCUMENTATION
checkpoint | Engage surveyors to carry out these works.
section | BACKFILL / COMPACTION
checkpoint | As per Electrical Services Drawings + Civil Specifications
section | TRENCH IDENTIFICATION MARKER PLATES
checkpoint | As Built Drawings
section | HAND OVER, SUBMISSION & DOCUMENTATION
checkpoint | O&M Manual
section | SIGNOFF
checkpoint | Please attach signatures of all employees involved in consultation, development & acceptance of this ITP
label | Include license number
checklist | ITC-220.1 - INGROUND WORKS
checkpoint | ATTACH ANY RELEVANT PHOTOS & DOCUMENTS
text | Conduit Run / Grid No
checkpoint | SURVEY & SETOUT WAS CORRECT AT TIME OF SURVEY (SURVEYOR TO COMPLETE & REFERENCE SETOUT INFO)
checkpoint | PERMIT TO DIG OBTAINED FROM BUILDER
checkpoint | CHECK ALIGNMENT, CORRECT WIDTH & DEPTH, AND SUITABILITY OF BASE CONFIRMED
checkpoint | CHECK CONDUIT SIZE / TYPE / QTY IS CORRECT
checkpoint | CHECK CONDUIT SPACING IS CORRECT
checkpoint | PHOTO OF TRENCH DETAIL & DEPTH
checkpoint | GFIS DETAIL FOR AS-BUILT DOCUMENTATION SURVEYOR TO COMPLETE
checkpoint | CONFIRM BACKFILL IS SUITABLE CHECK COMPACTION & FREQUENCY REQUIREMENTS
holdpoint | HOLD POINT PRIOR TO BACKFILL
checkpoint | GEO TO CONFIRM
checkpoint | SUITABILITY OF PROPOSED BACKFILL
checkpoint | TEST 1 PER 2 LAYERS EVERY 40M
checkpoint | CONFIRM LAYERS BEING REPLACED. IE. GEO-FAB / ROAD BASE / GENERAL FILL / ETC NOTE: LAYER THICKNESS IS 250MM MAX LOOSE
checkpoint | TRENCH MARKERS
checkpoint | GEOTECH RESULTS REVIEWED

## Delay Checklists
checklist | DELAY (CIVILS / INGROUNDS)
checkpoint | DELAY IN INSTALLATION OF CIVILS / INGROUNDS
text | Type of delay (rock / PFAS / etc). Only applicable if 20T excavator can not rip out rock.
checkpoint | PHOTO OF DELAY ISSUE
checkpoint | LOCATION OF DELAY ISSUE
text | Drawing, Conduit Run & Grid No.
hold point | BUILDER SITE INSTRUCTION TO PROCEED
label | (Do not proceed until the Builder has signed off) Builder is required to sign off on any non-rippable rock using a 20T excavator as per Contract
checkpoint | TIME TAKEN & DETAILS OF THE DELAY
text | Enter the time taken to remove & details (eg. weight / size / etc)
checkpoint | PHOTO OF DELAY ISSUE RESOLVED
checkpoint | ADDITIONAL COSTS
text | Enter the additional bedding sand / backfill / compaction / etc due to trench enlargement
hold point | BUILDER FINAL SIGN OFF
checklist | DELAY (GENERAL)
checkpoint | DELAY IN INSTALLATION OF WORKS
text | Description of the issue causing delay to our installation works
checkpoint | PHOTO OF DELAY ISSUE
checkpoint | LOCATION OF DELAY ISSUE
text | Drawing & Grid No
hold point | BUILDER ACKNOWLEDGEMENT
label | (Do not proceed until the Builder has signed off)

## Delivery Checklists
checklist | MATERIAL DELIVERY
checkpoint | PHOTO OF MATERIALS DELIVERED
date | DATE OF ON HIRE
holdpoint | FREDON EMPLOYEE RECEIVING GOODS
label | Fredon employee to sign for goods receival
checkpoint | PHOTO OF DELIVERY DOCKED - MARKED UP
label | Complete reconciliation of goods received against delivery docket to ensure the delivery docket matches what has been received
checkpoint | ANYTHING ON BACK ORDER?
label | Goods on back order = FAIL
checkpoint | LOCATION OF STORAGE
text | Enter location of goods being stored
checklist | PLANT HIRE
checkpoint | PHOTO OF PLANT DELIVERED
checkpoint | PHOTO OF PLANT SERIAL NUMBER
date | DATE OF ON HIRE
holdpoint | FREDON EMPLOYEE RECEIVING PLANT
label | Fredon employee to sign for plant receival
checkpoint | PURCHASE ORDER REFERENCE NUMBER
label | Leave blank. This is to be filled in by Project Manager / Site Manager / Project Administrator
checkpoint | PHOTO OF PLANT OFF HIRED
date | DATE OF OFF HIRE