## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Type B - Lot Register
| Scope |  |  | Site QA | Type B
Rows
|  | McGregor Road North | dynamic | McGregor Rd - North | Type B | Site QA
|  | McGregor Road South | dynamic | McGregor Rd - South | Type B | Site QA
|  | HKWRR North | dynamic | HKWRR North | Type B | Site QA
|  | HKWRR South | dynamic | HKWRR South | Type B | Site QA
Columns
|  | Lot Map | Lot map | 1.1.1 - Lot Map | 1.0 Pre-start activities
|  | Surveyor Report Reference | Surveyor report reference | 2.1.1 - Surveyor Report Reference | 2.0 Set Out
|  | Signed Hold Points |  | AUTHORITY HOLDPOINT
|  | Incoming Material Docket | Incoming material docket | 3.0.1 - Incoming Material Docket | 3.0 Placement of Type B Material
|  | Compaction Test Result | NATA Test Report: Compaction | 4.2 - Compaction Testing / Moisture Testing | 4.0 Geotechnical Analysis
|  | CBR Test Result | NATA Test Report: CBR and Swell | 4.1 - CBR/Swell – Initial Testing | 4.0 Geotechnical Analysis
|  | Proof Roll | Proof roll if applicable - comment reasoning if N/A | 3.6.1 - Proof roll if applicable | 3.0 Placement of Type B Material
|  | Lot Status | Lot Status | Lot Conformance | 6.0 Work Lot Close Out
|  | Lot Opened On | Lot opened date: | Lot Conformance | 6.0 Work Lot Close Out
|  | Lot Opened By | Lot opened by: | Lot Conformance | 6.0 Work Lot Close Out
|  | NCR Raised? | NCR raised? | Lot Conformance | 6.0 Work Lot Close Out
|  | NCR Raised date | NCR Raised Date: | Lot Conformance | 6.0 Work Lot Close Out
|  | NCR Closed? | NCR closed? | Lot Conformance | 6.0 Work Lot Close Out
|  | NCR Closed Date | NCR Closed Date: | Lot Conformance | 6.0 Work Lot Close Out
|  | NCR No. | NCR Number: | Lot Conformance | 6.0 Work Lot Close Out
|  | Comments | Comments | Lot Conformance | 6.0 Work Lot Close Out