## ITP-024
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-XX
[11 empty] | Revision : 0 | Date :
Client: |  | DPT |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Midland HWY/ Clyde rd RAB |  | Insitu Concrete Pit |  | Name: Jarrod Rodrigues |  | Name: | Damon Bromwich |  | Name: Shaun Kent
Contract No: |  |  |  | Specifications: SD1131
|  |  |  | Structure / Component: Stormwater Drainage Pits |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Midland HWY |  | Date : 12/03/2021 |  | Date : 12/03/2021 |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | •Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Pit material classification |  | Each delivery | •Concrete used shall have a mininmum strength of 32MPa and be • Steel fabric shall be F92 reinforcement | SD1131 | Visual Inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Backfill and bedding material classificaiton |  | Prior to start | •All crused rock used in the works shall be Class 3, 20mm nominal size. | Cl 18.0 | Verify | Test reports from supplier | HP* | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Set out pit location |  | Prior to backfilling | •The line, level and location of all pits & structures must be in accordance with the provided design drawings. •The position of all pits are to be confirmed with the superintendent if ambiguity arises from the drawings. | Survey file / Drawings | Survey Conformance Report | Survey Report. This ITP signed off | WP | Fulton Hogan Engineer | N/A
2.2 | Excavation |  | Each trench | •Any trench which may have been excavated to a greater depth than necessary shall be filled into the required level with concrete 1:3:6 mix. Any loose material shall be removed. •Trench shall be battered, benched or shored in line with WorkSafe code of practice when required by assessment under 1.5m in depth and is mandatory over 1.5m. •No stockpiles within 2m of end of the trench to reduce bearing pressure. | Section 705 | Visual Inspection | This ITP signed off | IP | Fulton Hogan Foreman | N/A |  | N/A
2.3 | Inspection of trench base |  | Each Lot | •Base of the trench shall be inspected prior to placement of bedding. | Section 701 | Visual Inspection | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.4 | Placement of bedding material |  | Each Lot | •A 100mm minimum layer of compacted class 3 crushed rock shall be used under base of pit | Section 701 | Visual Inspection | This ITP signed off | IP | Fulton Hogan Foreman | N/A |  | N/A
2.5 | Concrete pre-pour inspection |  | Each Lot | Confirm minimum wall thickness and Mesh Cover as per SD1131. Inspect bedding to confirm is compacted to correct depth and free of as water or debris. | SD1131 | Visual Inspection | This ITP signed off | WP | Fulton Hogan Engineer / DPT Superintendent |  |  | N/A
2.6 | Concrete pour and pit construction |  | Each Lot | •All pits are to be constructed in accordance with Vicroads Standard Drawing SD1131. •All pits are to be constructed in accordance with Vicroads standards 701 &705. Pit should also be constructed in accordance with site specific drawings. •Concrete Vibrator must be used | SD1131 Section701 Section705 | Visual inspection | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.7 | Pit base shaped with concrete to match pipe invert |  | Each Lot | •Construct as shown on Standard Drawing SD1131 | SD1131 | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.8 | Placement of pit covers |  | Each Lot | •All pits shall be fitted with standard Vicroads specificed on the drawings of appropriate class. | SD1131 | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FHDB |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.