## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-033 - Insitu Concrete Pit | itp |  |  |  |  | ITP-033 - Insitu Concrete Pit
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.3 - Pit material classification
label | FREQUENCY: Each delivery
label | ACCEPTANCE CRITERIA: Concrete used shall have a mininmum strength of 32MPa and be
label | ○ Steel fabric shall be F92 reinforcement
label | REFERENCE DOCUMENTS: SD1131
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.4 - Backfill and bedding material classificaiton
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: All crused rock used in the works shall be Class 3, 20mm nominal size.
label | REFERENCE DOCUMENTS: Cl 18.0
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test reports from supplier
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Set out pit location
label | FREQUENCY: Prior to backfilling
label | ACCEPTANCE CRITERIA: The line, level and location of all pits & structures must be in accordance with the provided design drawings.
label | ○ The position of all pits are to be confirmed with the superintendent if ambiguity arises from the drawings.
label | REFERENCE DOCUMENTS: Survey file / Drawings
label | INSPECTION/TEST METHOD: Survey Conformance Report
label | RECORD OF CONFORMITY: Survey Report. This ITP signed off.
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.2 - Excavation
label | FREQUENCY: Each trench
label | ACCEPTANCE CRITERIA: Any trench which may have been excavated to a greater depth than necessary shall be filled into the required level with concrete 1:3:6 mix. Any loose material shall be removed.
label | ○ Trench shall be battered, benched or shored in line with WorkSafe code of practice when required by assessment under 1.5m in depth and is mandatory over 1.5m.
label | ○ No stockpiles within 2m of end of the trench to reduce bearing pressure.
label | REFERENCE DOCUMENTS: Section 705
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Foreman
date | Date Completed:
checkpoint | 2.3 - Inspection of trench base
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Base of the trench shall be inspected prior to placement of bedding.
label | REFERENCE DOCUMENTS: Section 701
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.4 - Placement of bedding material
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: A 100mm minimum layer of compacted class 3 crushed rock shall be used under base of pit
label | REFERENCE DOCUMENTS: Section 701
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Foreman
date | Date Completed:
checkpoint | 2.5 - Concrete pre-pour inspection
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Confirm minimum wall thickness and Mesh Cover as per SD1131. Inspect bedding to confirm is compacted to correct depth and free of as water or debris.
label | REFERENCE DOCUMENTS: SD1131
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer / DPT Superintendent
date | Date Completed:
checkpoint | 2.6 - Concrete pour and pit construction
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All pits are to be constructed in accordance with Vicroads Standard Drawing SD1131.
label | ○ All pits are to be constructed in accordance with Vicroads standards 701 &705. Pit should also be constructed in accordance with site specific drawings.
label | ○ Concrete Vibrator must be used
label | REFERENCE DOCUMENTS: SD1131 Section701 Section705
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.7 - Pit base shaped with concrete to match pipe invert
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Construct as shown on Standard Drawing SD1131
label | REFERENCE DOCUMENTS: SD1131
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 2.8 - Placement of pit covers
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All pits shall be fitted with standard Vicroads specificed on the drawings of appropriate class.
label | REFERENCE DOCUMENTS: SD1131
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: