## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Add Photos |  | Photos: | c2b9f5f5-2b86-49a5-80f3-38190f852ab7
| section | Details
| checkpoint | Please upload all relevant photos and press PASS
| checklist | W25 Wiri RAP Interface ITP | itp | W25 Wiri RAP Interface ITP | eee20048-8037-42bb-85a5-211fe3f8605a
| section | Details
| checkpoint | 1 - Issued For Construction Drawings
14e560e1-e462-5822-9ef7-bfb47765a793 | note | SPECIFICATION REFERENCE: IFC Drawings Issued by Client/Engineer
468ea300-0531-5d42-802a-c97b0c452e38 | note | ACCEPTANCE CRITERIA: Issued For Construction Drawings Available
e1fb5811-2352-58ff-a9a8-1c4e213b001e | note | DATE/SIGN: Contractor Rep - H
| signoff | HOLD POINT
| checkpoint | 2 - Underground Services Confirmation
e4393529-e18e-515f-8143-b2f8416059a0 | note | SPECIFICATION REFERENCE: CTS Permit to Work
98dc5e73-06b9-5037-9761-40fe188eb1e4 | note | ACCEPTANCE CRITERIA: Underground Services Drawings to accompany permit and marked out onsite where excavation is to be undertaken
721a346e-2504-56ca-af3e-36a9d3e1c1cd | note | DATE/SIGN: Contractor Rep - P
3aaf4a53-eef7-5063-a8bf-f7bafb5ef9f4 | note | ○ CTS Civil Inspector - R
| checkpoint | 3 - Survey & Setout
44700001-d822-54a7-9581-ed17aa8d2da8 | note | SPECIFICATION REFERENCE: IFC Drawings
5626be32-5086-51db-ae78-0eb5b638bea2 | note | ○ CTS General Civil Construction Spec
0020406b-98d5-5a67-bf14-38c33676700b | note | ○ CTS Excavation Works Spec
5583ac0b-ab89-5d29-a05f-45c52d9ed749 | note | ACCEPTANCE CRITERIA: Foundations and embedded items shall be setout following the tolerances, heights and positions shown in each foundations respective drawing.
0e36f685-a029-5a4e-bf13-dfa447d561ce | note | DATE/SIGN: Contractor Rep - P
| checkpoint | 4 - Waste Management & Disposal
97e0785c-2c79-52a0-a125-a6b222b7790b | note | SPECIFICATION REFERENCE: CTS General Civil Construction Spec
5113ea89-293e-580e-87b7-0cd9952b48de | note | ○ CTS Excavation Works Spec
a958e955-b8e6-5e61-b32a-09f41857db7f | note | ○ CTS Contaminated Environmental Ground Soil Managenet Plan RW-231
4f1713a1-a69f-56d5-a614-e2c465186600 | note | ACCEPTANCE CRITERIA: Waste management plan prepared and followed. Supporting documents available on request
652514ef-12e0-518b-b07e-7798bd7434c1 | note | DATE/SIGN: Contractor Rep - P
5a80dbf3-5ebb-5b06-8ca5-49373d423a26 | note | ○ CTS Civil Inspector - R
| checkpoint | 5A - Demolition
0896c0f7-9fc3-5c57-9aa9-cb07866dbbcd | note | SPECIFICATION REFERENCE: IFC Drawings
cb80c843-5038-5bd4-8aec-01530a8c4026 | note | ACCEPTANCE CRITERIA: Existing pedestal removed at ground level
166bad3d-f6ff-53b9-9526-7307b612e2b0 | note | ○ Concrete removed to approved landfill
c121a744-9235-5af3-abd9-c2a6cec9522e | note | DATE/SIGN: Contractor Rep - P
95239fec-10c4-5e23-9396-d72997b24440 | note | ○ CTS Civil Inspector - R
| checkpoint | 5B - Position of Pump Pedestal Setout
2c9d9d9b-d617-5a6b-90fc-a81cf981e9c9 | note | SPECIFICATION REFERENCE: IFC Drawings
7db8fb62-f099-5944-a68e-7b434d42f1e5 | note | ACCEPTANCE CRITERIA: Setout as per IFC Drawings
f362729c-2dc3-51c8-8c57-3d59fd2542d1 | note | DATE/SIGN: Contractor Rep - P
ee9a611f-5e82-5ca7-afb8-8c32adbb5124 | note | ○ CTS Civil Inspector - R
| checkpoint | 5C - Pump pedestal location Cleaned & Scabbled
4c7b2ede-4a02-59d6-b99f-bd2e227dc2d2 | note | SPECIFICATION REFERENCE: IFC Drawings
e2f95c6d-067c-5c43-b5c0-b48654effbfa | note | ACCEPTANCE CRITERIA: Foundation area cleaned and free from contamination and dust/oil or grease, surface roughened to accept further concrete pour
e78a5186-5455-5c9a-8412-994daea7c2b2 | note | DATE/SIGN: Contractor Rep - P
6ccb5418-d312-53c9-93e9-584991ffc614 | note | ○ CTS Civil Inspector - R
| checkpoint | 5D - Cast in Items - Bolts & Nuts
fd0500fb-ea20-5fd5-aa8c-8c1c7e80dfa8 | note | SPECIFICATION REFERENCE: IFC Drawings
516ea30d-0249-5c9a-b082-ff6c04d21050 | note | ○ CTS General Civil Construction Specification
5b51cdde-f82e-5586-9804-20a45cefdd7d | note | ○ CTS Epoxy Grouting of Anchor Bolts
a5995309-ec0c-59f1-ac52-b320dfea8f2d | note | ○ Manufacturers Documentation
ce19b1a7-e3c3-5de1-8b2e-d10164b71617 | note | ○ Inspection Records
825b30e4-a02e-51cc-87e7-9ad4fe0f1eec | note | ACCEPTANCE CRITERIA: If drilled in, Epoxy Grout Shall be Ramset C8 placed in accordance with manufacturers recommendations to the levels and positions setout in the drawings
0713b261-a2be-58df-8dd2-5e78a09d2518 | note | ○ Drilled holes for Anchors shall be inspected
b7f20fbc-1c79-5331-8eae-1398aa24986d | note | ○ Cast in anchor bolts shall be set to spec in IFC drawings and positioned with template to design measurenments in IFC drawings
e519a704-14e0-5435-9cd0-a19a73e12d2d | note | DATE/SIGN: Contractor Rep - P
59067b11-c40c-5bef-bae0-134044ce4bc1 | note | ○ CTS Civil Inspector - R
| checkpoint | 5E - Formwork, Reinforcing & Concrete
3bce4f58-6017-5f28-95e1-36da7599bbe7 | note | SPECIFICATION REFERENCE: IFC Drawings
ef24c0aa-97b8-5b9b-aefe-ee2723537ede | note | ○ CTS General Civil Construction Specification
f05e6526-b0ca-57d5-a340-e231fb120698 | note | ○ NZS3109/3112
07004e69-bfe3-5058-864f-b60c0249c886 | note | ○ Manufacturers Documentation
4c761a38-aa3a-5f33-a1a9-c1026520dfa4 | note | ○ Inspection Records
b21452db-5f6c-5887-a1de-28cdba4aa2b2 | note | ACCEPTANCE CRITERIA: All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
6b1e4f02-525c-5d7c-9282-5d9f39e8154b | note | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
9578af37-733e-5e4b-9426-80c1fd91dd1a | note | ○ All reinforcing and formwork to comply with IFC drawings
05fbe7ef-d807-5675-a05e-292e6a65315d | note | ○ Concrete to be min 30MPa at 28 days
cf14c741-3da0-5cd7-ac7e-8667c14dc34c | note | ○ Testing of concrete per CTS Specifications
ffb56e24-fb0d-5c96-931f-5763d1242ca0 | note | ○ Prepour Inspection Record Filled out Prior to Concrete
28111e96-4951-592d-97bb-b4aac03fbb4d | note | DATE/SIGN: Contractor Rep - P
ba64b285-ed3f-59b7-8e7e-4e402769f56f | note | ○ CTS Civil Inspector - H
| signoff | HOLD POINT
| checkpoint | 5F - Grouting of Baseplate
9f1a3564-9666-53d7-ac62-cd4bb5f78cd0 | note | SPECIFICATION REFERENCE: IFC Drawings
05677506-4adb-591c-80b7-e3a853c55b59 | note | ○ CTS General Civil Construction Specification
caec6071-9cb3-5a63-b5be-6797c3ca56da | note | ○ Manufacturers Documentation
1aec489a-688c-5978-a2ac-0f701bdf6e76 | note | ACCEPTANCE CRITERIA: Grouting shall be Sika 212 or Sika 214 placed in accordance with manufacturers recommendations and the IFC drawings
d173e079-d339-5975-861d-5a5ffd103d68 | note | DATE/SIGN: Contractor Rep - P
5baf711a-e76f-5464-8f3a-963e999f63e3 | note | ○ CTS Civil Inspector - W
| checkpoint | 6A - Demolition
761da63b-a1a8-5f37-9f5a-0cec9b6e43a9 | note | SPECIFICATION REFERENCE: IFC Drawings
ac18e0b4-d4db-5868-9f0f-e4bb315e48c8 | note | ACCEPTANCE CRITERIA: Existing pedestal removed at ground level
a7dc4c7c-16a7-58a9-b485-e88d453c85a5 | note | DATE/SIGN: Contractor Rep - P
fdd41716-64ec-5ece-b04e-f4186b6a4838 | note | ○ CTS Civil Inspector - R
| checkpoint | 6B - Position of Pump Pedestal Setout
3ad2afbc-632b-5950-854e-64a7fd197376 | note | SPECIFICATION REFERENCE: IFC Drawings
9481dd41-bb84-53c9-8f12-5e4bcad32c2a | note | ACCEPTANCE CRITERIA: Setout as per drawings
b1f7e5ea-ba00-5b48-a571-55b312131584 | note | DATE/SIGN: Contractor Rep - P
fdd270bd-744c-58a4-89b6-abf755425d7a | note | ○ CTS Civil Inspector - R
| checkpoint | 6C - Pump Pedestal Location Cleaned & Scabbled
1d5a68be-e702-5178-8e9a-6352db2d8090 | note | SPECIFICATION REFERENCE: IFC Drawings
06e814cb-5acd-5627-9156-964d66ab3307 | note | ACCEPTANCE CRITERIA: Foundation area cleaned and free from contamination and dust/oil or grease, surface roughened to accept further concrete pour
44fe54f5-edf6-5f83-b437-a7ca80a54a98 | note | DATE/SIGN: Contractor Rep - P
ecc32e14-094f-58b4-9dd9-96e1617ac11c | note | ○ CTS Civil Inspector - R
| checkpoint | 6D - Cast in Items - Bolts & Nuts
a42b9470-1de7-5dbe-9886-cb91a08a5da4 | note | SPECIFICATION REFERENCE: IFC Drawings
a4ff2d4a-8e76-59cf-9635-afabffa8248d | note | ○ CTS General Civil Construction Specification
dcd9374d-4b00-5f90-b287-30b128b0d85a | note | ○ CTS Epoxy Grouting of Anchor Bolts
67967c49-14c9-5642-a90f-7e0500063ca1 | note | ○ Manufacturers Documentation
b4b01dbf-a3e7-535f-9779-00af0432dad8 | note | ○ Inspection Records
b59e4260-afda-5111-8413-0547d51bb717 | note | ACCEPTANCE CRITERIA: If drilled in, Epoxy Grout Shall be Ramset C8 placed in accordance with manufacturers recommendations to the levels and positions setout in the drawings
5b019f9f-0269-5e8f-a130-cd21bb4c33f6 | note | ○ Drilled holes for Anchors shall be inspected
1893ccf0-b0a9-5ad8-976d-23ab09e5e892 | note | ○ Cast in anchor bolts shall be set to spec in IFC drawings and positioned with template to design measurenments in IFC drawings
3ba1910c-cdcf-5f7f-9f13-0a499131d151 | note | DATE/SIGN: Contractor Rep - P
1fe459e1-9272-5bc0-b73d-415ac1d5fe6d | note | ○ CTS Civil Inspector - R
| checkpoint | 6E - Formwork, Reinforcing & Concrete
ef15eee4-1c51-584a-9457-3610ae4d6c27 | note | SPECIFICATION REFERENCE: IFC Drawings
5761dd29-ef59-5d01-9ef0-3ac317991477 | note | ○ CTS General Civil Construction Specification
2f852e19-1f93-51b7-8069-142a653a6fd7 | note | ○ NZS3109/3112
97e43c32-18e9-53e3-8b71-b0ac885840fc | note | ○ Manufacturers Documentation
e1bc7cdb-d20b-5bfb-9e34-664823ae4b59 | note | ○ Inspection Records
1be8ac9f-bde5-5217-a99b-9add801ad4f5 | note | ACCEPTANCE CRITERIA: All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
d16ebe42-6827-5951-83e9-17ae4e79c48f | note | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
a30cfdf5-cb16-5fa4-a89b-662e781b96da | note | ○ All reinforcing and formwork to comply with IFC drawings
5b499405-cf4f-5d89-afea-867c2289a50f | note | ○ Concrete to be min 30MPa at 28 days
e9f65d37-8ce9-51d1-9ccf-139231c8e439 | note | ○ Testing of concrete per CTS Specifications
227fdd9e-c7f8-5775-bfa7-a8d67a1ca2a3 | note | ○ Prepour Inspection Record Filled out Prior to Concrete
635de7f4-d637-5e1d-b668-694189f6df4f | note | DATE/SIGN: Contractor Rep - P
5820d878-b238-57cd-baa0-b0f65d5d8eb8 | note | ○ CTS Civil Inspector - H
| signoff | HOLD POINT
| checkpoint | 6F - Grouting of Baseplate
e58ba7fb-0bc8-5191-81cc-712cb0956ae8 | note | SPECIFICATION REFERENCE: IFC Drawings
e0ca1210-9ec7-5068-9700-5e1229ad034e | note | ○ CTS General Civil Construction Specification
c3df7bc7-b12e-50b4-b559-f84430b02e84 | note | ○ Manufacturers Documentation
61b33721-f0a1-5295-92c9-4ad420d2c08c | note | ACCEPTANCE CRITERIA: Grouting shall be Sika 212 or Sika 214 placed in accordance with manufacturers recommendations and the IFC drawings
ccac55dc-faf8-5441-8e32-53699dfbb62f | note | DATE/SIGN: Contractor Rep - P
3d20f4d0-9524-5edf-9aee-7620fb3402f0 | note | ○ CTS Civil Inspector - W
| checkpoint | 7A - Setout of Pipe Sleeper
6e0ecc0d-6071-59e1-89eb-13d3083d72e4 | note | SPECIFICATION REFERENCE: IFC Drawings
51cf838a-7d6f-5942-991d-5b8eb3d70e76 | note | ACCEPTANCE CRITERIA: Comply with setout in drawings
f81e1182-c264-59d3-bc8d-5f9779689ee0 | note | DATE/SIGN: Contractor Rep - P
921dd59f-a68a-5202-ad3c-b2cc0923c1a0 | note | ○ CTS Civil Inspector - R
| checkpoint | 7B - Excavation & Foundation Preparation inc Site Concrete
03bd86fb-7848-5513-91b2-ccbe88c3388a | note | SPECIFICATION REFERENCE: IFC Drawings
c81abbc8-c6a5-525e-863c-fdbac8fd7ed7 | note | ○ CTS Excavation Works Specification
13aaea2f-8f5b-5e40-8661-bcbc51affac1 | note | ○ CTS General Civil Construction Specification
11ac930d-db4a-5553-b57b-8b900dac4d5e | note | ACCEPTANCE CRITERIA: Excavated as per IFC drawings to line and levels shown
d070c471-b6b7-5ba9-8207-212b60965b74 | note | ○ Foundation compaction Inspection Record completed
91c04762-2395-5b90-9466-206d19234db0 | note | DATE/SIGN: Contractor Rep - P
43cc0ae5-7efb-550f-8a6e-fe2a9a0ed499 | note | ○ CTS Civil Inspector - W
| checkpoint | 7C - Formwork, Reinforcing & Concrete
73730a53-1ee8-5069-b151-241f6270c18c | note | SPECIFICATION REFERENCE: IFC Drawings
5bd114fe-015c-5e97-8a63-c8b8c0b3d5ec | note | ○ CTS General Civil Construction Specification
a179dd76-5275-5680-b27b-198c319e5c9b | note | ○ NZS3109/3112
e6cb0121-36c9-53d7-ba03-42bf65962353 | note | ○ Manufacturers Documentation
e7c1aba3-22da-50e3-bff5-bfd0b1abdd9e | note | ○ Inspection Records
c50085fd-734a-5480-a87d-806c63a19e77 | note | ACCEPTANCE CRITERIA: All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
09497384-c249-52cf-931d-6923dce989e1 | note | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
72eec2c4-b0e6-5f7b-95ea-548662e830df | note | ○ All reinforcing and formwork to comply with IFC drawings
d705247c-b7ad-5957-8ff9-1eb8d26f78f2 | note | ○ Concrete to be min 30MPa at 28 days
34392d43-2244-535f-a235-d7bcc8a4f148 | note | ○ Testing of concrete per CTS Specifications
a722ca94-5069-5758-a1d7-aec98c97545a | note | ○ Prepour Inspection Record Filled out Prior to Concrete
d412e189-8e8d-5432-b273-efbed17f6dfc | note | DATE/SIGN: Contractor Rep - P
7ef845bb-cd14-565f-abd5-41e02da3e714 | note | ○ CTS Civil Inspector - H
| signoff | HOLD POINT
| checkpoint | 8A - Position of Pump Pedestal Setout
6fc5f9f5-06bc-525c-8989-b8969e60bce4 | note | SPECIFICATION REFERENCE: IFC Drawings
5354e3e4-8ce1-5552-8b33-e84bcd89b7a7 | note | ACCEPTANCE CRITERIA: Setout as per drawings
f30a7b57-8b32-5d39-ac78-d347d948cd28 | note | DATE/SIGN: Contractor Rep - P
83e62704-337a-55a3-b903-a39d551d0d9a | note | ○ CTS Civil Inspector - R
| checkpoint | 8B - Excavation & Foundation Preparation inc Site Concrete
95c771e9-61f1-5763-b856-e82364c36cc0 | note | SPECIFICATION REFERENCE: IFC Drawings
6d73a70a-3c49-59cc-b948-90f5a4df3280 | note | ○ CTS Excavation Works Specification
1f79658e-32bc-5eb1-8605-8b178605f003 | note | ○ CTS General Civil Construction Specification
c4595fdf-3cdb-503f-8ad6-3b938e503846 | note | ACCEPTANCE CRITERIA: Excavated as per IFC drawings to line and levels shown
3eb2e2f9-1507-53c2-86df-7e87815bfbd0 | note | ○ Foundation compaction Inspection Record completed
9faafceb-26bd-5f05-ad03-dd668e675793 | note | DATE/SIGN: Contractor Rep - P
c2e4746f-ff31-5843-bec6-520523e84adf | note | ○ CTS Civil Inspector - W
| checkpoint | 8C - Formwork, Reinforcing & Concrete
97100f36-1c03-5a0d-b07c-b7847a327ace | note | SPECIFICATION REFERENCE: IFC Drawings
195d7b1a-cc50-5e48-827d-d1ad57c7e0de | note | ○ CTS General Civil Construction Specification
03078014-0499-511f-bd0a-8d4e857d753a | note | ○ NZS3109/3112
a23d43a2-7ef3-543f-95e3-179f4ae8cd3c | note | ○ Manufacturers Documentation
6cbd6517-7002-5031-a2ea-cfbe119f8454 | note | ○ Inspection Records
a71fed5a-f071-5a9b-86aa-089c155c74ed | note | ACCEPTANCE CRITERIA: All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
768331b6-361b-5665-8ba1-9e01fd1a1e2b | note | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
89d6fc31-9064-5065-a113-511e6c4ec5d3 | note | ○ All reinforcing and formwork to comply with IFC drawings
9822f7a2-9a6b-59b0-8645-27acd234aac4 | note | ○ Concrete to be min 30MPa at 28 days
5c397737-5f52-523a-8443-e35331f82848 | note | ○ Testing of concrete per CTS Specifications
8984d014-768e-5963-9e18-42712a4d194c | note | ○ Prepour Inspection Record Filled out Prior to Concrete
8cda9e98-30a9-53ec-97e9-ab681be73fbb | note | DATE/SIGN: Contractor Rep - P
586b7e30-fb24-5893-9e9c-5e7182e994b1 | note | ○ CTS Civil Inspector - H
| signoff | HOLD POINT
| checkpoint | 9A - Position of Slab Extension Setout
2212b1d4-be07-5007-8221-f495aa32a17e | note | SPECIFICATION REFERENCE: IFC Drawings
7812d237-fa72-53ea-9907-40d8db16daa1 | note | ACCEPTANCE CRITERIA: Setout as per drawings
d9e1ea7a-bf6a-5667-b194-7931d2ca5305 | note | DATE/SIGN: Contractor Rep - P
aae0bc18-a83e-5979-821e-ba71e23da7ba | note | ○ CTS Civil Inspector - R
| checkpoint | 9B - Excavation & Foundation Preparation inc Site Concrete
affeaa09-3819-5423-bfc2-8e9c4a59fd7c | note | SPECIFICATION REFERENCE: IFC Drawings
51f4e0a3-bb6f-586c-a9d8-1abd3277ac0a | note | ○ CTS Excavation Works Specification
03667025-54d7-5810-a501-21cda3cc64b5 | note | ○ CTS General Civil Construction Specification
4a0cbdb7-7dfe-5d8b-80a5-b16b7b91e7cf | note | ACCEPTANCE CRITERIA: Excavated as per IFC drawings to line and levels shown
f2216c29-7e2a-58b3-bab3-0593bdad13f1 | note | ○ Foundation compaction Inspection Record completed
e904b868-51ca-5a27-b860-e8d93f19b5aa | note | DATE/SIGN: Contractor Rep - P
cfe40430-7ba3-5065-8886-838beb7f6335 | note | ○ CTS Civil Inspector - W
| checkpoint | 9C - Formwork, Reinforcing & Concrete
33af660b-a477-5715-ac85-1295102c18d0 | note | SPECIFICATION REFERENCE: IFC Drawings
9a0d11c7-5f51-5077-bbf2-c0519d3967bc | note | ○ CTS General Civil Construction Specification
06b73b4a-efe7-576a-b7c6-a448c7afe72c | note | ○ NZS3109/3112
1e995f95-fb56-5722-a366-329a9631e0a3 | note | ○ Manufacturers Documentation
0cc224ad-eee2-55d5-9190-565817c48875 | note | ○ Inspection Records
22ddf9c2-7547-592f-8a90-a0de454de92d | note | ACCEPTANCE CRITERIA: All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
1d42735e-9abc-5608-88f3-002804ca41b4 | note | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
d82337dc-4955-52ee-9ad1-3f6d51aae21f | note | ○ All reinforcing and formwork to comply with IFC drawings
5978997c-9bad-593d-a303-f42f66d9c1b8 | note | ○ Concrete to be min 30MPa at 28 days
a9fd78a9-f6e9-51cd-b728-9efc8b22607f | note | ○ Testing of concrete per CTS Specifications
29c4d6ec-58b2-5629-8a51-2c9d38e3b7dc | note | ○ Prepour Inspection Record Filled out Prior to Concrete
831b69b4-0c14-553e-910e-36ddec90f56b | note | DATE/SIGN: Contractor Rep - P
e7e28e51-3359-5e8a-9481-c7941f93435a | note | ○ CTS Civil Inspector - H
| signoff | HOLD POINT
| checkpoint | 10A - Position of Slab Extension Setout
a6c70885-1237-5e3a-9d80-7e54a44443f8 | note | SPECIFICATION REFERENCE: IFC Drawings
29a57d79-fd38-58ee-a6ed-409b94c799b9 | note | ACCEPTANCE CRITERIA: Setout as per drawings
a8966890-33d6-503a-b122-6e5a03e63fa6 | note | DATE/SIGN: Contractor Rep - P
835abeb1-6570-588b-a28e-c07066d077e2 | note | ○ CTS Civil Inspector - R
| checkpoint | 10B - Excavation & Foundation Preparation inc Site Concrete
0c59225d-426b-5eb9-ae7e-9edc33031b73 | note | SPECIFICATION REFERENCE: IFC Drawings
35d19600-4bf2-5e3b-a1ba-9e6e2e51074b | note | ○ CTS Excavation Works Specification
9f14793f-04c6-5c34-ae7b-0318fe0517a1 | note | ○ CTS General Civil Construction Specification
690f7240-1b50-59bd-b8de-4e2fab30b22b | note | ACCEPTANCE CRITERIA: Excavated as per IFC drawings to line and levels shown
30223d43-b313-5568-9b48-022946a1aeb7 | note | ○ Foundation compaction Inspection Record completed
0c0f7e27-eb5a-5a3b-9c83-4efb689468f9 | note | DATE/SIGN: Contractor Rep - P
ea2c5c60-c401-574d-8763-9570b69c7b72 | note | ○ CTS Civil Inspector - W
| checkpoint | 10C - Formwork, Reinforcing & Concrete
4f0e142e-4945-5a25-b17f-49abb3cd647e | note | SPECIFICATION REFERENCE: IFC Drawings
29a8d6ec-f352-5fb5-b30c-094349eb44c2 | note | ○ CTS General Civil Construction Specification
7ea3d663-e0a9-560f-925f-35aa14f2f167 | note | ○ NZS3109/3112
23003765-e2cc-5cbf-b713-7a0eca545e69 | note | ○ Manufacturers Documentation
138a5209-af39-50e8-a344-283076bc0961 | note | ○ Inspection Records
d974fd5b-e525-5aa5-8a5f-f8de93890c38 | note | ACCEPTANCE CRITERIA: All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
d630ed08-283b-546a-a58e-e17e724525dd | note | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
fbd6e0ef-3c46-5fc8-9cb5-8fb88275467f | note | ○ All reinforcing and formwork to comply with IFC drawings
7c062043-7ada-5de9-836a-887b76e30859 | note | ○ Concrete to be min 30MPa at 28 days
69f703dc-ff31-503c-a4b8-97869dab5692 | note | ○ Testing of concrete per CTS Specifications
40c46186-e210-55f3-abb2-c1c71af5cbb5 | note | ○ Prepour Inspection Record Filled out Prior to Concrete
f22ee24b-7f1e-5061-a610-20a5b27250ee | note | DATE/SIGN: Contractor Rep - P
58933062-0ea3-5b71-9be7-03312bf6f723 | note | ○ CTS Civil Inspector - H
| signoff | HOLD POINT
| checkpoint | 11 - Complete final Civil Inspection and close off ITP
66c14816-65ca-58ac-8888-cba232f498f3 | note | SPECIFICATION REFERENCE: IFC Drawings
b71df2a6-7f9b-570f-8495-bf5497863770 | note | ○ CTS General Civil Construction Specification
0d453ec2-f050-508a-bbdd-0f4e0f8ddcc9 | note | ○ Manufacturers Specification
9a2dd5b8-959c-597f-874d-712ecd5f8973 | note | ACCEPTANCE CRITERIA: ITP/QC has been completed; all steps & hold points signed byrelevant party.
594e5a3d-f787-51c2-b981-b37a17b1f5f4 | note | ○ All work completed as per work pack, and any field instructions issued during construction compiled
ff62b707-b324-5c89-8b5f-02028973c6c3 | note | DATE/SIGN: Contractor Rep - P
859e308d-4afd-5754-ba03-4512b3dbe1e8 | note | ○ CTS Civil Inspector - H
| signoff | HOLD POINT
| checkpoint | 12 - Non-Conformance Reporting
5ffbb2cd-32e1-5f8f-8bf3-52c6adc1bfd4 | note | SPECIFICATION REFERENCE: UCC Internal NCR and or Lucidity event NCR
fcd8f443-4710-59f5-89cc-f0a4874e8789 | note | ○ QC Requirements for Civil Works
c702d77f-f278-5548-8cc4-d1ec227384de | note | ACCEPTANCE CRITERIA: All Non-Conformance reports and Investigations are attached and closed out
f9822a94-bb06-5e2f-b355-e91091e9a173 | note | DATE/SIGN: Contractor Rep - R
| checkpoint | 13 - As Built & Final Design Documentation
e59f8b8e-a15b-50f9-863d-f33dc925e698 | note | ACCEPTANCE CRITERIA: Confirmation From Engineer on as built records & redline mark ups
3400d94f-c590-5556-97d8-f02b0109d68e | note | DATE/SIGN: Contractor Rep - P
| checkpoint | 14 - Reference Info, Specifications
74408157-1fb1-572b-80ae-c9db22b85b9d | note | ACCEPTANCE CRITERIA: All Reference Information and relevant Product Specifications
528c98b0-965a-52bc-984c-a7da35a863c8 | note | DATE/SIGN:
| checkpoint | 15 - Punch Listing
0963cbbb-e9b0-5b5d-87dd-a62360b70442 | note | SPECIFICATION REFERENCE: CTS QC Requirments for Civil Work
b171023d-4b16-5075-8c2b-8f5734211755 | note | ACCEPTANCE CRITERIA: All punch list items are closed out in the relevant timeframe to the required standard
5a210d89-74f5-5dfd-a31d-f20124920c58 | note | DATE/SIGN: Contractor Rep - P
ca2a679d-3bc0-5416-a954-f182b1464e98 | note | ○ Project/Construction Engineer - R
| checkpoint | 16 - Compilation of ITP
7c8bfb5e-8e25-58b0-a4f4-5f2beef2fef4 | note | ACCEPTANCE CRITERIA: ITP Completed and Signed off
4dc37894-7258-57d7-9387-666d76b42912 | note | DATE/SIGN: Contractor Rep - H
faf5d619-7aa8-535d-821b-f5c168bc43f3 | note | ○ Project/Construction Engineer - H
| signoff | HOLD POINT